## CAR FORMAT
MUMBAI INTERNATIONAL AIRPORT LTD.
CHANGE AUTHORISATION REQUEST & APPROVAL
PROJECT | Interior Work for MUM Good Times Bar - T1B |  | CAR NO :- | 1
LOCATION |  |  | WORK ORDER NO & WO DATE :- (Latest amended one) | Semolina/PO/23-24/000781
WORK DESCRIPTION | Interior Work for MUM Good Times Bar - T1B |  | OMDA Ref.
CONTRACTOR'S NAME | M/S Lok Pratik Constructions |  | CONTRACTUAL DATE OF COMPLETION :-
ORIGINAL CONTRACT VALUE (Rs) | DEVIATION /VARIATION VALUE (Rs) | REVISED CONTRACT VALUE (Rs) | % VARIATION | REMARKS
(A) | (B) | ( C) = (A) + (B) | (D) = {(B) /(A)}% | (E)
626174.9 | 1438102 | 2064276.9
Whether Extention of Time Required :-
IF YES THEN :-
Note : This extention should be recommended only in case of major increase in scope of work.
COMPLETION DATE AS PER CONTRACT | EXTENTION GRANTED UPTO | REMARKS
AUTHORIZATION
Requested By |  | Recommended by | Approved By
Name | Mr Ashish Nagar | Sr Manager | AVP | AVP | GM Finance
Sign
Title
Date
CONTRACTOR'S ACCEPTANCE
Name | Mr Prakash C Amarnani | Note :This document shall form a part of contract & shall be treated as an amendment to the existing Work Order.
Sign
Title
Date

## DEVIATED ITEMS (ANNEX 1 -SECA)
ANNEXURE -1
SO No :- Semolina/PO/23-24/000781
CAR No :- | 1
Interior Work for MUM Good Times Bar - T1B
SECTION: A (DEVIATED ITEMS)
VARIATION
SR.NO | DESCRIPTION | UNIT | BOQ QTY | BOQ RATE (Rs) | BOQ AMOUNT (Rs) | REV QTY | REV AMOUNT (Rs) | Qty |  | Amount(Rs) | REMARKS
PART 1
1 | Veneer finish (Polish) - 1. Scraping of old veneer surface polish on existing veneer. 2. Doing New polish on surface of existing veneer in approved shade as per instruction from EIC. Include 2 coats of layer polish and 3rd coat of final polish. LOCATION - Polishing all existing surfaces with veneer finish | M2 | 131.14 | 1500 | 196710 | 120.76 | 181140 |  | -10.38
2 | buffing- solid acrylic surfaces - Buffing entire white solid acrylic surfaces of front counter until uniform semi-gloss appearance is achieved. Including all required material for the activity. LOCATION - Buffing white solid acrylic surfaces of front counter | M2 | 12.25 | 750 | 9187.5 | 17.54 | 13155 |  | 5.29 | 3967.5
3 | re-painting of wall, ceiling - 1. Scraping of old wall paints Ceiling paints. 2. Doing New paint on surface of existing walls ceiling in approved shade as per instruction from EIC.Include 2 coats of primer and 2rd coat of final paint.. LOCATION - Entire outlet walls ceilings | M2 | 270.83 | 280 | 75832.4 | 173.34 | 48535.2 |  | -97.49
4 | louvrers shutter to be re polished - polished on existing finish of lower back counter and lower front counter, complete as per instruction from EIC. LOCATION - Lower back counter and lower front counter | M2 | 5.28 | 1500 | 7920 | 6.89 | 10335 |  | 1.61 | 2415
5 | Increase lux level of existing lightsReplacement of old dull lights with new lights of 9 watt warm white and 4000 lux level each - 1. Removing of existing light fittings handingover to EIC. 2. Providing fixing of new approved light fittings on same location as per instruction from EIC. Includes all neceassry electrical wirings electrical hardware items. LOCATION - dining area and counter (BOH) | EA | 49 | 1200 | 58800 | 64 | 76800 |  | 15 | 18000
6 | Buffing of existing 220MM high SS skirting - Buffing of existing SS skirting 220 mm Ht. in entier outlet with neceassry cleaning agent. | M2 | 13.51 | 500 | 6755 | 14.25 | 7125 |  | 0.74 | 370
7 | New Signages - providing and fixing of new signages of height 500mm and length to be in proportion to the height. DIMENSION - ht=500mm | EA | 2 | 48000 | 96000 | 2 | 96000 |  | 0 | 0
PART 2
9 | Cleaning of existing flooring - Deep Cleaning of existing flooring with chemical including rectification of damages. Dining area seating area | M2 | 110 | 250 | 27500 | 130.57 | 32642.5 |  | 20.57 | 5142.5
10 | Cleaning of existing floor tiles dados in kitchen, store, behind front counter and smoking room - Deep Cleaning of existing floor tiles dados in kitchen, store, behind front counter and smoking room with chemical including rectification of damages. LOCATION - kitchen, store, smoking room, behind front counter | M2 | 38.7 | 150 | 5805 | 0 | 0 |  | -38.7
11 | New glass shutter - Providing fixing 12 mm thick extra clear toughne glass door, as per detail dwg onsite instruction by EIC. Include all necessary hardware accessories fittings. LOCATION - Extra clear toughen glass door. | M2 | 1.76 | 6000 | 10560 | 1.77 | 10620 |  | 0.01 | 60
12 | Replacement of damaged floor tiles if required - 1. Removal of old damage floor tile. 2. Providing Fixing of floor tile matching with the existing floor. LOCATION - Replacement of existing floor tile | M2 | 5.4 | 2200 | 11880 | 14.45 | 31790 |  | 9.05 | 19910
13 | 6mm ply fire rated ply - providing and fixing 6 mm fire rated ply on the existing ply under the front and back counters of BOH area LOCATION - BOH - under front and back counters | M2 | 15.03 | 1500 | 22545 | 6.48 | 9720 |  | -8.55
14 | 12 mm fire rated ply - providing and packing pest open area permanantly with 12 mm fire rated ply under the front and back counters of BOH area LOCATION - BOH - under front and back counters | M2 | 9.75 | 1600 | 15600 | 21.29 | 34064 |  | 11.54 | 18464
15 | white solid acrylic surface matching with existing - providing and fixing white solid acrylic surface (corian) on the existing front counter, finish to match with the existing surface.Cut out on it to be done as per the size of induction. LOCATION - front serving counter | M2 | 4.68 | 13500 | 63180 | 2.04 | 27540 |  | -2.64
16 | Low height cane Screens - P F of cane screen in 20 x 40mm thk MS frame in brown powder coating as per the design. LOCATION - partition between lounge and dining seating DIMENSION - upto 1200mm height | Rmt | 3.58 | 5000 | 17900 | 0 | 0 |  | -3.58
| TOTAL |  |  |  | 626174.9 |  | 579466.7 |  |  | 68329
| CGST @ 9% |  |  |  | 56355.741 |  | 52152.003 |  |  | 6149.61
| SGST @ 9% |  |  |  | 56355.741 |  | 52152.003 |  |  | 6149.61
| GRAND TOTAL |  |  |  | 738886.382 |  | 683770.706 |  |  | 80628.22

## Extra Items (Annexure II)
ANNEXURE -II EXTRA ITEMS
SO No :- Semolina/PO/23-24/000781
CAR No :- 1
Interior Work for MUM Good Times Bar - T1B
SECTION: B (EXTRA ITEMS)
Variation
SR.NO. | DESCRIPTION | UNIT | OLD QTY | OLD RATE | OLD AMT (Rs) | Old qty | Old rate | old Amt | NEW QTY | New RATE (Rs.) | AMOUNT (Rs) | Qty | Amount (Rs.) | REMARKS- ITEM CODE
Civil Work
1 | Repair of Chairs/Single seater Sofa ,Replacing old Leatherite with Sarom Bently make ,approved Shade ,Providing 2" Foam if required including all necessary hardware etc Complete. | EA | [6 empty] | 35 | 7000 | 245000
2 | Repairing the existing tables , replacing the mica & Buffing/Polishing as per instruction of engineer incharge etc complete. | EA | [6 empty] | 20 | 5900 | 118000
3 | Dismantling concrete , removing exisitng damaged/ chocked drain line . Providing & Fixing 63mm PVC Pipe and re concreting the same including cleaning the site , removal of debris outside airport premise etc complete. | Lump | [6 empty] | 1 | 35000 | 35000
4 | Providing & Fixing SS Sink with drain board of approved make and quality Including removing the existing damaged sink. | Lump | [6 empty] | 1 | 15000 | 15000
5 | Swan neck sink cock of Jaguar make | EA | [6 empty] | 1 | 4800 | 4800
6 | Providing & fixing 12mm thick toughened glass in fixed windows including making cutouts for Glass holders. | M2 | [6 empty] | 6.97 | 6800 | 47396
7 | Providing & fixing Reception Table as per Drawing, Made with 19mm Marine ply ,1mm laminate Marino make both side i/c all necessary Hardware etc Complete. | No | [6 empty] | 2 | 30000 | 60000 |  |  | Negotiated and Finalised on 09/05/24
8 | Providing & fixing SS Glass Holders . | Nos | [6 empty] | 26 | 600 | 15600
9 | Supplying Single seater Sofa with side covered rest, match to existing design and Leatherite. | Nos | [6 empty] | 5 | 22000 | 110000
10 | Supply & Fixing Wall Mounted Flat Exhaust Chimney with Carbon Filter, Duct less as approved by In charge. Size- 600 x 540mm | Nos | [6 empty] | 2 | 12000 | 24000
11 | Supply & Fixing 1200 watt Induction Plate of Prestige Make. | Nos | [6 empty] | 6 | 2000 | 12000
12 | Supply & Fixing Dish Washer Celfrost B-30. Size- 600 x 600 x 800mm | No | [6 empty] | 1 | 218000 | 218000
13 | Supply & Fixing Open Deck Chiller of Blue Star Make. | No | [6 empty] | 1 | 220000 | 220000
14 | Equipment Loading , Unloading & Shifting the same inside airport Premises SHA area including Transport charges . | LS | [6 empty] | 1 | 35000 | 35000
15 | Making core cutting 50mm dia in Corian finished main counter. | Nos | [6 empty] | 8 | 2000 | 16000
16 | Dismantling Gyp board ceiling | M2 | [6 empty] | 6.51 | 200 | 1302
17 | Providing and fixing at all height false ceilling of 12.5mm thick tapered edge gypsum board conforming to IS : 2095 including providing and fixing of frame wirk made of galvanised in accordance with zinc coating of grade 350 as per IS : 277 and consisting of angle cleats of size 25 mm wide x 1.6mm thick with flanges of 22 mm and 37mm at 1200mm centre to centre one flange fixed to the ceilling with dash fastner 12.5mm dia x 40 mm long with 6mm dia bolts to the angle hangers of 25x25x0.55 mm of required length, and other end of angle hanger being fixed with nut and bolts to G.I channels 45mmx15mmx0.9mm running at the rate of 1200mm centre to centre to which the ceiling section 0.5 mm thick bottom wedge of 80 mm with tapered flanges of 26mm each having clips of 10.5 mm at 450mm centre to centre shall be fixed in a direction prependicular to G.I channel with connecting clips made out of 2.64 mm dia x 230 mm long G.I wire at every junction including fixing the gypsum board with ceiling section and perimeter channels 0.5mm thick 27mm high having flanges of 20mm and 30mm long, the perimeter of ceiling fixed to wall/partition with the help of rawl plugs at 450 mm centre to centre with 25 mm long drive-all screws @ 230 mm interval including jointing and fixing to a flush finish of tapered and square edges of the gypsum board with recommended filler, paper tapes, finisher and two manufactures specification and also including the coat of making openings for light fittings, grills diffusers, cutouts made with frame of perimeter channels suitably fixed all complete as per drawing and specification and direction of the Engineer-in- charge but excluding the cost of painting. | M2 | [6 empty] | 6.51 | 1200 | 7812
18 | Making Cut /Opening in Gypboard Ceiling for Laying IT cables and Fixing 12.5 mm Gyp board after finishing the same . | Nos | [6 empty] | 8 | 2000 | 16000
| PLUMBING WORK | [9 empty] | 0
1 | Providing & fixing CPVC FTA of Size 40MM of Approved make including necessary fittings etc complete | Nos | [6 empty] | 3 | 400 | 1200
2 | SUPPLYING AND FIXING ON WALL FACE UNPLASTICISED RIGID PVC PIPES OF M/S SUPREME INDUSTRIES/FINOLEX IN TOILET AND SHAFT CONFORMING TO IS:13592 TYPE A INCLUDING JOINTING WITH SEALED RING CONFORMING TO IS:5382 LEAVING 10 MM GAP FOR THERMAL EXPANSION. SINGLE SOCKETED PIPES SIZE:DN40 | RMT | [6 empty] | 2.1 | 200 | 420
3 | Providing & fixng PVC Reducer socket of size 50mm x 40 mm | Nos | [6 empty] | 3 | 150 | 450
4 | Providing & fixing PVC connector Pipe. | Nos | [6 empty] | 3 | 300 | 900
5 | Providing & fixing CP Brass Jaguar Pillar tap. | Nos | [6 empty] | 1 | 2200 | 2200
6 | Providing & fixing 100 ltr water tank i/c making hole ,Nipple ,checknut etc Comp. | Nos | [6 empty] | 1 | 2800 | 2800
7 | Providing & fixing 1/2 HP Booster/Pressure pump of Crompton make with all necessary fittings. | Nos | [6 empty] | 1 | 14500 | 14500
8 | Providing & fixng CP Brass Angle cock. | Nos | [6 empty] | 1 | 2100 | 2100
9 | Providing & fixing Brass FTA of Size 32MM of Approved make including necessary fittings etc complete | Nos | [6 empty] | 2 | 800 | 1600
10 | Providing & fixing Brass MTA of Size 20MM of Approved make including necessary fittings etc complete | Nos | [6 empty] | 3 | 450 | 1350
11 | Fixing Greece Trap supplied by client with all necessary fittings & Hardware. | No | [6 empty] | 1 | 4000 | 4000
12 | Fixing of SS Racks in Kitchen walls with all necessary hardwares. | Nos | [6 empty] | 2 | 1500 | 3000
| Electrical Work | [9 empty] | 0
1 | Supplying and erecting PVC flexible cable 4sqmm 3 core FRLS copper conductor complete erected on wall / celling as per specification | Rmt | [6 empty] | 23.7 | 240 | 5688
2 | Supply, Installation, Testing & Commissioning of 32A Industrial Point Three Phase with Powder coated MS Box,MCB ,3 Pin Industrial Socket & Top of Legrand make. | No | [6 empty] | 1 | 11000 | 11000
3 | Supply, Installation, Testing & Commissioning of 20A Industrial Point Single Phase with Powder coated MS Box,MCB ,3 Pin Industrial Socket & Top of Legrand make. | Nos | [6 empty] | 3 | 3500 | 10500
4 | Wiring for the light points with 2X1.5 sq mm PVC insulated copper conductor 650V grade FRLS wires in concealed or surface mounted 20/25mm dia MMS PVC conduit as required including providing 6 amps flush type PVC moulded switches, cover plate,5 sided 1.2mm thick G.I. Box one module for housing switches and earthing of the fixtures and outlet box with 1.5 mm PVC insulated copper conductor 650V grade green earth wire.(switches-as/approved make)- | [9 empty] | 0
a | Primary (First) light point controlled by a 6A switch. | Nos | [6 empty] | 3 | 1600 | 4800
b | Secondary (Loop) light point looped to first point | Nos | [6 empty] | 3 | 1200 | 3600
c | First Point wiring with 6A,5pin wall socket outlet and controlled by a 6A switch | Nos | [6 empty] | 2 | 2200 | 4400
d | Extra loop point wiring with 6A, 5 pin wall socket outlet and controlled by a 6A switch | Nos | [6 empty] | 4 | 1600 | 6400
e | First Point wiring with 16A,5pin wall socket outlet and controlled by a 16A switch | Nos | [6 empty] | 13 | 3000 | 39000
f | Extra loop point wiring with 16A, 5 pin wall socket outlet and controlled by a 16A switch | Nos | [6 empty] | 11 | 2100 | 23100
5 | Supply, Installation, Testing & Commissioning of mains with 2 X 2.5 sq.mm and earth wire 1.5 sqmm FRLS PVC copper wire ,in rigid conduit min.20 mm dia,including all required accessories,etc as per specification. | Rmt | [6 empty] | 8.5 | 190 | 1615
6 | Supplying and erecting Metal LED Hanging Lights of approved design. | Nos | [6 empty] | 4 | 3500 | 14000
7 | Supply, Installation, Testing & Commissioning LED Strip Light. | Rmt | [6 empty] | 16.6 | 400 | 6640
8 | Providing & Fixing 12W LED Driver. | Nos | [6 empty] | 2 | 1800 | 3600
| Total of Section B :- Extra Items |  | Rs | [7 empty] | 1369773
| CGST @ 9% |  | Rs | [7 empty] | 123279.57
| SGST @ 9% | [9 empty] | 123279.57
| GRAND TOTAL | [9 empty] | 1616332.14
| Total(Section A + Section B) without taxes Rs. | [9 empty] | 1949239.7 | (A)

## Sheet1 (hidden)
WO No 7500000002 SWD
S No | DESCRIPTION | NOS | L | B | H | T.QTY
1 | S/L 5 nos of 10 mts RCC Hume pipe
|  | 1 |  |  |  | 1 | LS
2 | Drains 600mm width
| Annawadi road corner to main nallah | 1 | 47.9 |  |  | 47.9
|  | 1 | 3.2 |  |  | 3.2
Annawadi road corner to Plot-2
| office gate | 1 | 52 |  |  | 52
| Plot-2 off gate to Annawadi | 1 | 67.3 |  |  | 67.3
[6 empty] | 170.4 | Rmt
Extra Items
1 | Demolishing cement concrete PQC
Main road drain
| Sides of drain | 2 | 67.3 | 0.5 | 0.85 | 57.205
0
| Bottom | 1 | 67.3 | 2 | 0.3 | 40.38
| Concrete road | 1 | 52 | 3.95 | 0.129 | 26.4966
0
|  | 1 | 55.8 | 3.95 | 0.15625 | 34.4391
0
| 1st Lair | 1 | 24 | 3.95 | 0.175 | 16.59
0
| 2nd Lair | 1 | 24 | 3.95 | 0.1 | 9.48
[6 empty] | 184.5907 | Cumt
2 | Demolishing RCC work 1:2:4
Main road drain
| Slab of drain | 1 | 67.3 | 2 | 0.15 | 20.19 | Cumt
3 | Demolishing Random Rubble Masonry
| Main road to proj Entrance | 1 | 22 | 0.6 | 0.6 | 7.92
|  | 1 | 22 | 0.45 | 2.27 | 22.473
| Proj off Ent to Proj Exit | 1 | 64.8 | 0.6 | 0.6 | 23.328
|  | 1 | 64.8 | 0.45 | 2.27 | 66.1932
| Proj Exit to Yellow Fever gate | 1 | 185.7 | 0.6 | 0.6 | 66.852
|  | 1 | 185.7 | 0.45 | 2.27 | 189.6926
| Plot 2 canteen to Entrance | 1 | 24.1 | 0.6 | 0.6 | 8.676
|  | 1 | 24.1 | 0.45 | 2.47 | 26.7872
| Gate to L&T office | 1 | 36.9 | 0.6 | 0.6 | 13.284
|  | 1 | 36.9 | 0.45 | 2.47 | 41.0144
| L&T to Annawadi | 1 | 37.3 | 0.6 | 0.6 | 13.428
|  | 1 | 37.3 | 0.45 | 2.47 | 41.459
| Yellow fever hos | 1 | 64.7 | 0.6 | 0.6 | 23.292
|  | 1 | 64.7 | 0.45 | 2.27 | 66.091
[6 empty] | 610.4902 | Cumt
4 | Dismentling/Removing chainlink
| Main road Hiranandani plot | 1 | 28.45 |  | 2.4 | 68.28
| Gate | 1 | 4.5 |  | 2.4 | 10.8
|  | 1 | 17.8 |  | 2.4 | 42.72
| Plot 2 canteen to Entrance | 1 | 24.1 |  | 1.25 | 30.125
| Gate to L&T office | 1 | 36.9 |  | 1.25 | 46.125
| Yellow fever hos | 1 | 64.7 |  | 1.3 | 84.11
[6 empty] | 282.16 | Sqmt
5 | Earthwork in excavation
For Drain
| Main rd to Proj off end | 1 | 91.6 | 2.95 | 1.5 | 405.33
| Proj Exit to Yellow Fever gate | 1 | 30 | 2.95 | 1.5 | 132.75
|  | 1 | 157.7 | 2.95 | 1.83 | 851.3434
| Yellow fever hos | 1 | 64.7 | 2.95 | 1.83 | 349.283
| For manhole | 1 | 3.4 | 3.4 | 2.25 | 26.01
| For Hume pipe,Road crossing | 1 | 7.5 | 2.4 | 2.23 | 40.14
|  | 1 | 7.5 | 2.4 | 2.2 | 39.6
| Plot 2 crossing | 1 | 12.5 | 2.4 | 2.05 | 61.5
| Yellow fever hos crossing | 1 | 5 | 2.4 | 1.83 | 21.96
| Road crossings | 3 | 7 | 2 | 1.9 | 79.8
| For Curb stone wide item no 18 | 1 | 120.1 | 0.2 | 0.2 | 4.804
[6 empty] | 2012.5204 | Cumt
6 | Soling with hard stone
| Between Proj Ent to Proj Exit | 1 | 36 | 2.95 | 0.23 | 24.426
| Drain from Proj Exit to Yellow Fever gate | 1 | 157.7 | 2.95 | 0.23 | 106.9994
| Yellow fever hos | 1 | 34.7 | 2.95 | 0.23 | 23.5439
| For manhole | 1 | 2.5 | 2.5 | 0.23 | 1.4375
| For Hume pipe,Road crossing | 2 | 7.5 | 1.8 | 0.23 | 6.21
| Plot 2 crossing | 1 | 12.5 | 1.8 | 0.23 | 5.175
| Yellow fever hos crossing | 1 | 5 | 1.8 | 0.23 | 2.07
| Road crossings | 3 | 7 | 1 | 0.23 | 4.83
For comp wall
| Proj off Ent to Proj Exit | 1 | 64.8 | 0.45 | 0.23 | 6.7068
| Proj Exit to Yellow Fever gate | 1 | 185.7 | 0.45 | 0.23 | 19.22
| Plot 2 canteen to Entrance | 1 | 24.1 | 0.45 | 0.23 | 2.4943
| Gate to L&T office | 1 | 36.9 | 0.45 | 0.23 | 3.8192
| L&T to Annawadi | 1 | 37.3 | 0.45 | 0.23 | 3.8605
| Yellow fever hos | 1 | 64.7 | 0.45 | 0.23 | 6.6964
[6 empty] | 217.4891 | Cumt
7 | Refilling with excavated earth
For Drain
Main rd to Proj off ent
|  | 2 | 21 | 0.15 | 0.5 | 3.15
|  | 2 | 21 | 0.45 | 0.5 | 9.45
|  | 2 | 21 | 0.75 | 0.5 | 15.75
| Proj off ent to Proj exit | 2 | 64.8 | 0.15 | 0.5 | 9.72
|  | 2 | 64.8 | 0.45 | 0.5 | 29.16
|  | 1 | 64.8 | 0.75 | 0.5 | 24.3
|  | 1 | 64.8 | 0.15 | 0.5 | 4.86
| Proj Exit to Yellow Fever gate | 2 | 187.7 | 0.15 | 0.5 | 28.155
|  | 2 | 187.7 | 0.45 | 0.5 | 84.465
|  | 1 | 187.7 | 0.75 | 0.5 | 70.3875
|  | 1 | 187.7 | 0.15 | 0.5 | 14.0775
| Yellow fever hos | 2 | 64.7 | 0.15 | 0.5 | 9.705
|  | 2 | 64.7 | 0.45 | 0.5 | 29.115
|  | 1 | 64.7 | 0.75 | 0.5 | 24.2625
|  | 1 | 64.7 | 0.15 | 0.5 | 4.8525
| For manhole | 2 | 3.4 | 0.6 | 2.25 | 9.18
|  | 2 | 2.2 | 0.6 | 2.25 | 5.94
| For Hume pipe,Road crossing | 2 | 7.5 | 0.4 | 1.6 | 9.6
|  | 1 | 7.5 | 2.4 | 0.32 | 5.76
|  | 2 | 7.5 | 0.4 | 1.6 | 9.6
|  | 1 | 7.5 | 2.4 | 0.3 | 5.4
| Plot 2 crossing | 2 | 12.5 | 0.4 | 1.6 | 16
|  | 1 | 12.5 | 2.4 | 0.12 | 3.6
| Yellow fever hos crossing | 2 | 5 | 0.4 | 1.5 | 6
| Road crossings | 6 | 7 | 0.35 | 1.57 | 23.079
[6 empty] | 455.569 | Cumt
8 | P/L cement concrete 1:2:4
PCC for drain
| Between Proj Ent to Proj Exit | 1 | 36 | 2.95 | 0.1 | 10.62
| Drain from Proj Exit to Yellow Fever gate | 1 | 157.7 | 2.95 | 0.1 | 46.5215
| Yellow fever hos | 1 | 34.7 | 2.95 | 0.1 | 10.2365
| PCC for manhole at main road | 1 | 2.5 | 2.5 | 0.1 | 0.625
PCC for comp wall
| Proj off Ent to Proj Exit | 1 | 64.8 | 0.45 | 0.1 | 2.916
| Proj Exit to Yellow Fever gate | 1 | 185.7 | 0.45 | 0.1 | 8.3565
| Plot 2 canteen to Entrance | 1 | 24.1 | 0.45 | 0.1 | 1.0845
| Gate to L&T office | 1 | 36.9 | 0.45 | 0.1 | 1.6605
| L&T to Annawadi | 1 | 37.3 | 0.45 | 0.1 | 1.6785
| Yellow fever hos | 1 | 64.7 | 0.45 | 0.1 | 2.9115
PCC on top of RR masonery
| Proj Exit to Yellow Fever gate | 1 | 185.7 | 0.45 | 0.1 | 8.3565
| L&T to Annawadi | 1 | 36.9 | 0.45 | 0.1 | 1.6605
| Yellow fever hos | 1 | 34.7 | 0.45 | 0.1 | 1.5615
| Ele Panel box fou | 1 | 1.25 | 0.85 | 0.3 | 0.31875
PCC for Paver Block
| Main road | 1 | 27.8 | 1.22 | 0.1 | 3.3916
|  | 1 | 4.41 | 3.5 | 0.1 | 1.5435
|  | 1 | 17.5 | 1.2 | 0.1 | 2.1
| PCC for Footpath | 1 | 21.3 | 1.9 | 0.15 | 6.0705
|  | 1 | 20.22 | 1.9 | 0.15 | 5.7627
| Less Manhole | 8 | 1.1 | 0.8 | 0.15 | -1.06
| PCC for Curb stone wide item no 18 | 1 | 120.1 | 0.15 | 0.1 | 1.8015
For Pole fixing
| Hiranandani plot | 19 | 0.3 | 0.3 | 0.3 | 0.513
| Proj off | 23 | 0.2 | 0.23 | 0.23 | 0.24334
| Plot-2 | 29 | 0.2 | 0.23 | 0.23 | 0.30682
[6 empty] | 119.1807 | Cumt
9 | P/L Ready mix concrete
a)M10
| For Hume pipe,Road crossing | 2 | 7.5 | 1.8 | 0.1 | 2.7
| Plot 2 crossing | 1 | 12.5 | 1.8 | 0.1 | 2.25
| Yellow fever hos crossing | 1 | 5 | 1.8 | 0.1 | 0.9
| Road crossings | 3 | 7 | 1 | 0.1 | 2.1
[6 empty] | 7.95 | Cumt
b)M15 (Encasing)
a)900mm dia hume pipe
| Main rd crossing | 2 | 7.5 | 1.3 | 1.5 | 29.25
| Plot-2 gate crossing | 1 | 12.5 | 1.3 | 1.5 | 24.375
| Less hume pipe | 1 | 27.5 | 0.635 |  | -17.4625
b)600mm dia
| Opp yellow fever hos crossing | 3 | 7 | 1 | 1.2 | 25.2
| Less hume pipe | 1 | 21 | 0.0706 |  | -1.4826
[6 empty] | 59.8799 | Cumt
c)M25 (Slab)
| Main road drain | 1 | 52.3 | 1.5 | 0.15 | 11.7675
| Less Manhole | 8 | 1.1 | 0.8 | 0.15 | -1.06
| Annawadi road corner to Plot-2 gate | 1 | 51.1 | 1.5 | 0.15 | 11.4975
| Less Manhole | 7 | 1.04 | 0.7 | 0.15 | -0.76
| Plot-2 off gate to Annawadi | 1 | 67.3 | 1.5 | 0.15 | 15.1425
| Less Manhole | 7 | 1.04 | 0.7 | 0.15 | -0.76
| Main road to proj Entrance | 1 | 26.8 | 1.5 | 0.15 | 6.03
| Proj Entrance | 1 | 7.07 | 1.5 | 0.23 | 2.4392
| Proj Ent end to proj exit | 1 | 50.66 | 1.5 | 0.15 | 11.3985
| Proj exit | 1 | 7.07 | 1.5 | 0.23 | 2.4392
| Proj Exit to Yellow Fever gate | 1 | 185.7 | 1.5 | 0.15 | 41.7825
| Less Manhole | 29 | 1.04 | 0.7 | 0.15 | -3.17
| Yellow fever hos | 1 | 64.7 | 1.5 | 0.15 | 14.5575
| Less Manhole | 4 | 1.04 | 0.7 | 0.15 | 0.4368
| Yellow Fever Ent | 1 | 4.9 | 1.5 | 0.23 | 1.6905
[6 empty] | 113.4316 | Cumt
10 | Reinforcement
12mm dia bar 100mm c/c
Short Span
| Main road drain i.e 52.30 rmt | 523 | 1.5 |  |  | 784.5
| Annawadi rd corner to Plot-2 gate i.e 52 | 521 | 1.5 |  |  | 781.5
| Plot-2 off gate to Annawadi i.e 67.30 | 674 | 1.5 |  |  | 1011
| Main road to proj Entrance i.e 26.8 | 269 | 1.5 |  |  | 403.5
| Proj Entrance i.e 2 X 7.07 | 144 | 1.5 |  |  | 216
| Proj Ent end to proj exit i.e 50.66 | 508 | 1.5 |  |  | 762
| Proj exit i.e 2 X 7.07 | 144 | 1.5 |  |  | 216
| Proj Exit to Yellow Fever gate i.e 185.70 | 1858 | 1.5 |  |  | 2787
| Yellow fever hos i.e 34.7 | 348 | 1.5 |  |  | 522
| Yellow Fever Ent i.e 2 X 4.90 | 100 | 1.5 |  |  | 150
| Less Manhole i.e 8 | 88 | 0.8 |  |  | -70.4
| Less Manhole i.e 47 | 517 | 0.8 |  |  | -413.6
[6 empty] | 7149.5 | Rmt
| Wt 0.89 Kg/rmt 7149.50 X 0.89 = |  |  |  | a) | 6363.06 | Kgs
10 mm dia bar 150mm c/c
Long Span
| Main road drain i.e 52.30 rmt | 11 | 52.3 |  |  | 575.3
| Lap | 8 | 0.6 |  |  | 4.8
| Annawadi rd corner to Plot-2 gate i.e 52 | 11 | 52 |  |  | 572
| Lap | 8 | 0.6 |  |  | 4.8
| Plot-2 off gate to Annawadi i.e 67.30 | 11 | 67.3 |  |  | 740.3
| Lap | 11 | 0.6 |  |  | 6.6
| Main road to proj Entrance i.e 26.8 | 11 | 26.8 |  |  | 294.8
| Lap | 5 | 0.6 |  |  | 3
| Proj Entrance i.e 2 X 7.07 | 22 | 7.07 |  |  | 155.54
| Proj Ent end to proj exit i.e 50.66 | 11 | 50.66 |  |  | 557.26
| Lap | 9 | 0.6 |  |  | 5.4
| Proj exit i.e 2 X 7.07 | 22 | 7.07 |  |  | 155.54
| Proj Exit to Yellow Fever gate i.e 185.70 | 11 | 185.7 |  |  | 2042.7
| Lap | 31 | 0.6 |  |  | 18.6
| Yellow fever hos i.e 34.7 | 11 | 34.7 |  |  | 381.7
| Lap | 6 | 0.6 |  |  | 3.6
| Yellow Fever Ent i.e 2 X 4.90 | 22 | 4.9 |  |  | 107.8
| Less Manhole i.e 8 | 40 | 1.1 |  |  | -44
| Less Manhole i.e 47 | 235 | 1.04 |  |  | -244.4
[6 empty] | 5341.34 | Rmt
| Wt 0.62 Kg/rmt 7149.50 X 0.89 = |  |  |  | b) | 3311.63 | Kgs
Coping
10 mm dia bar
| Coping on brick work-Item no 17 | 2 | 123.97
Hooks 230 c/c
Cutting Length0.32
| Proj off Ent to Proj Exit i.e 54.42 | 238 | 0.32 |  |  | 76.16
| Plot 2 canteen to Entrance i.e 24.1 | 106 | 0.32 |  |  | 33.92
| Plot-2 gate to Annawadi i.e 37 | 162 | 0.32 |  |  | 51.84
[6 empty] | 161.92 | Rmt
| Wt 0.62 Kg/rmt |  |  |  | c) | 100.39 | Kgs
[6 empty] | 9775.08 | Kgs
11 | Centring & Shuttring
Drain Slab
| Annawadi road corner to main nallah slab | 1 | 47.9 | 0.6 |  | 28.74
| Sides | 2 | 47.9 | 0.15 |  | 14.37
| Slab | 1 | 3.2 | 0.6 |  | 1.92
| Sides | 2 | 3.2 | 0.15 |  | 0.96
| Annawadi road corner to Plot-2 slab | 1 | 51.1 | 0.6 |  | 30.66
| Side | 1 | 51.1 | 0.15 |  | 7.665
| Side | 1 | 27.9 | 0.15 |  | 4.185
| Plot-2 gate to Annawadi | 1 | 69.8 | 0.6 |  | 41.88
|  | 1 | 69.8 | 0.15 |  | 10.47
| Main rd to Proj off Exit | 1 | 91.6 | 0.6 |  | 54.96
|  | 1 | 91.6 | 0.15 |  | 13.74
|  | 2 | 7.07 | 0.23 |  | 3.2522
|  | 2 | 7.07 | 0.08 |  | 1.1312
|  | 1 | 21 | 0.15 |  | 3.15
| Proj off Exit to Yellow Fever hospital | 1 | 187.7 | 0.6 |  | 112.62
|  | 1 | 187.7 | 0.15 |  | 28.155
| Yellow fever hospital | 1 | 64.7 | 0.6 |  | 38.82
|  | 1 | 64.7 | 0.15 |  | 9.705
Hume pipe Encasing
| Main rd crossing | 4 | 7.5 | 1.6 |  | 48
|  | 2 | 12.5 | 1.6 |  | 40
| Opp yellow fever hos crossing | 6 | 7 | 1 |  | 42
Copping above RR masonery
| Proj off Exit to Yellow fever hospital | 2 | 185.7 | 0.15 |  | 55.71
| Plot 2 gate to Annawadi | 2 | 37.3 | 0.15 |  | 11.19
| Yellow fever hospital | 2 | 64.7 | 0.15 |  | 19.41
| Coping on brick work-Item no 17 | 2 | 123.97 | 0.1 |  | 24.794
[6 empty] | 647.4874 | Sqmt
12 | P/L NP-2 hume pipe
a)900mm dia
| Main rd crossing | 2 | 7.5 |  |  | 15
| Plot-2 gate crossing | 1 | 12.5 |  |  | 12.5
[6 empty] | 27.5 | Rmt
b)600mm dia
| Opp yellow fever hos crossing | 3 | 7 |  |  | 21 | Rmt
13 | RR Masonery wall
| Proj off Ent to Proj Exit foundation | 1 | 64.32 | 0.6 | 0.6 | 23.1552
| Proj off Exit to Yellow fever hospital foun | 1 | 185.7 | 0.6 | 0.6 | 66.852
| Wall | 1 | 185.7 | 0.45 | 2.27 | 189.6926
| Plot 2 canteen to Entrance foun | 1 | 24.1 | 0.6 | 0.6 | 8.676
| Plot-2 gate to Annawadi foun | 1 | 74.8 | 0.6 | 0.6 | 26.928
| Wall | 1 | 37.3 | 0.45 | 2.4 | 40.284
| Yellow fever hospital foun | 1 | 64.7 | 0.6 | 0.6 | 23.292
| wall | 1 | 64.7 | 0.45 | 2.27 | 66.091
Drain
| Main rd to Proj off Exit | 2 | 91.6 | 1 | 0.5 | 91.6
|  | 2 | 91.6 | 0.7 | 0.5 | 64.12
|  | 2 | 91.6 | 0.4 | 0.5 | 36.64
| Proj off Exit to Yellow Fever hospital | 2 | 187.7 | 1 | 0.5 | 187.7
|  | 2 | 187.7 | 0.7 | 0.5 | 131.39
|  | 2 | 187.7 | 0.4 | 0.5 | 75.08
| Yellow fever hospital | 2 | 64.7 | 1 | 0.5 | 64.7
|  | 2 | 64.7 | 0.7 | 0.5 | 45.29
|  | 2 | 64.7 | 0.4 | 0.5 | 25.88
| Main rd Manhole | 2 | 2.2 | 0.6 | 2 | 5.28
|  | 2 | 1 | 0.6 | 2 | 2.4
| End of drain | 4 | 0.6 | 0.6 | 1.5 | 2.16
1177.2108
14 | Pointing work on RR Masonery
| Proj off Exit to Yellow fever hospital | 2 | 187.5 |  | 2.27 | 851.25
| Plot-2 gate to Annawadi | 2 | 37.3 |  | 2.4 | 179.04
| Yellow fever hospital | 2 | 64.7 |  | 2.27 | 293.738
[6 empty] | 1324.028 | Sqmt
15 | Brick work in cement morter
| Proj off Ent to Proj Exit | 1 | 54.42 | 0.23 | 1.12 | 14.0186
| Pillers | 23 | 0.4 | 0.1 | 1.12 | 1.0304
| Plot 2 canteen to Entrance | 1 | 24.1 | 0.23 | 1.12 | 6.2082
| Pillers | 8 | 0.4 | 0.1 | 1.12 | 0.3584
| Plot-2 gate to Annawadi | 1 | 36.9 | 0.23 | 1.12 | 9.5054
| Pillers | 16 | 0.4 | 0.1 | 1.12 | 0.7168
| Car parking wall | 1 | 1.1 | 0.23 | 1.2 | 0.3036
|  | 1 | 0.5 | 0.23 | 0.45 | 0.05175
|  | 1 | 0.43 | 0.23 | 0.37 | 0.036593
| Piller | 2 | 0.37 | 0.16 | 1.22 | 0.14445
| Gate opening | 1 | 7.35 | 0.23 | 1.2 | 2.0286
[6 empty] | 34.4028 | Cumt
16 | 15mm Cement plaster
| Proj off Ent to Proj Exit | 2 | 54.42 |  | 1.22 | 132.7848
| Top | 1 | 54.42 |  | 0.25 | 13.605
| Piller jams | 46 | 0.12 |  | 1.22 | 6.7344
| Piller top | 23 | 0.4 |  | 0.12 | 1.104
| Plot 2 canteen to Entrance | 2 | 24.1 |  | 1.22 | 58.804
| Top | 1 | 24.1 |  | 0.25 | 6.025
| Piller jams | 16 | 0.12 |  | 1.22 | 2.3424
| Piller top | 8 | 0.4 |  | 0.12 | 0.384
| Plot-2 gate to Annawadi | 2 | 36.9 |  | 1.22 | 90.036
| Top | 1 | 36.9 |  | 0.25 | 9.225
| Piller jams | 32 | 0.12 |  | 1.22 | 4.6848
| Piller top | 16 | 0.4 |  | 0.12 | 0.768
| Column sides | 24 | 0.5 |  | 2.65 | 31.8
| Column top | 6 | 0.5 |  | 0.5 | 1.5
| RR Masonery patta |  |  |  |  | 0
| Proj off Exit to Yellow fever hospital | 1 | 187.5 |  | 0.7 | 131.25
| Plot-2 gate to Annawadi | 1 | 37.3 |  | 0.7 | 26.11
| Yellow fever hospital | 1 | 64.7 |  | 0.7 | 45.29
| Car parking wall | 1 | 1.1 |  | 1.2 | 1.32
|  | 1 | 0.5 |  | 0.45 | 0.225
|  | 1 | 0.43 |  | 0.37 | 0.1591
| Piller | 2 | 0.37 |  | 1.22 | 0.9028
| Gate opening | 1 | 7.35 |  | 1.2 | 8.82
| Toilet |  |  |  |  | 573.8743 | Sqmt
17 | 100mm coping
| Proj off Ent to Proj Exit | 1 | 54.42 |  |  | 54.42
| Plot 2 canteen to Entrance | 1 | 24.1 |  |  | 24.1
| Plot-2 gate to Annawadi | 1 | 36.9 |  |  | 36.9
| Car parking wall | 1 | 2.3 |  |  | 2.3
| Gate opening | 1 | 7.35 |  |  | 7.35
[6 empty] | 125.07 | Rmt
18 | P/F cement concrete curb stone
| Car parking area | 1 | 5 |  |  | 5
|  | 1 | 10 |  |  | 10
|  | 1 | 1.03 |  |  | 1.03
|  | 1 | 1.8 |  |  | 1.8
|  | 1 | 2.53 |  |  | 2.53
| Garden | 1 | 54.92 |  |  | 54.92
| Foot path | 1 | 24.6 |  |  | 24.6
|  | 1 | 20.22 |  |  | 20.22
[6 empty] | 120.1 | Rmt
19 | P/F S F R C gratting cover of size 1000 X 700
X 50mm
| Foot path | 8 |  |  |  | 8
| Car parking area (Broken) | 6 |  |  |  | 6
[6 empty] | 14 | Nos
20 | P/F S F R C gratting cover of size 1000 X 1000
| X 100mm | 1 |  |  |  | 1 | No
21 | P/F S F R C gratting cover of size 1200 X 1000
| X 100mm | 1 |  |  |  | 1 | No
22 | P/F S F R C gratting cover of size 1070 X 670
X 100mm
| Main rd to Annawadi | 14 |  |  |  | 14
| Main rd to Yellow fever | 29 |  |  |  | 29
| Yellow Fever hos | 4 |  |  |  | 4
[6 empty] | 47 | Nos
23 | P/F Paver block
a) 60mm thk
| Main rd Footpath | 1 | 21.3 | 1.9 |  | 40.47
|  | 1 | 20.22 | 1.9 |  | 38.418
| Less Manhole | 8 | 1.1 | 0.8 |  | -7.04
[6 empty] | 71.848 | Sqmt
b)100mm thk
| Main road | 1 | 27.8 | 1.5 |  | 41.7
|  | 1 | 4.41 | 3.5 |  | 15.435
|  | 1 | 17.5 | 1.5 |  | 26.25
[6 empty] | 83.385 | Sqmt
24 | Fixing St Steel grill
| Proj off | 1 | 52.4 |  | 1.5 | 78.6
| Plot-2 | 1 | 24.1 |  | 1.5 | 36.15
|  | 1 | 36.9 |  | 1.5 | 55.35
| Yellow fever hos | 1 | 64.7 |  | 1.3 | 84.11
| Garden | 1 | 54.92 |  | 0.6 | 32.952
| Gate of Hiranandani | 1 | 4.5 |  | 2.4 | 10.8
[6 empty] | 297.962 | Sqmt
25 | Fixing chainlink fencing
| Main road Hiranandani plot | 1 | 28.45 |  | 2.4 | 68.28
|  | 1 | 17.8 |  | 2.4 | 42.72
| Car parking area | 1 | 24.1 |  | 1.2 | 28.92
|  | 1 | 30 |  | 1.2 | 36
[6 empty] | 175.92 | Sqmt
26 | P/F Chainlink fencing
| Car parking area | 1 | 80.2 |  | 1.25 | 100.25
| Ele Panel box | 1 | 2.9 |  | 1.25 | 3.625
[6 empty] | 103.875 | Sqmt
27 | Steel work
Angle 50 X 50 X 6mm
| Car parking area fencing Post | 13 | 1.5 |  |  | 19.5 | Rmt
| Wt 4.50 Kg/rmt |  |  |  | a) | 87.75 | Kgs
Angle 40 X 40 X 6mm
| Car parking area fencing Post | 17 | 1.5 |  |  | 25.5
|  | 2 | 80.2 |  |  | 160.4
| Ele Panel box Post | 4 | 1.5 |  |  | 6
| Clits | 34 | 0.15 |  |  | 5.1
| Clits for Pipe poles | 77 | 0.15 |  |  | 11.55
[6 empty] | 208.55 | Rmt
| Wt 3.5 Kg/rmt |  |  |  | b) | 729.93 | Kgs
ISMC 150 X 75
| To support cover | 2 | 1.8 |  |  | 3.6
| Wt 16.80 Kg/rmt |  |  |  | c) | 60.48
| For Yellow fever Gate approx |  |  |  | d) | 1100 | Kgs
[6 empty] | 1978.16 | Kgs
28 | P/F welding C class GI pipe
a)50mm dia pipe
| Proj off | 23 | 1.5 |  |  | 34.5
| Plot-2 | 11 | 1.5 |  |  | 16.5
|  | 18 | 1.5 |  |  | 27
[6 empty] | 78 | Rmt
b)32 mm dia pipe
| Garden area | 25 | 0.9 |  |  | 22.5 | Rmt
29 | Painting two coats of synthetic enamal paint
St Steel grill
| Proj off | 2 | 52.4 |  | 1.5 | 157.2
| Plot-2 | 2 | 24.1 |  | 1.5 | 72.3
|  | 2 | 36.9 |  | 1.5 | 110.7
| Yellow fever hos | 2 | 64.7 |  | 1.3 | 168.22
| Garden | 2 | 54.92 |  | 0.6 | 65.904
Chainlink fencing
| Car parking area | 2 | 80.2 |  | 1.25 | 200.5
| Ele Panel box | 2 | 2.9 |  | 1.25 | 7.25
[6 empty] | 782.074 | Sqmt
30 | Disposal of bldg debris
Total excavation for drain & wall wide item
| No 5 | 1 | 1862.87 |  |  | 1862.9
| Refilling of earth wide item No 7 | 1 | 465.17 |  |  | -465.17
[6 empty] | 1397.73 | Cumt
31 | Credit of stone
| Dismentling of RR wall wide item no 3 | 1 | 567.81 |  |  | 567.81
| 50 % stone obtained from above i.e 567.81 X50% = |  |  |  |  | 283.9 | Cumt