## Summry
|  | Helper (950Rs per day) | Technician-1 (1150Rs per day) | Technician-2 (1150Rs per day) | Amount
| IDLI.COM | 10 | 32 | 2 | 48800
| FISHERMAN SITE | 9.5 | 32.5 | 2 | 48900
| NOURISH | 6.5 | 30 | 2 | 43175
| JHAKKAS | 7 | 31 | 2 | 44800
| Baker shack | 6 | 29 | 1.5 | 40925
| Cafechino | 6 | 29 | 1 | 40300
266900
ARROW ELECTRICAL
SITE:ALL MOPA AIRPOT
S.N | Description | UNIT | AMOUNT
1 | Supply material For all outlet | INR | 242330
2 | December-22 labour charge | INR | 92700
3 | January -23 labour charge | INR | 123825
4 | February-23 Labour charge | INR | 50375
| Grand total |  | 509230
|  | GST | 18%
91661.4
| Total with Gst |  | 600891.4

## Supply
M/s. ARROW ELECTRICAL
SUB:Material supply bill
Client : | TFS | DATE: |  | 2023-01-24
Name of Site: | MOPA AIRPOT GOA
Nature of Work: | Electrical Works
S.NO | Description | Unit | QTY | RATE | AMOUNT | Remark
I | IDLI.COM
a | sitc 6/16A Socket outlet - 1Nos. & 16A Switch - 1Nos.(Raw/UPS Power) | nos | 24 | 770 | 18480 | Ret ref-central kitchen:PO/MOPA/22-23/000250
b | sitc secondary light loop point | nos | 9 | 1250 | 11250 | Ret ref-central kitchen:PO/MOPA/22-23/000250
c | sitc 32 amps 4P MCB with 32A 5 Pin Ray Roll Socket complete with all mounting accessories waterproof (IP-65) | nos | 2 | 14000 | 28000 | Ret ref-central kitchen:PO/MOPA/22-23/000250
d | sitc 32A 4P MCB Add on in DB | nos | 2 | 1450 | 2900 | Ret ref-central kitchen:PO/MOPA/22-23/000250
e | 15 amp top for equipment | nos | 2 | 150 | 300
f | 25 mm gi conduit with all accessories | MTR | 3 | 220 | 660 | Ret ref-central kitchen:PO/MOPA/22-23/000250
f | 25 mm gi Flexibale with all accessories | MTR | 6 | 60 | 360 | Ret ref-central kitchen:PO/MOPA/22-23/000250
g | Labour Supply - Helper | No of days | 10
| Labour Supply - Tech -1 | No of days | 32
| Labour Supply - Tech -2 | No of days | 2
CCTV
a | RG-6 cu cable polycab handover by ajmal | MTR | 200 | 52 | 10400
b | RG-6 cu cable polycab for cctv | MTR | 300 | 52 | 15600
C | 2cx 1.5 sq mm polycab frls wire for cctv | MTR | 200 | 45 | 9000
| Taging All DB and switch socket (Total outlet-7) | No | 1
ii | FISHERMAN SITE
a | sitc 6/16A Socket outlet - 1Nos. & 16A Switch - 1Nos.(Raw/UPS Power) | nos | 31 | 770 | 23870 | Ret ref-central kitchen:PO/MOPA/22-23/000250
b | 15 amp top for equipment | nos | 1 | 150 | 150
c | 3 mod pvc back box | nos | 1 | 80 | 80
iii | NOURISH
a | sitc 6/16A Socket outlet - 1Nos. & 16A Switch - 1Nos.(Raw/UPS Power) | NOS | 29 | 770 | 22330 | Ret ref-central kitchen:PO/MOPA/22-23/000250
b | sitc 5/15 Top for equipment | NOS | 5 | 150 | 750
iv | JHAKKAS
a | sitc 6/16A Socket outlet - 1Nos. & 16A Switch - 1Nos.(Raw/UPS Power) | nos | 6 | 770 | 4620 | Ret ref-central kitchen:PO/MOPA/22-23/000250
b | sitc 5/15 top | nos | 5 | 150 | 750
c | 3 mod pvc back box | nos | 2 | 80 | 160
v | Baker shack
a | 6/16A Socket outlet - 1Nos. & 16A Switch - 1Nos.(Raw/UPS Power) | nos | 35 | 770 | 26950 | Ret ref-central kitchen:PO/MOPA/22-23/000250
b | 5/15 top | nos | 3 | 150 | 450
c | Hanging light | nos | 7 | 220 | 1540
d | DB dressing charge | nos | 1 | 2500 | 2500
e | 10 sq mm cu wire for db dressing | mtr | 16 | 180 | 2880
vi | Cafechino
a | sitc 4+1 power strip (fuse+mov)3mtr wire | nos | 2 | 1250 | 2500
b | sitc 6/16A Socket outlet - 1Nos. & 16A Switch - 1Nos.(Raw/UPS Power) | nos | 4 | 770 | 3080 | Ret ref-central kitchen:PO/MOPA/22-23/000250
c | Mcb dummy | nos | 6 | 45 | 270
VII | Supply, of RG 6 Cable for CCTV mention in idli.com
a | RG-6 cu cable polycab handover by ajmal | MTR | 200 | 52 | 10400
b | RG-6 cu cable polycab for cctv | MTR | 300 | 52 | 15600
C | 2cx 1.5 sq mm polycab frls wire for cctv | MTR | 200 | 45 | 9000
VIII | Taging All DB and switch socket (Total outlet-7) | NOS | 7 | 2500 | 17500
Total amount |  |  |  |  | 242330
Sign |  |  | Sign | …...........................
CERTIFIED BY |  |  |  | Accepted By
Knight Frank |  |  |  | Arrow Electricals
IDLI.COM
FISHERMAN SITE
NOURISH
JHAKKAS
Baker shack
Cafechino

## DEC-22
ARROW ELECTRICAL |  |  | LABOUR ATTANDANCE FOR OTHER OUTLETS WORK IN DECEMBER 2022 MOPA GOA
S.N. | NAME | CATEGORY | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04 | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2022-12-31 | PRESENT | RATE | ACCOUNT | REMARKS
1 | ASHOK SOLKAR | ELECTRICIAN | 1 | 2 | 2 | 2 | 1.5 | 2 | 1.5 |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 1 | 1 |  | 1.5 | 2 | 1.5 | 1.5 | 1.5 | 29 | 1150 | 33350
2 | ASHOK SUDH | ELECTRICIAN | 1 | 2 | 2 | 2 | 1.5 | 2 | 1.5 |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 1 | 1 |  | 1.5 | 2 | 1.5 | 1.5 | 1.5 | 29 | 1150 | 33350
3 | MANISH | ELECTRICIAN | 2022-12-27: 1.5; 2022-12-28: 2; 2022-12-29: 1.5; 2022-12-30: 1.5; 2022-12-31: 1.5 | 8 | 1150 | 9200
4 | ANANT | ELECTRICIAN | 2022-12-27: 1.5; 2022-12-28: 2; 2022-12-29: 1.5; 2022-12-30: 1.5; 2022-12-31: 1.5 | 8 | 1150 | 9200
5 | Ratnakar | ELECTRICIAN | 2022-12-27: 1.5; 2022-12-28: 2; 2022-12-29: 1.5; 2022-12-30: 1.5; 2022-12-31: 1.5 | 8 | 950 | 7600
TOTAL | [35 empty] | 92700
| Sign | [33 empty] | Sign | ….............................
| CERTIFIED BY | [33 empty] | Accepted By
| Knight Frank |  | 2022-12-01: helper man hr; 2022-12-02: technician man hr |  | Arrow Electricals
| SITE NAME | IDLI.COM | 2022-12-01: 2; 2022-12-02: 13; 2022-12-03: 16850
|  | FISHERMAN SITE | 2022-12-01: 2; 2022-12-02: 13; 2022-12-03: 16850
|  | NOURISH | 2022-12-01: 1; 2022-12-02: 12; 2022-12-03: 14750
|  | JHAKKAS | 2022-12-01: 1; 2022-12-02: 12; 2022-12-03: 14750
|  | Baker shack | 2022-12-01: 1; 2022-12-02: 12; 2022-12-03: 14750
|  | Cafechino | 2022-12-01: 1; 2022-12-02: 12; 2022-12-03: 14750
|  |  | 82 days |  | 92700
1.5

## JAN 23
ARROW ELECTRICAL |  |  | LABOUR ATTANDANCE FOR OTHER OUTLETS WORK IN JAN 2023 MOPA GOA
S.N. | NAME | CATEGORY | 2023-01-01 | 2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-06 | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | PRESENT | RATE | ACCOUNT | REMARKS
1 | ASHOK SOLKAR | ELECTRICIAN | 1 | 1.5 | 3.5 | 1.5 | [6 empty] | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 24 | 1150 | 27600
2 | ASHOK SUDH | ELECTRICIAN | 2 | 1.5 | 3.5 | 1.5 | [6 empty] | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 23 | 1150 | 26450
3 | MANISH | ELECTRICIAN | 2023-01-01: 2; 2023-01-02: 1.5; 2023-01-03: 3.5; 2023-01-04: 1.5; 2023-01-25: 1; 2023-01-26: 1 | 10.5 | 1250 | 13125
4 | ANANT | ELECTRICIAN | 2 | 1.5 | 3.5 | 1.5 | [6 empty] | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 25 | 1150 | 28750
5 | Ratnakar | ELECTRICIAN | 2023-01-01: 2; 2023-01-02: 1.5; 2023-01-03: 3.5; 2023-01-04: 1.5 | 8.5 | 950 | 8075
6 | Arvind | ELECTRICIAN | 2023-01-02: 1.5; 2023-01-03: 3.5; 2023-01-04: 1.5 | 6.5 | 1150 | 7475
7 | pachoo | ELECTRICIAN | 2023-01-02: 1.5; 2023-01-03: 3.5; 2023-01-04: 1.5 | 6.5 | 950 | 6175
8 | ajay | ELECTRICIAN | 2023-01-02: 1.5; 2023-01-03: 3.5; 2023-01-04: 1.5 | 6.5 | 950 | 6175
TOTAL | [32 empty] | 123825
| Sign | [29 empty] | Sign | ….............................
| CERTIFIED BY | [29 empty] | Accepted By
| Knight Frank | [29 empty] | Arrow Electricals
|  |  | 3.5833 | 10.5 | 13.0833
| SITE NAME | IDLI.COM | 2023-01-01: 5; 2023-01-02: 2; 2023-01-03: 13; 2023-01-04: 22200
|  | FISHERMAN SITE | 2023-01-01: 4.5; 2023-01-02: 2; 2023-01-03: 13.5; 2023-01-04: 22300
|  | NOURISH | 2023-01-01: 3; 2023-01-02: 2; 2023-01-03: 13; 2023-01-04: 20300
|  | JHAKKAS | 2023-01-01: 3; 2023-01-02: 2; 2023-01-03: 13; 2023-01-04: 20300
|  | Baker shack | 2023-01-01: 3; 2023-01-02: 1.5; 2023-01-03: 13; 2023-01-04: 19675
|  | Cafechino | 2023-01-01: 3; 2023-01-02: 1; 2023-01-03: 13; 2023-01-04: 19050
123825
1.5

## Feb 23
ARROW ELECTRICAL |  |  | LABOUR ATTANDANCE FOR OTHER OUTLETS WORK IN FEB 2023 MOPA GOA
S.N. | NAME | CATEGORY | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18 | 2023-02-19 | 2023-02-20 | 2023-02-21 | 2023-02-22 | PRESENT | RATE | ACCOUNT | REMARKS
1 | ASHOK SOLKAR | ELECTRICIAN | 2023-02-01: 1.5; 2023-02-02: 1; 2023-02-03: 1.5; 2023-02-04: 2; 2023-02-05: 1; 2023-02-06: 1; 2023-02-07: 1; 2023-02-08: 1.5; 2023-02-09: 1; 2023-02-10: 1; 2023-02-11: 1; 2023-02-12: 1; 2023-02-13: 1 | 15.5 | 1150 | 17825
2 | ASHOK SUDH | ELECTRICIAN | [22 empty] | 0 | 1150 | 0
3 | MANISH | ELECTRICIAN | [22 empty] | 0 | 1250 | 0
4 | ANANT | ELECTRICIAN | 2023-02-01: 1.5; 2023-02-02: 1; 2023-02-03: 1.5; 2023-02-04: 2; 2023-02-05: 1; 2023-02-06: 1; 2023-02-07: 1; 2023-02-08: 1.5; 2023-02-09: 1; 2023-02-10: 1; 2023-02-11: 1; 2023-02-12: 1; 2023-02-13: 1 | 15.5 | 1150 | 17825
5 | Ratnakar | ELECTRICIAN | 2023-02-01: 1.5; 2023-02-02: 1; 2023-02-03: 1.5; 2023-02-04: 2; 2023-02-05: 1; 2023-02-06: 1; 2023-02-07: 1; 2023-02-08: 1.5; 2023-02-09: 1; 2023-02-10: 1; 2023-02-11: 1; 2023-02-12: 1; 2023-02-13: 1 | 15.5 | 950 | 14725
TOTAL | [26 empty] | 50375
| Sign | [23 empty] | Sign | ….............................
| CERTIFIED BY | [23 empty] | Accepted By
| Knight Frank | Project Engineer | [22 empty] | Arrow Electricals
| SITE NAME | IDLI.COM | 2023-02-01: 3; 2023-02-02: 6; 2023-02-03: 9750
|  | FISHERMAN SITE | 2023-02-01: 3; 2023-02-02: 6; 2023-02-03: 9750
|  | NOURISH | 2023-02-01: 2.5; 2023-02-02: 5; 2023-02-03: 8125
|  | JHAKKAS | 2023-02-01: 3; 2023-02-02: 6; 2023-02-03: 9750
|  | Baker shack | 2023-02-01: 2; 2023-02-02: 4; 2023-02-03: 6500
|  | Cafechino | 2023-02-01: 2; 2023-02-02: 4; 2023-02-03: 6500
50375
1.5