## NT Item
HYD_FF25a_Millies Cookies_Civil & Interior_NT Items |  |  | Joint Measurement Sheet
S.N | Category | Item Name | UOM | Length | Width | Height | Nos | Qty
1 | Civil | Wall Plaster work on AAC block work upto 13-18 mm | SQM |  |  |  |  | 72.104
|  | Entry Left Box |  | 1.2 | 3.2 |  | 1 | 3.84
|  | Entry Left Box |  | 2.11 | 3.2 |  | 1 | 6.752
|  | Centre Box |  | 0.67 | 3.2 |  | 4 | 8.576
|  | Centre Box |  | 1.72 | 3.2 |  | 2 | 11.008
|  | DB wall |  | 5.3 | 3.2 |  | 2 | 33.92
|  | less Door |  | 0.62 | 1.8 |  | -2 | -2.232
|  | Partition Wall |  | 1.6 | 3.2 |  | 2 | 10.24
2 | Civil | Screed - Supply and install screed upto thickness 100 as required to raise floor level | SQM |  |  |  |  | 70.235
|  | Sitting Area |  | 2.3 | 0.45 |  | 1 | 1.035
|  | Sitting Area |  | 0.3 | 1.2 |  | 1 | 0.36
|  | Sitting Area |  | 3.6 | 1.75 |  | 1 | 6.3
|  | Sitting Area |  | 2.13 | 1.2 |  | 1 | 2.556
|  | Sitting Area |  | 0.4 | 1.75 |  | 1 | 0.7
|  | Sitting Area |  | 3.67 | 1.2 |  | 1 | 4.404
|  | Sitting Area |  | 3.7 | 0.6 |  | 1 | 2.22
|  | Sitting Area |  | 1 | 0.85 |  | 1 | 0.85
|  | Sitting Area |  | 3 | 4.5 |  | 1 | 13.5
|  | Sitting Area |  | 3 | 1.2 |  | 1 | 3.6
|  | Counter Area |  | 9 | 0.9 |  | 1 | 8.1
|  | Counter Area |  | 2.3 | 0.3 |  | 1 | 0.69
|  | Kitchen Area |  | 9.6 | 2.4 |  | 1 | 23.04
|  | Kitchen Area |  | 9.6 | 0.3 |  | 1 | 2.88
3 | Interior | 3D CNC cut pattern front of counter in PU paint finish | SQFT |  |  |  |  | 83
4 | Interior | 3D pattern Above Bulkhead paneling with PU finish | SQFT |  |  |  |  | 399.225
|  | Left |  | 5330 | 1200 |  | 1 | 68.8482
|  | Front |  | 12360 | 1700 |  | 1 | 226.1787
|  | Right |  | 4400 | 2200 |  | 1 | 104.1981
5 | Interior | Paneling at cornor at videowall (PLY + Black Paint ) | SQFT | 1980 | 3000 |  | 1 | 63.9397
6 | Interior | Guard Rail 38mm SS 304 pipe | RM | 12.07 |  |  | 1 | 12.07
7 | Interior | SS Skirting -100 mm height | RM | 20.26 |  |  | 1 | 20.26
8 | Interior | Front Façade - Wall Paneling - 12mm ply | SQFT |  |  |  |  | 371.4984
|  | Front Wall - Out side |  | 12360 | 3000 |  | 1 | 399.1389
|  | Front wall - Inside |  | 9600 | 3000 |  | 1 | 310.0108
|  | less Arch 1 |  | 3700 | 2090 |  | -2 | -166.4801
|  | Less arch 1 - fluted glass |  | 620 | 3100 |  | -2 | -41.3778
|  | Less Arch 2 |  | 3630 | 2090 |  | -2 | -163.3305
|  | Less Arch 2 Fluted Glass |  | 620 | 3100 |  | -2 | -41.3778
|  | Entry Wall - - Front side |  | 4400 | 3000 |  | 1 | 142.0883
|  | Entry Wall - Back Side |  | 3800 | 3000 |  | 1 | 122.7126
|  | Less arch |  | 3400 | 2100 |  | -2 | -153.7137
|  | Less Arch Fluted glass |  | 620 | 2710 |  | -2 | -36.1722
9 | Interior | Bulkhead MS Cladding back side paneliing HDHMR 12 mm | SQFT |  |  |  |  | 113.8859
|  | Front |  | 12360 | 500 |  | 1 | 66.5231
|  | Right |  | 4400 | 1000 |  | 1 | 47.3628
10 | Interior | Door Frame - DB Box - 130 mm Wide - Ply | RFT | 4.46 |  |  |  | 4.46
11 | Interior | Door With louvers in DB room - Size 1800x630mm | Nos | 1 |  |  |  | 1
12 | Interior | Wall Paneling 12mm ply inside of outlet | SQFT |  |  |  |  | 88.1593
|  | Entry Box Wall - Inside |  | 2030 | 3000 |  | 1 | 65.5544
|  | Entry Box Wall - Inside |  | 700 | 3000 |  | 1 | 22.605
13 | Plumbing | Sink - Rear Counter | Nos | 1 |  |  |  | 1 | 18x16x8 mm SS Sink Heavy Duty
14 | Plumbing | Mixer at Water Sink | Nos | 2 |  |  |  | 2 |  | Parrywere -G4715 DROPLATE BASIN MIXER
15 | Electrical | Rubber Mat Size - 1300x800mm | Nos | 1 |  |  |  | 1
16 | Sprinkler | Flexible Pipe -Sink Bottom + Bottle Tap | Nos | 1 |  |  |  | 1
17 | Elcetrical | Installation of Light type -1 | Nos | 6 |  |  |  | 6
|  | Installation of Light type -2 | Nos | 8 |  |  |  | 8
|  | Installation of Light type -3 | Nos | 7 |  |  |  | 7
Jaguar - AQT-CHR-3057P
18 | Plumbing | Angle Valve | Nos | 6 |  |  |  | 6
19 | Plumbing | Flexible Pipe ( Gyser 2 ft ) | Nos | 2 |  |  |  | 2
20 | Sprinkler | Sprinkler - Flexible pipe - 1500 mm | Nos | 8 |  |  |  | 8
21 | Elcetrical | Camera Wiring point till DB room ( Cat 6A Wiring With Conduit ) | Nos | 3 |  |  |  | 3 | 42 RMT
22 | Elcetrical | CAT -6A wiring point at counter for POS & Internet ( Counter to DB Room with conduit ) | Nos | 4 |  |  |  | 4 | 37 RMT
23 | Electrical | Wire Manager ( POS + Coffee Machine ) | Nos | 2 |  |  |  | 2
24 | Barricade | LHS Wall Extension | Sqft | 10 | 16 |  | 1 | 160
|  | Back LHS Extension | Sqft | 11 | 10 |  | 1 | 110
|  | Back RHS Extension | Sqft | 13 | 16 |  | 1 | 208
|  | Above 8ft Flex Back Side | Sqft | 45 | 4 |  | 1 | 180
|  | Back Centre Barricade Extension | Sqft | 7 | 10 |  | 1 | 70
25 | Barricade | Removal of barricade | Lot | 1 |  |  |  | 1 | Done by GHL Vendor | Accept
26 | Mis | Provide shutter and partion along with shelf in read counter | Sq Ft |  |  |  |  | 19.0715 | Qty in Sq ft
|  | Front shutter |  | 655 | 760 |  | 1 | 5.3584
|  | Partition |  | 900 | 783 |  | 1 | 7.5856
|  | Shelf |  | 727 | 783 |  | 1 | 6.1275