## Summary Sheet
Summary of Carl's Jr.
SL NO. | Description | As Per PO | Executed Amount | NT Items | Deviation
1 | Civil & Interior | 4436610.38 | 4647967.135 |  | 211356.755
2 | Plumbing | 296350 | 265095 |  | -31255
3 | Ad. Plumbing Work | 7100
3 | NT Items |  |  | 395076.1 | 395076.1
Total |  | 4740060.38 | 4913062.135 | 395076.1 | 575177.855
Summary of Carl's Jr.
SL NO. | Description | As Per PO | Executed Amount | Billing | Fresh PR
1 | Civil & Interior | 4436610.38 | 4647967.135 | 4249328.1296 | 398639.0054
2 | Plumbing | 296350 | 265095 | 265095
3 | Ad. Plumbing Work | 7100
3 | NT Items |  |  |  | 395076.1
Total |  | 4740060.38 | 4913062.135 | 4514423.1296 | 793715.1054

## ID
|  | Interior works for Carls Jr FF 018 HYD |  |  |  | As per PO | Vendor Name : Impulse Branding | Executed | Vendor Name : Impulse Branding | Discussed for Billing |  | PR
Sr No. | Item Code | Item Name | Item Description | UOM | Qty | Unit Price | Amount | Qty | Amount
1 |  | ID | ID | NOS | 1 |  | 4436610.38 |  | 4647967.135 |  | 4249328.1296 |  | 398639.0054
1 |  | SECTION 1 - PRELIMINARIES | SECTION 1 - PRELIMINARIES
2 | 1.01 | Insurance (EC CAR) | Insurance (EC CAR) | Sum | 1 | 5600
3 | 1.02 | Site setting-out | Site setting-out | Sum | 1 | 45000
4 | 1.03 | Supervision and Coordination with Other trades | Supervision and Coordination with Other trades | Sum | 1 | 56000
5 | 1.04 | Supply, install and demolish the hoarding | Supply, install and demolish the hoarding | Sum | 1 | 35000
6 | 1.05 | General protection works to the existing finishes | General protection works to the existing finishes | Sum | 1 | 25000
7 | 1.06 | Make good the all affected surround area | Make good the all affected surround area | Sum | 1 | 32000
8 | 1.07 | Daily cleaning and waste disposal | Daily cleaning and waste disposal | Sum | 1 | 45000
9 | 1.08 | Final cleaning and waste disposal | Final cleaning and waste disposal | Sum | 1 | 25000
10 | 1.09 | Statutory Obligations, Regulations and Specification | Statutory Obligations, Regulations and Specification | Sum | 1 | 20000
11 | 1.10 | Provision of as-built drawings upon completion of works | Provision of as-built drawings upon completion of works | Sum | 1 | 45000
12 | 1.11 | To comply with the fitting-out house rules | To comply with the fitting-out house rules | Sum | 1 | 35000
13 | 1.12 | India Construction Sites (Safety) Regulations | India Construction Sites (Safety) Regulations | Sum | 1 | 25000
14 | 1.13 | Safety Precautions | Safety Precautions | Sum | 1 | 40000
15 | 1.14 | Samples, finishes, drawings submission to relevant parties | Samples, finishes, drawings submission to relevant parties | Sum | 1 | 55000
16 | 1.15 | Others (Please list the items in details) | Others (Please list the items in details) | Sum | 1 | 14000
17 |  | SECTION 2 - WALL AND PARTITIONING | SECTION 2 - WALL AND PARTITIONING
18 | 2.01 | Supply and installation of masonry wall of thickness as indicated, as per drawings and as per the approved manufacturer s specifications including all necessary consumables, supports and fittings, all complete in all aspects in accordance with instruction | Supply and installation of masonry wall of thickness as indicated, as per drawings and as per the approved manufacturer s specifications including all necessary consumables, supports and fittings, all complete in all aspects in accordance with instruction
19 | a | 100mm thick masonry wall including 100X100 Mm Concrete Framing (M.20 Mix With Nominal Reinforcements) | 100mm thick masonry wall including 100X100 Mm Concrete Framing (M.20 Mix With Nominal Reinforcements) | Sqm | 64.33 | 1674 | 107688.42 | 97.3833 | 163019.6442 | 64 | 107136 | 33.3833 | 55883.6442
20 | 2.02 | Supply and installation of dry wall partition of thickness as indicated, as per drawings and as per the approved manufacturer s specifications including all necessary consumables, supports and fittings, all complete in all aspects in accordance with instr | Supply and installation of dry wall partition of thickness as indicated, as per drawings and as per the approved manufacturer s specifications including all necessary consumables, supports and fittings, all complete in all aspects in accordance with instr
21 | a | 50mm thick dry wall partition (height upto true ceiling) | 50mm thick dry wall partition (height upto true ceiling) | Sqm | 12.03 | 5130 | 61713.9 | 30.408 | 155993.04 | 12 | 61560 | 18.408 | 94433.04
22 |  | SECTION 3 - FINISHING AND WATERPROOFING | SECTION 3 - FINISHING AND WATERPROOFING
23 | 3.01 | Waterproofing - Supply and install approved waterproofing system to kitchen with testing, warranty, in accordance withthe drawings and specifications(Sample is subject to Employer s approval) Dwg ref 02GA-103A | Waterproofing - Supply and install approved waterproofing system to kitchen with testing, warranty, in accordance withthe drawings and specifications(Sample is subject to Employer s approval) Dwg ref 02GA-103A | Sqm | 75.25 | 1836 | 138159 | 54 | 99144 | 54 | 99144
24 | 3.02 | Screed - Supply and install screed (upto thickness as provided in the drawing) as approved in accordance with the drawings and specifications Dwg ref 02GA-10 | Screed - Supply and install screed (upto thickness as provided in the drawing) as approved in accordance with the drawings and specifications Dwg ref 02GA-10 | Sqm | 53.52 | 1250 | 66900 | 54 | 67500 | 54 | 67500
25 | 3.03 | Flooring - Supply and install [FL01] - 600x1200mm Concrete Ceramic Floor Tile including all necessary consumables in accordance with the drawings and specifications. Dwg ref 02GA-103 | Flooring - Supply and install [FL01] - 600x1200mm Concrete Ceramic Floor Tile including all necessary consumables in accordance with the drawings and specifications. Dwg ref 02GA-103 | Sqm | 49.31 | 2916 | 143787.96 | 80 | 233280 | 49 | 142884 | 31 | 90396
26 | 3.04 | Flooring - Supply and install [FL02] - 560x560mm Grey Colour Kota Stone including all necessary consumables in accordance with the drawings and specifications Dwg ref 02GA-103 | Flooring - Supply and install [FL02] - 560x560mm Grey Colour Kota Stone including all necessary consumables in accordance with the drawings and specifications Dwg ref 02GA-103 | Sqm | 77.81 | 2646 | 205885.26 | 54 | 142884 | 54 | 142884
27 | 3.05 | Flooring - Supply and install [FL03] - S.S Floor Reducer Trim including all necessary consumables in accordance with the drawings and specifications Dwg ref 02GA-103 | Flooring - Supply and install [FL03] - S.S Floor Reducer Trim including all necessary consumables in accordance with the drawings and specifications Dwg ref 02GA-103 | Rmt | 31.8 | 1250 | 39750 | 34.1 | 42625 | 32 | 40000 | 2.1 | 2625
28 | 3.06 | Flooring - Supply and install [FL04] - S.S Floor Cover Trim including all necessary consumables in accordance with the drawings and specifications Dwg ref 02GA-103 | Flooring - Supply and install [FL04] - S.S Floor Cover Trim including all necessary consumables in accordance with the drawings and specifications Dwg ref 02GA-103 | Rmt | 0.9 | 1350 | 1215 | 0 | 0 | 0
29 | 3.07 | Ceiling - Supply and install Gypsum ceiling with paint [CL01] including all necessary fitting, supports, accessories, consumables, opening,etc.in accordance with the drawings and specifications Dwg ref 02GA-104 | Ceiling - Supply and install Gypsum ceiling with paint [CL01] including all necessary fitting, supports, accessories, consumables, opening,etc.in accordance with the drawings and specifications Dwg ref 02GA-104 | Sqm | 11.49 | 2538 | 29161.62 | 11 | 27918 | 11 | 27918
30 | 3.08 | Ceiling - Supply and install Gypsum ceiling with paint [CL02] including all necessary fitting, supports, accessories, consumables, opening,etc.in accordance with the drawings and specifications Dwg ref 02GA-104 | Ceiling - Supply and install Gypsum ceiling with paint [CL02] including all necessary fitting, supports, accessories, consumables, opening,etc.in accordance with the drawings and specifications Dwg ref 02GA-104 | Sqm | 47 | 2538 | 119286 | 47 | 119286 | 47 | 119286
31 | 3.09 | Ceiling - Supply and install Grid ceiling amstrong Equivalent [CL03] including all necessary fitting, supports, accessories, consumables, opening,etc.in accordance with the drawings and specifications Dwg ref 02GA-104 | Ceiling - Supply and install Grid ceiling amstrong Equivalent [CL03] including all necessary fitting, supports, accessories, consumables, opening,etc.in accordance with the drawings and specifications Dwg ref 02GA-104 | Sqm | 46.34 | 2430 | 112606.2 | 46 | 111780 | 46 | 111780
32 | 3.10 | Ceiling - Supply and install Baffle Ceiling including all necessary fitting, supports, accessories, consumables, opening,etc.in accordance with the drawings and specifications Dwg ref 02GA-104 | Ceiling - Supply and install Baffle Ceiling including all necessary fitting, supports, accessories, consumables, opening,etc.in accordance with the drawings and specifications Dwg ref 02GA-104 | Sqm | 46.34 | 5940 | 275259.6 | 60 | 356400 | 46 | 273240 | 14 | 83160
33 | 3.11 | Wall - Supply and install [WP01] - Old whitewood imitation panels claddings to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Wall - Supply and install [WP01] - Old whitewood imitation panels claddings to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Sqm | 18.08 | 7020 | 126921.6 | 22.1 | 155142 | 18 | 126360 | 4.1 | 28782
34 | 3.12 | Wall - Supply and install [WP02] Grey Painted Brick Imitation Panels Claddings to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Wall - Supply and install [WP02] Grey Painted Brick Imitation Panels Claddings to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Sqm | 13.15 | 7020 | 92313 | 13.6804 | 96036.408 | 13 | 91260 | 0.6804 | 4776.408
35 | 3.13 | Wall - Supply and install [PT04] - Grey Colour Paint TAL 7022 to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Wall - Supply and install [PT04] - Grey Colour Paint TAL 7022 to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Sqm | 59.4 | 713 | 42352.2 | 67.2764 | 47968.0732 | 59 | 42067 | 8.2764 | 5901.0732
36 | 3.14 | Wall - Supply and install [WT02] -100x300 mm Ceramic tiles with 1mm Spacer, grouted with Grey colour epoxy to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Wall - Supply and install [WT02] -100x300 mm Ceramic tiles with 1mm Spacer, grouted with Grey colour epoxy to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Sqm | 81 | 3348 | 271188 | 59.502 | 199212.696 | 59.502 | 199212.696
37 | 3.15 | Wall - Supply and install [PT06] - White Colour Paint RAL 9003 9016 to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Wall - Supply and install [PT06] - White Colour Paint RAL 9003 9016 to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Sqm | 13.86 | 713 | 9882.18 | 14.88 | 10609.44 | 14 | 9982 | 0.88 | 627.44
38 | 3.16 | Wall - Supply and install [WT01] -300x600 mm Wooden Effect Ceramice Wall tile, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Wall - Supply and install [WT01] -300x600 mm Wooden Effect Ceramice Wall tile, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Sqm | 24.42 | 3132 | 76483.44 | 22.2048 | 69545.4336 | 22.2048 | 69545.4336
39 | 3.17 | Wall - Supply and install [GR01] -Geometric Pattern Vinyl Wall Coverings, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Wall - Supply and install [GR01] -Geometric Pattern Vinyl Wall Coverings, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Sqm | 40.5 | 3024 | 122472 | 51.6 | 156038.4 | 41 | 123984 | 10.6 | 32054.4
40 |  | SECTION 4 - FIXTURES AND FITTINGS | SECTION 4 - FIXTURES AND FITTINGS
41 | 4.01 | Front Counter [J01] Supply installation of Front Counter [J01] Size As per dwg; [SU01] - Counter Top, Fascia Finish, Ply carcass With Solid Surface-White Diamond; [MT01] - Grey Colour Powder Coated Metal Skirting Ral 7022 150mm Rise [LM02] - Shutter, I | Front Counter [J01] Supply installation of Front Counter [J01] Size As per dwg; [SU01] - Counter Top, Fascia Finish, Ply carcass With Solid Surface-White Diamond; [MT01] - Grey Colour Powder Coated Metal Skirting Ral 7022 150mm Rise [LM02] - Shutter, I | Set | 1 | 275000 | 275000 | 1 | 275000 | 1 | 275000
42 | 4.02 | Booth Seat [J02] Supply installation of Booth Seat [J02] Size As per dwg; [UP01] - Booth Seat Finish with Grey Colour Leatherette; [LM01] - Back rest, Ply carcass Fnish with Oak wood LAminate [PT03] - 25x25 mm thick Metal Frame Finish with Grey Colour | Booth Seat [J02] Supply installation of Booth Seat [J02] Size As per dwg; [UP01] - Booth Seat Finish with Grey Colour Leatherette; [LM01] - Back rest, Ply carcass Fnish with Oak wood LAminate [PT03] - 25x25 mm thick Metal Frame Finish with Grey Colour | Set | 5 | 76000 | 380000 | 5 | 380000 | 5 | 380000
43 | 4.03 | Perch Table [J03] Supply installation of Perch Table [J04] Size As per drawing [LM03] - Box, Perch top, Box Fascia Finish with Refresh Oak Wood Laminate; [MT05] - Metal Mesh finish with Grey Colour Powder Coated RAL 7022 [PT03] - 25x25 mm thick Metal F | Perch Table [J03] Supply installation of Perch Table [J04] Size As per drawing [LM03] - Box, Perch top, Box Fascia Finish with Refresh Oak Wood Laminate; [MT05] - Metal Mesh finish with Grey Colour Powder Coated RAL 7022 [PT03] - 25x25 mm thick Metal F | Set | 1 | 77700 | 77700 | 1 | 77700 | 1 | 77700
44 | 4.04 | Bulk Head [J04] Supply installation of Bulk Head [J04] Size As per drawing [MT03] - 85X20 Mm Thk Aluminium Slats Finish With (Pt01,Pt02,Pt07); [PT04] - Bulkhead Fascia ,Ply carcass Finish With Grey Colour Paint Ral 7022 including all necessary consuma | Bulk Head [J04] Supply installation of Bulk Head [J04] Size As per drawing [MT03] - 85X20 Mm Thk Aluminium Slats Finish With (Pt01,Pt02,Pt07); [PT04] - Bulkhead Fascia ,Ply carcass Finish With Grey Colour Paint Ral 7022 including all necessary consuma | Set | 1 | 1325800 | 1325800 | 1 | 1325800 | 1 | 1325800
45 | 4.05 | Servery Bulk Head [J05] Supply installation of Servery Bulk Head [J05] Size As per drawing [GR01] -Ply Carcass Finish With Geometric Pattern Vinyl Wall Coverings; [GR01] -Top, Fascia Finish With Geometric Pattern Vinyl Wall Coverings; including all nec | Servery Bulk Head [J05] Supply installation of Servery Bulk Head [J05] Size As per drawing [GR01] -Ply Carcass Finish With Geometric Pattern Vinyl Wall Coverings; [GR01] -Top, Fascia Finish With Geometric Pattern Vinyl Wall Coverings; including all nec | Set | 1 | 21160 | 21160 | 1 | 21160 | 1 | 21160
46 | 4.06 | Ceiling Element[J06] Supply installation of Ceiling Element[J06] Size As per drawing [PT02] -50X50 Mm Thk Metal Frames Finish With Traffic Yellow Colour Paint Ral 1023; including all necessary consumables, fitting and accessories, in accordance with th | Ceiling Element[J06] Supply installation of Ceiling Element[J06] Size As per drawing [PT02] -50X50 Mm Thk Metal Frames Finish With Traffic Yellow Colour Paint Ral 1023; including all necessary consumables, fitting and accessories, in accordance with th | Set | 1 | 50400 | 50400 | 1 | 50400 | 1 | 50400
47 | 4.07 | Planter Box[J07] Supply installation of Planter Box [J07] Size As per drawing [LM03] - Top Finish with Refresh Oak Wood Laminate; [LM01] | Planter Box[J07] Supply installation of Planter Box [J07] Size As per drawing [LM03] - Top Finish with Refresh Oak Wood Laminate; [LM01] | Set | 1 | 67650 | 67650 | 1 | 67650 | 1 | 67650
48 | 4.08 | L-Shaped Table [J08] Supply installation ofL Shaped Table [J08] Size 600mm L x 625mm B x 950mm H [LM01] - Top finish with Oak Wood Laminate; [MT05] - Metal Mesh finish with Grey Colour Powder Coated RAL 7022 [PT03] - 25x25 mm thick Metal Frame Finish w | L-Shaped Table [J08] Supply installation ofL Shaped Table [J08] Size 600mm L x 625mm B x 950mm H [LM01] - Top finish with Oak Wood Laminate; [MT05] - Metal Mesh finish with Grey Colour Powder Coated RAL 7022 [PT03] - 25x25 mm thick Metal Frame Finish w | Set | 2 | 10075 | 20150 | 2 | 20150 | 2 | 20150
49 | 4.09 | Condiment Unit [J09] Supply installation of Condiment Unit[J09] Size 1100 mm Lx 580 mm B x 810mm H [PT03] - Top, Side fascia Finish, Ply carcass with Grey Colour Paint RAL 7022; [MT02] - Ply Carcass Finish With Grey Colour Powder Coated Aluminium Corru | Condiment Unit [J09] Supply installation of Condiment Unit[J09] Size 1100 mm Lx 580 mm B x 810mm H [PT03] - Top, Side fascia Finish, Ply carcass with Grey Colour Paint RAL 7022; [MT02] - Ply Carcass Finish With Grey Colour Powder Coated Aluminium Corru | Set | 1 | 34200 | 34200 | 1 | 34200 | 1 | 34200
50 | 4.10 | Order Station [J10] Supply installation of Order Staion[J10] Size 1200 mm Lx 150 mm B x 2800mm H [PT03] - 150x50 mm, 60x20mm thick Metal Frame Finish with Grey Colour Paint RAL 7022; | Order Station [J10] Supply installation of Order Staion[J10] Size 1200 mm Lx 150 mm B x 2800mm H [PT03] - 150x50 mm, 60x20mm thick Metal Frame Finish with Grey Colour Paint RAL 7022; | Set | 1 | 70300 | 70300 | 1 | 70300 | 1 | 70300
51 | 4.11 | Door [J11] Supply installation of Door[J11] Size 900 mm Lx 2100mm H [PT03] - 50x100 mm Frame Finish with Grey Colour Paint RAL 7022; Door Vision Panel with 8mm Thcik Plain Glass, ALuminium Glass Profile Concealed Aluminium Hnadle on both sides; | Door [J11] Supply installation of Door[J11] Size 900 mm Lx 2100mm H [PT03] - 50x100 mm Frame Finish with Grey Colour Paint RAL 7022; Door Vision Panel with 8mm Thcik Plain Glass, ALuminium Glass Profile Concealed Aluminium Hnadle on both sides; | Set | 1 | 38850 | 38850 | 1 | 38850 | 1 | 38850
52 | 4.12 | Isolated Louver Door [J12] Supply installation of Isolated Louver Door[J12] Size 700 mm Lx 2100mm H [PT03] - 50x50 mm Frame Finish with Grey Colour Paint RAL 7022; Concealed Aluminium Hnadle on both sides; | Isolated Louver Door [J12] Supply installation of Isolated Louver Door[J12] Size 700 mm Lx 2100mm H [PT03] - 50x50 mm Frame Finish with Grey Colour Paint RAL 7022; Concealed Aluminium Hnadle on both sides; | Set | 1 | 32375 | 32375 | 1 | 32375 | 1 | 32375
53 | 6.01 | SECTION 6 - PROVISIONAL SUMS | SECTION 6 - PROVISIONAL SUMS | Sum | 1 | 0 | 0

## Plumbing
|  | Plumbing for Carles Jr FF 018 HYD |  |  | Pikture Perfect (R1) | Vendor Name : Impulse Branding | Executed | Vendor Name : Impulse Branding
Sr No. | Item Code | Item Name | UOM | Qty | Unit Price | Amount | Qty | Amount
1 |  | Plumbing Work | NOS | 1 |  | 296350 |  | 265095
1 | A | CONNECTING INTEGRATING UNIT MEP SERVICES TO AIRPORT MEP SERVICES BUILDING
2 |  | If any termination or connection of the unit services is required outside the site location (i.e., connection termination of the MEP unit to the airport MEP service or airport external façade or roof, etc.), then the contractor has to work in consultation with the airport to plan, design, and detail such connections. The contractor is to do all necessary site surveys to verify the optimal routing for the services in such cases. Finally, the contractor is to make good on any penetrations after installation, including providing fire seals as required as per airport requirements.
3 | B | DRAINAGE SYSTEM
4 |  | INTERCEPTORS SEPERATORS
5 | B.1.1 | Installing, Testing Commissioning of Greese Trap or Grease Interceptor (Above Ground floor) of 304 grade stainless steel material with interceptor body, preforated bucket, baffles, integral trap, inlet outlep pipe sleeve and stainless steel interceptor cover of approved make and with all necessary fittings connectors etc. (Make Nugreen , Kessel and Concessionaire can propose another make in SS material.)NGT 50 - Flow Rate (2.20 LPS 132 LPM) | Nos | 1 | 75000 | 75000 | 1 | 75000
6 |  | VALVES ACCESSORIES
7 | B.2 | Supplying, Installing, Testing Commissioning of ABS Air Admittance Valve conforming to EN 12380, with an air admittance air flow rate of 6.1 L s and a temperature range of operation from -20 C to + 60 C of approved make with all necessary adapters, fittings and connectors etc. (Make Astral Supreme for Pipe and Fittings)
8 | B.2.1 | 32 mm Dia | Nos | 1 | 6500 | 6500 | 0 | 0
9 |  | DRAINS, TRAPS CLEANOUTS
10 | B.4 | Supplying, Installing, and testing of AISI 304 grade Stainless Steel Floor Drain with top square anti-slip mesh grating drain cover of 350 X 350 mm, lateral horizontal outlet, with removable waste basket, odor water seal trap of approved make with all necessary adapters, fittings, and connectors etc. (Make Custom made)
11 | B.4.1 | 50 mm Dia - Outlet | Nos | 4 | 9000 | 36000 | 6 | 54000
12 | B.5 | Supplying, Installing, and testing of uPVC P Trap (self-cleaning type) with odor water seal trap of approved make with all necessary adapters, fittings and connectors, etc.
13 | B.5.1 | 32 mm Dia Outlet | Nos | 6 | 1800 | 10800 | 0 | 0
14 | B.6 | Supplying, Installing Testing of cast iron Floor Trap (150 mmx 150 mm) with Stainless Steel slotted top cover, odour water seal trap of approved make with all necessary adapters, fittings and connectors etc. (Makes NECO or equivalent with Airport approval)
15 | B.6.1 | 75 mm Dia - Outlet | Nos | 1 | 2400 | 2400 | 0 | 0
16 |  | DRAINAGE SYSTEMS PIPING
17 | B.7 | Supplying, Installing, Testing, and Commissioning of uPVC Pipe, for drainage with all necessary fittings such as bends, wye s, reducers, san tee s, double wye s, double combinations, san cross, and cleanout plugs etc, of approved make. and with all necessary supports clamps for the above-raised floor pipes as per standards and site conditions requirements. (Make Astral Supreme for Pipe and Fittings)
18 | B.7.1 | 32 mm Dia | Mtr | 2 | 410 | 820 | 0 | 0
19 | B.7.2 | 40 mm Dia | Mtr | 10 | 500 | 5000 | 0 | 0
20 | B.7.3 | 50 mm Dia | Mtr | 25 | 650 | 16250 | 12 | 7800
21 | B.7.4 | 75 mm Dia | Mtr | 6 | 850 | 5100 | 9.4 | 7990
22 | C | WATER SUPPLY SYSTEM
23 |  | WATER SUPPLY EQUIPMENTS
24 | C.1 | Supply, Installation, Testing Commissioning of Electric Water Heater with safety valve arrangement and accessories like angle valve, flexible pipes, C.P bolts, screws, washers, etc. and proper supports necessary as per standards and site condition requirements. (Make Ariston Racold or equivalent with Airport approval)
25 | C.1.1 | 65 Liters vertical storage water heater | Nos | 1 | 40200 | 40200 | 1 | 40200
26 | C.2 | Supply, Installation, Testing Commissioning of RO Filteration Unit for supplying pure filtered potable water to equipments like Combi-steamers baking ovens, Fresh water taps Coolers, Coffee Espresso machines, Dish-washers, Post-mix machines, Ice-machines, and Boiling-water taps etc. with necessary prefilters, filter cartridges, manifold heads, mounting brackets, shutoff valves, flushing valves, pressure gauges, and suitable connectors etc. Final make, model and details to be finalized by specialist vendor after examining the water test report of incoming water supply provided at site. (Make Eco Smart Livpure or equivalent with Airport approval)
27 | C.2.1 | 15 Ltrs Hr - Flow Rate | Nos | 1 |  |  | 0 | 0
28 |  | WATER SUPPLY PIPE VALVES ACCESSORIES
29 | C.3 | Supply, Installation, Testing Commissioning of Brass Ball Valve with full bore lever operated, SS ball and stem with a pressure rating of 16 Bar of approved make and with all necessary fittings. (Makes NECO or equivalent with Airport approval)
30 | C.3.1 | 25 mm Dia | Nos | 2 | 2250 | 4500 | 1 | 2250
31 | C.4 | Supply, Installation, Testing, and Commissioning of chrome plated Angle Valve with wall flange rosette for all plumbing equipment fixtures with a pressure rating of 16 Bar of approved make and with all necessary fittings. Including making good the wall partition as per Architectural Interior Design and as per relevant standards. (Makes NECO or equivalent with Airport approval)
32 | C.4.1 | 15 mm Dia Inlet (Outlet size to fit with plumbing eqp fixture connection) | Nos | 21 | 1850 | 38850 | 19 | 35150
33 |  | COLD WATER SUPPLY PIPING
34 | C.5 | Supply, Installation, Testing Commissioning of (Chlorinated Poly Vinyl Chloride) CPVC Pipe conforming to IS 15778, ASTM D 2846, in SDR 11 Class 1, (temperature range of maximum 82°C) with all necessary fittings such as sockets, bends, elbows, tees, reducers, unions etc, and proper supports necessary as per standards and site condition requirements. (Make Astral Supreme for Pipe and Fittings)
35 | C.5.1 | 15 mm Dia | Mtr | 16 | 355 | 5680 | 0 | 0
36 | C.5.2 | 20 mm Dia | Mtr | 10 | 430 | 4300 | 71 | 30530
37 | C.5.3 | 25 mm Dia | Mtr | 13 | 550 | 7150 | 14.5 | 7975
38 | C.6 | Supply, Installation, Testing Commissioning of Copper Pipe conforming to BS 2871 EN 1057, (continous operating temperature range of maximum 90°C) with all necessary fittings such as sockets, bends, elbows, tees, reducers, unions etc, and proper supports necessary as per standards and site condition requirements. (Make Manibhadra fittings or equivalent with Airport approval)
39 | C.6.1 | 15 mm Dia | Mtr | 10 | 1350 | 13500 | 0 | 0
40 | C.6.2 | 22 mm Dia | Mtr | 12 | 1750 | 21000 | 0 | 0
41 |  | PIPING THERMAL INSULATION
42 | C.7 | Supply fixing of Pipe Insulation of 13 mm thick, with Polyethylene-based, closed-cell foam pipe insulation and polymer protective coating to prevent external mechanical damage of approved make for Hot water pipe with a operating temperature range of 0°C to 100°C, Thermal conductivity (?) 0.038 W m-K @ 40°C including suitable adhesives to fix the insulation to pipe. (Make Thermax, Maxima, Fuelpac or equivalent)
43 | C.7.1 | 15 mm Dia | Mtr | 10 | 150 | 1500 | 0 | 0
44 | C.7.2 | 22 mm Dia | Mtr | 12 | 150 | 1800 | 28 | 4200

## Additional Plumbing
| Add PLB at Carls Jr. HYD |  |  | Pikture Perfect (R1) | Vendor Name : Impulse Branding
Sr No. | Item Name | UOM | Qty | Unit Price | Amount
1 | Plumbing - Add | NOS | 1 |  | 7100
1 | Supplying, Installing, and testing of uPVC P Trap (self-cleaning type) with odor water seal trap of approved make with all necessary adapters, fittings and connectors, etc. 32 mm Dia Outlet | Nos | 1 | 2200 | 2200
2 | Supply, Installation, Testing Commissioning of Brass Ball Valve with full bore lever operated, SS ball and stem with a pressure rating of 16 Bar of approved make and with all necessary fittings. (Makes NECO or equivalent with Airport approval) 25 mm Dia | Nos | 2 | 2450 | 4900

## Measurement Sheet
| Interior works for Carls Jr FF 018 HYD |  | PO QTY |  | Executed
Sr No. | Item Name | Item Description | UOM | Qty | Nos. | L | W | Qty
1 | ID | ID | NOS | 1
1 | SECTION 1 - PRELIMINARIES | SECTION 1 - PRELIMINARIES
2 | Insurance (EC CAR) | Insurance (EC CAR) | Sum | 1
3 | Site setting-out | Site setting-out | Sum | 1
4 | Supervision and Coordination with Other trades | Supervision and Coordination with Other trades | Sum | 1
5 | Supply, install and demolish the hoarding | Supply, install and demolish the hoarding | Sum | 1
6 | General protection works to the existing finishes | General protection works to the existing finishes | Sum | 1
7 | Make good the all affected surround area | Make good the all affected surround area | Sum | 1
8 | Daily cleaning and waste disposal | Daily cleaning and waste disposal | Sum | 1
9 | Final cleaning and waste disposal | Final cleaning and waste disposal | Sum | 1
10 | Statutory Obligations, Regulations and Specification | Statutory Obligations, Regulations and Specification | Sum | 1
11 | Provision of as-built drawings upon completion of works | Provision of as-built drawings upon completion of works | Sum | 1
12 | To comply with the fitting-out house rules | To comply with the fitting-out house rules | Sum | 1
13 | India Construction Sites (Safety) Regulations | India Construction Sites (Safety) Regulations | Sum | 1
14 | Safety Precautions | Safety Precautions | Sum | 1
15 | Samples, finishes, drawings submission to relevant parties | Samples, finishes, drawings submission to relevant parties | Sum | 1
16 | Others (Please list the items in details) | Others (Please list the items in details) | Sum | 1
17 | SECTION 2 - WALL AND PARTITIONING | SECTION 2 - WALL AND PARTITIONING
18 | Supply and installation of masonry wall of thickness as indicated, as per drawings and as per the approved manufacturer s specifications including all necessary consumables, supports and fittings, all complete in all aspects in accordance with instruction | Supply and installation of masonry wall of thickness as indicated, as per drawings and as per the approved manufacturer s specifications including all necessary consumables, supports and fittings, all complete in all aspects in accordance with instruction
19 | 100mm thick masonry wall including 100X100 Mm Concrete Framing (M.20 Mix With Nominal Reinforcements) | 100mm thick masonry wall including 100X100 Mm Concrete Framing (M.20 Mix With Nominal Reinforcements) | Sqm | 64.33 |  |  |  | 97.3833
[6 empty] | 6 | 3.43 | 20.58
[6 empty] | 1.04 | 2.12 | -2.2048
[6 empty] | 2.27 | 3.43 | 7.7861
[6 empty] | 3.25 | 3.43 | 11.1475
[6 empty] | 4.46 | 3.43 | 15.2978
[6 empty] | 1.12 | 3.3 | 3.696
[6 empty] | 7.47 | 3.3 | 24.651
[6 empty] | 4.17 | 3.43 | 14.3031
[6 empty] | 0.62 | 3.43 | 2.1266
20 | Supply and installation of dry wall partition of thickness as indicated, as per drawings and as per the approved manufacturer s specifications including all necessary consumables, supports and fittings, all complete in all aspects in accordance with instr | Supply and installation of dry wall partition of thickness as indicated, as per drawings and as per the approved manufacturer s specifications including all necessary consumables, supports and fittings, all complete in all aspects in accordance with instr
21 | 50mm thick dry wall partition (height upto true ceiling) | 50mm thick dry wall partition (height upto true ceiling) | Sqm | 12.03 |  |  |  | 30.408
[6 empty] | 3.99 | 3.1 | 12.369
[6 empty] | 3.71 | 3.1 | 11.501
[6 empty] | 3.5 | 3.1 | 10.85
[6 empty] | 2.2 | 1.96 | -4.312
22 | SECTION 3 - FINISHING AND WATERPROOFING | SECTION 3 - FINISHING AND WATERPROOFING
23 | Waterproofing - Supply and install approved waterproofing system to kitchen with testing, warranty, in accordance withthe drawings and specifications(Sample is subject to Employer s approval) Dwg ref 02GA-103A | Waterproofing - Supply and install approved waterproofing system to kitchen with testing, warranty, in accordance withthe drawings and specifications(Sample is subject to Employer s approval) Dwg ref 02GA-103A | Sqm | 75.25 |  |  |  | 54
24 | Screed - Supply and install screed (upto thickness as provided in the drawing) as approved in accordance with the drawings and specifications Dwg ref 02GA-10 | Screed - Supply and install screed (upto thickness as provided in the drawing) as approved in accordance with the drawings and specifications Dwg ref 02GA-10 | Sqm | 53.52 |  |  |  | 54
25 | Flooring - Supply and install [FL01] - 600x1200mm Concrete Ceramic Floor Tile including all necessary consumables in accordance with the drawings and specifications. Dwg ref 02GA-103 | Flooring - Supply and install [FL01] - 600x1200mm Concrete Ceramic Floor Tile including all necessary consumables in accordance with the drawings and specifications. Dwg ref 02GA-103 | Sqm | 49.31 |  |  |  | 80
26 | Flooring - Supply and install [FL02] - 560x560mm Grey Colour Kota Stone including all necessary consumables in accordance with the drawings and specifications Dwg ref 02GA-103 | Flooring - Supply and install [FL02] - 560x560mm Grey Colour Kota Stone including all necessary consumables in accordance with the drawings and specifications Dwg ref 02GA-103 | Sqm | 77.81 |  |  |  | 54
27 | Flooring - Supply and install [FL03] - S.S Floor Reducer Trim including all necessary consumables in accordance with the drawings and specifications Dwg ref 02GA-103 | Flooring - Supply and install [FL03] - S.S Floor Reducer Trim including all necessary consumables in accordance with the drawings and specifications Dwg ref 02GA-103 | Rmt | 31.8 |  |  |  | 34.1
28 | Flooring - Supply and install [FL04] - S.S Floor Cover Trim including all necessary consumables in accordance with the drawings and specifications Dwg ref 02GA-103 | Flooring - Supply and install [FL04] - S.S Floor Cover Trim including all necessary consumables in accordance with the drawings and specifications Dwg ref 02GA-103 | Rmt | 0.9
29 | Ceiling - Supply and install Gypsum ceiling with paint [CL01] including all necessary fitting, supports, accessories, consumables, opening,etc.in accordance with the drawings and specifications Dwg ref 02GA-104 | Ceiling - Supply and install Gypsum ceiling with paint [CL01] including all necessary fitting, supports, accessories, consumables, opening,etc.in accordance with the drawings and specifications Dwg ref 02GA-104 | Sqm | 11.49 |  |  |  | 11
30 | Ceiling - Supply and install Gypsum ceiling with paint [CL02] including all necessary fitting, supports, accessories, consumables, opening,etc.in accordance with the drawings and specifications Dwg ref 02GA-104 | Ceiling - Supply and install Gypsum ceiling with paint [CL02] including all necessary fitting, supports, accessories, consumables, opening,etc.in accordance with the drawings and specifications Dwg ref 02GA-104 | Sqm | 47 |  |  |  | 47
31 | Ceiling - Supply and install Grid ceiling amstrong Equivalent [CL03] including all necessary fitting, supports, accessories, consumables, opening,etc.in accordance with the drawings and specifications Dwg ref 02GA-104 | Ceiling - Supply and install Grid ceiling amstrong Equivalent [CL03] including all necessary fitting, supports, accessories, consumables, opening,etc.in accordance with the drawings and specifications Dwg ref 02GA-104 | Sqm | 46.34 |  |  |  | 46
32 | Ceiling - Supply and install Baffle Ceiling including all necessary fitting, supports, accessories, consumables, opening,etc.in accordance with the drawings and specifications Dwg ref 02GA-104 | Ceiling - Supply and install Baffle Ceiling including all necessary fitting, supports, accessories, consumables, opening,etc.in accordance with the drawings and specifications Dwg ref 02GA-104 | Sqm | 46.34 |  |  |  | 60
33 | Wall - Supply and install [WP01] - Old whitewood imitation panels claddings to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Wall - Supply and install [WP01] - Old whitewood imitation panels claddings to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Sqm | 18.08 |  |  |  | 22.1
34 | Wall - Supply and install [WP02] Grey Painted Brick Imitation Panels Claddings to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Wall - Supply and install [WP02] Grey Painted Brick Imitation Panels Claddings to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Sqm | 13.15 |  |  |  | 13.6804
[6 empty] | 9.75 | 1.21 | 11.7975
[6 empty] | 3.49 | 1.21 | 4.2229
[6 empty] | 1.2 | 1.95 | -2.34
35 | Wall - Supply and install [PT04] - Grey Colour Paint TAL 7022 to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Wall - Supply and install [PT04] - Grey Colour Paint TAL 7022 to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Sqm | 59.4 |  |  |  | 67.2764
[6 empty] | 9.75 | 1.21 | 11.7975
[6 empty] | 3.49 | 1.21 | 4.2229
[5 empty] | 2 | 3.01 | 6.5 | 39.13
[6 empty] | 28.2 | 0.43 | 12.126
36 | Wall - Supply and install [WT02] -100x300 mm Ceramic tiles with 1mm Spacer, grouted with Grey colour epoxy to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Wall - Supply and install [WT02] -100x300 mm Ceramic tiles with 1mm Spacer, grouted with Grey colour epoxy to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Sqm | 81 |  | 28.2 | 2.11 | 59.502
37 | Wall - Supply and install [PT06] - White Colour Paint RAL 9003 9016 to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Wall - Supply and install [PT06] - White Colour Paint RAL 9003 9016 to walls, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Sqm | 13.86 | 8 | 0.6 | 3.1 | 14.88
38 | Wall - Supply and install [WT01] -300x600 mm Wooden Effect Ceramice Wall tile, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Wall - Supply and install [WT01] -300x600 mm Wooden Effect Ceramice Wall tile, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Sqm | 24.42 |  |  |  | 22.2048
[6 empty] | 3.25 | 2.88 | 9.36
[6 empty] | 4.46 | 2.88 | 12.8448
39 | Wall - Supply and install [GR01] -Geometric Pattern Vinyl Wall Coverings, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Wall - Supply and install [GR01] -Geometric Pattern Vinyl Wall Coverings, all in accordance with the drawings and specifications. Dwg ref 02GA-102, 03IL-300 to 03IL-304 | Sqm | 40.5 |  |  |  | 51.6
| Initial Installation |  |  |  | 41 |  |  | 41
| Damaged by branding team |  |  |  | 8 |  |  | 8
| TV Box |  |  |  | 2.6 |  |  | 2.6
40 | SECTION 4 - FIXTURES AND FITTINGS | SECTION 4 - FIXTURES AND FITTINGS
41 | Front Counter [J01] Supply installation of Front Counter [J01] Size As per dwg; [SU01] - Counter Top, Fascia Finish, Ply carcass With Solid Surface-White Diamond; [MT01] - Grey Colour Powder Coated Metal Skirting Ral 7022 150mm Rise [LM02] - Shutter, I | Front Counter [J01] Supply installation of Front Counter [J01] Size As per dwg; [SU01] - Counter Top, Fascia Finish, Ply carcass With Solid Surface-White Diamond; [MT01] - Grey Colour Powder Coated Metal Skirting Ral 7022 150mm Rise [LM02] - Shutter, I | Set | 1 | 1 |  |  | 1
42 | Booth Seat [J02] Supply installation of Booth Seat [J02] Size As per dwg; [UP01] - Booth Seat Finish with Grey Colour Leatherette; [LM01] - Back rest, Ply carcass Fnish with Oak wood LAminate [PT03] - 25x25 mm thick Metal Frame Finish with Grey Colour | Booth Seat [J02] Supply installation of Booth Seat [J02] Size As per dwg; [UP01] - Booth Seat Finish with Grey Colour Leatherette; [LM01] - Back rest, Ply carcass Fnish with Oak wood LAminate [PT03] - 25x25 mm thick Metal Frame Finish with Grey Colour | Set | 5 | 5 |  |  | 5
43 | Perch Table [J03] Supply installation of Perch Table [J04] Size As per drawing [LM03] - Box, Perch top, Box Fascia Finish with Refresh Oak Wood Laminate; [MT05] - Metal Mesh finish with Grey Colour Powder Coated RAL 7022 [PT03] - 25x25 mm thick Metal F | Perch Table [J03] Supply installation of Perch Table [J04] Size As per drawing [LM03] - Box, Perch top, Box Fascia Finish with Refresh Oak Wood Laminate; [MT05] - Metal Mesh finish with Grey Colour Powder Coated RAL 7022 [PT03] - 25x25 mm thick Metal F | Set | 1 | 1 |  |  | 1
44 | Bulk Head [J04] Supply installation of Bulk Head [J04] Size As per drawing [MT03] - 85X20 Mm Thk Aluminium Slats Finish With (Pt01,Pt02,Pt07); [PT04] - Bulkhead Fascia ,Ply carcass Finish With Grey Colour Paint Ral 7022 including all necessary consuma | Bulk Head [J04] Supply installation of Bulk Head [J04] Size As per drawing [MT03] - 85X20 Mm Thk Aluminium Slats Finish With (Pt01,Pt02,Pt07); [PT04] - Bulkhead Fascia ,Ply carcass Finish With Grey Colour Paint Ral 7022 including all necessary consuma | Set | 1 | 1 |  |  | 1
45 | Servery Bulk Head [J05] Supply installation of Servery Bulk Head [J05] Size As per drawing [GR01] -Ply Carcass Finish With Geometric Pattern Vinyl Wall Coverings; [GR01] -Top, Fascia Finish With Geometric Pattern Vinyl Wall Coverings; including all nec | Servery Bulk Head [J05] Supply installation of Servery Bulk Head [J05] Size As per drawing [GR01] -Ply Carcass Finish With Geometric Pattern Vinyl Wall Coverings; [GR01] -Top, Fascia Finish With Geometric Pattern Vinyl Wall Coverings; including all nec | Set | 1 | 1 |  |  | 1
46 | Ceiling Element[J06] Supply installation of Ceiling Element[J06] Size As per drawing [PT02] -50X50 Mm Thk Metal Frames Finish With Traffic Yellow Colour Paint Ral 1023; including all necessary consumables, fitting and accessories, in accordance with th | Ceiling Element[J06] Supply installation of Ceiling Element[J06] Size As per drawing [PT02] -50X50 Mm Thk Metal Frames Finish With Traffic Yellow Colour Paint Ral 1023; including all necessary consumables, fitting and accessories, in accordance with th | Set | 1 | 1 |  |  | 1
47 | Planter Box[J07] Supply installation of Planter Box [J07] Size As per drawing [LM03] - Top Finish with Refresh Oak Wood Laminate; [LM01] | Planter Box[J07] Supply installation of Planter Box [J07] Size As per drawing [LM03] - Top Finish with Refresh Oak Wood Laminate; [LM01] | Set | 1 | 1 |  |  | 1
48 | L-Shaped Table [J08] Supply installation ofL Shaped Table [J08] Size 600mm L x 625mm B x 950mm H [LM01] - Top finish with Oak Wood Laminate; [MT05] - Metal Mesh finish with Grey Colour Powder Coated RAL 7022 [PT03] - 25x25 mm thick Metal Frame Finish w | L-Shaped Table [J08] Supply installation ofL Shaped Table [J08] Size 600mm L x 625mm B x 950mm H [LM01] - Top finish with Oak Wood Laminate; [MT05] - Metal Mesh finish with Grey Colour Powder Coated RAL 7022 [PT03] - 25x25 mm thick Metal Frame Finish w | Set | 2 | 2 |  |  | 2
49 | Condiment Unit [J09] Supply installation of Condiment Unit[J09] Size 1100 mm Lx 580 mm B x 810mm H [PT03] - Top, Side fascia Finish, Ply carcass with Grey Colour Paint RAL 7022; [MT02] - Ply Carcass Finish With Grey Colour Powder Coated Aluminium Corru | Condiment Unit [J09] Supply installation of Condiment Unit[J09] Size 1100 mm Lx 580 mm B x 810mm H [PT03] - Top, Side fascia Finish, Ply carcass with Grey Colour Paint RAL 7022; [MT02] - Ply Carcass Finish With Grey Colour Powder Coated Aluminium Corru | Set | 1 | 1 |  |  | 1
50 | Order Station [J10] Supply installation of Order Staion[J10] Size 1200 mm Lx 150 mm B x 2800mm H [PT03] - 150x50 mm, 60x20mm thick Metal Frame Finish with Grey Colour Paint RAL 7022; | Order Station [J10] Supply installation of Order Staion[J10] Size 1200 mm Lx 150 mm B x 2800mm H [PT03] - 150x50 mm, 60x20mm thick Metal Frame Finish with Grey Colour Paint RAL 7022; | Set | 1 | 1 |  |  | 1
51 | Door [J11] Supply installation of Door[J11] Size 900 mm Lx 2100mm H [PT03] - 50x100 mm Frame Finish with Grey Colour Paint RAL 7022; Door Vision Panel with 8mm Thcik Plain Glass, ALuminium Glass Profile Concealed Aluminium Hnadle on both sides; | Door [J11] Supply installation of Door[J11] Size 900 mm Lx 2100mm H [PT03] - 50x100 mm Frame Finish with Grey Colour Paint RAL 7022; Door Vision Panel with 8mm Thcik Plain Glass, ALuminium Glass Profile Concealed Aluminium Hnadle on both sides; | Set | 1 | 1 |  |  | 1
52 | Isolated Louver Door [J12] Supply installation of Isolated Louver Door[J12] Size 700 mm Lx 2100mm H [PT03] - 50x50 mm Frame Finish with Grey Colour Paint RAL 7022; Concealed Aluminium Hnadle on both sides; | Isolated Louver Door [J12] Supply installation of Isolated Louver Door[J12] Size 700 mm Lx 2100mm H [PT03] - 50x50 mm Frame Finish with Grey Colour Paint RAL 7022; Concealed Aluminium Hnadle on both sides; | Set | 1 | 1 |  |  | 1
53 | SECTION 6 - PROVISIONAL SUMS | SECTION 6 - PROVISIONAL SUMS | Sum | 1
Sr No. | Item Name | UOM | UOM | Qty
1 | Plumbing Work | NOS | NOS | 1
1 | CONNECTING INTEGRATING UNIT MEP SERVICES TO AIRPORT MEP SERVICES BUILDING
2 | If any termination or connection of the unit services is required outside the site location (i.e., connection termination of the MEP unit to the airport MEP service or airport external façade or roof, etc.), then the contractor has to work in consultation with the airport to plan, design, and detail such connections. The contractor is to do all necessary site surveys to verify the optimal routing for the services in such cases. Finally, the contractor is to make good on any penetrations after installation, including providing fire seals as required as per airport requirements.
3 | DRAINAGE SYSTEM
4 | INTERCEPTORS SEPERATORS
5 | Installing, Testing Commissioning of Greese Trap or Grease Interceptor (Above Ground floor) of 304 grade stainless steel material with interceptor body, preforated bucket, baffles, integral trap, inlet outlep pipe sleeve and stainless steel interceptor cover of approved make and with all necessary fittings connectors etc. (Make Nugreen , Kessel and Concessionaire can propose another make in SS material.)NGT 50 - Flow Rate (2.20 LPS 132 LPM) | Nos | Nos | 1 | 1 |  |  | 1
6 | VALVES ACCESSORIES
7 | Supplying, Installing, Testing Commissioning of ABS Air Admittance Valve conforming to EN 12380, with an air admittance air flow rate of 6.1 L s and a temperature range of operation from -20 C to + 60 C of approved make with all necessary adapters, fittings and connectors etc. (Make Astral Supreme for Pipe and Fittings)
8 | 32 mm Dia | Nos | Nos | 1 | 0 |  |  | 0
9 | DRAINS, TRAPS CLEANOUTS
10 | Supplying, Installing, and testing of AISI 304 grade Stainless Steel Floor Drain with top square anti-slip mesh grating drain cover of 350 X 350 mm, lateral horizontal outlet, with removable waste basket, odor water seal trap of approved make with all necessary adapters, fittings, and connectors etc. (Make Custom made)
11 | 50 mm Dia - Outlet | Nos | Nos | 4 | 6 |  |  | 6
12 | Supplying, Installing, and testing of uPVC P Trap (self-cleaning type) with odor water seal trap of approved make with all necessary adapters, fittings and connectors, etc.
13 | 32 mm Dia Outlet | Nos | Nos | 6 | 0 |  |  | 0
14 | Supplying, Installing Testing of cast iron Floor Trap (150 mmx 150 mm) with Stainless Steel slotted top cover, odour water seal trap of approved make with all necessary adapters, fittings and connectors etc. (Makes NECO or equivalent with Airport approval)
15 | 75 mm Dia - Outlet | Nos | Nos | 1 | 0 |  |  | 0
16 | DRAINAGE SYSTEMS PIPING
17 | Supplying, Installing, Testing, and Commissioning of uPVC Pipe, for drainage with all necessary fittings such as bends, wye s, reducers, san tee s, double wye s, double combinations, san cross, and cleanout plugs etc, of approved make. and with all necessary supports clamps for the above-raised floor pipes as per standards and site conditions requirements. (Make Astral Supreme for Pipe and Fittings)
18 | 32 mm Dia | Mtr | Mtr | 2
19 | 40 mm Dia | Mtr | Mtr | 10
20 | 50 mm Dia | Mtr | Mtr | 25 | 12 |  |  | 12
21 | 75 mm Dia | Mtr | Mtr | 6 | 9.4 |  |  | 9.4
22 | WATER SUPPLY SYSTEM
23 | WATER SUPPLY EQUIPMENTS
24 | Supply, Installation, Testing Commissioning of Electric Water Heater with safety valve arrangement and accessories like angle valve, flexible pipes, C.P bolts, screws, washers, etc. and proper supports necessary as per standards and site condition requirements. (Make Ariston Racold or equivalent with Airport approval)
25 | 65 Liters vertical storage water heater | Nos | Nos | 1 | 1 |  |  | 1
26 | Supply, Installation, Testing Commissioning of RO Filteration Unit for supplying pure filtered potable water to equipments like Combi-steamers baking ovens, Fresh water taps Coolers, Coffee Espresso machines, Dish-washers, Post-mix machines, Ice-machines, and Boiling-water taps etc. with necessary prefilters, filter cartridges, manifold heads, mounting brackets, shutoff valves, flushing valves, pressure gauges, and suitable connectors etc. Final make, model and details to be finalized by specialist vendor after examining the water test report of incoming water supply provided at site. (Make Eco Smart Livpure or equivalent with Airport approval)
27 | 15 Ltrs Hr - Flow Rate | Nos | Nos | 1 | 0 |  |  | 0
28 | WATER SUPPLY PIPE VALVES ACCESSORIES
29 | Supply, Installation, Testing Commissioning of Brass Ball Valve with full bore lever operated, SS ball and stem with a pressure rating of 16 Bar of approved make and with all necessary fittings. (Makes NECO or equivalent with Airport approval)
30 | 25 mm Dia | Nos | Nos | 2 | 1 |  |  | 1
31 | Supply, Installation, Testing, and Commissioning of chrome plated Angle Valve with wall flange rosette for all plumbing equipment fixtures with a pressure rating of 16 Bar of approved make and with all necessary fittings. Including making good the wall partition as per Architectural Interior Design and as per relevant standards. (Makes NECO or equivalent with Airport approval)
32 | 15 mm Dia Inlet (Outlet size to fit with plumbing eqp fixture connection) | Nos | Nos | 21 | 19 |  |  | 19
33 | COLD WATER SUPPLY PIPING
34 | Supply, Installation, Testing Commissioning of (Chlorinated Poly Vinyl Chloride) CPVC Pipe conforming to IS 15778, ASTM D 2846, in SDR 11 Class 1, (temperature range of maximum 82°C) with all necessary fittings such as sockets, bends, elbows, tees, reducers, unions etc, and proper supports necessary as per standards and site condition requirements. (Make Astral Supreme for Pipe and Fittings)
35 | 15 mm Dia | Mtr | Mtr | 16 |  |  |  | 0
36 | 20 mm Dia | Mtr | Mtr | 10 | 71 |  |  | 71
37 | 25 mm Dia | Mtr | Mtr | 13 | 14.5 |  |  | 14.5
38 | Supply, Installation, Testing Commissioning of Copper Pipe conforming to BS 2871 EN 1057, (continous operating temperature range of maximum 90°C) with all necessary fittings such as sockets, bends, elbows, tees, reducers, unions etc, and proper supports necessary as per standards and site condition requirements. (Make Manibhadra fittings or equivalent with Airport approval)
39 | 15 mm Dia | Mtr | Mtr | 10 | 0 |  |  | 0
40 | 22 mm Dia | Mtr | Mtr | 12 | 0 |  |  | 0
41 | PIPING THERMAL INSULATION
42 | Supply fixing of Pipe Insulation of 13 mm thick, with Polyethylene-based, closed-cell foam pipe insulation and polymer protective coating to prevent external mechanical damage of approved make for Hot water pipe with a operating temperature range of 0°C to 100°C, Thermal conductivity (?) 0.038 W m-K @ 40°C including suitable adhesives to fix the insulation to pipe. (Make Thermax, Maxima, Fuelpac or equivalent)
43 | 15 mm Dia | Mtr | Mtr | 10 | 0 |  |  | 0
44 | 22 mm Dia | Mtr | Mtr | 12 | 28 |  |  | 28
Add PLB at Carls Jr. HYD
Sr No. | Item Name | UOM | UOM | Qty
1 | Plumbing - Add | NOS | NOS | 1
1 | Supplying, Installing, and testing of uPVC P Trap (self-cleaning type) with odor water seal trap of approved make with all necessary adapters, fittings and connectors, etc. 32 mm Dia Outlet | Nos | Nos | 1
2 | Supply, Installation, Testing Commissioning of Brass Ball Valve with full bore lever operated, SS ball and stem with a pressure rating of 16 Bar of approved make and with all necessary fittings. (Makes NECO or equivalent with Airport approval) 25 mm Dia | Nos | Nos | 2

## NT Items
Sr No. | Item Name | UOM | Qty | Rate | Amount | MDS Feedback | PPDS Feedback
1 | SIPOREX BAT COBA- upto 100MM P L light wt. Solid Block (siporex or Aerocon) bat coba to conceal drainage plumbing lines for Grease trap of average thk of 100 mm with CM 1 4 top layer should be finished properly to receive flooring layer on it [ DISH WASH AREA] | Sq.Mtr | 54 | 1350 | 72900 | Floor filling was issued as part of Civil works BOQ and drawings which was issued before tender pack |  | Item Name SIPOREX BAT COBA- upto 100MM P L light wt. Solid Block (siporex or Aerocon) bat coba to conceal drainage plumbing lines for Grease trap of average thk of 100 mm with CM 1 4 top layer should be finished properly to receive flooring layer on it [ DISH WASH AREA] MDS Feedback Floor filling was issued as part of Civil works BOQ and drawings which was issued before tender pack PPDS Feedback
2 | 50mm PCC Providing Laying PCC 1 3 6 of average thk 100mm of M 10 grade of concrete ( 1 cement 3 coarse sand 6graded stone aggregate 10 mm nominal size) BOH AREA | Sq.Mtr | 83 | 1242 | 103086 | PCC was issued as part of Civil works BOQ and drawings which was issued before tender pack | As Guest Area Was Down From Airport FFL, As per site condition, on site decision taken for this JOB. | Item Name 50mm PCC Providing Laying PCC 1 3 6 of average thk 100mm of M 10 grade of concrete ( 1 cement 3 coarse sand 6graded stone aggregate 10 mm nominal size) BOH AREA MDS Feedback PCC was issued as part of Civil works BOQ and drawings which was issued before tender pack PPDS Feedback As Guest Area Was Down From Airport FFL, As per site condition, on site decision taken for this JOB.
3 | SS EDGE PROFILE P F of Stainless steel section edge profile protectors of size 19mm x 19mm x 1.5mm thick to protect all corners of the walls columns in kitchen | R.Mtr | 33 | 1218.75 | 40218.75 | Additional item as this was not considered in design / detailing |  | Item Name SS EDGE PROFILE P F of Stainless steel section edge profile protectors of size 19mm x 19mm x 1.5mm thick to protect all corners of the walls columns in kitchen MDS Feedback Additional item as this was not considered in design / detailing PPDS Feedback
4 | P&F of MS frame for RO plant and covering of the same with ply Boxing (750mm Deep) | Sq.Mtr | 1.63 | 34445 | 56145.35 | As per MDS design we have proposed normal compact type water filter unit. If a RO Plant is installed at site then this should been a TFS call. |  | Item Name P&F of MS frame for RO plant and covering of the same with ply Boxing (750mm Deep) MDS Feedback As per MDS design we have proposed normal compact type water filter unit. If a RO Plant is installed at site then this should been a TFS call. PPDS Feedback
5 | TRAP DOOR OPENABLE P F Trap door made of 19mm marine ply finished with approved laminate of 1.0mm thickness with all necessary frame work in salwood hardware fittings complete as per the detailed drawing instruction | Nos. | 2 | 16800 | 33600 | As per MDS design there is no Trap doors since the Mechanical equipments above false ceiling are in BOH area,which have grid ceiling this doesn't require trapdoors and not sure why these additional 2 nos of Trap doors required please clarify. |  | Item Name TRAP DOOR OPENABLE P F Trap door made of 19mm marine ply finished with approved laminate of 1.0mm thickness with all necessary frame work in salwood hardware fittings complete as per the detailed drawing instruction MDS Feedback As per MDS design there is no Trap doors since the Mechanical equipments above false ceiling are in BOH area,which have grid ceiling this doesn't require trapdoors and not sure why these additional 2 nos of Trap doors required please clarify. PPDS Feedback
6 | Furniture Assembling | Nos. | 4 | 1000 | 4000 | Not sure what this cost is for |  | Item Name Furniture Assembling MDS Feedback Not sure what this cost is for PPDS Feedback
7 | RO Plant and Water tank Connection | Nos. | 1 | 3500 | 3500 | Refer point 4. |  | Item Name RO Plant and Water tank Connection MDS Feedback Refer point 4. PPDS Feedback
8 | P&F of Ply frame for airport shaft door with laminate finish. | R.Mtr | 10.5 | 2112 | 22176 | This was not there intitially.Additional design element added after BAR is introduced. |  | Item Name P&F of Ply frame for airport shaft door with laminate finish. MDS Feedback This was not there intitially.Additional design element added after BAR is introduced. PPDS Feedback
9 | P&F of sink mixture | Nos. | 5 | 7500 | 37500 | This is suppose to be under Equipment scope. |  | Item Name P&F of sink mixture MDS Feedback This is suppose to be under Equipment scope. PPDS Feedback
10 | P&F of push button tap | Nos. | 1 | 4500 | 4500 | This is suppose to be under Equipment scope. |  | Item Name P&F of push button tap MDS Feedback This is suppose to be under Equipment scope. PPDS Feedback
11 | P&F of UPVC Ball Valve | Nos. | 2 | 1850 | 3700 | As per MDS design we have proposed 4 nos of Brass ball valve note sure why this uPVC ball valve is required. | Installed 1 in water supply line and 1 before connecting to RO plant for service and maintenance purpose of RO. | Item Name P&F of UPVC Ball Valve MDS Feedback As per MDS design we have proposed 4 nos of Brass ball valve note sure why this uPVC ball valve is required. PPDS Feedback Installed 1 in water supply line and 1 before connecting to RO plant for service and maintenance purpose of RO.
12 | Supplying, Installing, Testing, and Commissioning of 100mm uPVC Pipe, for drainage with all necessary fittings such as bends, wye s, reducers, san tee s, double wye s, double combinations, san cross, and cleanout plugs etc, of approved make. and with all necessary supports clamps for the above-raised floor pipes as per standards and site conditions requirements. (Make Astral Supreme for Pipe and Fittings) | R.Mtr | 11 | 1250 | 13750 | As per MDS design there are only 50 mm Dia & 75 mm Dia Drain Pipe in drawing and BOQ not sure why 100 mm Dia uPVC Drain pipe is required. | On Site Decision , as per discussion with project team. | Item Name Supplying, Installing, Testing, and Commissioning of 100mm uPVC Pipe, for drainage with all necessary fittings such as bends, wye s, reducers, san tee s, double wye s, double combinations, san cross, and cleanout plugs etc, of approved make. and with all necessary supports clamps for the above-raised floor pipes as per standards and site conditions requirements. (Make Astral Supreme for Pipe and Fittings) MDS Feedback As per MDS design there are only 50 mm Dia & 75 mm Dia Drain Pipe in drawing and BOQ not sure why 100 mm Dia uPVC Drain pipe is required. PPDS Feedback On Site Decision , as per discussion with project team.
[5 empty] | 395076.1 |  |  | Item Name MDS Feedback PPDS Feedback