## Summary Sheet
Summary Sheet_Fdt_Working_Rv1.2_21.11.2024
S.N | Item Description | PO Amount | Amount ( Adjusted ) | PO Required | Remarks
Biryani Bhai
1 | Curry Kitchen ( Guwahati ) | 1347011 | 921352.44 |  | Semolina/PO/23-24/000428 dated : 13.02.2024
2 | Coffee Box | 1007785 | 48000 |  | Semolina/PO/23-24/000430 dated : 13.02.2024
3 | Additional Item ( As per design ) | 0 | 0 | 233640.55
4 | TOTAL | 2354796 | 969352.44 | 233640.55
5 | GST 18% | 423863.28 | 174483.4392 | 42055.299
6 | G.TOTAL | 2778659.28 | 1143835.8792 | 275695.849
Note - Any additional job / item will be chargable extra
Equipment Unloading & Shifting Charges extra

## Biryani Bhai
| CURRY KITCHEN | Size - 6.0x2.5x2.7m | GUWAHATI | INDOOR | PO - Semolina/PO/23-24/000428 dated : 13.02.2024 |  |  |  |  | BIRYANI BHAI |  | LUCKNOW | Size - 6.0x2.5x2.7m
S.No | Head | Description | Drawing Ref No. | Make | Size | UOM | Qty | Rate | Amount(INR) | NEW QTY | Rate | Amount(INR) | Remarks
1 | MS Work | Providing & fixing of MS work in single section fixed with or without connecting plate including cutting, hoisting, fixing in position and applying a priming coat of approved red oxide steel primer at the top all complete. Item includes all MS steel items including sections, MS plates of grade Yst- 250,cleats,stiffners, anchor fasteners/ bolts, sleeves for pipes and wire management etc, as required for fixing. |  | Jindal/Tata | MB Sheet | Kgs | 670 | 165 | 110550 | 559.9697 | 165 | 92395.006
2 | Base & Flooring | Providing and fixing of 18mm FR Ply with 1.5mm thick aluminium checker sheet finish mounted over MS pipe 50mm SHS , C/C 600x600mm grid, 4mm thick MS Sheet |  | Century Ply, Tata/ Jindal | MB Sheet | Sqm | 15.3 | 4000 | 61200 | 15.352 | 4000 | 61408
3 | ACP Work (for Ceiling) | Providing , installing and fixing in position FR Aluminium Composite Panel Cladding for linear as well as curvilinear portions of the building , for all heights and all levels etc. including: a) Structural analysis & design and preparation of shop drawings') Back framing for panel as suited to site condition.eg.Alluminium or MS box sections etc c) Providing, fabricating and supplying and fixing panels of aluminium composite panel cladding in pan shape in metallic colour of approved shades as per specifications below. The Contractor shall provide wall with aluminium composite panel cladding, having all the performance characteristics all complete . (MS Structure cost not included in it) |  | Timex Alu decor or equivalent | MB Sheet | Sqm | 21.6 | 3500 | 75600 | 0 | 3500 | 0 | Not Required
4 | Shade for Roof | Providing & fixing of of 6mm Semi Transparent/opac sheet with MS Framing fix with self screw with required paint finish. (note : MS Structure is not included in this cost) |  |  | 6x 4 | Sqm | 24 | 1500 | 36000 | 0 | 1500 | 0 | Not Required
5 | Rafter's Foof | Providing and fixing of Wooden Rafter 12mm HDMR Laminate cladding with approved shade matt finish. |  | Century Ply & Merino |  | Rmt. | 19.2 | 1650 | 31680 | 0 | 1650 | 0 | Not Required
6 | Plywood Panelling | Providing , installing and fixing in position FR Plywood for linear as well as curvilinear portions of the building , for all heights and all levels & one side laminate finish etc. (MS Frame work charged seperatly) Includes all the performance characteristics all complete with 12mm PR Ply. |  | Century or equivalent |  | Sqm | 51.12 | 3200 | 163584 | 66.7884 | 3200 | 213722.784
7 | Wall Tile | Providing , installing and fixing in of yellow moroccon pattern tile on back wall |  | Somany/Kajaria or equivelant | MB Sheet | Sqm | 19.8 | 2400 | 47520 | 15.444 | 2400 | 37065.6
8 | Corian Cladding | Providing & fixing of 12mm Acrylic solid surface outside of side partion & front low height partion (Base Rate : 850 Sqft.) |  | LG Hi mac | MB Sheet | Sqm | 2.99 | 12500 | 37375 | 5.5149 | 12500 | 68936.25
9 | Paint | Apply of 2 coat white duco paint on pillar & side partition left&right |  | Asian Paint | MB Sheet | Sqm | 7.38 | 2400 | 17712 | 10.152 | 2400 | 24364.8
10 | Wooden Panelling | Providing & fixing of vertical groove laminate outside of side partion & horizontal groove wooden front full height cladding on existing plywood partition (Marino Laminate Base Rate : 65 Sqft.) |  |  | 2400x600x2, 2250x900x1, | Sqm | 5.175 | 3600 | 18630 | 0 | 3600 | 0 | Not Required
11 | Flap Door | Providing & Fixing of Slab & Flap door made of 18mm FR Ply with solid acrylic surface & inside laminate finish , Hydraulic hinges, SS knob, tower bolt etch. |  |  | 1x.9 | EA | 1 | 8800 | 8800 | 1 | 8800 | 8800
12 | Awning/Canvas | P& F Awnings on both of side Red & White Colour SRF make cloths with 40 mm x 40mm x3mm Thick Asian make squire aluminium pipe frame including 02 coat red oxide paint , 02 coat Asian make primer, and 02 coat Asian make oil paint on Rolling frame. |  | Cavas, HP Latex | 6000x1000x1, 3000x1000x2 | Sqm | 12 | 3600 | 43200 | 0 | 3600 | 0 | Not Required
13 | Kitchen Wooden Counter | Providing & Installation of counter made of FR Plywood with approved shade laminate finish, , two solft close drawers storage shutter door, (As per approved GFC) | 2 | Century Ply, FGV hinges | 1900x750x900 | No. | 2 | 36000 | 72000 | 0 | 36000 | 0 | Cant used
14 | Sink Cabinet | Providing and fixing of Sink counter made of 18mm FR Ply with laminate finish, 450x500mm SS 304 sink, shutter storage, plumbing fitting etc.(As Per approved GFC) | 9 | Century/Merino, SS Sink | 1500x750x900 | No. | 1 | 45760 | 45760 | 1 | 45760 | 45760 | Note; Change of Laminate & finishing charged separetly
15 | POS Counter | Providing and fixing of POS counter made of 18mm FR Ply with solid acryilc surface top finish, Step & inside laminate finish, two drawer, key board tray, storage, wire manager etc. (As per approved GFC) | 7 | Century/Merino/ FGV | 825x750x900 | No. | 2 | 45000 | 90000 | 1 | 45000 | 45000 | Note; Change of Laminate & finishing charged separetly
16 | Skink New Sensor Tap | Providing & Fitting of Sensor Tap as required |  | Euronics |  | Nos. | 1 | 7500 | 7500 | 1 | 7500 | 7500
17 | Water Pump | Providing & Fitting of Waterpump as required (Crompton AQUAGOLD 100-33 Residential Water Pump Self Priming Regenerative 1 HP Single Phase) |  | Crompton |  | Nos. | 1 | 8500 | 8500 | 1 | 8500 | 8500
18 | Site Storages | Providing and installation of make of 18mm & 12mm Fr Plywood with approved laminate finish with hinges soft closed shutter. |  | Century/Merino/ FGV | 1155x650x640 | Nos. | 1 | 22500 | 22500 | 1 | 22500 | 22500 | If will be used after refabrication,change of laminate & drawer removal, addon base & back | 1230 | 100 | 210
19 | Pendant Light | LED Light fixtures-Supply, installation, testing & commissioning of lighting fittings/ fixtures complete with LED driver, complete as required:- (Hanging Lamp) |  | Havells, Syska or equivalent |  | No. | 5 | 2500 | 12500 | 5 | 2500 | 12500
20 | Linear Profile Light | Providing & fixing linear profile light consealed in Rafter |  | Custom Make | 1200x1 | No. | 8 | 1800 | 14400 | 8 | 1800 | 14400
21 | Electrical | Supply and Laying of 1.5mm, 2.5mm & 4sqmm wiring with PVC conduit , 5amp & 15amp switch socket with box & plate,, MCB, ELCB, as per requirement or as approved electrical drawing |  | Polycab, Finolex, Roma, Crompton | 6000x3000 | No. | 1 | 88000 | 88000 | 1 | 88000 | 88000
22 | Industrial Socket | Industrial Socket & Panel Box (32amp ) |  |  |  | No. | 8 | 3500 | 28000 | 3 | 3500 | 10500
23 | Branding | Supply and pasting of HP latex printed artwork on grey back LG/Ivory/Pioneer media as per approved design artwork |  | HP Latex, 3M , LG Vinyl or equivalent |  | Sqft. | 0 | 150 | 0 | 0 | 150 | 0 | If Required
24 | Curry Kitchen LOGO | Front logo signaged fixed front chiller counter, UV Printed 3mm raised acrylic . |  | A cast , NGX , Osram | 900x900 | No. | 1 | 12000 | 12000 | 0 | 12000 | 0 | Not Required
25 | Curry Kitchen Header Signage | Providing and fixing of backlit channelium raised signages, NGX LED & Osram water proof supply with all required support structure (2100x 500x 1pcs) |  | A cast , NGX , Osram |  | No. | 1 | 22500 | 22500 | 1 | 22500 | 22500 | Briyan Bhai Signage
26 | Menu Board | Providing and fixing of Auto snap channel 32x32 powder coated with acrylic 040 & Clear Acrylic, edge lit LED, Changeable Translite Print. |  | A cast , NGX , Osram | 2x 3 | No. | 3 | 4500 | 13500 | 3 | 4500 | 13500
27 | TV Screen Menu | 32" LED TV with hanging Stand |  | Samsung/LG |  | No. |  | 28000 | 0 | 0 | 28000 | 0 | If Required
28 | CCTV Camera (4 Channel DVR) | DVR 5MP, 1 TB, 4 nos. 5MP Camera with Audio, 16" Display Monitor, 90mtr. D Link Wire |  | Hikvision |  | Set | 1 | 48000 | 48000 | 1 | 48000 | 48000
29 | Installation | Guwahati Airport |  |  |  | EA | 1 | 58000 | 58000 | 1 | 52000 | 52000 | T3 DOMESTIC LUCKNOW, Revised Cost
30 | Transportation | Guwahati Airport |  |  |  | EA | 1 | 78000 | 78000 | 1 | 24000 | 24000 | T3 DOMESTIC LUCKNOW, Revised Cost
31 | Labour Union Charges | Extra as on actual | [7 empty] | 0 | 0 | 0 | Not Required
32 | Side Wall Partition | Supply & Fixing of Wooden laminate finish Partition , make of MS 40mm SHS pipe Outer Frame, with 18mm HMDR CNC Jalli with Laminate with Match color paint in groove HMDR Cladding with approved wooden laminate finish , cutout as per design. |  |  | 2.44x2.150x2 | Sqm. | 10 | 7400 | 74000 | 0 | 7400 | 0 | Not Required
| TOTAL (A) | [7 empty] | 1347011 |  |  | 921352.44
| Coffee Box | BOQ for Coffee Cart: 4x 2.6x 3 (mtr.) | GUWAHATI | INDOOR | PO -Semolina/PO/23-24/000430 dated : 13.02.2024 |  |  |  |  | BIRYANI BHAI |  | LUCKNOW | Size - 6.0x2.5x2.7m
S.No | Head | Description | Refence Picture | Make | Size(in mm) | Unit | Qty | Rate | Amount (INR)
1 | MS Work | Providing & fixing of MS work in single section fixed with or without connecting plate including cutting, hoisting, fixing in position and applying a priming coat of approved red oxide steel primer and powder coated paint of approved shared at the top all complete. Item includes all MS steel items including sections, MS plates of grade Yst- 250,cleats,stiffners, anchor fasteners/ bolts, sleeves for pipes and wire management etc, as required for fixing. |  | Jindal/Tata |  | Kgs | 370 | 165 | 61050 | 0 |  |  | Unutilized
2 | Base & Flooring | Providing and fixing of 18mm FR Ply with 1.5mm thick aluminium checker sheet finish mounted over MS pipe 50mm SHS , C/C 600x600mm grid, 4mm thick MS Sheet |  | Century Ply, Tata/ Jindal | 400x2.50 | Sqm | 10.08 | 4000 | 40320 | 0 |  |  | Unutilized
3 | ACP Work (Ceiling) | Providing , installing and fixing in position FR Aluminium Composite Panel Cladding for linear as well as curvilinear portions of the building , for all heights and all levels etc. including: a) Structural analysis & design and preparation of shop drawings') Back framing for panel as suited to site condition.eg.Alluminium or MS box sections etc c) Providing, fabricating and supplying and fixing panels of aluminium composite panel cladding in pan shape in metallic colour of approved shades as per specifications below. The Contractor shall provide wall with aluminium composite panel cladding, having all the performance characteristics all complete . (approved Shade) (MS Structure cost not included) |  | Timex Alu decor or equivalent | 4x3.6 | Sqm | 14.4 | 3500 | 50400 | 0 |  |  | Unutilized
4 | Shade for Roof | Providing & fixing of of 6mm Semi Transparent/opac sheet with MS Framing fix with self screw with required paint finish. (note : MS Structure is not included in this cost) |  |  | 4x 4 | Sqm | 16 | 1500 | 24000 | 0 |  |  | Unutilized
5 | Rafter's Foof | Providing and fixing of Wooden Rafter 12mm HDMR Laminate cladding with approved shade matt finish. |  | Century Ply & Veneer |  | Rmt. | 12 | 1650 | 19800 | 0 |  |  | Unutilized
6 | Plywood Panelling | Providing , installing and fixing in position FR Plywood for linear as well as curvilinear portions of the building , for all heights and all levels & one side laminate finish etc. (MS Frame work charged seperatly) Includes all the performance characteristics all complete with 12mm PR Ply. |  | Century or equivalent |  | Sqm | 40.32 | 3200 | 129024 | 0 |  |  | Unutilized
7 | Wall Tile | Providing , installing and fixing in of red brick pattern tile on back wall |  | Customise Make | 4000x2700 | Sqm | 11 | 2400 | 26400 | 0 |  |  | Unutilized
8 | Corian Cladding | Providing & fixing of 12mm Acrylic solid surface outside of side partion & front low height partion (Base Rate : 850 Sqft.) |  | LG Hi mac | 4000x1000x1 | Sqm | 4 | 12500 | 50000 | 0 |  |  | Unutilized
9 | Paint | Apply of black duco paint on pillar & side partition left&right |  | Duco Paint | 2400x600 x2, 300x3000x4 | Sqm | 6 | 2400 | 14400 | 0 |  |  | Unutilized
10 | Flap Door | Providing & Fixing of Slab & Flap door made of 18mm FR Ply with solid acrylic suface & inside laminate finish , Hydraulic hinges, SS knob, tower bolt etch. |  | Century Ply, FGV hinges | 900x800 | EA | 1 | 8800 | 8800 | 0 |  |  | Unutilized
11 | Awining/Canvas | P& F Awinings on both of side Red & White Colour SRF make cloths with 40 mm x 40mm x3mm Thick Asian make squire aluminium pipe frame including 02 coat red oxide paint , 02 coat asian make primer, and 02 coat asian make oil paint on Rolling frame. |  | Cavas, HP Latex | 4000x1000x1, 3000x1000x2 | Sqm | 10 | 3600 | 36000 | 0 |  |  | Unutilized
12 | Kitchen Wooden Counter | Providing & Installation of counter made of FR Plywood with approved shade laminate finish, 2 nos soft close drawers, storage, MS pipe support (As per approved GFC) | 10 | Century Ply, FGV hinges | 2325x750x900 | No. | 1 | 52405 | 52405 | 0 |  |  | Unutilized
13 | Sink Cabinet | Providing and fixing of Sink counter made of 18mm FR Ply with laminate finish, 450x500mm SS 304 sink, storage, plumbing fitting etc.(As Per approved GFC) | 9 | Century/Merino, SS Sink | 1500x750x900 | No. | 1 | 44486 | 44486 | 0 |  |  | Unutilized
14 | POS Counter | Providing and fixing of POS counter made of 18mm FR Ply with solid acryilc surface top finish, Step & inside laminate finish, two drawer, key board tray, storage, wire manager etc. (As per approved GFC) | 7 | Century/Merino/ FGV | 825x750x900 | No. | 1 | 42000 | 42000 | 0 |  |  | Unutilized
15 | Chiller Counter | Providing & Installation of counter made of FR Plywood with approved shade laminate finish, 2 nos soft close drawers, storage, MS pipe support (As per approved GFC) | 8 | Century/Merino/ FGV | 2025x750x900 | No. | 1 | 48000 | 48000 | 1 | 48000 | 48000
16 | Skink New Sensor Tap | Providing & Fitting of Sensor Tap as required |  | Euronics |  | Nos. | 1 | 7500 | 7500
17 | Water Pump | Providing & Fitting of Waterpump as required |  | Crompton AQUAGOLD 100-33 Residential Water Pump Self Priming Regenerative 1 HP Single Phase |  | Nos. | 1 | 8500 | 8500 |  |  |  | Unutilized
18 | Linear Profile Light | Providing & fixing linear profile light consealed in Rafter |  | Custom make | 1200x1 | No. | 5 | 1800 | 9000 |  |  |  | Unutilized
19 | Electrical | Supply and Laying of 1.5mm, 2.5mm & 4sqmm wiring with PVC conduit , 5amp & 15amp switch socket with box & plate, DB panel, MCB, ELCB, as per requirement or as approved electrical drawing |  | Polycab, Finolex, Roma, Crompton | 4000x3000 | EA | 1 | 51000 | 51000 |  |  |  | Unutilized
20 | industrial Socket | Industrial Socket & Panel Box (32amp ) |  |  |  | No. | 5 | 3200 | 16000 |  |  |  | Unutilized
21 | Branding | Supply and pasting of HP latex printed artwork on grey back LG/Ivory/Pioneer media as per approved design artwork |  | HP Latex, 3M , LG Vinyl or equivalent | 600x4000 | Sqm | 2.4 | 1500 | 3600 |  |  |  | Unutilized
22 | Signages1 | Providing and fixing of backlit channelium raised signages, NGX LED & Osram water proof supply with all required support structure (1800x500x1 ps) |  | A cast , NGX , Osram |  | No. | 1 | 16000 | 16000 |  |  |  | Unutilized
23 | Menu Board | Providing and fixing of Auto snap channel 32x32 powder coated with acrylic 040 & Clear Acrylic, edge lit LED, Changeable Translite Print. |  | A cast , NGX , Osram | 2x 3 | No. | 3 | 4500 | 13500 |  |  |  | Unutilized
24 | TV Screen Menu | 32" LED TV with hanging Stand |  | Samsung/LG |  | No. |  | 28000 | 0 |  |  |  | Unutilized
25 | CCTV Camera (4 Channel DVR) | DVR 5MP, 1 TB, 4 nos. 5MP Camera with Audio, 16" Display Monitor, 90mtr. D Link Wire |  | Hikvision |  | Set | 1 | 38600 | 38600 |  |  |  | Unutilized
26 | Installation | Guwahati Airport |  |  |  | EA | 1 | 52000 | 52000 |  |  |  | Unutilized
27 | Transportation | Guwhati Airport |  |  |  | EA | 1 | 71000 | 71000 |  |  |  | Unutilized
28 | Labour Union Charges | Extra as on actual | [10 empty] | Unutilized
29 | Pendant Light | LED Light fixtures-Supply, installation, testing & commissioning of lighting fittings/ fixtures complete with LED driver, complete as required:- (Hanging Lamp) |  | Havells, Syska or equivalent |  | No. | 4 | 2500 | 10000 |  |  |  | Unutilized
30 | Side Wall Partition | Supply & Fixing of Wooden laminate finish Partition , make of MS 40mm SHS pipe, with 8mm HMDR Cladding with approved wooden laminate finish , 5mm Acrylic tringle cutout as per design. |  |  | 2.44x2.150x2 | Sqm. | 10 | 6400 | 64000 |  |  |  | Unutilized
| TOTAL (B) | [7 empty] | 1007785 |  |  | 48000
| GRAND TOTAL (A+B) | [10 empty] | 969352.44
NOTE: | GST Extra

## Additional Item
LKN_Biryani Bhai _Additional Item_Quotation_Rv1.2_21.11.24
S.No | Head | Description | Make | Size | UOM | Qty | Rate | Amount(INR)
33 | Sink Cabinet (Change of Laminate) | Change of laminate as per new design | GreenLam 277 SUD Charcoal | 1500x750x900 | No. | 1 | 7200 | 7200
34 | POS Counter Change of Laminate) | Change of laminate as per new design | GreenLam 277 SUD Charcoal | 825x750x900 | No. | 1 | 6400 | 6400
35 | POS New Counter | Providing and fixing of POS counter made of 18mm FR Ply , two drawer, storage, wire manager etc. (As per approved GFC) (Note Top Solid Acrylic surface ll be charged separetly) | Century/Greenlam/ FGV/Ebco | 870x750x900 | No. | 2 | 38000 | 76000
36 | Storage Counter( Re - fabrication ) | Refabrication & Change of laminate inside & out, removal of drawer, adding shutter doors, base plateform, addon thick back. | Century/Greenlam/ FGV Ebco | 1230x750x825 | No. | 1 | 16800 | 16800
37 | Chillar Counter ( Re - fabrication ) | Refabrication & Change of laminate inside & out, removal of drawer, adding shutter doors, base plateform, addon thick back. | Century/Greenlam/ FGV Ebco | 2025x750x900 | No. | 1 | 16000 | 16000
38 | Side Counter | Providing and fixing of counter made of 18mm FR Ply Outside & inside laminate finish, one shutter etc. (As per approved GFC) | Century/Greenlam/ FGV Ebco | 520x750x900 | No. | 1 | 18000 | 18000
39 | Chimney Boxing | Making and provide of a chimney plywood boxing FR 18mm with laminate finish out side , with required fixing detail | Century/Greenlam Laminate | 450x450x100 | No. | 2 | 2400 | 4800
40 | Glass Partition | Providing & Fixing of 10mm Glass Clear Toughened with groove fixing detail on partition top as per design front of the right counters. | Saint Gobain | 300x3000 | Sqm | 0.915 | 3500 | 3202.5
41 | Flute Panel | Provding & Fixing of approved charcol façade & counter(Left & Front) (In Clad Curve Series) | CUR 306 |  | Sqm | 10.773 | 2850 | 30703.05
42 | SS Guard Rail | Providing & Fixing of SS Guard Rail 38mm DIA pipe , with arms fixing with floor or counter. | SS 304 | 5200x150 | Rmt. | 5.2 | 1800 | 9360
43 | SS Skirting | Providing & Fixing of SS 1.2mm thick skirting 100mm 2 side of counter | SS 304 | 2450+6000x100 | Rmt. | 8.45 | 1500 | 12675
44 | DB Panel | Supply & Fixing of 12mm Way DB Panel wit 1 No. RCB & MCB 12 No's. | L&T |  | No | 1 | 12500 | 12500
45 | Main Cable | Supply & Fixing of 4 core 10 Sqm Coppe Cable for main DB to Meter | Polycab, Finolex, Roma, Crompton |  | Mtr. | 10 | 750 | 7500
46 | Electrical Meter | Supply & Installation Single phase meter | Liberty 200 |  | Nos | 1 | 12500 | 12500
| TOTAL © | [6 empty] | 233640.55

## MB SHEET
| BIRIYANI BHAI | INDOOR AREA _6000x2575x2700H(mm) | LOCATION | T3 AIRPORT DOMASTIC LUCK | Measurement sheet
S.No | Head | Description | Make | Size | UOM | Length | Width | Height /Thick | No. | Qty | Final to billing BOQ
1 | MS Work | Providing & fixing of MS work in single section fixed with or without connecting plate including cutting, hoisting, fixing in position and applying a priming coat of approved red oxide steel primer at the top all complete. Item includes all MS steel items including sections, MS plates of grade Yst- 250,cleats,stiffners, anchor fasteners/ bolts, sleeves for pipes and wire management etc, as required for fixing. | Jindal/Tata |  | Kgs |  |  |  |  | 559.9697 | 559.9697
|  | Back Structure - 40x40x1.5mm, Horizontal |  |  |  | 6.08 | 0.04 | 0.0015 | 5 | 57.2736
|  | Vertical |  |  |  | 2.6 | 0.04 | 0.0015 | 10 | 48.984
|  | Bottom Structure -50x50x1.5mm Horizontal |  |  |  | 6.08 | 0.05 | 0.0015 | 5 | 71.592
|  | Vertical |  |  |  | 2.525 | 0.05 | 0.0015 | 10 | 59.4638
|  | Left Side-40x40x1.5 Horizontal with bulkhead |  |  |  | 2.45 | 0.04 | 0.0015 | 5 | 23.079
|  | Vertical with bulkhead |  |  |  | 1.297 | 0.04 | 0.0015 | 5 | 12.2177
|  | Right Side-40x40x1.5 Horizontal |  |  |  | 2.45 | 0.04 | 0.0015 | 5 | 23.079
|  | Vertical |  |  |  | 2.6 | 0.04 | 0.0015 | 5 | 24.492
|  | Front Side-40x40x1.5 with bulkhead, Horizontal |  |  |  | 6.08 | 0.04 | 0.0015 | 3 | 34.3642
|  | Horizontal |  |  |  | 4.028 | 0.04 | 0.0015 | 1 | 7.5888
|  | Horizontal |  |  |  | 4.426 | 0.04 | 0.0015 | 1 | 8.3386
|  | Vertical |  |  |  | 0.947 | 0.04 | 0.0015 | 6 | 10.7049
|  | Bulkhead |  |  |  | 0.31 | 0.04 | 0.0015 | 8 | 4.6723
|  | Pillar (50x50x1.5) |  |  |  | 2.6 | 0.05 | 0.0015 | 3 | 18.369
|  | Roof Horizontal Pipe (40mmx40mmx1.5) Horizontal |  |  |  | 6.08 | 0.04 | 0.0015 | 5 | 57.2736
|  | Vertical |  |  |  | 2.525 | 0.04 | 0.0015 | 10 | 47.571
2 | Base & Flooring | Providing and fixing of 18mm FR Ply with 1.5mm thick aluminium checker sheet finish mounted over MS pipe 50mm SHS , C/C 600x600mm grid, | Century Ply, Tata/ Jindal |  | Sqm | 6.08 | 2.525 |  | 1 | 15.352 | 15.352
3 | ACP Work (for Ceiling) | Providing , installing and fixing in position FR Aluminium Composite Panel Cladding for linear as well as curvilinear portions of the building , for all heights and all levels etc. including: a) Structural analysis & design and preparation of shop drawings') Back framing for panel as suited to site condition.eg.Alluminium or MS box sections etc c) Providing, fabricating and supplying and fixing panels of aluminium composite panel cladding in pan shape in metallic colour of approved shades as per specifications below. The Contractor shall provide wall with aluminium composite panel cladding, having all the performance characteristics all complete . (MS Structure cost not included in it) | Timex Alu decor or equivalent | 6000x3600 | Sqm |  |  |  | 0 | 0 | 0
4 | Shade for Roof | Providing & fixing of of 6mm Semi Transparent/opac sheet with MS Framing fix with self screw with required paint finish. (note : MS Structure is not included in this cost) |  | 6x 4 | Sqm |  |  |  | 0 | 0 | 0
5 | Rafter's Foof | Providing and fixing of Wooden Rafter 12mm HDMR Laminate cladding with approved shade matt finish. | Century Ply & Merino |  | Rmt. |  |  |  | 0 | 0 | 0
6 | Plywood Panelling | Providing , installing and fixing in position FR Plywood for linear as well as curvilinear portions of the building , for all heights and all levels & one side laminate finish etc. (MS Frame work charged seperatly) Includes all the performance characteristics all complete with 12mm PR Ply. | Century or equivalent |  | Sqm |  |  |  |  | 66.7884 | 66.7884
|  | Back Wall |  |  |  | 6.08 | 2.6 | 2 | 31.616
|  | Front |  |  |  | 6.08 | 0.987 | 2 | 12.0019
|  | Left Wall |  |  |  | 2.5 | 0.987 | 2 | 4.935
|  | Right Wall |  |  |  | 2.5 | 2.6 | 2 | 13
|  | Façade |  |  |  | 6.08 | 0.4 | 2 | 4.864
|  | Façade Left |  |  |  | 2.5 | 0.4 | 2 | 2
|  | Less Flap Door |  |  |  | 0.825 | 0.987 | -2 | -1.6285
7 | Wall Tile | Providing , installing and fixing in of yellow moroccon pattern tile on back wall | Somany/Kajaria or equivelant |  | Sqm |  |  |  |  | 15.444 | 15.444
|  | Back Wall |  |  |  | 6.08 | 1.8 | 1 | 10.944
[6 empty] | 2.5 | 1.8 | 1 | 4.5
8 | Corian Cladding | Providing & fixing of 12mm Acrylic solid surface outside of side partion & front low height partion, Top (Base Rate : 850 Sqft.) black | Hi Mack/Hyus |  | Sqm |  |  |  |  | 5.5149 | 5.5149
|  | Partition end cap top front |  |  |  | 6.08 | 0.15 | 1 | 0.912
|  | Partition end cap top Left |  |  |  | 2.5 | 0.15 | 1 | 0.375
|  | Sink Counter |  |  |  | 1.5 | 0.783 | 1 | 1.1745
|  | POS counter 1 |  |  |  | 1.708 | 0.825 | 1 | 1.4091
|  | POS counter 2 |  |  |  | 0.87 | 0.783 | 1 | 0.68121
|  | Side Counter |  |  |  | 1.23 | 0.783 | 1 | 0.96309
9 | Paint | Apply of 2 coat white enamel emulsion paint on pillar & side partition left&right | Duco Paint |  | Sqm |  |  |  |  | 10.152 | 10.152
|  | Roof Horizontal & Vertical Pipe (40mmx40mm) |  |  |  | 6.08 | 0.04 | 5 | 4.864
|  | Roof Horizontal & Vertical Pipe (40mmx40mm) |  |  |  | 2.525 | 0.04 | 10 | 4.04
|  | Pillar |  |  |  | 2.6 | 0.04 | 3 | 1.248
10 | Wooden Panelling | Providing & fixing of vertical groove laminate outside of side partion & horizontal groove wooden front full height cladding on existing plywood partition (Marino Laminate Base Rate : 65 Sqft.) |  | 2400x600x2, 2250x900x1, | Sqm |  |  |  | 0 | 0 | 0
11 | Flap Door | Providing & Fixing of Slab & Flap door made of 18mm FR Ply with laminate finish , hinges, SS knob, tower bolt etch. |  |  | No |  | 0.824 | 0.987 | 1 | 1 | 1
12 | Awning/Canvas | P& F Awnings on both of side Red & White Colour SRF make cloths with 40 mm x 40mm x3mm Thick Asian make squire aluminium pipe frame including 02 coat red oxide paint , 02 coat Asian make primer, and 02 coat Asian make oil paint on Rolling frame. | Cavas, HP Latex | 6000x1000x1, 3000x1000x2 | Sqm |  |  |  | 0 | 0 | 0
13 | Kitchen Wooden Counter | Providing & Installation of counter made of FR Plywood with approved shade laminate finish, , two solft close drawers storage shutter door, (As per approved GFC) | Century Ply, FGV hinges | 1900x750x900 | No. |  |  |  | 0 | 0 | 0
14 | Sink Cabinet | Providing and fixing of Sink counter made of 18mm FR Ply with laminate finish, 450x500mm SS 304 sink, shutter storage, plumbing fitting etc.(As Per approved GFC) | Century/Merino, SS Sink | 1500x750x900 | No. | No. | 1.5 | 0.75 | 0.9 | 1 | 1
15 | POS Counter | Providing and fixing of POS counter made of 18mm FR Ply with solid acryilc surface top finish, Step & inside laminate finish, two drawer, key board tray, storage, wire manager etc. (As per approved GFC) | Century/Merino/ FGV | 825x750x900 | No. | No. | 0.825 | 0.75 | 0.9 | 1 | 1
16 | Skink New Sensor Tap | Providing & Fitting of Sensor Tap as required | Euronics |  | Nos. |  |  |  | 1 | 1 | 1
17 | Water Pump | Providing & Fitting of Waterpump as required(Crompton AQUAGOLD 100-33 Residential Water Pump Self Priming Regenerative 1 HP Single Phase) | Crompton |  | Nos. |  |  |  | 1 | 1 | 1
18 | Side Storages | Providing and installation of make of 18mm & 12mm Fr Plywood with approved laminate finish with hinges soft closed shutter. | Century/Merino/ FGV | 1155x900x750 | Nos. | 1.15 | 0.9 | 0.75 |  | 0 | 0
19 | Pendant Light | LED Light fixtures-Supply, installation, testing & commissioning of lighting fittings/ fixtures complete with LED driver, complete as required:- (Hanging Lamp) | Havells, Syska or equivalent |  | No. |  |  |  |  | 5 | 5
20 | Linear Profile Light | Providing & fixing linear profile light consealed in Rafter | Custom Make | 1200x1 | No. |  |  |  |  | 8 | 8
21 | Electrical | Supply and Laying of 1.5mm, 2.5mm & 4sqmm wiring with PVC conduit , 5amp & 15amp switch socket with box & plate, MCB, ELCB, as per requirement or as approved electrical drawing | Polycab, Finolex, Roma, Crompton | 6000x2576 | No. |  |  |  |  | 1 | 1
22 | Industrial Socket | Industrial Socket & Panel Box (32amp ) |  |  | No. |  |  |  |  | 3 | 3
23 | Branding | Supply and pasting of HP latex printed artwork on grey back LG/Ivory/Pioneer media as per approved design artwork | HP Latex, 3M , LG Vinyl or equivalent |  | Sqft. |  |  |  |  | 0 | 0
24 | BIRYANI BHAI LOGO | Front logo signaged fixed front chiller counter, UV Printed 3mm raised acrylic . | A cast , NGX , Osram | 900x900 | No. |  |  |  |  | 0 | 0
25 | BIRYANI BHAI Header Signage | Providing and fixing of backlit channelium raised signages, NGX LED & Osram water proof supply with all required support structure (1200x 300x 1pcs) | A cast , NGX , Osram |  | No. | 1.2 | 0.3 |  | 1 | 1 | 1
26 | Menu Board | Providing and fixing of Auto snap channel 32x32 powder coated with acrylic 040 & Clear Acrylic, edge lit LED, Changeable Translite Print. | A cast , NGX , Osram | 2x 3 | No. | 0.6 | 0.9 |  | 3 | 3 | 3
27 | TV Screen Menu | 32" LED TV with hanging Stand | Samsung/LG |  | No. |  |  |  | 0 | 0 | 0
28 | CCTV Camera (4 Channel DVR) | DVR 5MP, 1 TB, 2nos. 5MP Camera with Audio, 16" Display Monitor, 90mtr. D Link Wire | Hikvision |  | Set |  |  |  | 1 | 1 | 1
29 | Installation | T3 DOMESTIC LUCKNOW |  |  | EA |  |  |  |  | 1 | 1
30 | Transportation | T3 DOMESTIC LUCKNOW |  |  | EA |  |  |  |  | 1 | 1
31 | Labour Union Charges | Extra as on actual |  |  | EA |  |  |  | 0 | 0 | 0
32 | Side Wall Partition | Supply & Fixing of Wooden laminate finish Partition , make of MS 40mm SHS pipe Outer Frame, with 18mm HMDR CNC Jalli with Laminate with Match color paint in groove HMDR Cladding with approved wooden laminate finish , cutout as per design. |  | 2.44x2.150x2 | Sqm. |  |  |  | 0 | 0 | 0
| Coffee Box | BOQ for Coffee Cart: 4x 2.6x 3 (mtr.)
1 | Chiller Counter | Providing & Installation of counter made of FR Plywood with approved shade laminate finish, 2 nos soft close drawers, storage, MS pipe support (As per approved GFC) | 2025x750x900 |  | No | 2.025 | 0.75 | 0.9 | 1 | 1 | 1
Addon Requirement after Design Change
33 | Sink Cabinet (Change of Laminate) | Change of laminate as per new design | GreenLam 277 SUD Charcoal | 1500x750x900 | No. | 1.5 | 0.75 | 0.9 | 0.9 | 1 | 1
34 | POS Counter Change of Laminate) | Change of laminate as per new design | GreenLam 277 SUD Charcoal | 825x750x900 | No. | 0.825 | 0.75 | 0.9 | 0.9 | 1 | 1
35 | POS New Counter | Providing and fixing of POS counter made of 18mm FR Ply , two drawer, storage, wire manager etc. (As per approved GFC) (Note Top Solid Acrylic surface ll be charged separetly) | Century/Greenlam/ FGV/Ebco | 870x750x900 | No. | 0.87 | 0.825 | 0.85 | 2 | 2 | 2
36 | Storage Counter | Refabrication & Change of laminate inside & out, removal of drawer, adding shutter doors, base plateform, addon thick back. | Century/Greenlam/ FGV Ebco | 1230x750x825 | No. | 1.23 | 0.75 | 0.825 | 0.9 | 1 | 1
37 | Chillar Counter | Refabrication & Change of laminate inside & out, removal of drawer, adding shutter doors, base plateform, addon thick back. | Century/Greenlam/ FGV Ebco | 2025x750x900 | No. | 2.025 | 0.75 | 0.9 | 0.9 | 1 | 1
38 | Side Counter | Providing and fixing of counter made of 18mm FR Ply Outside & inside laminate finish, one shutter etc. (As per approved GFC) | Century/Greenlam/ FGV Ebco | 520x750x900 | No. | 0.52 | 0.75 | 0.9 | 0.9 | 1 | 1
39 | Chimney Cover | Making and provide of a chimney plywood boxing FR 18mm with laminate finish out side , with required fixing detail |  | 450 x450x100 | No. | 0.45 | 0.45 | 0.1 | 2 | 2 | 2
40 | Glass Partition | Providing & Fixing of 10mm Glass Clear Toughened with groove fixing detail on partition top as per design front of the right counters. | Saint Gobain | 300x3000 | Sqm | 3 | 0.305 |  | 1 | 0.915 | 0.915
41 | Flute Panel | Provding & Fixing of approved charcol façade & counter(Left & Front) (In Clad Curve Series) | CUR 306 |  | Sqm |  |  |  |  | 10.773 | 10.773
[6 empty] | 2.45 | 0.95 | 1 | 2.3275
[6 empty] | 2.45 | 0.31 | 1 | 0.7595
[6 empty] | 6.1 | 0.95 | 1 | 5.795
[6 empty] | 6.1 | 0.31 | 1 | 1.891
42 | SS Guard Rail | Providing & Fixing of SS Guard Rail 38mm DIA pipe , with arms fixing with floor or counter. | SS 304 | 5200x150 | Rmt. | 5.2 |  | 1 | 5.2 | 5.2 | 5.2
43 | SS Skirting | Providing & Fixing of SS 1.2mm thick skirting 100mm 2 side of counter | SS 304 | 2450+6000x100 | Rmt. | 8.45 |  | 1 | 8.45 | 8.45 | 8.45
44 | DB Panel | Supply & Fixing of 12mm Way DB Panel wit 1 No. RCB & MCB 12 No's. | L&T |  | No |  |  |  | 1 | 1 | 1
45 | Main Cable | Supply & Fixing of 4 core 10 Sqm Coppe Cable for main DB to Meter | Polycab, Finolex, Roma, Crompton |  | Mtr. |  |  |  | 10 | 10 | 10
46 | Electrical Meter | Supply & Installation Single phase meter | Liberty 200 |  | Nos |  |  |  | 1 | 1 | 1