## F&B
S.No. | Location | Unit No. | Area (sqm) | Category | Final Brand | Concessionaire | For Design | For Concessionaire | Line of Design (LOD) | Mechanical, Electrical, Plumbing Fire (MEPF ) | IT | Expected Date from Chapman Taylor | DS Floated | DS Approved | LOI Floated | LOI Status | Designer Name | Onboarding Date | Design First-Cut date | Actual submission date | Comments/ Inputs from NMIAL & C&W | Final Layout from SKPL | Render Submission | Tender Docket | PO Issue to Contractor | HOTO to Non Aero from Projects | Dates As per disc. 23 oct 24 (Vendor Mob.) | HOTO to Concessioner | Vendor Mobilization/Site Kick off | Fit-out time | Fit-out Completion | GO LIVE
1 | DOM-SHA | H2-0186(H2-0273+H2-0275) | 128.92 | Coffee | AJ Kitchen | SKPL | [6 empty] | N | N | N | N | BRAND | 2024-11-22 | 2024-11-29 | 2024-12-02 | 2024-12-05 | 2024-12-12 | 2024-12-22 | 2025-01-03 | 2025-01-15 | 2024-11-15 | 2024-12-15 | 2024-12-15 | 2025-01-18 | 60 | 2025-03-19 | 2025-03-20
2 | DOM-SHA | H2-0191(H2-0056+H2-190) | 572.82 | Mumbai local restaurants(4 Cuisines wise | KMC*+Bayroute | SKPL | [6 empty] | Y | Y | N | N | ACME | 2024-10-18 | 2024-10-31 | 2024-11-04 | 2024-11-09 | 2024-11-22 | 2024-12-12 | 2024-12-27 | 2025-01-03 | 2024-11-15 | 2024-12-15 | 2025-01-11 | 2025-01-12 | 120 | 2025-05-12 | 2025-05-13
3 | DOM-SHA | H2-0192(H2-0189) | 215.51 | Mumbai local restaurants(4 Cuisines wise | FOO+Bombay Brasserie | SKPL | [6 empty] | Y | Y | N | N | ARA | 2024-10-18 | 2024-10-31 | 2024-11-04 | 2024-11-09 | 2024-11-23 | 2024-11-25 | 2024-12-10 | 2024-12-17 | 2024-11-15 | 2024-12-15 | 2024-12-25 | 2024-12-26 | 120 | 2025-03-15 | 2025-03-16
4 | DOM-SHA | H2-0225(H2-0260) | 124.62 | South Indian | Gully Kitchen | SKPL | [6 empty] | Y | Y | N | N | NSA | 2024-10-18 | 2024-10-31 | 2024-11-04 | 2024-11-09 | Awaited | 2024-11-25 | 2024-12-10 | 2024-12-20 | 2024-11-15 | 2024-12-15 | 2024-12-25 | 2024-12-26 | 120 | 2025-03-15 | 2025-03-16
5 | DOM-SHA | H2-0209(H2-0261) | 86.01 | South Indian | Gully Kitchen | SKPL | [6 empty] | Y | Y | N | N | NSA | 2024-10-18 | 2024-10-31 | 2024-11-04 | 2024-11-09 | Awaited | 2024-11-25 | 2024-12-10 | 2024-12-19 | 2024-11-15 | 2024-12-15 | 2024-12-25 | 2024-12-26 | 120 | 2025-03-15 | 2025-03-16
6 | DOM-SHA | H2-7071(H2-0203) | 425.36 | Indian Food Hall | Mid-end Coffee(anchor)+ Food Hall | SKPL | [6 empty] | Y | Y | N | N | ACME | 2024-10-18 | 2024-10-31 | 2024-11-04 | 2024-11-09 | On hold. LOD to revise | 2024-11-25 | 2024-12-10 | 2024-12-17 | 2024-11-15 | 2024-12-15 | 2024-12-25 | 2024-12-26 | 110 | 2025-03-05 | 2025-03-06
7 | DOM-SHA | H2-0202(H2-0259) | 489.32 | Indian Food Hall | Mid-end Coffee(anchor)+ Food Hall | SKPL | [6 empty] | Y | Y | N | N | ACME | 2024-10-18 | 2024-10-31 | 2024-11-04 | 2024-11-09 | On hold. LOD to revise | 2024-11-25 | 2024-12-10 | 2024-12-17 | 2024-11-15 | 2024-12-15 | 2024-12-25 | 2024-12-26 | 110 | 2025-03-05 | 2025-03-06
8 | DOM-SHA | H2-0058(H2-7073) | 384.48 | Intl Casual Dining | Wagamama | SKPL | [6 empty] | Y | Y | N | N | MDS | 2024-10-18 | 2024-11-20 | 2024-11-22 | 2024-11-26 | 2024-12-10 | 2024-12-25 | 2025-01-09 | 2025-01-16 | 2024-11-15 | 2024-12-15 | 2025-01-24 | 2025-01-25 | 110 | 2025-05-15 | 2025-05-16
9 | DOM-SHA | H2-0201(H2-0054) | 299.1 | Microbrewery | Beer Bar | SKPL | [6 empty] | Y | Y | N | N | FKD | 2024-10-18 | 2024-10-31 | 2024-11-04 | 2024-11-09 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-01 | 2024-11-07 | 2024-12-15 |  |  |  |  | 1899-12-31
10 | DOM-Departure Pier | W2-0048 | 32 | QSR | Idli.com | SKPL | [6 empty] | N | N | N | N | NSA | 2024-10-18 | 2024-10-31 | 2024-11-04 | 2024-11-09 | 2024-11-20 | 2024-12-05 | 2024-12-20 | 2024-12-08 | 2024-10-30 | 2024-12-15 |  |  |  |  | 1899-12-31
11 | DOM-Departure Pier | W2-0058 | 58 | Coffee | Subway | SKPL | [6 empty] | Y | Y | N | N | Brand | 2024-10-18 | 2024-11-20 | 2024-11-27 | 2024-11-30 | 2024-12-07 | 2024-12-22 | 2024-12-29 | 2025-01-05 | 2024-10-30 | 2024-12-15 | 2025-01-13 | 2025-01-14 | 110 | 2025-05-04 | 2025-05-05
12 | DOM Bus Gates | H0-0201 | 11.7 | Coffee | Third Wave Coffee | SKPL | [6 empty] | Y | Y | N | N | NSA | 2024-10-18 | 2024-10-31 | 2024-11-28 | 2024-12-01 | 2024-12-08 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2024-10-30 | 2024-12-15 | 2025-01-14 | 2025-01-15 | 110 | 2025-05-05 | 2025-05-06
13 | Bus Gates(Intl) | H0-0208 | 10.64 | Grab&Go | Flying Bites | SKPL | [6 empty] | Y | Y | N | N | NSA | 2024-10-18 | 2024-10-31 | 2024-11-29 | 2024-12-02 | 2024-12-09 | 2024-12-24 | 2024-12-31 | 2025-01-07 | 2024-10-30 | 2024-12-15 | 2025-01-15 | 2025-01-16 | 110 | 2025-05-06 | 2025-05-07
14 | Intl SHA | H2-0102(H2-0271) | 257 | Coffee+Chef concept+Tasting Bar | Gordon Ramsay | SKPL | [6 empty] | Y | Y | N | N | AJ | 2024-10-18 | 2024-11-20 | 2024-11-30 | 2024-12-03 | 2024-12-10 | 2024-12-25 | 2025-01-01 | 2025-01-08 | 2025-01-15 | 2024-12-15 | 2025-01-16 | 2025-01-17 | 110 | 2025-05-07 | 2025-05-08
15 | Intl SHA | H2-0235(H2-0055,H2-0112) | 560.74 | Premium Food Hall | Nando’s | SKPL | [6 empty] | Y | Y | N | N | ARA | 2024-10-21 | 2024-11-20 | 2024-12-01 | 2024-12-04 | 2024-12-11 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-15 | 2024-12-15 | 2025-01-17 | 2025-01-18 | 120 | 2025-05-18 | 2025-05-19
16 | Intl SHA | H2-0237 | 65.95 | Premium Food Hall | Chef Pillai | SKPL | [6 empty] | Y | Y | N | N | ARA | 2024-10-18 | 2024-11-20 | 2024-12-02 | 2024-12-05 | 2024-12-12 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-01-15 | 2024-12-15 | 2025-01-18 | 2025-01-19 | 110 | 2025-05-09 | 2025-05-10
17 | Intl SHA | H2-0238 | 63.62 | Premium Food Hall | Harpal Sokhi | SKPL | [6 empty] | Y | Y | N | N | ARA | 2024-10-18 | 2024-11-20 | 2024-12-03 | 2024-12-06 | 2024-12-13 | 2024-12-28 | 2025-01-04 | 2025-01-11 | 2025-01-15 | 2024-12-15 | 2025-01-19 | 2025-01-20 | 110 | 2025-05-10 | 2025-05-11
18 | Intl SHA | H2-0233(H2-0263) | 21.97 | Grab & Go | Bombay Sweet Shop | SKPL | [6 empty] | Y | Y | N | N | Muffins | 2024-10-18 | 2024-11-20 | 2024-12-04 | 2024-12-07 | 2024-12-14 | 2024-12-29 | 2025-01-05 | 2025-01-12 | 2024-11-15 | 2024-12-15 | 2025-01-20 | 2025-01-21 | 110 | 2025-05-11 | 2025-05-12
19 | Intl SHA Piers | E2-0041 | 42 | Vegetarian Concept(including Gujarati concept) | Thepla House | SKPL | [6 empty] | Y | Y | N | N | Muffins | 2024-10-18 | 2024-11-20 | 2024-12-05 | 2024-12-08 | 2024-12-15 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-15 | 2024-12-15 | 2025-01-21 | 2025-01-22 | 110 | 2025-05-12 | 2025-05-13
20 | Forecourt | F2-0002 | 52 | Coffee | Hatti Kaapi | SKPL | [6 empty] | Y | Y | N | N | Muffins
21 | Forecourt | F2-0007 | 54 | Mumbai Street Food | Mumbai Street Food | SKPL | [6 empty] | Y | Y | N | N | NSA
22 | Forecourt | F0-0001(F0-0002) | 387.78 | Microbrewery | Microbrewery | SKPL | [6 empty] | Y | Y | N | N | FKD
23 | Forecourt | F0-0023(F0-0024) | 104 | Casual Dining | Nando’s /Jamie's Pizzeria | SKPL | [6 empty] | N | N | N | N | ARA
24 | Forecourt | F0-0019(F0-0020) | 199 | QSR | WOW eats - Momos china kulfi | SKPL | [6 empty] | Y | Y | N | N | Brand
25 | Forecourt | F0-0016(F0-0018) | 234 | QSR | KFC+Dominos | SKPL | [6 empty] | Y | Y | N | N | Brand
26 | Forecourt | FM - 0052(FM-0015+FM-0016) | 627 | Microbrewery | Microbrewery | SKPL | [6 empty] | Y | Y | N | N | FKD
27 | Intl SHA | H3 5017 | 2616 | International Lounge | International Lounge | SKPL | [10 empty] | Design Wilkes | [9 empty] | 2024-01-15
SKPL - 26 outlet // 16 designer on board
|  | Phase 1 |  | Brands | [5 empty] | Location | [5 empty] | Location
|  | 6 outlet first cut - 18th Oct |  | Foo+Bayroute | Mid-end Coffee(anchor)+ Food Hall | Mid-end Coffee(anchor)+ Food Hall | Kids' Gaming Zone (services) | Tech Grab & Go+ CTN | Pravasi | Domestic piers. Project update - Handover on need basis. |  |  | Wagamama | Subway | Third Wave Coffee | 30th Oct// 7th Nov// 15th Nov
|  | 3 outlet |  | Eric Kaysar | Microbrewery | Idli.com |  |  |  | SHA - 15th Nov. | [5 empty] | 30th Oct// 7th Nov// 15th Nov
Formulas:
Fit-out Completion = [Vendor Mobilization/Site Kick off]+[Fit-out time]
Fit-out Completion = [Fit-out time]+[HOTO to Non Aero from Projects]
Onboarding Date = [1]SKPL!O4
Onboarding Date = [Onboarding Date, row above]
Render Submission = [Final Layout from SKPL]+20
Render Submission = [Design First-Cut date]+25
Tender Docket = [Render Submission]+15
PO Issue to Contractor = [Tender Docket]+7
HOTO to Concessioner = MAX([Tender Docket]+15,[HOTO to Non Aero from Projects])
Vendor Mobilization/Site Kick off = [HOTO to Concessioner]+1
GO LIVE = [Fit-out Completion]+1
Comments/ Inputs from NMIAL & C&W = [Actual submission date]+3
Final Layout from SKPL = [Comments/ Inputs from NMIAL & C&W]+7

## Boardout sizes
S.No. | Location | Unit No. | Area (sqm) | Category | Final Brand | Concessionaire | Designer Name | Height | Width | Total Arean sqmt | Door | Flex
1 | DOM-SHA | H2-0186(H2-0273+H2-0275) | 128.92 | Coffee | AJ Kitchen | SKPL | BRAND | 4 | 12 | 48 | 4'-6"-2nos | 48
2 | DOM-SHA | H2-0191(H2-0056+H2-190) | 572.82 | Mumbai local restaurants(4 Cuisines wise | KMC*+Bayroute | SKPL | ACME | 4 | 46.5 | 186 | 4'-6"-3 nos | 186
3 | DOM-SHA | H2-0192(H2-0189) | 215.51 | Mumbai local restaurants(4 Cuisines wise | FOO+Bombay Brasserie | SKPL | ARA | 4 | 8 | 32 | 4'-6"-1nos | 32
4 | DOM-SHA | H2-0225(H2-0260) | 124.62 | South Indian | Gully Kitchen | SKPL | NSA | 4 | 16 | 64 | 4'-6"-1nos | 64
5 | DOM-SHA | H2-0209(H2-0261) | 86.01 | South Indian | Gully Kitchen | SKPL | NSA | 4 | 16 | 64 | 4'-6"-2 nos | 64
6 | DOM-SHA | H2-7071(H2-0203) | 425.36 | Indian Food Hall | Mid-end Coffee(anchor)+ Food Hall | SKPL | ACME | 4 | 12 | 48 | 4'-6"-1 nos | 48
7 | DOM-SHA | H2-0202(H2-0259) | 489.32 | Indian Food Hall | Mid-end Coffee(anchor)+ Food Hall | SKPL | ACME | 4 | 12 | 48 | 4'-6"-2nos | 48
8 | DOM-SHA | H2-0058(H2-7073) | 384.48 | Intl Casual Dining | Wagamama | SKPL | MDS | 4 | 71 | 284 | 4'-6"-3nos | 284
9 | DOM-SHA | H2-0201(H2-0054) | 299.1 | Microbrewery | Beer Bar | SKPL | FKD | 4 | 5 | 20 | 4'-6"-2nos | 20
10 | DOM-Departure Pier | W2-0048 | 32 | QSR | Idli.com | SKPL | NSA | 4 | 5 | 20 | 4'-6"-1nos | 20
11 | DOM-Departure Pier | W2-0058 | 58 | Coffee | Subway | SKPL | Brand | 4 | 8 | 32 | 4'-6"-1nos | 32
12 | DOM Bus Gates | H0-0201 | 11.7 | Coffee | Third Wave Coffee | SKPL | NSA | 4 | 5 | 20 | 4'-6"-1nos | 20
13 | Bus Gates(Intl) | H0-0208 | 10.64 | Grab&Go | Flying Bites | SKPL | NSA | 4 | 7 | 28 | 4'-6"-1nos | 28
14 | Intl SHA | H2-0102(H2-0271) | 257 | Coffee+Chef concept+Tasting Bar | Gordon Ramsay | SKPL | AJ | 4 | 12 | 48 | 4'-6"-1nos | 48
15 | Intl SHA | H2-0235(H2-0055,H2-0112) | 560.74 | Premium Food Hall | Nando’s | SKPL | ARA | 4 | 67 | 268 | 4'-6"-2 nos | 268
16 | Intl SHA | H2-0237 | 65.95 | Premium Food Hall | Chef Pillai | SKPL | ARA | 4 | inc in point 16 |  | 4'-6"-1 nos
17 | Intl SHA | H2-0238 | 63.62 | Premium Food Hall | Harpal Sokhi | SKPL | ARA | 4 | inc in point 16 |  | 4'-6"-1 nos
18 | Intl SHA | H2-0233(H2-0263) | 21.97 | Grab & Go | Bombay Sweet Shop | SKPL | Muffins | 4 | 6 | 24 | 4'-6"-1 nos | 24
19 | Intl SHA Piers | E2-0041 | 42 | Vegetarian Concept(including Gujarati concept) | Thepla House | SKPL | Muffins | 4 | 5 | 20 | 4'-6"-1 nos | 20
20 | Forecourt | F2-0002 | 52 | Coffee | Chayoos | SKPL | Muffins |  |  | 0 | still awaited for drwg | still awaited for drwg
21 | Forecourt | F2-0007 | 54 | Mumbai Street Food | Mumbai Street Food | SKPL | NSA |  |  | 0 | still awaited for drwg | still awaited for drwg
22 | Forecourt | F0-0001(F0-0002) | 387.78 | Microbrewery | Microbrewery | SKPL | FKD |  |  | 0 | still awaited for drwg | still awaited for drwg
23 | Forecourt | F0-0023(F0-0024) | 104 | Casual Dining | Nando’s /Jamie's Pizzeria | SKPL | ARA |  |  | 0 | still awaited for drwg | still awaited for drwg
24 | Forecourt | F0-0019(F0-0020) | 199 | QSR | WOW eats - Momos china kulfi | SKPL | Brand |  |  | 0 | still awaited for drwg | still awaited for drwg
25 | Forecourt | F0-0016(F0-0018) | 234 | QSR | KFC+Dominos | SKPL | Brand |  |  | 0 | still awaited for drwg | still awaited for drwg
26 | Forecourt | FM - 0052(FM-0015+FM-0016) | 627 | Microbrewery | Microbrewery | SKPL | FKD |  |  | 0 | still awaited for drwg | still awaited for drwg
27 | Intl SHA | H3 5017 | 2616 | International Lounge | International Lounge | SKPL | Design Wilkes |  |  | 0 | still awaited for drwg | still awaited for drwg
[7 empty] | TOTAL |  |  | 1254