## BOQ Extra Qty
BOQ EXTRA QUANTITY
SR. NO. | WBS LEVEL 2 | SHORT ITEM DESCRIPTION | LONG ITEM DESCRIPTION | DIMENSIONS | UOM | QTY. |  | RA EXTRA Qty | UOM | RATE | AMOUNT
2 | Cement/ bison board | Cement/ bison board on top of flase flooring paltform | Providing and fixing of 25-30mm cement/ bison board sheet on top of steel plateform to recieve heavy duty tiles. Rate to include, cutting, cleaning of joints, finishing junction, skirting backing, adhesive, hardware Complete in all aspect as per as per PMC/ Architect approval. |  | Sqft | 600
[7 empty] | TOTAL | 712.16 | SQFT
[7 empty] | BOQ QTY | 600
[7 empty] | EXTRA | 112.16 |  | 130 | 14580.8
| Frame Work/ support structure | Main MS structure to support ceiling | P/F MS framework of various section sizes finished with approved shade of powder coating with all necessary hardware with base plate/ self standing support from the floor. the cost include welding, grinding, chemfuring, grounding on the floor till RCC slab level, anchor fastner, required hardware, repair work of damage flooring, cleaning. etc complete
|  | a | 75X50mm MS box section (main vertical support) |  | RFT | 164 | TOTAL | 208 | RFT
[7 empty] | BOQ QTY | 164
[7 empty] | EXTRA | 44 |  | 700 | 30800
|  | b | 50X50mm MS box section (main horizontal frame) |  | RFT | 330
[7 empty] | TOTAL | 485.56 | RFT
[7 empty] | BOQ QTY | 330
[7 empty] | EXTRA | 155.56 |  | 275 | 42779
| Loading unloading |  | Loading unloading- All material shifting & loading, unloading |  | JOB | 1 | TOTAL | 1 | Job
[7 empty] | BOQ QTY | 1
[7 empty] | EXTRA | 0 |  | 10000 | 0
| Parametric structure | 25mm thk birch plywood rafter from floor to ceiling | Providing and fixing of 25mm thk birch ply lasercut in specific pattern with interlocking provision having supports from MS framework finished with PU polish with color pigment as per specification/ approved shade.Rate to include corner clips, hardware to support the framework cutting, cleaning of joints, finishing junction, suspended kit, adhesive Complete in all aspect as per as per PMC/ Architect approval. | Plank size 600mm wide | Sq ft | 3200
[7 empty] | TOTAL | 4770.836 | SQFT
[7 empty] | BOQ QTY | 3200
[7 empty] | EXTRA | 1570.836 |  | 340 | 534084.24
| Plywood partition | 75mm thk plywood partition behind the counter | Providing, making and fixing of 18 thk plywood partition having 25mm x 40mm aluminium framework @ 600mm c/c in vertical and horizontal direction with all necessary required framing. plywood partition to be finished with approved veneer on both side with PU polish. The partition bottom to have 200 x 200 mm plywood boxing for drain pipe finished with veneer on top & 150 mm ss skirting all aroung.Cost including grooved/ pattern as per approved design, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  | Sq ft | 380
[7 empty] | TOTAL | 397.6 | sqft
[7 empty] | BOQ QTY | 380
[7 empty] | EXTRA | 17.6 |  | 950 | 16720
| Wall/ partition tile dry cladding | handmade subway Tiles Size 100 x 200 WRAPAFELLA | Providing and fixing handmade subway Tiles dry Cladding / Dado as per approved shade, size and pattern on dry partition as per specific pattern as approved by PMC/ architect. the cost include required chemical/ adhesive, epoxy grouted with app. shade (Sal Grout), Tile cutting, cleaning of joints, finishing junction of plaster, curing etc. Complete and as per drawing. | Tile size - 100 x 200mm | Sqft | 60
[7 empty] | TOTAL | 89.1
[7 empty] | BOQ QTY | 60 | sqft
[7 empty] | EXTRA | 29.1 |  | 130 | 3783
|  | handmade subway Tiles Size 100 x 200 3RD WAVE COFFEE | Providing and fixing handmade subway Tiles dry Cladding / Dado as per approved shade, size and pattern on dry partition as per specific pattern as approved by PMC/ architect. the cost include required chemical/ adhesive, epoxy grouted with app. shade (Sal Grout), Tile cutting, cleaning of joints, finishing junction of plaster, curing etc. Complete and as per drawing. | Tile size - 100 x 200mm | Sqft | 60
[7 empty] | TOTAL | 77 | sqft
[7 empty] | BOQ QTY | 60
[7 empty] | EXTRA | 17 |  | 130 | 2210
| Tv Boxing | Plywood boxing for Led TV | Providing, making and fixing of 150mm deep plywood boxing with 18mm thk plywood having 25mm x 25 mm aluminium framework @ 600mm c/c in vertical and horizontal direction with all necessary required framing. the boxing to be finished with approved veneer on all visible side with PU polish. cost including grooved/ pattern as per approved design, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | 2400mm L X 300mm H X 150mm D & 1750mmL X 300mmH X 150mmD | Sq ft | 30
[7 empty] | TOTAL | 31.52 | sqft
[7 empty] | BOQ QTY | 30
[7 empty] | EXTRA | 1.52 |  | 700 | 1064
| 1.15 | ANGLE COCK | Angle Cock with PVC pipe connection upto WHB/sink/Geyser connection |  | NOS | 7
[7 empty] | TOTAL | 12 | NOS
[7 empty] | BOQ QTY | 7
[7 empty] | EXTRA | 5 |  | 1000 | 5000
|  | GRAND TOTAL AMOUNT | [8 empty] | 651021.04