## ADDITIONAL WORKS
DATE: 13-11-2023
To
M/s. Travel Food Services Pvt Ltd
Masala Kitchen,
Mezanine Floor,
Chennai Airport.
Chennai.
ADDITIONAL WORKS
SL NO | DESCRIPTION | UOM | QTY | RATE | AMOUNT | REMARKS
1 | BARRIGADE WORK: Removing the exhisting frame work & made frame work as per the site condition on top fixing exhisting vinyl. | Sqft | 360 | 40 | 14400
2 | Providing & making temporary door for back side entrance | Ls | 1 | 7000 | 7000
3 | Dismantling the exhisting RCC wall 1'0" thick & 1'-6" high. | Sqft | 36 | 800 | 28800
4 | Removing the exhisting coloum SS sheet & aluminium powder coated sheet with back ply & M.S structure. Necessary area provide additional M.S. support | Ls | 1 | 25000 | 25000
5 | Providing & making RCC coloum for back entry door opening area made out of 10mm dia rod 6"x6"x 2250mm on both sides & top side also. | Rft | 20 | 800 | 16000
6 | Coba filling additional height 180mm (in BOQ only 300mm high) excess qtuantity claiming | Sqft | 148 | 100 | 14800
7 | Providing & making steps with brick works & filling & PCC | Nos | 3 | 4000 | 12000
8 | Laying exhisting net working wiring 14.2 mtr x 12 nos | Rmtr | 170.4 | 50 | 8520
9 | Providing & laying 3+ cable for camera | Rmtr | 123 | 185 | 22755
10 | Providing & fixing exhaust hood | Nos | 4 | 6500 | 26000
11 | Drain Chamber 600x600x500mm with SS grating included. | Nos | 1 | 24000 | 24000
12 | Drain Chamber 700x225x500mm with SS grating included | Nos | 1 | 20000 | 20000
13 | 100mm dia UPVC pipe for drain work. | Rmtr | 3 | 1200 | 3600
14 | Providing & making 25mm GI sq tube on both sides 12mm waterproof ply on top 1mm thick white laminate, and top portion 19mm thick waterproof ply on top leather finish granite. Size: 1450x750x925. | Nos | 2 | 35000 | 70000
15 | Removing exhisting boxing with MS frame & alter the same with necessary supports & etc for TV | Ls | 1 | 8000 | 8000
16 | 6sqmm 5 runs for tandoor wiring 23.8 mtr x2 nos + Mk 34 10.3mtr | Rmtr | 60.6 | 550 | 33330
17 | 95 sqmm 3.5 core aluminium aroumed cable with necessary gland, lugs & laying charges included. | Mtr | 35 | 1200 | 42000
18 | Removing the barrigade | Sqft | 360 | 25 | 9000
19 | MDF jali with duco painting | Sqft | 68.25 | 450 | 30712.5
20 | 40MM UPVC UNION Below sink | Nos | 2 | 1200 | 2400
21 | 50MM UPVC UNION dish wash | Nos | 2 | 1450 | 2900
22 | 60MM UPVC UNION sink in kitchen | Nos | 2 | 1800 | 3600
23 | Panasonic 40" TV | Nos | 4 | 39488 | 157952
|  |  | TOTAL |  | 582769.5
|  |  | CGST @ 9% |  | 52449.255
|  |  | SGST @ 9% |  | 52449.255
|  |  | GRAND TOTAL |  | 687668.01
Camera wiring measurement
1 | Dvr to camera 1 tanddor above | 1 | 18
| Cam 2 Pos above | 1 | 16
| Cam 3 foh door above | 1 | 12
| Cam 4 foh door back side | 1 | 12
| Cam 5 warmer & hood corner | 1 | 16
| Cam 6 Dish wash front | 1 | 7
| Cam 7 Dish wash inside | 1 | 9
| Cam 8 Customer front area | 1 | 14
| Cam 9 back corridor | 1 | 9
| Cam 10 store room area | 1 | 10
|  |  | 123 | 123 | Rmtr

## LUMPSUM DETAIL BREAKUP
DETAILS OF LUMPSUM AMOUNTS
SLNO | DESCRIPTION | UOM | QTY | RATE | AMOUNT
2 | Providing & making temporary door for back side entrance
| Plywood cost | Sqft | 32 | 30 | 960
| Aluminium cost 2"X1"-12'-0" | Length | 2 | 490 | 980
| Transport cost from factory to site | No | 1 | 1500 | 1500
| Labour cost | Wages | 2 | 1000 | 2000
| Hardwares | Lot | 1 | 600 | 600
| Labour transport charges | Actuals | 1 | 300 | 300
|  |  |  | TOTAL | 6340
| Profit @ 15% |  |  |  | 951
| ACTUAL COSTING |  |  |  | 7291
4 | Removing the exhisting coloum SS sheet & aluminium powder coated sheet with back ply & M.S structure. Necessary area provide additional M.S. support
| Labour charges for four days For removing the sheet and frame | Set | 4 | 2500 | 10000
| Welding alteration work | Labour | 2 | 2500 | 5000
| Carpentry for fixing work | Labour | 2 | 2500 | 5000
| Welding machine rent | Rent | 1 | 500 | 500
| Transport charges | Lot | 1 | 1200 | 1200
|  |  |  | TOTAL | 21700
| Profit @ 15% |  |  |  | 3255
| ACTUAL COSTING |  |  |  | 24955
18 | Removing exhisting boxing with MS frame & alter the same with necessary supports & etc.
| Templete ply 19mm 1 sheet | Sqft | 1 | 3040 | 3040
| Plywood transport | Lot | 1 | 800 | 800
| Carpentry Labour | Labour | 0.25 | 2500 | 625
| Side boxing one portion removing & alteration labour charges | Labour | 1 | 2500 | 2500
|  |  |  | TOTAL | 6965
| Profit @ 15% |  |  |  | 1044.75
| ACTUAL COSTING |  |  |  | 8009.75

## CALCULATION PAINT (hidden)
| 403 | 443.3 | 444 | 67.66 | 6.1 | 73.76 | 517.76 | 518
| 6.6 | 2.1 | 13.86
| 2.6 | 2.1 | 5.46
19.32
|  |  | 21.252 | 22
2.8 | 19.32 | 2.8 | 24.92
|  |  | 27.412 | 28
[6 empty] | 3.3 | 1.2 | 2.1
12 | 3 |  | 36
2.4 | 2 | 1.8 | 8.64
|  |  | 44.64 | 49.104
49