## Extra Item
BHAKAR INTERIOR
#33, GROUND FLOOR, NEW APOLLO IND ESTATE, MOGRA VILLAGE ROAD, ANDHERI EAST, MUMBAI - 400 069
To, |  |  |  |  | Date :- 25.08.2024
Kapco Banquets & Catering Pvt. Ltd.
Worli Mumbai - 400018
Sub :- Revised Quotation for Extra Interior work at Blue Sea Banquet.
Sr. No | Description | Quantity | Unit | Rate | Amount | Remarks
1 | Removing Exiting loose materil from the colunm & re plaster with using Micro pour Cement plaster for Existing wall crack and columns crack area (only laber) | 100 | RFT | 150 | 15000
2 | Existing Bulk head Demolition |  |  |  | 0
a | Bulked bottom with Trap door | 509.4386 | Sq.ft | 124.84 | 63598.3138 | Rate As per Existing Approved
b | Above A.C unit Partition | 560.3846 | Sq.ft | 44.59 | 24987.5495 | Rate As per Existing Approved
c | Ply Partition | 959.9443 | Sq.ft | 44.59 | 42803.9156 | Rate As per Existing Approved
3 | Existing Loose Marble Removing | 189.0158 | Sq.ft | 44.59 | 8428.2163 | Rate As per Existing Approved
4 | Removing Staircase side wall Mirror Cladding | 261.5221 | Sq.ft | 44.59 | 11661.2724 | Rate As per Existing Approved
6 | Removing Existing Fabric wall ply paneling with wooden Partition. | 658.8752 | Sq.ft | 44.59 | 29379.2453 | Rate As per Existing Approved
7 | Providing & Fixing Mirror Paneling at Staircase made to be Alluminium framing with 12mm thk Plywood with 6mm thk Mirror & border metal profile as per detail drawing & design given by architect. | 261.5221 | Sq.ft | 850 | 222293.8224 | New
8 | Providing & Fixing Aluminium framing made to be 25 mm *25 mm Alluminium pipe for Fabric wall paneling. | 658.8752 | Sq.ft | 240.77 | 158637.3829 | Rate As per Existing Approved
9 | Providing & Fixing 12mm thk Plywood on Existing framing for Fabric wall paneling. | 658.8752 | Sq.ft | 160.51 | 105756.059 | Rate As per Existing Approved
10 | P/A Texture paint on Front Facade existing Fin top including scrapping of exiting plaster filling of crack, fixing of calcium silicate board in between two finns including approved color shead on it (ashian paint) | 1775 | Sq.ft | 130 | 230750
11 | P/F 100*100 mm M.S. Angle for Main door fixing | 18 | Rft | 650 | 11700
12 | New Bulk head Above Framing
a | P/F Bulkhead inside ceilling made 50mm x 50mm M.S. pipe for framing and 50mm x 50mm L Angel with 12mm thk plywood & Rubber Sheet insulation with above waterproofing work as per detail drawing & design given by architect. (Note :- ACP Cladding & UV board fixing item already Considered in existing work order.) | 1546 | Sq.ft | 1072.555 | 1658170
13 | Main entrance Portal
a | MS structure including both side Aluminum framing |  |  |  | 674255
14 | Double height entrance portal
| Removing of existing marble with existing panelling and new aglomorated marble fixing on new framing and ply |  |  |  | 72703
15 | Structural support for staircase landing
| Providing & Fixing MS C chenal for 150mm x 75mm x 5mm with necessary base plate & angle bolt for Staircase area. |  |  |  | 18812
| Total Amount |  |  |  | 3348935.7773
| GST @ 18% |  |  |  | 602808.4399
| Total Amount with GST |  |  |  | 3951744.2172
Note :
1 | Rates of Items highlighted with blue colour are checked and verified.
2 | Final expected cost of Bulkhead is as below : | Qty | Rate | Amount
2a | As per extra item 12a above | 1546 | 1072.555 | 1658170
2b | ACP sheet along with framing over the bulkhead (Rate as per tender BOQ) | 269 | 625 | 168125
2c | Trap door framing, trap door with UV board (Rate as per tender BOQ) | 256 | 1248 | 319488
2d | UV board under the bulkhead other than trap door area. (negotiated rate) | 300 | 400 | 120000
|  | Total expected cost of Bulkhead as per extra item |  | 2265783
3 | Amount loaded in Tender BOQ
3a | BOQ Line item 139 : ACP cladding | 1500 | 624.21 | 936315
3b | BOQ Line item 193 : UV board ceiling under Bulkhead | 450 | 1248.42 | 561789
|  | Total amount loaded in BOQ for Bulkhead work |  | 1498104
|  | Net incremental Amount |  | 767679
Net incremental cost on Main Entry Portal
|  | As per new Drawing |  | 674255
|  | As per Work Order Amount |  | 239733
|  | Diffrence Cost Increased | 0 | 434522