## NFA-SO (hidden)
Adani Airport Holdings Ltd
[8 empty] | Plant Code | 112A
Note for Approval
For Amendment of Service Order
Ref. No. |  | GAU/Soil Inv. Consultant |  |  |  | Date: |  | 2022-11-02
Project Name & Location: |  | Lokpriya Gopinath Bordoloi International Airport, Guwahati |  |  |  | Project WBS |  | D-2026-01-P1-AL-CM-PC-SY-
Work/Package |  | Appointment of Consultant for Soil Investigation Work for CSD land parcels (Land Areas: 18.53 Acre)
A. | Requisition | 1. | Name of Project Manager |  |  |  | to be appointed
|  | 2. | SO Requisition no. & date |  |  |  | 2022-08-16
|  | 3. | Date of Last release
|  | 4. | Target date for placement of SO |  |  |  | 2022-09-06
|  | 5. | Justify delay, if any |  |  |  | -
|  | 6. | Target date for Mobilization of Consultant
|  | 7. | Explain & justify if any delays are likely |  |  |  | -
|  | 8. | Any other significant information about PR |  |  |  | -
B. | Bidding | RFP issued on |  |  |  |  | 2022-08-16
|  | Proposals received on |  |  |  |  | 2022-08-23 | 2022-08-31
C. | Proposal Details | Parties to Whom Enquiry Issued. |  |  |  |  | R0 offer (Rs. Lakhs) | R1 offer (Rs. Lakhs) | Position
|  | 1 | Geotest Engineers |  |  |  | 16.5 | 8.232 | L1
|  | 2 | Gaveshana Geosciences |  |  |  | 11.07 | 8.76 | L2
|  | 3 | SS Solution |  |  |  | 11.44 | 11.04 | L3
|  | 4 | Bose Engineers |  |  |  | 14.25 | 12.516 | L4
D. | Basis & Justification | 1. Basis and justification for the recommendation:
|  | a. | Lowest offer |  |  |  | Yes
|  | b. | Repeat order |  |  |  | -
|  | c. | Prices as per pervious SO |  |  |  | -
|  | d. | Based on SO approved SOR |  |  |  | -
|  | e. | Based on the internal cost estimate
|  | f. | Others (specify in details) - (in case of other than lowest, indicate the financial impact)
2. Supporting enclosures (please specify):
|  | a. | Schedule of Approximate Quantities and Unit Rates |  |  |  | Yes
|  | b. | Comparatives statement of quoted & revised prices and internal estimates |  |  |  | Yes
|  | c. | Quotations of the parties |  |  |  | Yes
|  | d. | Last Order Price details
3. Emergency PR
|  | a. | Was it an Emergency PR? |  |  |  | No
|  | b. | If Yes, Was there any implication (Incase of implication specify amount and provide justification in the General Remarks). |  |  |  | -
E. | Consultant | Consultant ’s name (and place) |  |  |  |  | M/s. Geotest Engineers Pvt. Ltd
|  | Whether the Consultant is pre-qualified: |  |  |  |  | No
|  | If no, has the prequalification been carried out satisfactorily: |  |  |  |  | Yes
|  | Consultant’s PF Registration No. |  |  |  |  | -
|  | Any other details: |  |  |  |  | -
F. | Price | Part A : |  |  |  |  | Recommended Price Rs. |  | Budget
|  | Basic Order Value: |  |  |  |  | 823200 |  | 2800000
|  | Provision for travel expenses |  |  |  |  | 0 |  | 0
|  | GST : 18 % |  |  |  |  | 148176 |  | 504000
|  | Total Implication including Basic Order value, travel expenses , GST : |  |  |  |  | 971376 |  | 3304000
|  | Price Basis : |  |  |  |  | Firm Price till completion of services
|  | Provision for Quantity Variation: |  |  |  |  | Nil
G. | SEZ Benefit | Whether eligible for SEZ benefit. |  |  |  |  | No.
|  | If yes then LOP No. |  |  |  |  | -
| Other Major Terms & Conditions | Schedule of Completion: |  |  | SO Commencement Date. |  | From the date of the Service Order or Notice to proceed whichever is later
[5 empty] | SO Completion Date. |  | 30 days from effective date
|  | Payment Terms: |  |  | Mobilization Advance: |  | Nil
[5 empty] | R/A Bills: |  | 1.Max. 2 bills can be raised , one on completion of field work and other at completion and submission of final report. 2. Billing on item rate basis for actual work done. Quantities mentioned in the Price Schedule are tentative and may vary to any extent. 3. Payment shall be made within 30 days from submission of bill
|  | Securities applicable and their validity: |  |  | Advance BG: |  | Nil
[5 empty] | Contract Performance BG: |  | Nil
[5 empty] | Retention Money: |  | Nil
[5 empty] | Any other guarantees: |  | -
|  | Insurance: |  |  | CAR Policy |  | NA
Third party insurance
Workmen compensation
Contractor’s P&M
[5 empty] | Professional Indemnity |  | NA
[5 empty] | Any other |  | Staff of their company and of sub consultants engaged are fully covered under the insurance policy including COVID-19 epidemic
|  | Liquidated damages |  |  |  |  | One percent (1%) of the SO Price (along with applicable GST), for each completed week of delay or part thereof, subject to a maximum of Five percent (5 %) of the SO Price.
|  | Defect Liability Period |  |  |  |  | NA
|  | Any other significant terms and conditions: |  |  |  |  | a) Employer shall retain the right to close the assignment at any stage, as per the needs of the overall development Program. In such an event the breakup of Fees as agreed in Price Schedule shall form the basis for finalization of payment of consultancy fees, after successful completion of the work for respective stage. b) Consultant shall arrange water and electricity for the use in its work/services at its own cost. c) Safety and security of the equipment and personnel of the Consultant deployed at the site shall be its own responsibility. The Consultant shall indemnify the Employer of all the related liabilities.
|  | Mention and justify significant deviations, if any: |  |  |  |  | -
I. | General Remarks | 1. Scope of Works & Plot Layout document was received from Design team consisting of BOQ
J. | Approvers’ Notes, if any
K. | Post Approval Notes | 1. Service Order No. _________________________ dated ____________.
2. Unconditional acceptance of Service Order received on ______________.
| Proposed by |  |  | Recommended by |  | Recommended by |  | Verified by
| Manish Mulchandani |  |  | Avadhesh Kr Singh |  | Parag Thakurdesai |  | Dushyant Kumar
| Manager - Contracts & Procurement (CSD) |  |  | AGM- Contracts & Procurement (CSD) |  | Head- Contracts & Procurement (CSD) |  | GM- Finance Controller (CSD)
| Approved by |  |  |  |  | Approved by
| Vishal Mirchandani |  |  |  |  | Dr. Malay Mahadevia
| CEO (CSD) |  |  |  |  | CEO (AAHL)

## Summary1
SR NO | List of outlet | Initial Amount | Final Amount
1 | AJ KITCHEN | 1205717.682 | 836779.682
2 | SHAWARMA CVCP | 463845 | 415695
4 | CHAI POINT F03 | 180675 | 165275
5 | CHAI POINT D 08 | 143150 | 131250
Amount of items removed from BOQ
| Total | 1993387.682 | 1548999.682
| Amount of items removed from BOQ | 113250
| Total Amount of Variation Claimed | 1880137.682 | 1548999.682
| Variation |  | 331138
| Variation% |  | 17.61%

## Summary
SR NO | List of outlet | amt
1 | AJ KITCHEN | 836779.682
2 | SHAWARMA CVCP | #REF!
4 | CHAI POINT F03 | #REF!
5 | CHAI POINT D 08 | #REF!
| Total | #REF!
| GST 18% | #REF!
| Total Amount | #REF!

## AJ KitechenVariation Statement
VARIATION STATEMENT
Project: |  | AJ KITCHEN
Package Details:
Previous SO No.:
Document Date:
SR NO | SERVICE NO | ITEM DESCRIPTION | UNIT | RATE | Previous BOQ |  | Variation |  |  | Revised BOQ |  | % Variation | Remarks
[5 empty] | QTY | AMOUNT | QTY | RATE | AMOUNT | QTY | AMOUNT
[6 empty] | 0 |  |  | 0 | 0 | 0
|  | SECTION 02 - FINISHES (WALL, FLOOR, CEILING & DOORS) |  |  |  | 0 |  |  | 0 | 0 | 0
NOTE |  | The Contractor is referred to the Specifications and Drawings for all details related to this Section of the works and he is to include for complying with all the requirement contained therein, whether or not they are specifically mentioned within the items description. |  |  |  | 0 |  |  | 0 | 0 | 0
1 |  | Partition walls
1.01 |  | Supply and installation of fire rated calcium silicate board Partition Wall with the necessory supports, fittings and fixtures (excluding final finishes). Purposed height is 4500mm, it may be change as per site conditions GI framing shall be considered | SQM | 1870 | 48.598 | 90878.26 |  | 0 | 0 | 48.598 | 90878.26
1.02 |  | Supply and installation of fire rated calcium silicate board cladding on the existing walls in the Kitchen & pot wash area to pass the MEP services & to receive the final finishes with the necessory supports, fittings and fixtures (excluding final finishes). Purposed height is 3000mm, it may be change as per site conditions GI framing shall be considered | SQM | 1870 | 35.78 | 66908.6 |  | 0 | 0 | 35.78 | 66908.6
|  | Supply and installation of Gypsum board cladding on the existing walls to pass the MEP services & to receive the final finishes with the necessory supports, fittings and fixtures in the FOH & dining area walls, Front elevations & columns. (excluding final finishes). Purposed height is 3000mm, it may be change as per site conditions GI framing shall be considered | SQM | 1150 | 80.924 | 93062.6 | 80.924 | 165 | 13352.46 | 80.924 | 106415.06
2 |  | FLOOR FINISHES
Floor / tiles finishes including grouting, pointing, polishing, backing and etc. as required to complete all in accordance with drawings and specifications & as per client approval.
2.01 |  | 150mm thick concrete floor screeding/AAC blocks to raise the floor to accomodate the drainage pipes and floor gratings & to receive floor finish in the Kitchen & pot wash areas; all in accordance with drawings & site conditions. Note: Total height of floor to be raised including floor finishes is 200mm in the kitchen & pot wash area only | SQM |  | 13.6 | 0 |  |  | 0 | 13.6 | 0
2.02 |  | Supply & installation of water proofing with all necessary items; all in accordance with drawings and below mentioned specification. Detailed specifications of the materials to be submitted to client | [6 empty] | 0 | 0 | 0
2.02a |  | Dry Area: 1 Layer of 4mm thick SBS Bituminous membrane with 24-hour water ponding test (inspected and approved from airports team). | SQM |  | 86.02 | 0 |  |  | 0 | 86.02 | 0
2.02b |  | Wet Areas: 2 Layers of 4mm thick SBS Bituminous membrane with 24-hour water ponding test including the sealing of Cores in the slab/walls (inspected and approved from airports team). | SQM |  | 17 | 0 |  |  | 0 | 17 | 0
2.03 |  | Supply and installation of self levelling with all necessary items; all in accordance with drawings. | SQM |  | 88.4 | 0 |  |  | 0 | 88.4 | 0
2.04 |  | Supply and installation of anti-skid 600 x 600 mm white floor tile in the kitchen & Pot wash area as per the drawings and renders. Note: Material to be approved by Clients team. Tile Base Rate = Rs. 60 per sft. | SQM | 1450 | 13.6 | 19720 | 13.6 | 0 | 0 | 13.6 | 19720
2.05 |  | Supply and installation of Stone Plastic Composite (SPC) flooring in the FOH dining area area; colour & design as per drawings & render. Note: material to be approved by Clients Team Tile Base Rate = Rs. 100 per sft. | SQM | 2000 | 57.75 | 115500 | 57.75 | 1399 | 80792.25 | 57.75 | 196292.25
2.06 |  | Supply and installation of Matt finish designer tiles in the FOH area; colour & design as per drawings & render. Note: material to be approved by Clients Team Tile Base Rate = Rs. 60 per sft. | SQM | 1450 | 20.75 | 30087.5 | 20.75 | 157 | 3257.75 | 20.75 | 33345.25
TOTAL OF FLOOR FINISHES
3 |  | SKIRTING
3.01 |  | supply & installation of 150mm HIGH Marble textured Corian material skirting - FOH area, matching with FOH Counter top corian as per the renders & drawings. Note: material to be approved by Clients Team | SQM | 8000 | 10 | 80000 |  |  | 0 | 10 | 80000
TOTAL OF SKIRTING
4 |  | WALL FINISHES
A |  | Kitchen & Pot Wash areas
4.01 |  | Supply & installation of 300x300 mm White wall tile in the kitchen & Pot wash area as per drawings and renders. Note: material to be approved by Clients Team Tile Base Rate = Rs. 30 per sft. | SQM | 1250 | 57.946 | 72432.5 | 57.946 | 107 | 6200.222 | 57.946 | 78632.722
4.02 |  | Supply and Installation of SS corner beeding on the corners of kitchen wall tiles. Size 50 mm | Rmt. | 1200 | 10 | 12000 |  |  |  | 10 | 12000
B |  | FOH Dining areas | [7 empty] | 0 | 0
4.03 |  | Supply & Painiting of matt finish paint RAL : 9012 on the walls of dining & FOH area as per the drawings & renders Note: Material to be approved by clients Team | SQM | 350 | 86.229 | 30180.15 |  |  |  | 86.229 | 30180.15
4.04 |  | Supply & installation of Wooden moulding cladding with paint finish on the walls of Dining & FOH area as per drawings and renders. Note: Material to be approved by clients Team 25mm size half round moulding | Rmt. | 650 | 100 | 65000 | 100 | 250 | 25000 | 200 | 90000 |  | 65 mm
4.05 |  | Supply & installation of Matt finish Oak wood veneer on the walls of FOH area as per drawings and renders. Size: 850 mm Length wall only Note: Material to be approved by clients Team | SQM | 7500 | 1.105 | 8287.5 |  |  |  | 1.105 | 8287.5
C |  | Front Elevation area. | [7 empty] | 0 | 0
4.06 |  | Supply & installation of Wooden moulding cladding with paint finish on the front elevation, columns as per drawings and renders. Note: Material to be approved by clients Team 25mm size half round moulding | Rmt. | 650 | 30 | 19500 | 30 | 450 | 13500 | 30 | 33000 |  | 40 mm
4.07 |  | Supply & installation of Marble textured Corian material cladding on the columns, walls as per drawings and renders. Note: Material to be approved by clients Team | SQM | 8000 | 10 | 80000 |  |  |  | 10 | 80000
TOTAL OF WALL FINISHES
5 |  | GYPSUM WORKS
5.01 |  | Supply & installation of bulkhead gypsum above the hood in white paint matt finish. Paint shall be included, as per the below hood sizes. Considered Ceiling height in kitchen is 2800mm
5.01A |  | Hood 1 - Hot Cooking line : 2600 L x 1000 W x 400 H mm | Nos | 45000 | 1 | 45000 |  |  |  | 1 | 45000
TOTAL OF GYPSUM WORKS
6 |  | CEILING WORKS |  |  |  | 0 |  |  | 0 | 0 | 0
6.01 |  | Supply & Installation of 600x600 mm metal tile ceiling in the Kitchen & Pot wash area with necessary support, fixtures & accessories as per drawings & renders Note: Material to be approved by Clients Team. Tile Base Rate = Rs. 60 per sft. | SQM | 1850 | 13.6 | 25160 | 13.6 | 107 | 25160 | 13.6 | 50320 | 100%
6.02 |  | Supply and Installation of Metal grid ceiling with hanging flowers in the FOH & Dining areas including the final finishes with necessary support, fixtures & accessories as per drawings & renders. Note: Material to be approved by Clients Team. | SQM | 3100 | 58 | 179800 |  |  | 0 | 58 | 179800 | 0%
6.03 |  | Supply and Installation of Gypsum false ceiling at the sides of walls with the cove lights provision in the the FOH & dining area with paint in White color finishes with necessary support, fixtures & accessories as per drawings & renders. Including access panel as per the MEP services and Cutting & finishing for the AC grill/diffuser and lights. Note: Material to be approved by Clients Team. GI frame shall be considered | SQM | 1150 | 50 | 57500 | 50 | 165 | 57500 | 50 | 115000 | 100%
6.04 |  | Supply and painting with matt finish paint on the slab & walls of void ceiling area of FOH & dinning, including paints on all MEP services & metal ceiling parts. Note: color to be selected/approved by Clients Team. | SQM | 350 | 70 | 24500 |  |  | 0 | 70 | 24500 | 0%
|  | TOTAL OF CEILING WORKS |  |  |  | 0 |  |  | 0 | 0 | 0
7 |  | DOORS & WINDOWS |  |  |  | 0 |  |  | 0 | 0 | 0
7.01 |  | Supply and installation of heavy duty single leaf both side swing wooden door with the door frame for kitchen, including all the fittings & accessories, with vision glass as per the drawings and showing in the renders. This door to be decorative and designed type matching with the FOH design. Dim: 2200H x 900W mm x 45T mm | Nos | 31500 | 1 | 31500 |  |  | 0 | 1 | 31500 | 0%
|  | TOTAL OF DOORS & WINDOWS |  |  |  | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
EXTRA ITEMS
1 |  | P/F 350 X 450 X 350 mm of front bulkhead ( top Bottom and inside area ) finish with 18 mm mdf boxing with laminate | RMT |  |  |  | 13.5 | 8000 | 108000 | 13.5 | 108000
2 |  | P/F 350 X 450 X 350 mm of front bulkhead ms frame ( top Bottom and inside area ) | RMT |  |  |  | 0 | 2250 | 0 | 0 | 0 |  | Still awaiting clarity on materials specification
3 |  | P/F 600 mm of front bulkhead vertical finish with 18 mm mdf paneling with laminate | RMT |  |  |  | 0 | 6500 | 0 | 0 | 0 |  | Still awaiting clarity on materials specification
4 |  | P/F700 mm of front bulkhead vertical finish with 18 mm mdf paneling with laminate | RMT |  |  |  | 0 | 7500 | 0 | 0 | 0 |  | Still awaiting clarity on materials specification
5 |  | Mesh jalli for ceiling With paint | Sqmt |  |  |  | 43 | 1100 | 47300 | 43 | 47300
6 |  | Supply and installation of 18 mm kota flooring in the kitchen & Pot wash area as per the drawings and renders. Note: Material to be approved by Clients team. | Sqmt |  |  |  | 13.6 | 2250 | 30600 | 13.6 | 30600
6 |  | Supply & installation of FOH counter made up of 18mm thick MR-MDF structured with Marble textured Corian material finish and front facia cladding with 6mm-thk Charcoal panel & Matt finish Oak wood veneer, LED Cove lighting, PU paint finish inner side portions, glass display with shelves to be made in the counter, soft closing drawers, storage & handleless cabinets, fillers, panels, skirting and all necessary support, fittings, accessories and profiles as per approved drawings and renders. | Nos |  |  |  | 0 | 55000 | 0 | 0 | 0 |  | Still awaiting clarity on materials specification
7 |  | Supply & installation of FOH Lounge counter made up of 19mm thick comm ply structured with Marble textured Corian material finish and front facia cladding with 6mm-thk Charcoal panel & Matt finish Oak wood veneer, LED Cove lighting, PU paint finish inner side portions, glass display with shelves to be made in the counter, soft closing drawers, storage & handleless cabinets, fillers, panels, skirting and all necessary support, fittings, accessories and profiles as per approved drawings and renders. | Sqmt |  |  |  | 4.94 | 30500 | 150670 | 4.94 | 150670
8 |  | P/F samples as per the list | Ls |  |  |  | 1 | 45000 | 45000 | 1 | 45000
9 |  | Wooden skirting moulding types for dining area | Rmt |  |  |  | 0 | 1450 | 0 | 0 | 0 |  | Still awaiting clarity on materials specification
1 |  | CHILLED WATER TYPE CEILING SUSPENDED AHU (AIR HANDLING UNIT) :
|  | CEILING SUSPENDED AHU :( ECO AIR, ZECO AIRCON ) | Nos |  |  |  | 1 | 148447 | 148447 | 1 | 148447
Supply and assembly of Ceiling Suspended Double skin cabinet type AHU Integrated (Air handling units) of following specifications:
Frame Structure: It shall consist of 48mm Extruded Aluminium with thermal break profile.
Panel: 45mm +/- 2mm thick double skin sandwich panels with rockwool insulation of density 64 kg/m3 or PUF insulation of 48 kg/m3 , The sheet thickness shall be minimum 0.6 mm for the outer skin precoated and 0.8 mm thickness for the inner skin of plain GI.
Filtration Section: It shall be provided with single stage washable type of prefilter 'MERV 8' first stage which shall be placed before coil section.
Coil Section: Chilled water coil Multi row deep constructed with Aluminium fins of min 0.11mm thick 12 Fins per inch, and copper tubes of min 27 Guage thickness HYRDOPHYLLIC coated fins. Copper tube shall be min 12.5mm diameter. AHRI certified coil.The coil face area velocity shall not exceed 2.5m/sec (500 fpm).
Drain Pan: Condensate drain pan shall be fabricated from 18G SS 304 powder coated, insulated with 13 mm thick closed cell elastomeric(nitrile rubber) insulation.
Fan Section: SISW / DIDW Direct drive backward curved fan. The fan section shall be provided with limt switch for safety to shut off fan during Opening of access door. Fan outlet velocity not to exceed 1600 FPM. The sound level shall not be exceed more than 60dB @ 1m from the source. Vibration isolators, Door Limit switch, UV Lamp as per Technical Specifications, AHU Summary Sheet and drawings. Total static pressue has to calculated by Contractor as per the configuration.
Other Details : AHU to house control box/ terminal box with Auto-Manual switch and incomer power terminal, with SPP, Over/ Undervoltage protection, shortcircuit protection and with no-nc contacts (potential free contact) to be provided for tripping on signal from Fire Dampers / Fire Alarm Panel. Power cable from Terminal box to motor & control cabling of required size upto the thermostat / sensor etc. to be provided. Internal electrical and control wiring of AHU to be provided as factory fitted from AHU supplier. The cost shall include all necessary supports & accessories required for installation.
Contractor shall design the chilled water coil according to the following conditions:
a. Coil air entering temperature - 75.4°F DB
b. Coil air leaving temperature - 54 deg. F DB/ 52.99 deg. F WB
c. Chilled water temperature entering - 6.0 deg. C/ 42.8 deg. F
d. Chilled water temperature leaving - 13.3 deg. C/ 55.9 deg. F
Make : VTS / Zeco / Citizen
Type Capacity Tonnage ESP No. of
(Cfm) TR (mm WG) Rows
CS AHU 3400 8.5 25 4/6
GENERAL NOTES:
LHS & RHS VALVE station location to be confirmed.
Fan outlet velocity - 1600 FPM
Contractor shall submit static pressure calculation for all above units to Client/Consultant.
Any change in motor HP shall be made at no extra cost to client.
Fan efficiency shall be minimum 75%
The cost shall be included liftting & shifting of each equipment / material with all necesaary arrnagement. Also, it shall be included the cost of scaffloding required for Installation of such material / equipment.
2 |  | 32 mm BTU Meter ( Johnsons /Control/ Titus,/ Belimo | Nos |  |  |  | 1 | 62000 | 62000 | 1 | 62000
3 |  | Liberty 370 Three phase electricity meter | Nos |  |  |  | 1 | 20000 | 20000 | 1 | 20000
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
|  | TOTAL AMOUNT |  |  |  | 1147017.11 |  |  | 836779.682 |  | 1983796.792 | 72.95%
|  | GST 18% |  |  |  | 206463.0798 |  |  | 150620.3428 |  | 357083.4226
[6 empty] | 1353480.1898 |  |  | 987400.0248 |  | 2340880.2146