## NFA-SO (hidden)
Adani Airport Holdings Ltd
[8 empty] | Plant Code | 112A
Note for Approval
For Amendment of Service Order
Ref. No. |  | GAU/Soil Inv. Consultant |  |  |  | Date: |  | 2022-11-02
Project Name & Location: |  | Lokpriya Gopinath Bordoloi International Airport, Guwahati |  |  |  | Project WBS |  | D-2026-01-P1-AL-CM-PC-SY-
Work/Package |  | Appointment of Consultant for Soil Investigation Work for CSD land parcels (Land Areas: 18.53 Acre)
A. | Requisition | 1. | Name of Project Manager |  |  |  | to be appointed
|  | 2. | SO Requisition no. & date |  |  |  | 2022-08-16
|  | 3. | Date of Last release
|  | 4. | Target date for placement of SO |  |  |  | 2022-09-06
|  | 5. | Justify delay, if any |  |  |  | -
|  | 6. | Target date for Mobilization of Consultant
|  | 7. | Explain & justify if any delays are likely |  |  |  | -
|  | 8. | Any other significant information about PR |  |  |  | -
B. | Bidding | RFP issued on |  |  |  |  | 2022-08-16
|  | Proposals received on |  |  |  |  | 2022-08-23 | 2022-08-31
C. | Proposal Details | Parties to Whom Enquiry Issued. |  |  |  |  | R0 offer (Rs. Lakhs) | R1 offer (Rs. Lakhs) | Position
|  | 1 | Geotest Engineers |  |  |  | 16.5 | 8.232 | L1
|  | 2 | Gaveshana Geosciences |  |  |  | 11.07 | 8.76 | L2
|  | 3 | SS Solution |  |  |  | 11.44 | 11.04 | L3
|  | 4 | Bose Engineers |  |  |  | 14.25 | 12.516 | L4
D. | Basis & Justification | 1. Basis and justification for the recommendation:
|  | a. | Lowest offer |  |  |  | Yes
|  | b. | Repeat order |  |  |  | -
|  | c. | Prices as per pervious SO |  |  |  | -
|  | d. | Based on SO approved SOR |  |  |  | -
|  | e. | Based on the internal cost estimate
|  | f. | Others (specify in details) - (in case of other than lowest, indicate the financial impact)
2. Supporting enclosures (please specify):
|  | a. | Schedule of Approximate Quantities and Unit Rates |  |  |  | Yes
|  | b. | Comparatives statement of quoted & revised prices and internal estimates |  |  |  | Yes
|  | c. | Quotations of the parties |  |  |  | Yes
|  | d. | Last Order Price details
3. Emergency PR
|  | a. | Was it an Emergency PR? |  |  |  | No
|  | b. | If Yes, Was there any implication (Incase of implication specify amount and provide justification in the General Remarks). |  |  |  | -
E. | Consultant | Consultant ’s name (and place) |  |  |  |  | M/s. Geotest Engineers Pvt. Ltd
|  | Whether the Consultant is pre-qualified: |  |  |  |  | No
|  | If no, has the prequalification been carried out satisfactorily: |  |  |  |  | Yes
|  | Consultant’s PF Registration No. |  |  |  |  | -
|  | Any other details: |  |  |  |  | -
F. | Price | Part A : |  |  |  |  | Recommended Price Rs. |  | Budget
|  | Basic Order Value: |  |  |  |  | 823200 |  | 2800000
|  | Provision for travel expenses |  |  |  |  | 0 |  | 0
|  | GST : 18 % |  |  |  |  | 148176 |  | 504000
|  | Total Implication including Basic Order value, travel expenses , GST : |  |  |  |  | 971376 |  | 3304000
|  | Price Basis : |  |  |  |  | Firm Price till completion of services
|  | Provision for Quantity Variation: |  |  |  |  | Nil
G. | SEZ Benefit | Whether eligible for SEZ benefit. |  |  |  |  | No.
|  | If yes then LOP No. |  |  |  |  | -
| Other Major Terms & Conditions | Schedule of Completion: |  |  | SO Commencement Date. |  | From the date of the Service Order or Notice to proceed whichever is later
[5 empty] | SO Completion Date. |  | 30 days from effective date
|  | Payment Terms: |  |  | Mobilization Advance: |  | Nil
[5 empty] | R/A Bills: |  | 1.Max. 2 bills can be raised , one on completion of field work and other at completion and submission of final report. 2. Billing on item rate basis for actual work done. Quantities mentioned in the Price Schedule are tentative and may vary to any extent. 3. Payment shall be made within 30 days from submission of bill
|  | Securities applicable and their validity: |  |  | Advance BG: |  | Nil
[5 empty] | Contract Performance BG: |  | Nil
[5 empty] | Retention Money: |  | Nil
[5 empty] | Any other guarantees: |  | -
|  | Insurance: |  |  | CAR Policy |  | NA
Third party insurance
Workmen compensation
Contractor’s P&M
[5 empty] | Professional Indemnity |  | NA
[5 empty] | Any other |  | Staff of their company and of sub consultants engaged are fully covered under the insurance policy including COVID-19 epidemic
|  | Liquidated damages |  |  |  |  | One percent (1%) of the SO Price (along with applicable GST), for each completed week of delay or part thereof, subject to a maximum of Five percent (5 %) of the SO Price.
|  | Defect Liability Period |  |  |  |  | NA
|  | Any other significant terms and conditions: |  |  |  |  | a) Employer shall retain the right to close the assignment at any stage, as per the needs of the overall development Program. In such an event the breakup of Fees as agreed in Price Schedule shall form the basis for finalization of payment of consultancy fees, after successful completion of the work for respective stage. b) Consultant shall arrange water and electricity for the use in its work/services at its own cost. c) Safety and security of the equipment and personnel of the Consultant deployed at the site shall be its own responsibility. The Consultant shall indemnify the Employer of all the related liabilities.
|  | Mention and justify significant deviations, if any: |  |  |  |  | -
I. | General Remarks | 1. Scope of Works & Plot Layout document was received from Design team consisting of BOQ
J. | Approvers’ Notes, if any
K. | Post Approval Notes | 1. Service Order No. _________________________ dated ____________.
2. Unconditional acceptance of Service Order received on ______________.
| Proposed by |  |  | Recommended by |  | Recommended by |  | Verified by
| Manish Mulchandani |  |  | Avadhesh Kr Singh |  | Parag Thakurdesai |  | Dushyant Kumar
| Manager - Contracts & Procurement (CSD) |  |  | AGM- Contracts & Procurement (CSD) |  | Head- Contracts & Procurement (CSD) |  | GM- Finance Controller (CSD)
| Approved by |  |  |  |  | Approved by
| Vishal Mirchandani |  |  |  |  | Dr. Malay Mahadevia
| CEO (CSD) |  |  |  |  | CEO (AAHL)

## Summary1
SR NO | List of outlet | Initial Amount | Final Amount
1 | AJ KITCHEN | 1205717.682 | 836779.682
2 | SHAWARMA CVCP | 463845 | 415695
4 | CHAI POINT F03 | 180675 | 165275
5 | CHAI POINT D 08 | 143150 | 131250
Amount of items removed from BOQ
| Total | 1993387.682 | 1548999.682
| Amount of items removed from BOQ | 113250
| Total Amount of Variation Claimed | 1880137.682 | 1548999.682
| Variation |  | 331138
| Variation% |  | 17.61%

## Shawarma Variation Statement
Project: |  | SHAWARMA, TACOS & MASALA KITCHEN
Package Details:
Previous SO No.:
Document Date:
SR NO | SERVICE NO | ITEM DESCRIPTION | UNIT | RATE | Previous BOQ |  | Variation |  |  | Revised BOQ |  | % Variation | Remarks
[5 empty] | QTY | AMOUNT | QTY | RATE | AMOUNT | QTY | AMOUNT
NOTE |  | CVCP EXTRA WORK
1
1.01 | 1 | Shawarma, Tacos and Masala Kitchen Front Counter Modification as per the revised drawing details | Nos |  |  |  | 2 | 25000 | 50000 | 2 | 50000
1.02 | 2 | 100mm Corian skirting with 12mm packing ply near front counter. | Rmt |  |  |  | 11 | 1850 | 20350 | 11 | 20350
| 3 | 150mmx150mmx150mm x 2700 mm height vertical bookends finish with laminate ( LM01 ) | Nos |  |  |  | 3 | 12000 | 36000 | 3 | 36000
| 4 | 12 Bison board paneling on external partition, Column and near glass | Sqmt |  |  |  | 36 | 1850 | 66600 | 36 | 66600
FF EXTRA WORK
| 1 | Providing, Laying, Jointing & Testing of Pipes for Sprinkler System - G.I Pipe confirming IS Codes Class `C' Heavy Pipe & with necessary support & anchore fastening from slab.
2 | a. | 25 mm dia | Rft. |  |  |  | 101 | 370 | 37370 | 101 | 37370
| b. | 32 mm dia | Rft. |  |  |  | 0 |  | 0 | 0 | 0
2.01 | c. | 40 mm dia | Rft. |  |  |  | 45 | 470 | 21150 | 45 | 21150
2.02 | d. | 50 mm dia | Rft. |  |  |  | 0 |  | 0 | 0 | 0
2.02a | e. | 65mm dia | Rft. |  |  |  | 11 |  | 0 | 11 | 0
2.02b | [9 empty] | 0 | 0
2.03 | 2 | Synthetic Enamel Paint. | [7 empty] | 0 | 0
2.04 | a. | 25 mm dia | Rft. |  |  |  | 101 | 55 | 5555 | 101 | 5555
2.05 | b. | 32 mm dia | Rft. |  |  |  | 0 |  | 0 | 0 | 0
2.06 | c. | 40 mm dia | Rft. |  |  |  | 45 | 65 | 2925 | 45 | 2925
| d. | 50 mm dia | Rft. |  |  |  | 0 |  | 0 | 0 | 0
3 | e. | 65mm dia | Rft. |  |  |  | 11 | 95 | 1045 | 11 | 1045
3.01 | [9 empty] | 0 | 0
| 3 | Providing & Fixing of Butterfly Valve. | [7 empty] | 0 | 0
4 | a. | 50 mm dia | No. | [6 empty] | 0 | 0
A | b. | 65 mm dia | No. |  |  |  | 1 | 7500 | 7500 | 1 | 7500
4.01 | [9 empty] | 0 | 0
4.02 | 4 | Providing & Fixing of Ball Valve. | [7 empty] | 0 | 0
B | a. | 25 mm dia | No. |  |  |  | 0 |  | 0 | 0 | 0
4.03 | b. | 32 mm dia | No. |  |  |  | 0 |  | 0 | 0 | 0
4.04 | c. | 40 mm dia | No. |  |  |  | 0 |  | 0 | 0 | 0
4.05 | d. | 50 mm dia | No. |  |  |  | 0 |  | 0 | 0 | 0
C | e. | 65 mm dia | No. |  |  |  | 1 | 4500 | 4500 | 1 | 4500
4.06 | [8 empty] | 0 | 0 | 0
4.07 | 5 | HEADER FITTING. | [6 empty] | 0 | 0 | 0
| a. | Flow Switch | No. |  |  |  | 1 | 4500 | 4500 | 1 | 4500
5 | b | Pressure Gauge | No. |  |  |  | 1 | 8500 | 8500 | 1 | 8500
5.01 | c | Air Release Valve | No. |  |  |  | 1 |  | 0 | 1 | 0
5.01A | d | 65 mm dia NRV | No. |  |  |  | 1 | 6500 | 6500 | 1 | 6500
[9 empty] | 0 | 0 | 0
| 6 | Providing & Fixing C.P. Brass 68 degree Quartzoid Bulb Sprinklers. Make : Tyco / viking temp rating standard coverage discharge coefficent k- 6.6 quick response UL listed & EN approved. | [6 empty] | 0 | 0 | 0
6 | a. | Pendant Type | No. |  |  |  | 11 | 750 | 8250 | 11 | 8250
6.01 | b. | UP Right Type | No. |  |  |  | 17 | 750 | 12750 | 17 | 12750
6.02 | 7 | Providing & Fixing C.P. Brass 79 degree(QR) Quartzoid Bulb Sprinklers. Make : Tyco / viking temp rating standard coverage discharge coefficent k- 6.6 quick response UL listed & EN approved for high temperature area in Kitchen temprating shall be 79degree c (QR) | [6 empty] | 0 | 0 | 0
6.03 | a. | Pendant Type | No. |  |  |  | 6 | 750 | 4500 | 6 | 4500
6.04 | b. | UP Right Type | No. |  |  |  | 0 |  | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
7 | 8 | Flexible Sprinkler Drop. | [6 empty] | 0 | 0 | 0
7.01 | a. | 25mm | No. |  |  |  | 17 | 2100 | 35700 | 17 | 35700
| b. | 100mm | No. |  |  |  | 0 |  | 0 | 0 | 0
| c. | 150mm | No. |  |  |  | 0 |  | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
1 | 9 | Drain Valve | No. |  |  |  | 0 |  | 0 | 0 | 0
1 | 1 | 32 mm BTU Meter ( Johnsons /Control/ Titus,/ Belimo | Nos |  |  |  | 1 | 62000 | 62000 | 1 | 62000
2 | 2 | Liberty 370 Three phase electricity meter | Nos |  |  |  | 1 | 20000 | 20000 | 1 | 20000
|  | TOTAL AMOUNT |  |  |  | 0 |  |  | 415695 |  | 415695
|  | GST 18% | [6 empty] | 74825.1 |  | 74825.1
|  | TOTAL AMOUNT WITH GST | [6 empty] | 490520.1 |  | 490520.1