## NT AJ 26.07.2024
AHM_AJ 1881_Additional_Items_Quotation_26.07.2024
S.NO. | Item Description | Location | Size | UOM | Qty | Rate | Amount | Remaeks
1 | Planter box with corian & paint finish | Entry FOH | 800X630X300mm | Nos | 1 | 28831 | 28831 | not part of BOQ Item , but as per 3D site rerequiment
2 | Steplizer for Coffee machine & mery chef machine | DB box |  | Nos | 2 | 16900 | 33800 | not part of BOQ Item , its site requirements for machine
3 | Basin mixer | Kitchen |  | Nos | 2 | 7850 | 15700 | not part of BOQ Item , its site requirements for sink
4 | Sensor pillar cock on foh back counter with electrical points 3M | Back counter |  | Nos | 1 | 3570 | 3570 | not part of BOQ Item , its site requirements for sink
5 | Angle cock | kitchen & back counter |  | Nos | 11 | 4950 | 54450 | not part of BOQ Item , its site requirements for plumbing points
6 | Grease trap complete fittings & connection pipe |  |  | Nos | 2 | 2150 | 4300 | not part of BOQ Item , its site requirements for plumbing line
7 | Mery chef machine new switch socket |  |  | Nos | 1 | 675 | 675 | not part of BOQ Item , its site requirements of universal switch socket
8 | Lifting station switch socket & wire 6M |  |  | Nos | 2 | 1470 | 2940 | not part of BOQ Item , its site requirements
9 | Fire Suppression & Gas leak detector switch socket |  |  | Nos | 2 | 950 | 1900 | not part of BOQ Item , its site requirements
10 | Firdge Relocation New electrical switch socket |  |  | Nos | 1 | 650 | 650 | not part of BOQ Item , its site requirements
11 | RO Relocation Extra CPVC Piping |  |  | Mtr | 10 | 352 | 3520 | not part of BOQ Item , its site requirements
12 | Extra Corian sheet installtion on counter vertical drops |  |  | Sheet | 2 | 12500 | 25000 | its site requirements as discussed in meeting calls with design team
13 | Wooden DB Box |  | 2100X750mmX2900mm | Nos | 1 | 133450 | 133450 | not part of BOQ Item , its site requirements as per drawing
14 | Coffee machine complete fittings for plumbing connection |  |  | Nos | 1 | 575 | 575 | not part of BOQ Item , its site requirements for machine
15 | Ice Cube machine plumbing connection with complete plumbing fittings |  |  | Nos | 1 | 750 | 750 | not part of BOQ Item , its site requirements for machine
16 | Golden T Profile installation & removal of ss profile |  |  | Mtr | 28 | 485 | 13580 | not part of BOQ Item , its site requirements according to drawing
17 | Hood Installation with complete fittings & duct fabrication for hood connection |  |  | Nos | 1 | 6520 | 6520 | not part of BOQ Item , its site requirements
18 | All Equipment shifting & installation |  |  | Lot | 1 | 35000 | 35000 | not part of BOQ Item , its site requirements
19 | Dishwasher machine plumbing connection & Installation |  |  | Lot | 1 | 250 | 250 | not part of BOQ Item , its site requirements for machine
20 | Kitchen both Sink complete plumbing connection with material |  |  | Nos | 2 | 1250 | 2500 | not part of BOQ Item , its site requirements for sink
21 | Extra Flower installtion |  |  | Lot | 1 | 22500 | 22500 | Additional quantity required , its site requirements
22 | Kitchen SS Shelf intalaltion 4 nos |  |  | Lot | 1 | 3500 | 3500 | not part of BOQ Item , its site requirements for shelf installtion
23 | Knee operated sink installation & piping |  |  | Nos | 1 | 850 | 850 | not part of BOQ Item , its site requirements
24 | Main LT Panel - Electrical as per Site requirement and SLD |  |  | Nos | 1 | 148500 | 148500 | not part of BOQ Item , its site requirements
25 | Wooden Flooring - Removing and new flooring installation |  |  | Sqm | 25 | 2000 | 50000 | not part of BOQ Item , its site requirements
26 | Grease trap complete fittings & connection pipe below sink |  |  | Lot | 1 | 2500 | 2500 | not part of BOQ Item , its site requirements
| TOTAL | [5 empty] | 595811