## NON PO Items
MOD - NON PO ITEMS
SN | LOCATION | ITEM DESCRIPTION | UNIT | L | B | H | QUANTITY | RATE | AMOUNT
1 | Façade Bulk Head | Providing and fixing of Bulkhead made of 12 mm thk ply with frame work of grid size 1.5x1.5 finished with orange paint of aproved shade, pannels fixed properly without any cavity or undulations. To inch thk Portal for running profile light on the edges & on top fornt smooth surface of 300 mm white for recieving toughned glass with all screw fashners etc complete. | SQFT | 30 | 2 |  | 60 | 2000 | 120000
| COST BIFURCATION | Frame Material | SQFT |  |  |  |  | 100
|  | Frame Labour | SQFT |  |  |  |  | 60
|  | Hardware & Tools | SQFT |  |  |  |  | 50
|  | 12 MM Thik Ply | SQFT |  |  |  |  | 390
|  | Carpentery Charges | SQFT |  |  |  |  | 320
|  | Making And Bending of Farma at cornners | SQFT |  |  |  |  | 180
|  | Making 10 mm Groove in front for lighting | SQFT |  |  |  |  | 100
|  | P/F Defuser Lights in the grouves | SQFT |  |  |  |  | 220
|  | Appling Two or more Coat Acrylic Putti to achive even surface | SQFT |  |  |  |  | 110
|  | Painting | SQFT |  |  |  |  | 90
|  | Painting Labour | SQFT |  |  |  |  | 60
|  | Glass Work on Top | SQFT |  |  |  |  | 320
2 | Electric Meter | P/F Secure Prepaid Meter 3P (10-100A) Liberty 370 | Nos |  |  |  | 1 | 26000 | 26000
Previously Approved Rate
3 | Signage Connection | P/L 3x2.5 sqm FRLS wire, MS Conduit with 10Amp MCB from main DB to the outer bulkhead | Job |  |  |  | 1 | 4800 | 4800
4 | Seating Area Tiles | P/L 600x600 mm Vetrified Floor Tiles | SQFT | 37.4 | 4.75 |  | 177.65
|  |  |  | 8.26 | 6.41 |  | 52.9466
|  |  |  | 8.8 | 12.86 |  | 113.168
|  |  |  | Total |  |  | 343.7646 | 180 | 61877.628
| COST BIFURCATION | Tiles | [5 empty] | 62
|  | Tiles Labour | [5 empty] | 30
|  | Base Prepration | [5 empty] | 38
|  | Cement Slurry for Fixing Tiles | [5 empty] | 20
|  | Transpotation From Store to Airport | [5 empty] | 15
|  | Labour Charges for Shifting Tiles From Parking to Store | [5 empty] | 15
5 | Brick Pattern Tiles | P/L 50x230 mm Brick Pattern Tiles with 3 mm Spacer | SQFT | 21.5 | 8.26 |  | 177.59 | 380 | 67484.2
| COST BIFURCATION | Tiles | [5 empty] | 75
|  | Tile Labour | [5 empty] | 110
|  | Tiles Cutting | [5 empty] | 80
|  | Base Prepration | [5 empty] | 38
|  | Cement Slurry for Fixing Tiles with Adhesive maintening 4 mm Groove | [5 empty] | 37
|  | Grouting | [5 empty] | 10
|  | Transpotation From Store to Airport | [5 empty] | 15
|  | Labour Charges for Shifting Tiles From Parking to Store | [5 empty] | 15
6 | Electrical Conduit | P/L MS Conduit 25 mm Dia in Seating Area | RFT | 112.2 |  |  | 112.2 | 80 | 8976
[6 empty] | TOTAL |  |  | 289137.828