## SUMMARY
S. No. | Particular | As Per BOQ | As Per Audited | Difference from PO Value
1 | Civil | 3779000 | 3373170.475 | 405829.525
2 | Interior | 7120474 | 5920678.675 | 1199795.325
3 | Miscallaneous | 506000 | 315697.5 | 190302.5
4 | Civil & Interior NT |  | 694642.394 | -694642.394
5 | Electrical | 1550764 | 1476951 | 73813
6 | Electrical NT |  | 618408 | -618408
7 | HVAC | 796025 | 806623.25 | -10598.25
8 | HVAC NT |  | 45000 | -45000
9 | Ventilation | 1500325 | 1588878 | -88553
10 | Ventilation NT |  | 44000 | -44000
11 | Fire Sprinkler | 250650 | 220666.5 | 29983.5
12 | Fire Sprinkler NT |  | 484565 | -484565
13 | PHE | 498530 | 364723.5 | 133806.5
14 | PHE NT |  | 198775 | -198775
15 | Music | 80600 | 76650 | 3950
16 | Gas & GLD | 128100 | 167500 | -39400
| Total | 16210468 | 16396929.294 | -186461.294
| GST 18% | 2917884.24 | 2951447.2729 | -33563.0329
| Grand Total | 19128352.24 | 19348376.5669 | -220024.3269

## CIVIL
BOQ of Civil work for Copper Chimney Project, Pune-Wakad | [6 empty] | 45185 |  |  | 20/9/2023 |  |  | R1 | [5 empty] | 20/9/2023 |  |  | R1 | [5 empty] | 20/9/2023
|  | GROUND FLOOR |  |  |  |  | FT |  | BOQ | [8 empty] | ACTUAL | [8 empty] | DIFFERENCE
SR.NO. | ITEM | DESCRIPTION | DRAWING NO | DIMENSION | UNIT | QTY. | RATE | AMOUNT | QTY. | RATE | AMOUNT | DEVIATION | REMARK | Purchase Remark | VIPL Remark 17.10.2023 | ARA Remark | VIPL Remark 13.11.2023 | QTY. | RATE | AMOUNT | DEVIATION | REMARK | Purchase Remark | VIPL Remark 17.10.2023 | ARA Remark | VIPL Remark 13.11.2023 | QTY. | RATE | AMOUNT | Claimed Amount | Actual Amount | Difference | Reason of deduction | APK Remark
GENERAL SITE WORKS
1 | Pest control at site | Providing Pest Control & Anti-termite treatment by appointing a specialized agency as per the specifications mentioned by the Bureau of Indian Standard & Agencies specification ( Whichever is higher ) for General Civil , Plumbing / Drainage & timber / Carpentry works , Gypsum related work including 5 Years guarantee under suitable undertaking on stamp paper etc complete as directed . ( Mode of Measurement to be on carpet area of floor & not the area of surface treated.) | N.A | N.A | SFT | 2600 | 15 | 39000 | 2600 | 15 | 39000 | 0 | [5 empty] | 2455.805 | 15 | 36837.075 | 36837.075 | [5 empty] | -144.195 | 15 | -2162.925 | 36837.075 | -2162.925 | 39000 |  | Vendor t submit pest control certificate
[30 empty] | 0 | 0 | 0
DEMOLITION WORKS | [29 empty] | 0 | 0 | 0
1 | Demolition Work | Demolition of existing 100/125 mm thick Brick wall with marble, including cleaning the surface & dump the debris's at ground floor debris point.Demolition of existing Pantry counter & wash basin counter, including cleaning the surface & dump the debris's at ground floor debris point. | N.A | N.A | SFT | 100 | 35 | 3500 | 100 | 35 | 3500 | 0 | Area may increase as per actuals |  |  |  |  | 0 | 35 | 0 | 0 | Area may increase as per actuals |  |  |  |  | -100 | 35 | -3500 | 0 | -3500 | 3500
2 | Wall Chasing | Removing of existing wall including 200-300mm thick wall/ sand cement layer, including cleaning the surface & dump the debris's at ground floor debris point. |  |  | RFT | 50 | 35 | 1750 | 50 |  | 0 | -1750 | [5 empty] | 0 |  | 0 | 0 | [5 empty] | -50 |  | 0 | 0 | 0 | 0
2 | Wall Puncture | Removing of POP punning and making wall puncture size of 200-600mm wide on existing wall, including cleaning the surface and proper plaster in line and level ready to paint & dump the debris's at ground floor debris point. | N.A | N.A | NO's | 5 | 1000 | 5000 | 5 | 1000 | 5000 | 0 | As actual |  |  |  |  | 0 | 1000 | 0 | 0 | As actual |  |  |  |  | -5 | 1000 | -5000 | 0 | -5000 | 5000
3 | Debris | Removing Debris out of site included loading, unloading & shifting as per statutory rules and regulations. | N.A | N.A | NO's | 2 | 7000 | 14000 | 2 | 7000 | 14000 | 0 | As actual |  |  |  |  | 63 | 7000 | 441000 | 441000 | As actual |  |  |  |  | 61 | 7000 | 427000 | 441000 | 427000 | 14000 |  | Challan required
[30 empty] | 0 | 0 | 0
INTERIOR CIVIL WORK | [29 empty] | 0 | 0 | 0
1 | Membrane Waterproofing | P&A Waterproofing on mother slabs & wall till 450mm height, with membrane water proofing treatment on the mother slab, before doing the treatment mother slab needs to clean properly up to the mark & dust free surface needs to achieve to apply the chemical (proof bond /BASF, Dr. Fixit / Equivalent make) & chemical needs to dry properly, After all there should be a water pond testing to be done for water tightness & rectifications of defects if any. Complete with 10 years performance guarantee with client's satisfaction. Entire process to be done under guideline & supervision of appointed engineering team. | [27 empty] | 0 | 0 | 0
| a | Kitchen -floor up to 1000mm |  | N.A | SFT | 720 | 90 | 64800 | 1000 | 90 | 90000 | 25200 | Upto 1meter Height | Rates are okay |  | Chnages done by mall team. |  | 742.9325 | 90 | 66863.925 | #VALUE! | Upto 1meter Height | Rates are okay |  | Chnages done by mall team. |  | -257.0675 | 90 | -23136.075 | 66863.925 | -23136.075 | 90000
| b | Kitchen -wall up to 600mm 1000mm |  | N.A | SFT | 300 | 90 | 27000 | 450 | 90 | 40500 | 13500 | Upto 1meter Height | Rates are okay |  |  |  | 565.5 | 90 | 50895 | 50895 | Upto 1meter Height | Rates are okay |  |  |  | 115.5 | 90 | 10395 | 50895 | 10395 | 40500
| c | Live kitchen -floor up to 1000mm |  | N.A | SFT | 120 | 90 | 10800 | 180 | 90 | 16200 | 5400 | Upto 1meter Height | Rates are okay |  |  |  | 103.5 | 90 | 9315 | 9315 | Upto 1meter Height | Rates are okay |  |  |  | -76.5 | 90 | -6885 | 9315 | -6885 | 16200
| d | Live kitchen -wall up to 600mm 1000mm |  | N.A | SFT | 80 | 90 | 7200 | 120 | 90 | 10800 | 3600 | Upto 1meter Height | Rates are okay |  |  |  | 117.75 | 90 | 10597.5 | 10597.5 | Upto 1meter Height | Rates are okay |  |  |  | -2.25 | 90 | -202.5 | 10597.5 | -202.5 | 10800
| e | Bar -floor up to 1000mm |  | N.A | SFT | 95 | 90 | 8550 | 150 | 90 | 13500 | 4950 | Upto 1meter Height | Rates are okay |  |  |  | 99.9125 | 90 | 8992.125 | 8992.125 | Upto 1meter Height | Rates are okay |  |  |  | -50.0875 | 90 | -4507.875 | 8992.125 | -4507.875 | 13500
| f | Bar -wall up to 600mm 1000mm |  | N.A | SFT | 60 | 90 | 5400 | 90 | 90 | 8100 | 2700 | Upto 1meter Height | Rates are okay |  |  |  | 99 | 90 | 8910 | 8910 | Upto 1meter Height | Rates are okay |  |  |  | 9 | 90 | 810 | 8910 | 810 | 8100
[30 empty] | 0 | 0 | 0
2 | Block Work | Providing and constructing Light weight blocks masonry in cement mortar 1:4 of approved make like Aerocon/Siporex etc. Job to include raking out joints, scaffolding, making openings walls, curing etc. in substructure and superstructure to its true line & level in cement mortar proportion as specified in all shapes, size, at all heights, depths, leads & locations etc. complete. The rate shall also include for cleaning of surface, hacking of RCC surface in contact with brickwork, racking of joints, providing, erecting, & dismantling steel scaffolding , curing for 10 days, including 75 mm thk. R.C.C. stiffener at approximately every 1000 mm ht. with required M.S. reinforcement bars and Lintels for Doors and wall openings etc. compete as per the drgs., details & specifications. | [27 empty] | 0 | 0 | 0 |  | Vendor to confirm line out before proceeding for wall work
| a | Using 150mm thk Walls upto 1200 mm |  | N.A | SFT | 90 | 190 | 17100 | 90 | 190 | 17100 | 0 | [5 empty] | 83 | 190 | 15770 | 15770 | [5 empty] | -7 | 190 | -1330 | 15770 | -1330 | 17100
| b | Using 150mm thk Walls upto 5000mm |  | N.A | SFT | 1500 | 190 | 285000 | 1500 | 190 | 285000 | 0 | [5 empty] | 1347.46 | 190 | 256017.4 | 256017.4 | [5 empty] | -152.54 | 190 | -28982.6 | 256017.4 | -28982.6 | 285000
| c | Using 100mm thk Walls upto 5000mm |  |  | SFT |  |  | 0 | 1700 | 170 | 289000 | 289000 |  | Ravi please re check the qty |  |  |  | 1408.74 | 170 | 239485.8 | 239485.8 |  | Ravi please re check the qty |  |  |  | -291.26 | 170 | -49514.2 | 239485.8 | -49514.2 | 289000
[30 empty] | 0 | 0 | 0
3 | Internal Plaster | P&A of single coat backing plaster of 15-18 mm thick in CM 1:4 proportion to the walls & others surface including scaffolding, curing the joints, etc. The rates are inclusive of providing chicken mesh of 18mm gauge & 150mm width at junction of brick & RCC etc. at the walls, columns, beams etc., seven days water treatment as anti crack of plaster. Complete as per site engineer's instruction. | N.A | N.A | [25 empty] | 0 | 0 | 0
| a | Bar Area & Live Kitchen (low height wall 1200mm) |  |  | SFT | 178 | 70 | 12460 | 178 | 70 | 12460 | 0 | [5 empty] | 277.04 | 70 | 19392.8 | 19392.8 | [5 empty] | 99.04 | 70 | 6932.8 | 19392.8 | 6932.8 | 12460
| b | Wall height (3600mm) consider |  |  | SFT | 4459 | 70 | 312130 | 2000 | 70 | 140000 | -172130 | [5 empty] | 3986.49 | 70 | 279054.3 | 279054.3 | [5 empty] | 1986.49 | 70 | 139054.3 | 279054.3 | 139054.3 | 140000
[30 empty] | 0 | 0 | 0
4 | PCC Work | Providing and laying up to 50-75 mm thick cement concrete flooring with 1:2:4 cement concrete laid to proper level and slope in alternate bays including compactions, filling joints, or as directed, finishing smooth with cement Mortar 1:1 of sufficient minimum thickness to give a smooth & even surface and curing etc. complete as per architects instructions. | N.A | N.A | SFT | 1000 | 120 | 120000 | 1000 | 120 | 120000 | 0 | [5 empty] | 840 | 120 | 100800 | 100800 | [5 empty] | -160 | 120 | -19200 | 100800 | -19200 | 120000 |  | Total area value to be considered based on jont check between APK & VART Team in presence Mr. hemant- Charcoal
[30 empty] | 0 | 0 | 0
5 | COBA Work (Modiform) | Modiform of Avg. thickness mentioned below; After laying of soil pipes, floor traps is completed the floor of the sunken portion shall be covered with Modiform manually with 15-20 mm wide joints in 20 mm thk. Waterproofing mortar 1:4 ( 1 cement : 4 coarse sand )in layers upto the full ht. of sunken portion, having top layer of 50 mm thk waterproof mortar 1:4 ( 1 cement : 4 coarse sand ) using specialized W.P. chemical, finished smooth / rough with floating coat of neat cement all complete and as per specification. | [27 empty] | 0 | 0 | 0
| a | Kitchen (300mm) appox | N.A | N.A | SFT | 720 | 250 | 180000 | 720 | 250 | 180000 | 0 | [5 empty] | 739.31 | 250 | 184827.5 | 184827.5 | [5 empty] | 19.31 | 250 | 4827.5 | 184827.5 | 4827.5 | 180000
| b | Live kitchen (300mm) appox | N.A | N.A | SFT | 105 | 250 | 26250 | 105 | 250 | 26250 | 0 | [5 empty] | 101.25 | 250 | 25312.5 | 25312.5 | [5 empty] | -3.75 | 250 | -937.5 | 25312.5 | -937.5 | 26250
| c | Bar (150mm) appox | N.A | N.A | SFT | 85 | 250 | 21250 | 85 | 250 | 21250 | 0 | [5 empty] | 89.19 | 250 | 22297.5 | 22297.5 | [5 empty] | 4.19 | 250 | 1047.5 | 22297.5 | 1047.5 | 21250
[30 empty] | 0 | 0 | 0
STONE & TILE WORKS | [29 empty] | 0 | 0 | 0
1 | KOTA Flooring | Providing and Laying KOTA stone of 19mm thk. on avg 40 mm thk bed of 1:4 cement mortar in proper line and level including neat cement float, filling joints with neat cement slurry of appropriate colour, cleaning, curing, rubbing, complete. Scope includes laying of floor protective cover on the floor and removing of the same when directed along with supply of all necessary materials, labour, tools and tackles complete in line with the Technical Specification, Drawings and as per the direction of the Architect & PMC. Including Polishing. | [27 empty] | 0 | 0 | 0
|  | Size : 550x550 Basic Rate : 55 Per SFT | [27 empty] | 0 | 0 | 0
| a | Kitchen |  | N.A | SFT | 695 | 180 | 125100 | 680 | 180 | 122400 | -2700 | [5 empty] | 740.685 | 180 | 133323.3 | 133323.3 | [5 empty] | 60.685 | 180 | 10923.3 | 133323.3 | 10923.3 | 122400
| b | Live kitchen |  |  | SFT | 120 | 180 | 21600 | 120 | 180 | 21600 | 0 | [5 empty] | 101.25 | 180 | 18225 | 18225 | [5 empty] | -18.75 | 180 | -3375 | 18225 | -3375 | 21600
| c | Bar |  |  | SFT | 95 | 180 | 17100 | 95 | 180 | 17100 | 0 | [5 empty] | 69.19 | 180 | 12454.2 | 12454.2 | [5 empty] | -25.81 | 180 | -4645.8 | 12454.2 | -4645.8 | 17100
| d | Liquor Store Room |  |  | SFT |  |  | 0 | 30 | 180 | 5400 | 5400 |  | Basic rate to reduced to Rs135 | Rate Quoted as per PO approved Rates | ok |  | 20 | 180 | 3600 | #VALUE! |  | Basic rate to reduced to Rs135 | Rate Quoted as per PO approved Rates | ok |  | -10 | 180 | -1800 | 3600 | -1800 | 5400
[30 empty] | 0 | 0 | 0
2 | Wooden finish herringbone pattern Tile Flooring | Fixing & laying of tiles for flooring which includes --bedding of appropriate thickness with mortar of 1:6 ratio (1cement:6sand), spreading of grey cement slurry with minimum of 2kg/ Sq.mt. ratio over bedding mortar, including 3mm spacer with epoxy grout of approved colour, adhesive of bal Endura or approved equivalent, making of hole where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc. as per design and drawing and directed by PMC etc. complete. | GROUND FLOOR | N.A | SFT | 1200 | 300 | 360000 | 1200 | 300 | 360000 | 0 | [5 empty] | 804 | 300 | 241200 | 241200 | [5 empty] | -396 | 300 | -118800 | 241200 | -118800 | 360000 |  | Total area value to be considered based on jont check between APK & VART Team in presence Mr. hemant- Charcoal
|  | size - 200x1200. Basic Rate : 150 Per SFT (make kajaria) | [27 empty] | 0 | 0 | 0
[30 empty] | 0 | 0 | 0
3 | Pattern Tile Flooring | Fixing & laying of tiles for flooring which includes --bedding of appropriate thickness with mortar of 1:6 ratio (1cement:6sand), spreading of grey cement slurry with minimum of 2kg/ Sq.mt. ratio over bedding mortar, including 3mm spacer with epoxy grout of approved colour, adhesive of bal Endura or approved equivalent, making of hole where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc. as per design and drawing and directed by PMC etc. complete. | GROUND+MEZZANINE FLOOR | N.A | SFT | 500 | 450 | 225000 | 500 | 450 | 225000 | 0 | [5 empty] | 492 | 450 | 221400 | 221400 | [5 empty] | -8 | 450 | -3600 | 221400 | -3600 | 225000 |  | Total area value to be considered based on jont check between APK & VART Team in presence Mr. hemant- Charcoal
|  | size - 300x300. Basic Rate : 220 Per SFT | [27 empty] | 0 | 0 | 0
[30 empty] | 0 | 0 | 0
4 | Wooden finish Tile skirting | Fixing & laying of 100mm high tiles for skirting with bedding of appropriate approved make adhesive & colour joint filler inclusive of making all groove/chamfering/rounding/hole where ever required, in proper line and level in all direction, polishing/finishing/cleaning etc. Complete as per detail drawing, specification and as directed by PMC. | GROUND+MEZZANINE FLOOR | N.A | RFT | 200 | 200 | 40000 | 200 | 200 | 40000 | 0 | [5 empty] | 108.24 | 200 | 21648 | 21648 | [5 empty] | -91.76 | 200 | -18352 | 21648 | -18352 | 40000 |  | Total area value to be considered based on jont check between APK & VART Team in presence Mr. hemant- Charcoal
|  | size - 100x1200. Basic Rate : 120 Per SFT | [27 empty] | 0 | 0 | 0
[30 empty] | 0 | 0 | 0
5 | Decorative Wall Tiles | Providing and fixing Glazed Decorative wall tiles which includes-approved make of adhesive like bal Endura or equivalent, grey cement paste with backing coat of 1:3 cement mortar not less than 12mm thick as & where ever required, joint filler of approved make and colour, as and where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc as per design, drawing and directed by PMC etc. all complete. | [27 empty] | 0 | 0 | 0 |  | Total area value to be considered based on jont check between APK & VART Team in presence Mr. hemant- Charcoal
|  | Size : 75x300 Rate : 275per SFT | [27 empty] | 0 | 0 | 0
| a | Live kitchen Wall tiles upto 2400mm ht |  |  | SFT | 300 | 500 | 150000 | 300 | 500 | 150000 | 0 | [5 empty] | 143.25 | 500 | 71625 | 71625 | [5 empty] | -156.75 | 500 | -78375 | 71625 | -78375 | 150000 |  | Ony Green Tile
| b | Bar Wall tiles upto 2400mm ht |  |  | SFT | 200 | 500 | 100000 | 200 | 500 | 100000 | 0 | [5 empty] | 0 | 500 | 0 | 0 | [5 empty] | -200 | 500 | -100000 | 0 | -100000 | 100000
[30 empty] | 0 | 0 | 0
6 | Sada Wall Tiles for kitchen | Providing and fixing Ceramic wall tiles which includes-approved make of adhesive like bal Endura or equivalent, dry cladding on bison board panelling, joint filler of approved make and colour, as and where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc as per design, drawing and directed by PMC etc. all complete. (Color - white/ ivory) | [27 empty] | 0 | 0 | 0
|  | Size : 300x600. Rate : 45per SFT | [27 empty] | 0 | 0 | 0
| a | Main kitchen and under counter wall tiles upto 2400mm ht |  |  | SFT | 1340 | 180 | 241200 | 1340 | 180 | 241200 | 0 | [5 empty] | 1599 | 180 | 287820 | 287820 | [5 empty] | 259 | 180 | 46620 | 287820 | 46620 | 241200
| b | Live Kitchen |  |  | SFT | 85 | 180 | 15300 | 85 | 180 | 15300 | 0 | [6 empty] | 180 | 0 | 0 | [5 empty] | -85 | 180 | -15300 | 0 | -15300 | 15300 |  | Cancelled du to duplication
| c | Bar Area |  |  | SFT | 65 | 180 | 11700 | 65 | 180 | 11700 | 0 | [5 empty] | 108.55 | 180 | 19539 | 19539 | [5 empty] | 43.55 | 180 | 7839 | 19539 | 7839 | 11700 |  | Total area value to be considered based on jont check between APK & VART Team in presence Mr.Hemant- Charcoal
| d | Liquor Store Room |  |  | SFT | 150 | 180 | 0 | 150 | 180 | 27000 | 27000 |  | Basic rate should be 125/- as tile basic rate given Rs 45/- | Rate Quoted as per PO approved Rates | OK |  | 151.52 | 180 | 27273.6 | #VALUE! |  | Basic rate should be 125/- as tile basic rate given Rs 45/- | Rate Quoted as per PO approved Rates | OK |  | 1.52 | 180 | 273.6 | 27273.6 | 273.6 | 27000 |  | Total area value to be considered based on jont check between APK & VART Team in presence Mr.Hemant- Charcoal
[30 empty] | 0 | 0 | 0
7 | SS Corner Guard | P&F of 304 grade 3mm thick SS Corner guard (30mm x 30mm, mat finished as per approved sample) fixing with conceal tile on each corner of the kitchen's wall before cladding of tiles, so that the corner may be protected from the damages. Complete in proper line & level and site engineer's instruction. |  | N.A | RFT | 80 | 300 | 24000 | 80 | 300 | 24000 | 0 | [6 empty] | 300 | 0 | 0 | [5 empty] | -80 | 300 | -24000 | 0 | -24000 | 24000
[30 empty] | 0 | 0 | 0
8 | Brass Inlay in Flooring | P&F ofe3mm thick antique brass floor inlay fixing with thread screws on each corner of the kitchen's wall before cladding of tiles, so that the corner may be protected from the damages. Complete in proper line & level and site engineer's instruction. |  | N.A | RFT | 100 | 300 | 30000 | 100 | 300 | 30000 | 0 | [5 empty] | 92.03 | 300 | 27609 | 27609 | [5 empty] | -7.97 | 300 | -2391 | 27609 | -2391 | 30000 |  | Total area value to be considered based on jont check between APK & VART Team in presence Mr.Hemant- Charcoal
9 | pass window jamb line | Providing and fixing 300mm wide granite jamb line for pass window in live kitchen area which includes-approved make of adhesive like bal Endura or equivalent, joint filler of approved make and colour, as and where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc as per design, drawing and directed by PMC etc. all complete. (Color - white/ ivory) |  |  | RFT |  |  | 0 | 6 | 600 | 3600 | 3600 |  | Require granite basic price | Granite Basic price 300/- per sqft |  |  | 21.08 | 600 | 12648 | 12648 |  | Require granite basic price | Granite Basic price 300/- per sqft |  |  | 15.08 | 600 | 9048 | 12648 | 9048 | 3600 |  | This granite is only 200mm wide vendor to charge rate accordingly
|  | TOTAL OF CIVIL WORK | [5 empty] | 2522190 |  |  | 2725960 | 203770 | [7 empty] | 2874733.525 | #VALUE! | [7 empty] | 148773.525 | 2874733.525 | 148773.525 | 2725960
0
POP & PAINTING WORK
1 | POP Punning | Providing and applying Plaster of Paris punning of average thickness 20-25mm to existing wall surfaces/ on existing tiles including chicken mesh in true level and plumb complete as per design and drawing Cleaning the surface properly with sand paper, filling cracks/holes with plaster of Paris. Applying lambi / putty (lambi/putty will be of good quality) sand papering the putty work on chamfers, etc.at any / all heights. Rate include cost for making grooves up to 12mm thick if required in horizontal or vertical direction near doors, windows, skirting, floor covering, masking tape and cleaning the area all complete as per drawing, design & manufactures specification. | [28 empty] | 0 | 0
| a | block work walls |  | N.A | SFT | 3500 | 50 | 175000 | 3500 | 50 | 175000 | 0 | [5 empty] | 211.29 | 50 | 10564.5 | 10564.5 | [5 empty] | -3288.71 | 50 | -164435.5 | 10564.5 | -164435.5 | 175000 |  | Total area value to be considered based on jont check between APK & VART Team in presence Mr.Hemant- Charcoal
| b | Exposed ceiling |  | N.A | SFT | 2600 | 50 | 130000 | 2600 | 50 | 130000 | 0 | [5 empty] | 1141.93 | 50 | 57096.5 | 57096.5 | [5 empty] | -1458.07 | 50 | -72903.5 | 57096.5 | -72903.5 | 130000
[31 empty] | 0 | 0
2 | Gypsum Ceiling | Providing, making and fixing of POP false ceiling as per manufacturer design and drawing including cut-outs for hvac grille, lights etc.at any / all heights. Rate quoted should be including of vertical drop of any heights, mouldings and size mentioned in drawings with necessary required framing in 450x 900 ultra Gyproc sections, fittings, and fixtures, scaffolding, floor covering, masking tape and cleaning the area all complete as per drawing, design & manufactures specification all complete. Rates do not include painting work. |  | N.A | SFT | 750 | 170 | 127500 | 750 | 170 | 127500 | 0 | [5 empty] | 644.25 | 170 | 109522.5 | 109522.5 | [5 empty] | -105.75 | 170 | -17977.5 | 0 | -17977.5 | 17977.5
[31 empty] | 0 | 0
3 | Metal Ceiling | Fitting of false ceiling consisting of 20g Aluminium planks made of pre-coated ( Top & Bottom ) & Size : 600mmx600mm tiles . False Ceiling with necessary supports , hangers etc. provided to install light fitting , fresh air grill etc. ( from Hunter Douglas or Armstrong ) |  | N.A | SFT | 900 | 290 | 261000 | 900 | 290 | 261000 | 0 | [5 empty] | 96 | 290 | 27840 | 27840 | [5 empty] | -804 | 290 | -233160 | 0 | -233160 | 233160
[31 empty] | 0 | 0
4 | Textured Wall Paint | Providing & applying three (03) coats of approved Plastic paint on walls including scraping, primer , filling with putty etc. complete with final coat no brush mark to be visible after painting colour shade as specified. |  | N.A | SFT | 2000 | 32 | 64000 | 2000 | 132 | 264000 | 200000 |  | why is rates escalated from 32 Psft to 100 Psft | Revised Rates Quoted As per ARA Design approved Stucco Texture Paint - 8473 - Royal Play | The team has seen the KG site before giving the quotation. Thye should have give considered this before. As the paint finish was clear. | It was a type of error from our 32/- per sqft is never for Texture paint | 1023.7975 | 132 | 135141.27 | #VALUE! |  | why is rates escalated from 32 Psft to 100 Psft | Revised Rates Quoted As per ARA Design approved Stucco Texture Paint - 8473 - Royal Play | The team has seen the KG site before giving the quotation. Thye should have give considered this before. As the paint finish was clear. | It was a type of error from our 32/- per sqft is never for Texture paint | -976.2025 | 132 | -128858.73 | #VALUE! | -128858.73 | #VALUE!
[31 empty] | 0 | 0
5 | Ceiling Paint ON Gypsum | Providing & applying three (03) coats of approved Plastic paint on exposed surface on ceiling including scraping, primer , filling with putty etc. complete with final coat no brush mark to be visible after painting colour shade as specified. |  | N.A | SFT | 690 | 32 | 22080 | 690 | 32 | 22080 | 0 | [5 empty] | 662.68 | 32 | 21205.76 | 21205.76 | [5 empty] | -27.32 | 32 | -874.24 | 21205.76 | 0 | 21205.76 |  | Total area value to be considered based on jont check between APK & VART Team in presence Mr.Hemant- Charcoal
[31 empty] | 0 | 0
6 | Expose Ceiling Paint including all beams | Providing & applying Three (03) coats of approved Plastic paint on exposed surface on ceiling including HVAC ducts, Sprinkler Pipes etc. complete with final coat no brush mark to be visible after painting colour shade as specified. |  | N.A | SFT | 1030 | 32 | 32960 | 1030 | 32 | 32960 | 0 | [5 empty] | 3131.06 | 32 | 100193.92 | 100193.92 | [5 empty] | 2101.06 | 32 | 67233.92 | 100193.92 | 67233.92 | 32960 |  | Total area value to be considered based on jont check between APK & VART Team in presence Mr.Hemant- Charcoal
[31 empty] | 0 | 0
7 | Duct painting | Providing & applying Three (03) coats of powder coat (as per approved shade) on exposed surface on metal duct including removing of old paint, required zink oxide paint etc. complete with final coat no brush mark to be visible after painting colour shade as specified. |  |  | SFT | 500 | 27 | 13500 | 500 | 70 | 35000 | 21500 |  | Rates are approved | Spray Paint |  |  | 526.75 | 70 | 36872.5 | 36872.5 |  | Rates are approved | Spray Paint |  |  | 26.75 | 70 | 1872.5 | 0 | 1872.5 | -1872.5
[31 empty] | 0 | 0
8 | Fire Sprinkler paint | Providing & applying Three (03) coats of fire rated paint as per standard on exposed surface on metal including removing of old paint etc. complete with final coat no brush mark to be visible after painting colour shade as specified. |  |  | SFT | 100 | 23 | 2300 | 100 | 55 | 5500 | 3200 |  | Rates should be 55/-SFt | Rate is revised |  |  | 0 | 55 | 0 | 0 |  | Rates should be 55/-SFt | Rate is revised |  |  | -100 | 55 | -5500 | 0 | -5500 | 5500 |  | Paint is part of fire sprinkler scope
TOTAL of POP & PAINTING WORK | [7 empty] | 828340 |  |  | 1053040 | 224700 | [7 empty] | 498436.95 | #VALUE! | [7 empty] | -554603.05 | #VALUE! | -553728.81 | #VALUE!

## INTERIOR
BOQ of Civil work for Copper Chimney Project, Pune-Wakad | [9 empty] | 18/9/2023 |  |  |  | R1
|  | GROUND FLOOR |  |  |  |  | FT |  |  | FT
SR.NO. | ITEM | DESCRIPTION | LOCATION | DIMENSION | UNIT | QTY. | RATE | AMOUNT | QTY. | RATE | AMOUNT | DEVIATION | IMAGE | REMARK | Purchase Remark | VIPL Remark | ARA Remark | VIPL Remark 13.11.2023 | QTY. | RATE | AMOUNT | QTY. | RATE | AMOUNT |  | Claimed quantity | Actual Quantity | Rate | APK Advise Rate | Claimed Amount | Actual Amount | Difference | Reason of deduction | APK Remark
DOORS |  | CARPENTRY WORK |  |  | BOQ | [13 empty] | ACTUAL |  |  | DIFFERENCE
1 | Kitchen Door | Providing & fixing in position of wooden FRD Double Leaf Door made up of 45mm thick firerated flush door shutter of approved make & thickness, Inner side finished with wooden laminate and outer side with veneer finish including providing & fixing 750mm X 200mm fire rated glass Vision panel and 12mm thk Wooden lipping all around, including of 2100mm X 300mm SS push plate and 300mm high SS kick plate, including P/F of Door frame made out of CP Teak / Ash wood or equivalent with melamine polish finish. Size of the frame approximate 175mm wide X 50mm thick. Applicable hardware's such as s/s handles/ ss push plate, floor spring and any other hardware etc required to complete the related works as per design & detail. door hardware make consider Dorma / Hafele/Ozon /equilient Need heavy duty floor spring & both sides openable. | KITCHEN ENTRY | 1200 X 2400 MM | NOS. | 1 | 50000 | 50000 | 1 | 50000 | 50000 | 0 |  | SS PVD Coating to be fixed to all edges of Door shutters. | Proposed rate 49600 | SS PVD 50mm Cosidered | no changes to be accepted. |  | 1 | 50000 | 50000 | 0 | 50000 | 0 |  | 1 | 1 | 50000 |  | 50000 | 50000 | 0 |  | Fire certificte to be attached
[20 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
2 | Kitchen Door beside buffet | Providing & fixing in position of wooden FRD single Leaf Door made up of 45mm thick firerated flush door shutter of approved make & thickness, Inner side finished with wooden laminate and outer side with veneer finish including providing & fixing 750mm X 200mm fire rated glass Vision panel and 12mm thk Wooden lipping all around, including of 2100mm X 300mm SS push plate and 300mm high SS kick plate, including P/F of Door frame made out of CP Teak / Ash wood or equivalent with melamine polish finish. Size of the frame approximate 175mm wide X 50mm thick. Applicable hardware's such as s/s handles/ ss push plate, floor spring and any other hardware etc required to complete the related works as per design & detail. door hardware make consider Dorma / Hafele/Ozon /equilient Need heavy duty floor spring & both sides openable. | LIVE KITCHEN ENTRY | 950 X 2400 MM | NOS. | 1 | 35000 | 35000 | 1 | 35000 | 35000 | 0 | [6 empty] | 1 | 35000 | 35000 | 0 | 35000 | 0 |  | 1 | 1 | 35000 |  | 35000 | 35000 | 0
[20 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
3 | Live Kitchen sliding Door | Providing & fixing in position of wooden FRD sliding door made up of 38mm thick firerated flush door shutter of approved make & thickness, both side to be finished with wooden laminate including providing & fixing 750mm X 200mm fire rated glass Vision panel and 12mm thk Wooden lipping all around, including conceal handle a and 300mm high SS kick plate, including P/F of Door frame made out of CP Teak / Ash wood or equivalent with melamine polish finish. Size of the frame approximate 175mm wide X 50mm thick. Applicable hardware's such as sliding channel, s/s handles/ ss push plate, lock, tower bolt and any other hardware etc required to complete the related works as per design & detail. door hardware make consider Dorma / Hafele/Ozon /equilient Need heavy duty floor spring & both sides openable. | LIVE KITCHEN ENTRY | 900X 2400 MM | NOS. | 1 | 35000 | 35000 | 1 | 35000 | 35000 | 0 | [6 empty] | 1 | 35000 | 35000 | 0 | 35000 | 0 |  | 1 | 1 | 35000 |  | 35000 | 35000 | 0
[27 empty] | 0 | 0 |  |  |  | 0
4 | Main Door | P/F 10 mm thk. toughened glass double leaf openable door with 20x 40mm MS framework with white/ black powder coating and bottom base wooden partiton height upto 600mm with wooden molding finish with duco paint and all necessary required groove, wooden framing, including glass door with heavy duty floor spring fixing with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. including door lock. | MAIN ENTRY | 1800X 2400MM | NOS. | 1 | 74400 | 74400 | 1 | 74400 | 74400 | 0 | [6 empty] | 1 | 74400 | 74400 | 0 | 74400 | 0 |  | 0 | 1 | 74400 |  | 74400 | 74400 | 0
5 | Trap Door | Providing and fixing trap doors for access to the service areas. The trap door shall have an external frame made of 50mm x 50mm in good quality seasoned wood scantling on which the shutter is hinged. Shutter shall be made of 19 mm. fire rated Plywood. The exposed side & Internal side shall be laminate finish. Concealed heavy duty hinges shall be used to mount the shutters and locking shall be provided with Allen key and panel locks. Sufficient number of hinges and locks shall be provided to avoid sagging of the shutter. Key also shall be supplied | NEAR LIVE KITCHEN | 1200X 900 MM | NOS. | 3 | 20000 | 60000 | 3 | 20000 | 60000 | 0 | [6 empty] | 1 | 20000 | 20000 | -2 | 20000 | -40000 | -1464681.0732 | 1 | 1 | 20000 |  | 20000 | 20000 | 0 |  |  | -1464681.0732
[27 empty] | 0 | 0
TOTAL DOORS | [7 empty] | 254400 |  |  | 254400 | 0 | [8 empty] | 214400 |  |  | -40000 |  | Total Door | 0 | 0 |  | 214400 | 214400 | 0
[27 empty] | 0 | 0
CARPENTRY WORK |  | CARPENTRY WORK | [8 empty] | #REF! | [15 empty] | 0 | 0
1 | Service Station | P/F service counters in duco finished from outer surface & top finished in veneer. The storage under the Counter should be provided with 6" ht. drawers at top row finished with wooden ribs. top of the shutter having C section brass inlay & below openable shutters finished with duco. the drawer should have internal partiton with fabric finish for cutlary Shutters made out of 19mm thk. firerated plywood finished with 1mm thk. laminate internally. The shutters to be provided with fittings such as hinges; handles; ball catch, locks etc. complete in all respect. The rates for the Shutters to be included. as per design and details. any 1drawer (in each service station) should have 3compartment made in ply finished with fabric for cutlery and bottom storage should have 1shelf for crockery, shelf in ply finished with white laminate | NEAR COLUMN | 1200mm L X 600mmW X 900H | NOS. | 3 | 40000 | 120000 | 3 | 48000 | 144000 | 24000 |  |  | 33%-Cost escalation on acccount of increment of material from commercial ply to fire rated ply |  | give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. | 20%-Cost escalation on acccount of increment of material from for Material changed Commercial to Fire Rated Ply | 3 | 48000 | 144000 | 0 | 48000 | 0 |  | 3 | 3 | 48000 |  | 144000 | 144000 | 0
|  | Plywood - branded firerated -- Greenply or Equivalent brand | [5 empty] | 0 |  |  | 0
|  | Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) | [5 empty] | 0 |  |  | 0
|  | Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.) | [5 empty] | 0 |  |  | 0
2 | CONSOLE_01 | The base CONSOLE finished in duco from outer surface & top finished in veneer. The storage under the Counter should be provided with 6" ht. drawers at top row finished with wooden ribs. top of the shutter having C section brass inlay & below openable shutters finished with duco. Shutters made out of 19mm thk. plywood finished with 1mm thk. laminate internally. The shutters to be provided with fittings such as hinges; handles; ball catch etc. complete in all respect. Including castor wheels (4nos) equipped wih 100mm wheels for smoothly running. The rates for the Shutters to be included. as per design and details. | NEAR HOSTESS DESK | 1265mm L X 500mmW X 900H | NOS. | 1 | 40000 | 40000 |  |  |  | -40000
Plywood - branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand
Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.)
Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.)
2a | CONSOLE_02 | The base CONSOLE finished in duco from outer surface & top finished in veneer. The storage under the Counter should be provided with 6" ht. drawers at top row finished with wooden ribs. top of the shutter having C section brass inlay & below openable shutters finished with duco. Shutters made out of 19mm thk. plywood finished with 1mm thk. laminate internally. The shutters to be provided with fittings such as hinges; handles; ball catch etc. complete in all respect. Including castor wheels (4nos) equipped wih 100mm wheels for smoothly running. The rates for the Shutters to be included. as per design and details. | NEAR BANQUETTE | 1540mm L X 500mmW X 900H | NOS. | 2 | 50000 | 100000 |  |  |  | -100000
Plywood - branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand
Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.)
Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.)
2b | CONSOLE_03 (for salad & dessert) | The base CONSOLE finished in duco from outer surface & top finished in veneer. The storage under the Counter should be provided with 6" ht. drawers at top row finished with wooden ribs. top of the shutter having C section brass inlay & below openable shutters finished with duco. Shutters made out of 19mm thk. plywood finished with 1mm thk. laminate internally. The shutters to be provided with fittings such as hinges; handles; ball catch etc. complete in all respect. Including castor wheels (4nos) equipped wih 100mm wheels for smoothly running. The rates for the Shutters to be included. as per design and details. | NEAR LIVE KITCHEN | 3895mm L X 500mmW X 900H | NOS. | 1 | 135000 | 135000 |  |  |  | -135000
Plywood - branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand
Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.)
Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.)
3 | MS Display Unit_01 | P/F Display unit having 20 x 20mm MS framework with black powder coat upto ceiling height, having wooden shelf @ every 350mm c/c including all necessary hardware etc. complete. 20mm thk sandwitched glass shelf with cane in center and with wooden frame. Plywood - branded fire rated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.) 20X20mm MS section finish with black powder coat 20mm thk sandwiched glass shelf with cane in center and with veneer finish frame | NEAR ENTRANCE | 1060mm L X 200mm W X 5000H | NOS. | 1 | 50000 | 50000 | 1 | 50000 | 50000 | 0 | [6 empty] | 1 | 50000 | 50000 | 0 | 50000 | 0 |  | 1 | 1 | 50000 |  | 50000 | 50000 | 0
|  | 20mm thk sandwiched glass shelf with cane in center and with veneer finish frame |  | 500mm x 200mm |  | 6 | 3500 | 21000 | 6 | 4500 | 27000 | 6000 |  |  | Why rate escalation on account of qty increase | Material changed to fire rated Rates Revised | give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. | Rates Revised 20%-Cost escalation on acccount of increment of material from for Material changed Commercial to Fire Rated Ply |  | 4500 | 0 | -6 | 4500 | -27000 |  | 6 | 0 | 4500 |  | 0 | 0 | 0
4 | MS Display Unit_02 | P/F Display unit having 20 x 20mm MS framework with black powder coat upto ceiling height, having wooden shelf @ every 350mm c/c including all necessary hardware etc. complete. 20mm thk sandwitched glass shelf with cane in center and with veneer finish frame | BEHIND BANQUETE SEATING | 1580mm L X 200mm W X 5000H | NOS. | 2 | 75000 | 150000 | 2 | 75000 | 150000 | 0 | [6 empty] | 2 | 75000 | 150000 | 0 | 75000 | 0 |  | 2 | 2 | 75000 |  | 150000 | 150000 | 0
|  | Plywood - branded firerated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand | [5 empty] | 0 |  |  | 0
|  | Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) | [5 empty] | 0 |  |  | 0
|  | Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.) | [5 empty] | 0 |  |  | 0
20X20mm MS section finish with black powder coat
|  | 20mm thk sandwiched glass shelf with cane in center and with veneer finish frame |  | 500mm x 200mm |  | 18 | 3500 | 63000 | 18 | 4500 | 81000 | 18000 |  |  | Why rate escalation on account of qty increase | Material changed to fire rated Rates Revised | give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. |  |  | 4500 |  | -18 | 4500 | -81000 |  | 18 | 0 | 4500 |  | 0 | 0 | 0
5 | Hostess Desk | Providing and fixing Hostess desk made out of approved make branded fire rated ply -- Greenply or Equivalent brand and finished with veneer as approved with veneer groves as per design with melamine matt polish 20X20mm MS section finish with black powder coated legs. with ss 3mm thick pvd coated 'CC' Logo |  | 1050mm L X 500mm W X 1050 H | NOS. | 1 | 35000 | 35000 | 1 | 42000 | 42000 | 7000 |  |  | 33% rate escalation on account of material change from commercial to fire rated ply not justified | Rates Revised | give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. | Rates Revised 20%-Cost escalation on acccount of increment of material from for Material changed Commercial to Fire Rated Ply | 1 | 42000 | 42000 | 0 | 42000 | 0 |  | 1 | 1 | 42000 |  | 42000 | 42000 | 0
|  | Desk to have 2 drawers of ht 155mm, finished with duco outside and veneer maching laminate inside with inbuilt recessed handles in wood and polish. | [5 empty] | 0 |  |  | 0
|  | Basic cost of Veneer : 140/- SFT | [5 empty] | 0 |  |  | 0
6 | Banquet back planter Box | Providing and fixing of 19mm thk fire rated Ply-- Greenply or Equivalent brand apron to be cladded with Veneer/Solid Wood all necessary required groove, wooden framing, approved make adhesive and cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  | 9145x 300 x 900 HT | NOS. | 1 | 65000 | 65000 | 1 | 78000 | 78000 | 13000 |  |  | 33% rate escalation on account of material change from commercial to fire rated ply not justified | Rates Revised | give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. | Rates Revised 20%-Cost escalation on acccount of increment of material from for Material changed Commercial to Fire Rated Ply | 1 | 78000 | 78000 | 0 | 78000 | 0 |  | 1 | 1 | 78000 |  | 78000 | 78000 | 0
[27 empty] | 0 | 0 |  | 0
7 | Banquet Seating | Providing, making and fixing sofa made out of wooden frame work and cladded with 12mm thk approved make branded fire rated Ply -- Greenply or Equivalent brand & approved fabric with required wooden frame, top rail having 38mm dia brass metal rail height upto 150mm and side to have a cane paneling with required wooden frame with incline backrest. the bottom to have storage under seat with heavy duty sliding trolly to keep crockey. finishing/cleaning/cutting/required fixture & fasteners etc. as per design & drawing & as directed by Project Manager etc. complete. Sofa will have high density rubber foam in angle.(Foam used should be approved and to be certified against poisonous and noxious fumes.) Rate includes upholstery of fabrics. Under seating Drawers with heavy duty trolley for storage. |  | 9145x 650 x 900 HT | NOS. | 2 | 115000 | 230000 | 2 | 195000 | 390000 | 160000 |  |  | 12,900/Rft for sofa is to high rate suggest the rate to be maintained to 9500/Rft in line with Air side | Rate for Revised Benquet Seating to 9500/- Rft Length 9.145 x 3.28 x 29.99 Rft 30 Rft x 9500/- = 2,85.000/- Per Nos | no change in design why the cost going too high. Only the plywood chnages to fire rated ply. give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. | - Rate revised 6500/- Per Rft added for Material changed Commercial to Fire Rated Ply + 38mm Dia brass top Rail add + Heavy duty sliding trolly storge added | 2 | 195000 | 390000 | 0 | 195000 | 0 |  | 2 | 2 | 195000 |  | 390000 | 390000 | 0
Veneer on exterior finish Basic cost @ 140Rs sft
Fabric Basic cost @ 600 per MTR
Size : W 650 x H 900
38mm dia brass top rail
Heavy duty sliding trolly for storage
8 | Cane Panel Shutter | P/F 75mm thk fire rated plywood partition finished with bamboo Cane from Single side, internal ply finished with laminate. structure to be made out of 40x20mm thk wooden frame with 12mm ply on both side, intermidiate member size of 40 x 20mm wooden frame/ bidding to be finished with melamine polish. to be finished with duco paint finish with necessary fittings as per design and details. | STORY WALL | 1200 x 2000 (H) | SQFT | 45 | 1100 | 49500 | 50 | 1650 | 82500 | 33000 | [6 empty] | 54.9 | 1650 | 90585 | 0 | 1650 | 0 |  | 36 | 54.9 | 1650 |  | 90585 | 90585 | 0
|  | Plywood - branded firerated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand |  |  | NOS. | 1 | 8000 | 8000 | 1 | 12000 | 12000 | 4000 | [7 empty] | 12000 | 0 | -1 | 12000 | -12000 |  | 1 | 0 | 12000 |  | 0 | 0 | 0
9 | Cane Panelling | P/F 75mm thk firerated plywood paneling finished with bamboo Cane from Single side, internal ply finished with laminate. structure to be made out of 40x20mm thk wooden frame with 12mm ply on both side, intermidiate member size of 40 x 20mm wooden frame/ bidding to be finished with melamine polish. to be finished with duco paint finish with necessary fittings as per design and details. | ABOVE BUFFET COUNTER, KITCHEN DOOR, ABOVE SHAFT DOOR, CURTAIN WALL, WALLPAPER WALL |  | SQFT | 190 | 1100 | 209000 | 500 | 1250 | 625000 | 416000 |  |  | Approved as per rate analysis | Rate Analyisis attached in separte sheet | ok |  | 542.27 | 1250 | 677837.5 | 42.27 | 1250 | 52837.5 |  | 612.6875 | 542.27 | 1250 |  | 677837.5 | 677837.5 | 0
|  | Plywood - branded fire rated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand | [24 empty] | 0 | 0
[27 empty] | 0 | 0
10 | Wall dado - Veneer panelling | Providing, making and fixing of wall panel made of 12mm thk branded fire rated Ply -- Greenply or Equivalent brand with Veneer finish with melamine polish having wooden molding all necessary required wooden framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | ALL WALLS | upto 900mm ht | SFT | 370 | 900 | 333000 | 370 | 1000 | 370000 | 37000 |  |  | There is no change in specs for this item so no escalation to be paid | Material changed to fire rated Rates Revised | give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. | Rates Revised 20%-Cost escalation on acccount of increment of material from for Material changed Commercial to Fire Rated Ply | 405.95 | 1000 | 405950 | 35.95 | 1000 | 35950 |  | 444.5 | 405.945 | 1000 |  | 405950 | 405945 | 5
|  | Basic Rate of Veneer @ 120 Rs per SFT | [5 empty] | 0 |  |  | 0 | [15 empty] | 0 | 0 |  | 0
[27 empty] | 0 | 0 |  | 0
11 | Moulding | Providing, making and fixing of \wooden mouldings as per detail drawing with grooves to be added with all necessary required wooden framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  | upto 900mm ht | SFT | 370 | 350 | 129500 | 370 | 350 | 129500 | 0 | [6 empty] | 333.43 | 350 | 116700.5 | -36.57 | 350 | -12799.5 |  | 368.565 | 333.43 | 350 |  | 116700.5 | 116700.5 | 0
[27 empty] | 0 | 0 |  | 0
12 | Ply boxing with Veneer finish on shaft | Providing, making and fixing fire rated ply boxing made out of wooden/ aluminium frame work and cladded with 12mm thk approved make branded fire rated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand finished with veneer from all side and top finished with veneer with melamine polish, with one openable shutter on push button. all with required frame finishing/cleaning/cutting/required fixture & fasteners etc. as per design & drawing & as directed by Project Manager etc. complete. |  |  | Sqft | 160 | 650 | 104000 | 180 | 650 | 117000 | 13000 | [6 empty] | 54.3 | 650 | 35295 | -125.7 | 650 | -81705 |  | 56 | 54.303 | 650 |  | 35295 | 35296.95 | -1.95
|  | Basic Rate of Veneer @ 120 Rs per SFT | [24 empty] | 0 | 0 |  | 0
[27 empty] | 0 | 0 |  | 0
13 | Storage Cabinet - with bamboo cane shutter | P/F louver shutter with fire rated plywood framework finished with veneer as per design & detail made in wood with openable shutters with bamboo cane paneling back side of the cane to be finished with laminate. Including all necessary required wooden framing, approved make adhesive and fasteners, Lock, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | ELECTRICAL PANEL | 1200 x 2600 (H) | NO. | 1 | 75000 | 75000 | 1 | 115000 | 115000 | 40000 |  |  | Rates approved as material changed to fire rated |  |  |  |  | 115000 | 0 | -1 | 115000 | -115000 |  | 2 | 0 | 115000 |  | 0 | 0 | 0
|  | Basic rate of Veneer @ 120 Rs per SFT | [24 empty] | 0 | 0 |  | 0
|  | Basic rate of laminate @ 50 Rs per SFT | [24 empty] | 0 | 0 |  | 0
[27 empty] | 0 | 0 |  | 0
12 | Ply boxing with leather finish granite panelling on façade column | Providing, making and fixing ply boxing made out of wooden/ aluminium frame work and cladded with 12mm thk approved make branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand finished with 18mm thk leather finish granite. all with required frame finishing/cleaning/cutting/required fixture & fasteners etc. as per design & drawing & as directed by Project Manager etc. complete. |  |  | Sqft | 100 | 1200 | 120000 |  |  |  | -120000 | [14 empty] | 0 | 0 |  | 0
[27 empty] | 0 | 0 |  | 0
14 | signage bulkhead Ply boxing with leather finish granite panelling on façade | Providing, making and fixing fire rated ply boxing made out of wooden/ aluminium frame work and cladded with 12mm thk approved make branded fire rated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand finished with 18mm thk leather finish granite. all with required frame finishing/cleaning/cutting/required fixture & fasteners etc. as per design & drawing & as directed by Project Manager etc. complete. |  |  | Sqft | 100 | 750 | 75000 | 100 | 1450 | 145000 | 70000 |  |  | Ther rate difference between commercial ply & fire rated ply of Rs 50/Sq Ft to be payable whereas actual claim amount is 100% higher | Rate Analysis Attached same as per Items No 29 | give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. | Rate Analysis already attached We have not received Sinage Bulkhead drawing at the time of Tender submission | 93.1875 | 1450 | 135121.875 | -6.8125 | 1450 | -9878.125 |  | 93.1875 | 93.1875 | 1450 |  | 135121.875 | 135121.875 | 0
[27 empty] | 0 | 0 |  | 0
15 | Planter Box above Banquete | Providing and fixing M.S frame stand made out of 20mm x 20mm hollow box sections with 19mm thk approved make branded fire rated Ply-- Greenply or Equivalent brand apron to be cladded with Veneer/Solid Wood all necessary required groove, wooden framing, approved make adhesive and cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  | 9145x 3100 x 300 HT | NOS. | 1 | 55000 | 55000 | 1 | 85000 | 85000 | 30000 |  |  | Approved |  |  |  | 1 | 85000 | 85000 | 0 | 85000 | 0 |  | 1 | 1 | 85000 |  | 85000 | 85000 | 0 |  | Photo Required
16 | Bar Counter | P/F Bar counter to be made out of 19mm thk approved make branded fire rated ply-- Greenply or Equivalent brand apron to be cladded with wood & bamboo cane as per detail and platform in white Marble finished based on ply with necessary ms barcket, Necessary opening should be made for fixing of stainless steel sink. Erecting brick wall for plumbing and Brick platform should be provided on floor below the platform of 100mm high brass skirting from outside. The top platform to have 50mm wide Marble finish fascia horizontally. |  | 2925x 450mm | [22 empty] | 0 | 0 |  | 0
|  | Plywood - branded fire rated Ply-- Greenply or Equivalent brand | [24 empty] | 0 | 0 |  | 0
|  | Marble Basic Rate 800/- per SQ.FT. | [24 empty] | 0 | 0 |  | 0
|  | Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) | [24 empty] | 0 | 0 |  | 0
| a | Top service Counter Ply Base with Neccesory Support to receved marble |  | 450mm Width | RFT | 25 | 750 | 18750 | 25 | 1200 | 30000 | 11250 |  |  | Approved |  |  |  | 8 | 1200 | 9600 | -17 | 1200 | -20400 |  | 10.25 | 8 | 1200 |  | 9600 | 9600 | 0
| b | Front Elevation (apron) to be to be made out of 19mm thk approved make branded fire rated Ply) -- Greenply or Equivalent brand with veneer finish frames, ply to be finished with duco and veneer frames to be finished with melamine polish. Top row finished with metal cane and 100mm skirting with veneer as per detailed Drawing & design. Provision for indirect lighting to be made |  |  | SFT | 45 | 1200 | 54000 | 45 | 1800 | 81000 | 27000 |  |  | Approved |  |  |  | 29.04 | 1800 | 52272 | -15.96 | 1800 | -28728 |  | 38.4375 | 29.04 | 1800 |  | 52272 | 52272 | 0
| c | 50mm thk Top service platform in Marble |  | 450mm Width | RFT | 25 | 1200 | 30000 | 25 | 1200 | 30000 | 0 | [6 empty] | 8 | 1200 | 9600 | -17 | 1200 | -20400 |  | 10.25 | 8 | 1200 |  | 9600 | 9600 | 0
| d | 38mm Dia Foot rest real brass antique finish at the bottom. |  |  | RFT | 25 | 2000 | 50000 | 25 | 2500 | 62500 | 12500 |  |  | Approved |  |  |  | 0 | 2500 | 0 | 0 | 2500 | 0 |  |  | 0 | 2500 |  | 0
| e | 750mm Flap door for bar area entry finished same as counter appron |  | 750x 1100mm | Nos | 1 | 5000 | 5000 | 1 | 5000 | 5000 | 0 | [6 empty] | 1 | 5000 | 5000 | 0 | 5000 | 0 |  | 1 | 1 | 5000 |  | 5000 | 5000 | 0
| f | 100mm high Wooden Skirting |  |  | RFT | 25 | 450 | 11250 | 25 | 450 | 11250 | 0 | [7 empty] | 450 | 0 | -25 | 450 | -11250 |  |  | 0 | 450 |  | 0
| g | P/F 75mm thk fire rated plywood partition finished with bamboo closed cane matting , internal ply finished with laminate. structure to be made out of 40x20mm thk wooden frame with 12mm ply on both side, intermidiate member size of 40 x 20mm wooden frame/ bidding to be finished with melamine polish. to be finished with duco paint finish with necessary fittings as per design and details. |  |  | SFT | 50 | 950 | 47500 | 50 | 1250 | 62500 | 15000 |  |  | Ther rate difference between commercial ply & fire rated ply of Rs 100/Sq Ft to be payable whereas actual claim amount is 100% higher | Rate revised 1250/- Per sqft same Item No 09 Cane Panlling Rate Considered | give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. | Rate Anlysis attached | 0 | 1250 | 0 | -50 | 1250 | -62500 |  |  | 0 | 1250 |  | 0
| f | Plywood - branded fire rated Ply-- Greenply or Equivalent brand | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
[27 empty] | 0 | 0 |  | 0
17 | Bar Display unit | P/F 350mm deep Bar display unit to be made out of 19mm thk approved make branded fire rated Ply -- Greenply or Equivalent brand with veneer finish, having brass shelf @ every 400mm c/c. The Backdrop made out of 12mm thk approved make branded fire rated Ply -- Greenply or Equivalent brand with finished with bronze mirror, front panelling to be veneer finsh. The shelves to be provided with necessary fittings etc. complete in all respect. The rates for shelves to be included. as per design and details. |  | 2925x 2000mm | SFT | 11 | 9000 | 99000 | 60 | 2500 | 150000 | 51000 |  |  | Approved | ok |  |  | 50.86 | 2500 | 127150 | -9.14 | 2500 | -22850 |  | 53.0625 | 50.8565 | 2500 |  | 127150 | 127141.25 | 8.75
|  | Plywood - branded fire rated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand | [24 empty] | 0 | 0 |  | 0
|  | Marble Basic Rate 600/- per SQ.FT. | [24 empty] | 0 | 0 |  | 0
|  | Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) | [24 empty] | 0 | 0 |  | 0
|  | Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.) | [24 empty] | 0 | 0 |  | 0
| a | Mirror Panelling |  |  | SFT | 30 | 850 | 25500 | 30 | 850 | 25500 | 0 | [6 empty] | 21.5 | 850 | 18275 | -8.5 | 850 | -7225 |  | 22.5 | 21.5 | 850 |  | 18275 | 18275 | 0
| b | brass shelves |  | 900mm X300mm | no. | 5 | 10000 | 50000 | 5 | 10000 | 50000 | 0 | [6 empty] | 4 | 10000 | 40000 | -1 | 10000 | -10000 |  | 4 | 4 | 10000 |  | 40000 | 40000 | 0
| c | brass patti |  |  | Rft | 50 | 750 | 37500 | 50 | 750 | 37500 | 0 | [6 empty] | 14.6 | 750 | 10950 | -35.4 | 750 | -26550 |  | 15 | 14.6 | 750 |  | 10950 | 10950 | 0
| d | Veneer Cladding |  |  | Sqft | 75 | 1300 | 97500 | 75 | 1300 | 97500 | 0 | [6 empty] | 12 | 1300 | 15600 | -63 | 1300 | -81900 |  | 12 | 12 | 1300 |  | 15600 | 15600 | 0
[27 empty] | 0 | 0 |  | 0
18 | Bar Counter Back | P&F of back counter of 600mm wide granite top working back counter, with 19mm thick fire rated plywood structure & 12mm plywood back, counter having 4 nos. of open able shutters (in 19mm thick plywood) on front side of the unit. Counter top to be finished with 19mm thick black galaxy granite with 38mm dual nose finished, counter front part, & all the visible part to be finished with 1mm thick wooden laminate, counter's internal part to be finished with 1mm thick light walnut laminate (selected make, basic cost INR. 1200.00/ sheet). Rate inclusive of all necessary hardware fittings - like hinges, draw telescopic channels, cup board lock, decorative antique bolt handle, wire managers, etc. (approved & branded make) & necessary cut out for services requirements. Counter having 50mm ht. 18 mm thick flamed granite skirting on front side on existing 150mm ht. kobah. Complete as per architectural detail drawing & site engineer's instruction. |  | 2925x 600mm | Rft | 11 | 5600 | 61600 | 11 | 8500 | 93500 | 31900 |  |  | Approved | ok |  |  | 8.39 | 8500 | 71315 | -2.61 | 8500 | -22185 |  | 8.5 | 8.39 | 8500 |  | 71315 | 71315 | 0
[27 empty] | 0 | 0 |  | 0
19 | Bar Bulkhead | P&F of 350mm wide Bar Bulkhead/ glass hanger having 25mm X 25MM brass metal/ SS PVD COATING box section in 2 layers having vertical and horizontal member @every 450mm c/c with 10mm thk toughthned glass shelf having provision for led profile light. brass metal to be brushed finish. the base including 8-10mm solid rods band in curve shape to hang the wine glass. the top portion to have 6-8mm thk flutted glass palnelling. Rate including all necessary hardware fittings to install the shelves, anchor fastner, ceiling support, scaffolding, etc. as required on site. Complete as per architectural detail drawing & site engineer's instruction. |  | 2925x 350mm | Rft | 11 | 5600 | 61600 | 11 | 15000 | 165000 | 103400 |  |  | contractore submit rae analysis for this item, contractors justifcation on rate escalation not accepted hence old rates to be maintained | Rate Analysis attached | no changes in design and specification | Rate Analysis attached We have not received Bulkhead drawing at the time of Tender submission | 10.2 | 15000 | 153000 | -0.8 | 15000 | -12000 |  | 11 | 10.2 | 15000 |  | 153000 | 153000 | 0
[27 empty] | 0 | 0 |  | 0
20 | Buffet Counter_01 | 12mm fire rated ply box structure, wooden 6" high, 2" to 1" dia legs as per drawing finished in approved polish Top made out of fire rated plywood and finished in marble top with mitred Buffet counter to have cutouts on couner top for chaffing dishes as per measurements. Structure to have base boxing to place chaffing dishes which with be finished with veneer as approved ( slot size 300mm x 300mmx 80mm ) Buffet front to have niches in front finished in veneer,polish as approved. Niche to have shelf finished in veneer and polish as per design detail Buffet front to have shutters in fire rated plywood, veneer and rattan mesh screen in beading finished in polish as approved as per design detail Provision of wiremanager slot and trunking as per design |  | 4185 (L) x 600 (D) x 750mm (H) | Rft | 14 | 9900 | 138600 | 14 | 15000 | 210000 | 71400 |  |  | Approved based upon historic rates paid at Airside | ok | ok |  | 13.66 | 15000 | 204900 | -0.34 | 15000 | -5100 |  | 14 | 13.66 | 15000 |  | 204900 | 204900 | 0
|  | Marble Basic Rate 600/- per SQ.FT. | [24 empty] | 0 | 0 |  | 0
|  | Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) | [24 empty] | 0 | 0 |  | 0
|  | Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.) | [24 empty] | 0 | 0 |  | 0
[27 empty] | 0 | 0 |  | 0
21 | Buffet Counter_02 | 12mm fire rated ply box structure, wooden 6" high, 2" to 1" dia legs as per drawing finished in approved polish Top made out of fire rated plywood and finished in marble top with mitred Buffet counter to have cutouts on couner top for chaffing dishes as per measurements. Structure to have base boxing to place chaffing dishes which with be finished with veneer as approved ( slot size 300mm x 300mmx 80mm ) Buffet front to have niches in front finished in veneer,polish as approved. Niche to have shelf finished in veneer and polish as per design detail Buffet front to have shutters in fire rated plywood, veneer and rattan mesh screen in beading finished in polish as approved as per design detail Provision of wiremanager slot and trunking as per design |  | 1575 (L) x 600 (D) x 750mm (H) | Rft | 6 | 9900 | 59400 | 6 | 15000 | 90000 | 30600 |  |  | Approved based upon historic rates paid at Airside | ok | ok |  | 4.78 | 15000 | 71700 | -1.22 | 15000 | -18300 |  | 5 | 4.78 | 15000 |  | 71700 | 71700 | 0
|  | Marble Basic Rate 600/- per SQ.FT. | [24 empty] | 0 | 0 |  | 0
|  | Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) | [24 empty] | 0 | 0 |  | 0
|  | Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.) | [24 empty] | 0 | 0 |  | 0
[27 empty] | 0 | 0 |  | 0
22 | Buffet Counter_03 | 12mm fire rated ply box structure, wooden 6" high, 2" to 1" dia legs as per drawing finished in approved polish Top made out of fire rated plywood and finished in marble top with mitred Buffet counter to have cutouts on couner top for chaffing dishes as per measurements. Structure to have base boxing to place chaffing dishes which with be finished with veneer as approved ( slot size 300mm x 300mmx 80mm ) Buffet front to have niches in front finished in veneer,polish as approved. Niche to have shelf finished in veneer and polish as per design detail Buffet front to have shutters in fire rated plywood, veneer and rattan mesh screen in beading finished in polish as approved as per design detail Provision of wiremanager slot and trunking as per design |  | 2100 (L) x 600 (D) x 750mm (H) | Rft | 7 | 9900 | 69300 | 7 | 15000 | 105000 | 35700 |  |  | Approved based upon historic rates paid at Airside | ok | ok |  | 7 | 15000 | 105000 | 0 | 15000 | 0 |  | 7 | 7 | 15000 |  | 105000 | 105000 | 0
|  | Marble Basic Rate 600/- per SQ.FT. | [24 empty] | 0 | 0 |  | 0
|  | Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) | [24 empty] | 0 | 0 |  | 0
|  | Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.) | [24 empty] | 0 | 0 |  | 0
[27 empty] | 0 | 0 |  | 0
18 | Bison board/ V board panelling | Providing, making and fixing of wall panelling made of 12mm thk branded bison board/ V board paneling on wall including ALU framework finish with all necessary required framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | KITCHEN WINDOW | 3900x 3500mm | SFT | 180 | 550 | 99000 |  |  |  | -99000 | [14 empty] | 0 | 0 |  | 0
[27 empty] | 0 | 0 |  | 0
23 | Entry Glass Partition | P/F 10 mm thk. toughened glass partitions with 20 x 40mm MS framework with white/ black powder coating and all necessary required groove, wooden framing, with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. Providing, making and fixing of wall panel made of 12mm thk fire rated ply -- Greenply or Equivalent brand with MDF finish with Duco paint and wooden molding as per design, all necessary required wooden framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. skirting in metal, brass finish (same as main door handle) | ENTRANCE | 7700x 3500mm | SFT | 300 | 950 | 285000 | 300 | 950 | 285000 | 0 |  |  | There is no spec change thus rate escalation should not be paid | Material changed to fire rated Rates Revised | give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. | Rates Revised 20%-Cost escalation on acccount of increment of material from for Material changed Commercial to Fire Rated Ply | 190.54 | 950 | 181013 | -109.46 | 950 | -103987 |  | 190.54 | 190.5387 | 950 |  | 181013 | 181011.765 | 1.235
24 | Main Door Handle | Providing, Supplying & fixing of double sided 3mm thk Sign handle in brass | ENTRANCE | 450mm x 450mm | NOS | 1 | 7500 | 7500 | 1 | 7500 | 7500 | 0 | [6 empty] | 0 | 7500 | 0 | -1 | 7500 | -7500 |  |  | 0 | 7500
[27 empty] | 0 | 0
TOTAL CARPENTRY WORK | [7 empty] | 3475000 |  |  | 4241750 | [9 empty] | 3475864.875 |  |  | -711470.125 | Total Carpentry Work |  | 0 | 0 | 0 | 3475864.875 | 3475851.84 | 13.035
[27 empty] | 0 | 0 |  | 0 | 0
|  | ADDITIONAL ITEMS | [24 empty] | 0 | 0 |  | 0 | 0
6 | Liquor Store Room Door | Providing & fixing in position of FRD Glass Single Leaf Door made up of 45mm thick commercial flush door shutter of approved make & thickness, Inner side finished with laminate and outer side with veneer finish including providing & fixing 750mm X 200mm glass Vision panel and 12mm thk Wooden lipping all around, including of 750mm X 200mm SS push plate and 200mm high SS kick plate, including P/F of Door frame made out of CP Teak / Ash wood or equivalent with melamine polish finish. Size of the frame approximate 175mm wide X 50mm thick. Applicable hardware's such as s/s handles, conceal door closer and any other hardware etc required to complete the related works as per design & detail. door hardware make consider Dorma / Hafele/Ozon /equilient | NOS. | [5 empty] | 1 | 30000 | 30000 | 30000 |  |  | Rates are approved | ok |  |  | 1 | 30000 | 30000 | 0 | 30000 | 0 |  | 1 | 1 | 30000 |  | 30000 | 30000 | 0
2 | CONSOLE | P/F service counters in duco finished from outer surface & top finished in veneer. The storage under the Counter should be provided with 6" ht. drawers at top row finished with wooden ribs. top of the shutter having C section brass inlay & below openable shutters finished with duco. the drawer should have internal partiton with fabric finish for cutlary Shutters made out of 19mm thk. firerated plywood finished with 1mm thk. laminate internally. The shutters to be provided with fittings such as hinges; handles; ball catch, locks etc. complete in all respect. The rates for the Shutters to be included. as per design and details. any 1drawer (in each service station) should have 3compartment made in ply finished with fabric for cutlery and bottom storage should have 1shelf for crockery, shelf in ply finished with white laminate | NEAR BANQUETTE | 1540mm L X 500mmW X 900H | NOS. |  |  |  | 2 | 60000 | 120000 | 120000 |  |  | Addiitional service counter rates approved |  |  |  | 2 | 60000 | 120000 | 0 | 60000 | 0 |  | 2 | 2 | 60000 |  | 120000 | 120000 | 0
|  | Plywood - branded fire rated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand | [24 empty] | 0 | 0 |  | 0 |  | 0
|  | Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) | [24 empty] | 0 | 0 |  | 0 |  | 0
|  | Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.) | [24 empty] | 0 | 0 |  | 0 |  | 0
25 | Bench Seating | Wooden bench with cane back rest & 25mm wooden framework base with 75mm cousion seat (branded form) approved shade of fabric including 4 number pillow. | WAITING AREA | 2700 x 550mm | NOS |  |  | 0 | 1 | 20000 | 20000 | 20000 | [6 empty] | 0 | 20000 | 0 | -1 | 20000 | -20000 |  |  | 0 | 20000 |  | 0 |  | 0
26 | Bison board/ v- board Paneling | Providing, making and fixing of wall paneling made of 12mm thk branded bison board/ V board paneling on wall including MS framework from slab to slab height of 5000mm. framework to be finished with zink oxide and enamel finish with all necessary required framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | All walls | 75mm (thick) 5000mm (height) | SFT |  |  | 0 | 2000 | 479 | 958000 | 958000 |  | MS Pipe 50 x 50 x 02 at 600mm C/c finish with one layer 12mm Fire rated Ply + 12mm Fire rated Gypsum | Approved | ok | ok |  | 1706.8 | 479 | 817557.2 | -293.2 | 479 | -140442.8 |  | 1730.5 | 1706.8 | 479 |  | 817557.2 | 817557.2 | 0
[27 empty] | 0 | 0 |  | 0 | 0 | 0
27 | MS framework for curtain wall | P/F of 20 x 20mm MS framework with black powder coat upto ceiling height, having intermediate memebr @ every 900mm c/c including all necessary hardware etc. complete. |  |  | SFT |  |  |  | 1750 | 140 | 245000 | 245000 |  | We have chaged unit from Rft to Sqft | Units should be proposed in Kg | In Kg unit is not workable price | you give the rate analysis for binu to approvae | Rate Anylisis Attached | 868.67 | 140 | 121613.8 | -881.33 | 140.3284 | -123675.6482 |  | 1232.775 | 868.67 | 140 |  | 121613.8 | 121613.8 | 0
28 | SS PVD COATING framework for wallpaper | P/F of 20 x 20mm ss brass pvd coating framework upto ceiling height, having intermediate memebr @ every 900mm c/c including all necessary hardware etc. complete. |  |  | SFT |  |  |  | 3300 | 100 | 330000 | 330000 |  |  | Rates approved | ok |  |  |  | 100 | 0 | -3300 | 100 | -330000 |  |  | 0 | 100 |  | 0 | 0 | 0
29 | FAÇADE granite bulkhead | Providing, making and fixing of bulkhead 600mm box paneling made of 12mm thk branded bison board/ V board paneling on wall including MS framework from slab. framework to be finished with zink oxide and enamel finish. the boxing to be finisged with black leather finish granite with granite molding in levels as per detail drawing. having required holes to fix the signage letter. cost inlcudes all necessary required framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  |  | SFT |  |  |  | 55 | 1450 | 79750 | 79750 |  |  | Proposed rate 342, attachment missing | Rate Analyisis attached |  |  |  | 1450 | 0 | -55 | 1450 | -79750 |  |  | 0 | 1450 |  | 0 | 0 | 0
[27 empty] | 0 | 0 |  | 0 | 0 | 0
30 | Glass PARTITION on live kitchen | P/F 10 mm thk.fire rated glass partitions with 20 x 40mm MS framework with white/ black powder coating and all necessary required groove, wooden framing, with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | Live kitchen |  | SFT |  |  |  | 60 | 4500 | 270000 | 270000 |  | Saint Goabain FRD Glass with Partion full system price quoted | Check with ARA vishal cinema we had done 560/ Sq ft glass partition why this is required? |  | this is a mall requirement, we have to submit the fire safety certificate to mall team. |  | 108.08 | 4500 | 486360 | 48.08 | 4500 | 216360 |  | 108.5 | 108.08 | 4500 |  | 488250 | 486360 | 1890
31 | flutted Glass PARTITION on live kitchen | P/F 8 mm thk. flutted glass partitions with 20 x 40mm MS framework with white/ black powder coating and all necessary required groove, wooden framing, with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | Live kitchen |  | SFT |  |  |  | 45 | 4500 | 202500 | 202500 |  | Spectfication same as per ITEM No 30 | Check with ARA vishal cinema we had done 560/ Sq ft glass partition why this is required? |  | this is a mall requirement, we have to submit the fire safety certificate to mall team. |  | 0 | 4500 | 0 | -45 | 4500 | -202500 |  |  | 0 | 4500 |  | 0 | 0 | 0
32 | cane screen | P/F of self supported bamboo cane screen having 30mm dia wooden framework with reuqired hinges and wooden frame/ bidding to be finished with melamine polish with necessary fittings as per design and details. | near buffet |  | SFT |  |  |  | 30 | 1550 | 46500 | 46500 |  |  | Proposed rate Rs 1250 | Rates Revised Easty.com site price 36,000/- + 3,900/- Trasportation = Total 39,900 + 7,095/- 20.5% (Shifing Material Ground to 2nd 10% + Overhead 2.5% + Profit 08%) = Grand Total Price = 46,995/- |  |  | 32 | 1550 | 49600 | 2 | 1550 | 3100 |  | 32 | 32 | 1550 |  | 49600 | 49600 | 0
[27 empty] | 0 | 0
TOTAL CARPENTRY ADDITONAL WORK | [10 empty] | 2301750 | [9 empty] | 1625131 |  |  | -676908.4482 | Total Wall Paper Additional work |  | 0 | 0 |  | 1627021 | 1625131 | 1890
[27 empty] | 0 | 0 |  |  |  | 0
| MISCELLANEOUS | [25 empty] | 0 | 0 |  |  |  | 0
1 | Texture wallpaper | P & F of texture wallpaper as per approval |  |  | SFT | 650 | 225 | 146250 | 400 | 200 | 80000 | -66250 | [6 empty] | 213.95 | 200 | 42790 | -186.05 | 200 | -37210 |  | 219.375 | 213.9462 | 200 |  | 42790 | 42789.24 | 0.76
|  | Basic rate- 155/Sq Ft | [24 empty] | 0 | 0 |  |  | 0 | 0
[27 empty] | 0 | 0 |  |  | 0 | 0
2 | Ceiling Fans | P & F of ceiling fans paper as per approval |  |  | NOS | 6 | 5000 | 30000 | 6 | 32000 | 192000 | 162000 | [6 empty] | 6 | 32000 | 192000 | 0 | 32000 | 0 |  | 6 | 6 | 32000 |  | 192000 | 192000 | 0
[27 empty] | 0 | 0 |  |  | 0 | 0
3 | Bamboo blind curtain on S.S PVD black coating framework / roller blinds | P & F of bamboo blind manual folding curtains as per approval |  |  | SFT | 150 | 250 | 37500 | 200 | 250 | 50000 | 12500 |  |  |  | QTY Variation | lets finalise the mockup first, then close the cost. |  | 203.63 | 250 | 50907.5 | 3.63 | 250 | 907.5 |  | 206.25 | 203.625 | 250 |  | 50907.5 | 50906.25 | 1.25
4 | Chef Photos | P/F of Chef Photos on wall of the required size |  |  | Nos |  |  |  | 8 | 3750 | 30000 | [7 empty] | 8 | 3750 | 30000 | 0 | 250 | 0
TOTAL MISCELLANEOUS | [7 empty] | 213750 |  |  | 352000 | 108250 | [8 empty] | 315697.5 |  |  | -36302.5 | [5 empty] | 285697.5 | 285695.49 | 2.01
Extra Items
Sr no | Items | Description |  |  | Unit |  |  |  | QTY | Rate | [10 empty] | Amount
1 |  | 12mm Additional ply for veneer paneling |  |  | Sqft |  |  |  | 308.78 | 210 | [10 empty] | 64843.8
2 |  | Ceiling ply for light & MS Support |  |  | Sqft |  |  |  | 50.875 | 210 | [10 empty] | 10683.75 | [5 empty] | Total |  |  | 3975962.375 | 3975947.33 | 15.045
3 |  | Installation of slotted angle rack with MS case & shutter |  |  | Nos |  |  |  | 5 | 7000 | [10 empty] | 35000
4 |  | Wooden trap door for signage 1'x1' |  |  | Nos |  |  |  | 3 | 1500 | [10 empty] | 4500
5 |  | Replacement of flex with MS Works |  |  | Nos |  |  |  | 1 | 20400 | [10 empty] | 20400
7 |  | Hood installation with required hardware |  |  | Nos |  |  |  | 5 | 4500 | [10 empty] | 22500
8 |  | MS Case for gas meter with shutter |  |  | Sqft |  |  |  | 24.6 | 300 | [10 empty] | 7380
9 |  | MS Frame for kitchen ceiling light |  |  | Nos |  |  |  | 9 | 4500 | [10 empty] | 40500
10 |  | MS Base for cold room machine |  |  | Nos |  |  |  | 1 | 7500 | [10 empty] | 7500
11 |  | Supply of PVC Pallate |  |  | Nos |  |  |  | 1 | 3600 | [10 empty] | 3600
12 |  | Supply of Safe |  |  | Nos |  |  |  | 1 | 20000 | [10 empty] | 20000
13 |  | MS Stand for UPS in kitchen passage |  |  | Nos |  |  |  | 1 | 3600 | [10 empty] | 3600
14 |  | Loading, Unloading & shifting all equipment and materials |  |  | Job |  |  |  | 1 | 65000 | [10 empty] | 65000
15 |  | Rework for bar counter wall ( door location ) with changing in plumbing & Electrical line |  |  | Job |  |  |  | 1 | 13500 | [10 empty] | 13500
16 |  | Wooden box for FOH Ceiling light |  |  | Nos |  |  |  | 10 | 1500 | [10 empty] | 15000
17 |  | Fixing of SS Shelf in kitchen |  |  | Nos |  |  |  | 15 | 500 | [10 empty] | 7500
18 |  | Supply & Installation of TV with additional breaket |  |  | Nos |  |  |  | 1 | 50750 | [10 empty] | 50750
19 |  | Installation of plants in FOH area |  |  | Labour |  |  |  | 8 | 750 | [10 empty] | 6000
20 |  | Gas burner works |  |  | Job |  |  |  | 1 | 6000 | [10 empty] | 6000
21 |  | Installation of CCTV Screen with breaket |  |  | Nos |  |  |  | 1 | 2500 | [10 empty] | 2500
22 |  | Wooden shelf for amplifier with veneer finish |  |  | Nos |  |  |  | 2 | 5800 | [10 empty] | 11600
23 |  | Fixing of bells with required fittings |  |  | Nos |  |  |  | 230 | 85 | [10 empty] | 19550
24 |  | MS Stand for glass washer & Ice cube machine |  |  | Nos |  |  |  | 2 | 3600 | [10 empty] | 7200
26 |  | Supply of staff locker |  |  | Nos |  |  |  | 1 | 30000 | [10 empty] | 30000
27 |  | Supply of Aluminium ladder |  |  | Nos |  |  |  | 1 | 6500 | [10 empty] | 6500
28 |  | Supply of chair |  |  | Nos |  |  |  | 1 | 5500 | [10 empty] | 5500
29 |  | Wooden display box with veneer finish for buffet |  |  | Nos |  |  |  | 4 | 4500 | [10 empty] | 18000
30 |  | Laying of fabric in console & Service station |  |  | Nos |  |  |  | 13 | 0 | [10 empty] | 0
31 |  | Installtion of soap dispensor in kitchen |  |  | Nos |  |  |  | 10 | 250 | [10 empty] | 2500
32 |  | Supply of portable LED in DB Area |  |  | Nos |  |  |  | 1 | 1500 | [10 empty] | 1500
33 |  | Additional marble on front wall in live kitchen ( 300mm wide ) |  |  | Rft |  |  |  | 12.5 | 900 | [10 empty] | 11250
34 |  | Modification of existing SS Table |  |  | Nos |  |  |  | 2 | 8500 | [10 empty] | 17000
35 |  | Fixing of double marble patti in pot wash area |  |  | Job |  |  |  | 1 | 4500 | [10 empty] | 4500
36 |  | Supply of wooden table for store keeper |  |  | Nos |  |  |  | 1 | 0 | [10 empty] | 0
37 |  | Wooden shelf for printer in kitchen area |  |  | Nos |  |  |  | 1 | 7500 | [10 empty] | 7500
38 |  | Supply & Installation of gypsum trap door ( one is 400mm & one is 600mm ) |  |  | Nos |  |  |  | 2 | 1750 | [10 empty] | 3500
40 |  | Supply & fixing of main door handle |  |  | Nos |  |  |  | 2 | 6647 | [10 empty] | 13294
41 |  | Supply & Installation of brass skirting |  |  | Rft |  |  |  | 24.75 | 975 | [10 empty] | 24131.25
42 |  | Grenite step for kitchen entry |  |  | Job | [15 empty] | 0
43 |  | Ramp in kitchen passage ( 5'x3' ) |  |  | Job |  |  |  | 1 | 15000 | [10 empty] | 15000
605282.8

## CIVIL & INTERIOR NT
Copper Chimney l Wakad Pune l Additional Works
Sr no | Description | Unit | Claimed quantity | Rate | Claimed Amount | Actual Quantity | Certified Rate | Actual Amount | Difference | Remark
1 | Supply & fixing of fire rated gypsum on wall paneling | Sqft | 1261 | 136 | 171496 | 1276.84 | 126 | 160881.84 | 10614.16
2 | Supply and laying of wallpaper in buffet counter ( Basic rate of wallpaper @ 250 rs per sqft ) | Sqft | 200.625 | 350 | 70218.75 | 207.349 | 350 | 72572.15 | -2353.4
3 | Oil base preparation for wallpaper | Sqft | 421.25 | 35 | 14743.75 | 421.2952 | 20 | 8425.904 | 6317.846
4 | Oil base paint on kitchen walls & Ceiling | Sqft | 1800.625 | 40 | 72025 | 1989.125 | 0 | 0 | 72025 | Need Justification from ARA design
5 | MS Plateform above door level for UPS (5'x3') | Job | 1 | 5000 | 5000 | 1 | 4000 | 4000 | 1000
6 | Glass film on live kitchen partition | Sqft | 54.375 | 150 | 8156.25 | 61.625 | 0 | 0 | 8156.25
7 | Bison board for DB & Water tank | Sqft | 63 | 160 | 10080 | 63 | 75 | 4725 | 5355
8 | Red paint on PT Slab | Job | 1 | 10000 | 10000 | 1 | 5000 | 5000 | 5000
9 | Sliding channel & Fire rated hinges for door with consultant charges ( Form A ) | Job | 1 | 73868 | 73868 | 1 | 36000 | 36000 | 37868 | Sliding door was already part of BOQ hardwares cannot be billed separate
10 | Transportation for equipment from wakad to BKC & Wakad to viman nagar | Job | 1 | 18000 | 18000 | 1 | 9000 | 9000 | 9000 | Not to be part of interior NT item site to take approval from RS sir.
11 | Transportation for Aqua guard (From Mall to Godown & Godown to mall with loading unloading) | Job | 1 | 10000 | 10000 | 1 | 4000 | 4000 | 6000 | Not to be part of interior NT item site to take approval from RS sir.
12 | SS Corner guard in kitchen area as per architect approval | Rft | 134 | 550 | 73700 | 134 | 290 | 38860 | 34840
13 | Bond it chemical for expose ceiling | Sqft | 1166.875 | 20 | 23337.5 | 1166.875 | 20 | 23337.5 | 0
14 | Main door | Nos | 1 | 88350 | 88350 | 1 | 13950 | 13950 | 74400 | Need Justification from ARA design
15 | Rework in live kitchen partition | Job | 1 | 10000 | 10000 | 1 | 2000 | 2000 | 8000 | Site team to justify the cose
16 | Compressure repair | Job | 1 | 22000 | 22000 | 1 | 21390 | 21390 | 610 | Not to be part of interior NT item site to take approval from RS sir.
17 | SS Equipments |  |  |  | 0 |  |  | 0 |  | Not to part of interior NT items
a | SS Table in bar area | Nos | 1 | 30000 | 30000 | 1 | 30000 | 30000 | 0 | Not to part of interior NT items
b | Live kitchen overhead shelf | Nos | 1 | 38500 | 38500 | 1 | 38500 | 38500 | 0 | Not to part of interior NT items
c | GN Pan rack wall mounted | Nos | 1 | 22000 | 22000 | 1 | 22000 | 22000 | 0 | Not to part of interior NT items
d | Wall mounted rack for oven | Nos | 1 | 6000 | 6000 | 1 | 6000 | 6000 | 0 | Not to part of interior NT items
e | Oil trey 4"x4" | Nos | 5 | 1500 | 7500 | 5 | 7500 | 37500 | -30000 | Not to part of interior NT items
f | Louver for hood | Nos | 1 | 5000 | 5000 | 1 | 5000 | 5000 | 0
g | Heater | Nos | 1 | 12500 | 12500 | 1 | 12500 | 12500 | 0 | Not to part of interior NT items
18 | Attic stock |  |  |  | 0 |  |  | 0
a | Flooring tile ( wooden ) | Box | 11 | 2010 | 22110 |  |  | 0 | 22110
b | Flooring tile ( pattern ) | Box | 2 | 2640 | 5280 |  |  | 0 | 5280
c | Metal ceiling tile | Nos | 8 | 800 | 6400 |  |  | 0 | 6400
d | Nahani trap jali | Nos | 2 | 750 | 1500 |  |  | 0 | 1500
e | Cane mesh jali | Roll | 4 | 3200 | 12800 |  |  | 0 | 12800
f | White tile for kitchen | Box | 2 | 540 | 1080 |  |  | 0 | 1080
19 | Electronic weighing scale | Nos | 1 | 17500 | 17500 | 1 | 17500 | 17500 | 0 | Not to part of interior NT items
20 | Blue star cold room | Nos | 1 | 66000 | 66000 | 1 | 66000 | 66000 | 0 | Not to part of interior NT items
21 | Rework on bar store door ( Additional veneer ) | Job | 1 | 8500 | 8500 | 1 |  | 0
22 | Flap & Wicket door in bar area | Job | 1 | 22500 | 22500 | 1 | 12500 | 12500 | 10000
23 | Additional boxing of automation panel | Job | 1 | 5000 | 5000 | 1 | 3200 | 3200 | 1800
24 | Temporary vinyl in bar area niche ( work hold ) | Roll | 3 | 1000 | 3000 | 3 |  | 0 | 3000
25 | Scotch guard work on sofa seating ( as per instruction ) | Job | 1 | 40000 | 40000 | 1 | 38000 | 38000 | 2000 | Need Justification from ARA design & clarification as to whose instruction
26 | Additional fabric behind sofa seating ( as per RM instruction ) | Job | 1 | 15000 | 15000 | 1 |  | 0 | 15000 | TO be approved from RS sir
27 | Supply of PU foam bottle as per requirement | Nos | 2 | 1500 | 3000 | 2 | 900 | 1800 | 1200 | Not to part of interior NT items
28 | Deep cleaning | Job | 1 | 60000 | 60000 | 1 |  | 0 | 60000 | TO be approved from RS sir
| Total |  |  |  | 1092145.25 |  |  | 694642.394 | 389002.856

## ELECTRICAL
BILL OF QUANTITY FOR ELECTRICAL WORK FOR CC - PUNE WAKAD
|  | TENDER BOQ. R0 |  | Final offer
|  | BOQ |  |  |  |  | Claimed |  |  | Audited |  |  | Difference from BOQ |  |  | Difference from Claimed Bill
SR. | DESCRIPTION OF ITEM | UNIT | QTY | Supply Rate | Installtion Rate | Amount | Claimed Quantity | Rate | Claimed Amount | Actual Quantity | Rate | Actual Amount | Actual Quantity | Rate | Actual Amount | Difference in Quantity | Rate | Difference in Amount | Remark
1 | PANELS / DBs
Supply and Installation of main LT panel,genarally conforming to IS 8623/IS-13947/IEC-439 front operated, dead back floor mounted , totally enclosed, compartmentalised, vermin proof,indoor, non-drawout type,power panel, fabricated out of 2mm thick CRCA sheets, fully powder coated after seven tank treatment, having gasketed & hinged cover on each cubicle with insulated door knob, incorporating horizontal and vertical copper busbars complete with all internal wiring, danger sign board, earth-bus and lugs, cable chamber, busbar chamber,aluminium anodized name plates etc.as required, including 2 nos. of 6" dia instrument cooling fan with switch and ventilation louvres with wire mesh,housing below mentioned switchgears / meters. 9W fitting with CFL lamp, switch shall be provided in each vertical section,:(Panel should conform to Form- 3b of IEC- 439) (GA drawing of the panel to be got approved from the Consultant before taking up fabrication and all panels to be factory inspected before despatch)
Notes: 1. All MCCBs shall have rotary handle
2. All MCCBs shall have phase spreader assembly on
both Line & Load ends.
3. All MCCB shall have Minimum Ics=16KA)
4. Incomer shall have auxilliary ON/OFF & TRIP status contacts and the same shall be wired up
electronic trip setting to Metering Compartment)
5. The panel shall conform to Form-3b as per IEC-439
6. All MCCB to be of Schneider/ABB make
7. All MCCB to be current limiting type, LSIG
8. Incomer MCCB to be shunt trip facility
Refer: SLD
1.1.1 | MAIN PANEL | Set | 1 | 175000 | 15000 | 190000 | 1 | 190000 | 190000 | 1 | 190000 | 190000 | 0 | 190000 | 0 | 0 | 190000 | 0
1.1.2 | KITCHEN DB | Set | 1 | 22500 | 4000 | 26500 | 1 | 26500 | 26500 | 1 | 26500 | 26500 | 0 | 26500 | 0 | 0 | 26500 | 0
1.1.3 | BAR DB (4WAY TPN - 7 SEGMENT) | Set | 1 | 22000 | 3000 | 25000 | 1 | 25000 | 25000 | 1 | 25000 | 25000 | 0 | 25000 | 0 | 0 | 25000 | 0
1.1.4 | KPDB (8WAY TPN - 7 SEGMENT) | Set | 1 | 24500 | 3000 | 27500 | 1 | 27500 | 27500 | 1 | 27500 | 27500 | 0 | 27500 | 0 | 0 | 27500 | 0
1.1.5 | LDB (8WAY TPN - 7 SEGMENT) | Set | 1 | 24500 | 3000 | 27500 | 1 | 27500 | 27500 | 1 | 27500 | 27500 | 0 | 27500 | 0 | 0 | 27500 | 0
1.1.6 | PDB (8WAY TPN - 7 SEGMENT) | Set | 1 | 24500 | 3000 | 27500 | 1 | 27500 | 27500 | 1 | 27500 | 27500 | 0 | 27500 | 0 | 0 | 27500 | 0
0
1.2 | Suply and installation of Four -Tier, Multi-Way, TPN, | [5 empty] | 0
| Distribution Board for Lighting & Power distribution, surface | [5 empty] | 0
| mounted on wall, sheet metal fabricated,powder coated, | [5 empty] | 0
| having dust-proof and vermin 'proof, gasketed and hinged | [5 empty] | 0
| acrylic door with all internals such as DIN rails, neutral-link, | [5 empty] | 0
| interconnected wiring complete with earthing lugs housing | [5 empty] | 0
| switchgears: (IP-43 with Metal Door) Refer: SLD & DB Schedule | [5 empty] | 0
| (Make: Legrand-Ekinoxe /Schneider) | [5 empty] | 0
1.2.1 | UPS SPN DB (16WAY SPN) | Set | 1 | 8500 | 1500 | 10000 | 1 | 10000 | 10000 | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 10000 | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1.3 | S & I of 32A,DP,MCB +20A NO/NC CONTACTOR, in powder coated sheet metal box for terminating UPS TO UPSDB etc. | Nos | 1 | 1350 | 250 | 1600 | 1 | 1600 | 1600 | 1 | 1600 | 1600 | 0 | 1600 | 0 | 0 | 1600 | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
1.4 | S & I of 32A, TP, MCB + 32A,415 V, Metal clad,Power socket in powder coated metal box for supplying power to Kitchen equipment etc. | Nos | 3 | 4550 | 750 | 15900 | 2 | 5300 | 10600 | 2 | 5300 | 10600 | -1 | 5300 | -5300 | 0 | 5300 | 0
0
1.5 | S & I of 32A,FP,MCB type Isolator, in powder coated sheet metal box for terminating power to equipment etc. | Nos | RO |  |  |  | 0
0
1.6 | S & I of 63A,,FP,MCB type Isolator, in powder coated sheet metal box for terminating power to equipment etc. | Nos | RO |  |  |  | 0
0
1.7 | S & I of 32A 3Pin Socket & 32A DP MCB with MS enclosure IP44 | Set | RO |  |  |  | 0
0
1.8 | S & I of 32A 4P ELMCB 300mA, Metal clad,Power socket in powder coated metal box for supplying power to AC & Kitchen equipment etc. | Nos | 2 | 4800 | 350 | 10300 | 1 | 5150 | 5150 | 1 | 5150 | 5150 | -1 | 5150 | -5150 | 0 | 5150 | 0
0
1.9 | S & I of 32/63A ELMCB 100mA, Metal clad,Power socket in powder coated metal box for supplying power to equipment etc. | Nos | RO |  |  |  | 0
0
| Sub Total of 1.0 |  |  |  |  | 361800 | 0 |  | 351350 |  |  | 351350 |  |  | -10450 | 0 |  | 0
0
2 | CABLES : | [5 empty] | 0
| Supply and laying, effecting proper connections, testing & commissioning of the following sizes of 1.1 KV XLPE armoured/ unarmoured PVC insulated PVC sheathed aluminium /copper conductor cables conforming to IS : 1554 and IS 694 for Flexible copper cable Part I - 1976 with latest amendments laid over MS supports in existing RCC ducts/ laid in ground /laid on Cable Trays including clamping the cables to supports in an approved manner as required complete with all accessories.All cables shall have thermo setting insulation XLPE and low emission of smoke and corrosive gas when affected by fire. Necessary Markers shall be provided at the intervals as per the specifications. | [5 empty] | 0
2.1.1 | 3.5C x 400 Sq.mm. AL XLPE Cable | R.M | RO |  |  |  | 0
2.1.2 | 3.5C x 300 Sq.mm. AL XLPE Cable | R.M | RO |  |  |  | 0
2.1.3 | 3.5C x 240 Sq.mm. AL XLPE Cable | R.M | RO |  |  |  | 0
2.1.4 | 3.5C x 185 Sq.mm. AL XLPE Cable | R.M | RO |  |  |  | 0
2.1.5 | 3.5C x 150 Sq.mm. AL XLPE Cable | R.M | RO |  |  |  | 0
2.1.6 | 3.5C x 120 Sq.mm. AL XLPE Cable | R.M | RO |  |  |  | 0
2.1.7 | 3.5C x 95 Sq.mm. AL XLPE Cable | R.M | RO |  |  |  | 0
2.1.8 | 3.5C x 70 Sq.mm. AL XLPE Cable- MAIN PANEL | R.M | 80 | 450 | 100 | 44000 | 0 | [5 empty] | -80 | 550 | -44000
2.1.9 | 3.5C x 50 Sq.mm. AL XLPE Cable | R.M | RO |  |  |  | 0
2.1.10 | 3.5C x 35 Sq.mm. AL XLPE Cable | R.M | RO |  |  |  | 0
2.1.11 | 3.5C x 25 Sq.mm. AL XLPE Cable | R.M | RO |  |  |  | 0
2.1.12 | 4C x 16 Sq.mm. AL XLPE Cable - PDB, KPDB, KDB, BAR DB & DISHWASHER | R.M | 130 | 180 | 60 | 31200 | 172 | 240 | 41280 | 144 | 240 | 34560 | 14 | 240 | 3360 | -28 | 240 | -6720
2.1.13 | 4C x 10 Sq.mm. CU XLPE Cable | R.M | RO |  |  |  | 0
2.1.14 | 4C x 6 Sq.mm. CU XLPE Cable | R.M | RO |  |  |  | 0
2.1.15 | 4C x 4 Sq.mm. CU XLPE Cable - AHU, LDB & PULVERISER | R.M | 57 | 200 | 70 | 15390 | 201 | 270 | 54270 | 122 | 270 | 32940 | 65 | 270 | 17550 | -79 | 270 | -21330
2.1.16 | 4C x 2.5 Sq.mm. CU XLPE Cable | R.M | RO |  |  |  | 0 | [8 empty] | 0 |  | 0
2.1.17 | 3C x 16 Sq.mm. CU XLPE Cable | R.M | RO |  |  |  | 0 | [8 empty] | 0 |  | 0
2.1.18 | 3C X 6sq.mm CU XLPE Cable | R.M | RO |  |  |  | 0 | [8 empty] | 0 |  | 0
2.1.19 | 3C X 4sq.mm CU XLPE Cable - UPS & UPS DB, REFRIG., FRESH AIR & EXHAUST | R.M | 84 | 160 | 65 | 18900 | 106 | 225 | 23850 | 104 | 225 | 23400 | 20 | 225 | 4500 | -2 | 225 | -450
2.1.20 | 3C x 2.5 Sq.mm. CU PVC Cable - UPS O/G | R.M | 70 | 110 | 50 | 11200 | 95 | 160 | 15200 | 73 | 160 | 11680 | 3 | 160 | 480 | -22 | 160 | -3520
2.1.21 | 3C X 4sq.mm CU PVC Cable | R.M | RO
2.1.22 | 3C X 1.5sq.mm CU PVC Cable-SIGNAGE | R.M | 20 | 75 | 60 | 2700 | [6 empty] | -20 | 135 | -2700
2.1.23 | 1C x 70 Sq.mm, Copper, Flexible, Bunched together | Mtr. | RO | 480 | 102 |  | 70 | 582 | 40740 | 50 | 582 | 29100 | 50 | 582 | 29100 | -20 | 582 | -11640
2.1.24 | 1C x 4 Sq.mm, Copper, Flexible, Bunched together -UPS | Mtr. | 25 | 50 | 10 | 1500 | [6 empty] | -25 | 60 | -1500
2.1.25 | 2C X 2.5sq.mm CU Cable - Kill switch UPS | R.M | 10 | 80 | 20 | 1000 | [6 empty] | -10 | 100 | -1000
2.2 | CABLE TERMINATION
Making cable and terminations including brass single compression glands and crimping type copper lugs for cable sizes mentioned below for aluminium or copper.
2.2.1 | 3.5C x 400 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.2 | 3.5C x 300 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.3 | 3.5C x 240 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.4 | 3.5C x 185 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.5 | 3.5C x 150 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.6 | 3.5C x 120 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.7 | 3.5C x 95 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.8 | 3.5C x 70 Sq.mm. AL XLPE Cable- MAIN PANEL | Nos. | 2 | 550 | 100 | 1300 | [6 empty] | -2 | 650 | -1300
2.2.9 | 3.5C x 50 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.10 | 3.5C x 35 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.11 | 3.5C x 25 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.12 | 4C x 16 Sq.mm. AL XLPE Cable - PDB, KPDB, KDB, BAR DB & DISHWASHER | Nos. | 10 | 450 | 100 | 5500 | 8 | 550 | 4400 | 8 | 550 | 4400 | -2 | 550 | -1100 | 0 | 550 | 0
2.2.13 | 4C x 10 Sq.mm. CU XLPE Cable | Nos. | RO
2.2.14 | 4C x 6 Sq.mm. CU XLPE Cable | Nos. | RO
2.2.15 | 4C x 4 Sq.mm. CU XLPE Cable - AHU, LDB & PULVERISER | Nos. | 6 | 250 | 70 | 1920 | 18 | 320 | 5760 | 16 | 320 | 5120 | 10 | 320 | 3200 | -2 | 320 | -640
2.2.16 | 4C x 2.5 Sq.mm. CU XLPE Cable | Nos. | RO
2.2.17 | 3C x 16 Sq.mm. CU XLPE Cable | Nos. | RO
2.2.18 | 3C X 6sq.mm CU XLPE Cable | Nos. | RO
2.2.19 | 3C X 4sq.mm CU XLPE Cable - UPS & UPS DB, REFRIG., FRESH AIR & EXHAUST | Nos. | 14 | 250 | 50 | 4200 | 6 | 300 | 1800 | 6 | 300 | 1800 | -8 | 300 | -2400 | 0 | 300 | 0
2.2.20 | 3C x 2.5 Sq.mm. CU PVC Cable - UPS O/G | Nos. | 4 | 200 | 50 | 1000 | 22 | 250 | 5500 | 12 | 250 | 3000 | 8 | 250 | 2000 | -10 | 250 | -2500
2.2.21 | 3C X 4sq.mm CU PVC Cable | Nos. | RO
2.2.22 | 3C X 1.5sq.mm CU PVC Cable-SIGNAGE | Nos. | 8 | 225 | 50 | 2200 | [6 empty] | -8 | 275 | -2200
2.2.23 | 1C x 70 Sq.mm, Copper, Flexible, Bunched together | Nos. | RO | 220 | 150 |  | 4 | 370 | 1480 | 4 | 370 | 1480 | 4 | 370 | 1480 | 0 | 370 | 0
2.2.24 | 1C x 4 Sq.mm, Copper, Flexible, Bunched together -UPS | Nos. | 12 | 55 | 20 | 900 | [6 empty] | -12 | 75 | -900
2.2.24 | 2C X 2.5sq.mm CU Cable - Kill switch UPS | Nos. | 2 | 72 | 40 | 224 | [6 empty] | -2 | 112 | -224
| Sub Total of 2 |  |  |  |  | 143134 |  |  | 194280 |  |  | 147480 |  |  | 4346 | 0 |  | -46800
3 | POINT WIRING :
3.1 | LIGHT POINT
Sub mains / Pre-Primary wiring i.e. from DB to room switch board shall be carried out for Pre-primary point using 1.5 sqmm copper stranded. All lighting fixture, wiring shall be carried out for primary point using 1.5 sqmm copper stranded & for secondary wiring 1.5sqmm copper stranded conductor 660/1100V grade PVC FRLS insulated wire in "MS Conduits" (including flexible conduits for drops to light fittings)". Individual junction / inspection boxes shall be provided for each lighting fitting for the purpose of looping from fitting to fitting.
also including insulated green color copper earth wire for each circuit and providing modular grid plate type switches,sockets etc. as required. Each light point to be terminated using 5A connector or 5A two pin female socket (for cove lighting) as directed at site. Each circuit feeding not more than 12-8 points/800 watts as per following configuration:(LDBs located at two locations as shown) (The Switch Socket cost shall be paid separately.)
From distribution board to switch board will be termed as Pre-primary point, average wiring length for Pre-primary point to be considered as 15 metres. From switch board to first light fitting and switch board to switch board will be termed as primary point, average wiring length for primary point to be considered as 3 metres and First fitting to subsequent fitting on the same circuit shall be termed as secondary point, average wiring length for secondary point to be considered as 5 metres. Light point wiring shall be included submains wiring from D.B. to room switch board.
Note: Length may vary as per actual site condition. Vendor shall be crossverify before bidding.
3.1.1 | Pre-Primary point (sub mains point) | Nos | 20 | 1400 | 350 | 35000 | 18 | 1750 | 31500 | 6 | 1750 | 10500 | -14 | 1750 | -24500 | -12 | 1750 | -21000
3.1.2 | Primary point | Nos | 15 | 1300 | 300 | 24000 | 32 | 1600 | 51200 | 25 | 1600 | 40000 | 10 | 1600 | 16000 | -7 | 1600 | -11200
3.1.3 | Secondary Point | Nos | 145 | 850 | 150 | 145000 | 135 | 1000 | 135000 | 109 | 1000 | 109000 | -36 | 1000 | -36000 | -26 | 1000 | -26000
3.2 | LIGHT POINT For Automation
All lighting fixture, wiring shall be carried out for primary point using 1.5 sqmm copper stranded & for secondary wiring 1.5sqmm copper stranded conductor 660/1100V grade PVC FRLS insulated wire in "MS Conduits" & 1 pair 1.5sqmm jacketed cable in Separate Conduit (including flexible conduits for drops to light fittings)". Individual junction / inspection boxes shall be provided for each lighting fitting for the purpose of looping from fitting to fitting.
From DB to first light fitting/driver will be termed as primary point, average wiring length for primary point to be considered as 25 metres and First fitting to subsequent fitting on the same circuit shall be termed as secondary point, average wiring length for secondary point to be considered as 5 metres. Light point wiring shall be included submains wiring from D.B. to room lights/Driver.
Note: Length may vary as per actual site condition. Vendor shall be crossverify before bidding.
3.2.1 | Primary point | Nos | RO
3.2.2 | Secondary Point | Nos | RO
3.3 | Power Point (Utility)
Primary wiring i.e. from DB to first power point shall be carried out for primary point using 3R x 2.5 sqmm copper stranded. Secondary wiring 2.5sqmm copper stranded conductor 660/1100V grade PVC FRLS insulated wire in "MS Conduit". Individual junction/inspection boxes shall be provided for each power point to loop from power point to a power point. Only 4 points looped in one circuit) From DB to First Socket.
From distribution board to first power point will be termed as primary point, average wiring length for primary point to be considered as 18 metres. First power point to subsequent power point on the same circuit shall be termed as secondary point, average wiring length for secondary point to be considered as 8 metres. Power point wiring shall be included wiring from D.B. to room indivisual power point.
Note: Length may vary as per actual site condition. Vendor shall be crossverify before bidding.
3.3.1 | Primary point | Nos | 22 | 2200 | 800 | 66000 | 19 | 3000 | 57000 | 19 | 3000 | 57000 | -3 | 3000 | -9000 | 0 | 3000 | 0
3.3.1 | Primary point ( Distance between Switch & socket Will be Average Length 2.5 Mtr. ) | Nos | RO
3.3.2 | Secondary Point | Nos | 16 | 1200 | 300 | 24000 | 22 | 1500 | 33000 | 22 | 1500 | 33000 | 6 | 1500 | 9000 | 0 | 1500 | 0
3.4 | Power Point (Kitchen & BAR)
Primary wiring i.e. from DB to first power point shall be carried out for primary point using 3R x 4 sqmm copper stranded. Secondary wiring 4sqmm copper stranded conductor 660/1100V grade PVC FRLS insulated wire in "MS Conduit". Individual junction/inspection boxes shall be provided for each power point to loop from power point to a power point. Only 4 points looped in one circuit) From DB to First Socket.
From distribution board to first power point will be termed as primary point, average wiring length for primary point to be considered as 12 metres. First power point to subsequent power point on the same circuit shall be termed as secondary point, average wiring length for secondary point to be considered as 2 metres. Power point wiring shall be included wiring from D.B. to room indivisual power point.
Note: Length may vary as per actual site condition. Vendor shall be crossverify before bidding.
3.4.1 | Primary point | Nos | 30 | 2000 | 600 | 78000 | 23 | 2600 | 59800 | 36 | 2600 | 93600 | 6 | 2600 | 15600 | 13 | 2600 | 33800
3.4.2 | Primary point ( Distance between Switch & socket Will be Average Length 2.5 Mtr. ) | Nos | RO
3.4.3 | Secondary Point | Nos | RO | 850 | 550 |  | 20 | 1400 | 28000 | 4 | 1400 | 5600 | 4 | 1400 | 5600 | -16 | 1400 | -22400
3.5 | S & I of MS conduits including all accessories, clamps, spacers, bends, tee, cross etc. as required at site for miscellaneous use in following sizes:
3.5.1 | 20mm dia | Mtr | RO
3.5.2 | 25mm dia | Mtr | 100 | 140 | 50 | 19000 | [6 empty] | -100 | 190 | -19000
3.6 | S & I of flexible GI conduits including all accessories, clamps, spacers, end adopters (Glands) etc. as required at site in following sizes:
3.6.1 | 20mm dia | Mtr | RO | 96 | 48 |  | 24 | 144 | 3456 | 24 | 144 | 3456 | 24 | 144 | 3456 | 0 | 144 | 0
3.6.2 | 25mm dia (COMMON) | Mtr | 75 | 140 | 40 | 13500 | [6 empty] | -75 | 180 | -13500
3.7 | Supply, Installation testing and commission of 240V-AC, wiring devices and its accessories such as modular type switch socket outlets with modular front plate, modular box, G.I. back box and all required accessories etc. Supply & Installation scope includes all civil works related to this job such as chiselling , making good with concrete and plaster, supply of fixing screw / wall plugs and other necessary hardware, marking identification numbers of circuits & interconnections of the switch /sockets as per standard drawing, complete as per site requirement. Switches and sockets may be individual or combined with bigger lighting switchboards, contractor to refer drawings to understand exact scope of work. LEGRAND
3.7.1 | 6A One way plate type switch | Nos. | 14 | 75 | 15 | 1260 | 19 | 90 | 1710 | 19 | 90 | 1710 | 5 | 90 | 450 | 0 | 90 | 0
3.7.2 | 6A Two way plate type switch | Nos. | RO
3.7.3 | 6/16A SOCKET & SWITCH | Nos. | 28 | 450 | 100 | 15400 | 43 | 550 | 23650 | 27 | 550 | 14850 | -1 | 550 | -550 | -16 | 550 | -8800
3.7.4 | 2Nos. 6/16A SOCKET & SWITCH | Sets | 6 | 650 | 100 | 4500 | 22 | 750 | 16500 | 8 | 750 | 6000 | 2 | 750 | 1500 | -14 | 750 | -10500
3.7.5 | 6/16A SOCKET & SWITCH - Kitchen | Sets | 42 | 450 | 100 | 23100 | 60 | 550 | 33000 | 66 | 550 | 36300 | 24 | 550 | 13200 | 6 | 550 | 3300
3.7.6 | 20A switch & socket outlet - Kitchen | Sets | 8 | 650 | 120 | 6160 | 8 | 770 | 6160 | 8 | 770 | 6160 | 0 | 770 | 0 | 0 | 770 | 0
3.7.7 | 20A Socket -AC | Nos. | RO
3.7.8 | 20A Industrial Socket (Outdoor IP65)-AC | Nos. | RO
3.7.9 | data cum telephone back GI BACK box 2”x2” suitable for data socket | Nos. | 4 | 350 | 100 | 1800 | 5 | 450 | 2250 | 5 | 450 | 2250 | 1 | 450 | 450 | 0 | 450 | 0
3.7.10 | Bell Push Switch | Nos. | RO | 350 | 150 |  | 1 | 500 | 500 | 1 | 500 | 500 | 1 | 500 | 500 | 0 | 500 | 0
3.7.11 | Buzzer Indication Set for 5/6 Bell Push | Nos. | RO | 1750 | 750 |  | 1 | 2500 | 2500 | 1 | 2500 | 2500 | 1 | 2500 | 2500 | 0 | 2500 | 0
| Sub Total of 3.0 |  |  |  |  | 456720 |  |  | 485226 |  |  | 422426 |  |  | -34294 | 0 |  | -62800
4 | RACEWAYS, CABLE TRAYS & JUNCTION BOX
4.1 | S & I of PVC trunking same as above but of size 100mm x 40mm x1.6 mm for power cables.(Electrical Room) | Mtr | RO
(PROFAB/ASIAN/Approved equivalent)
4.2 | S & I of trunking same as above but of size 85mm x 38mm x1.6 mm thick for power/data cables. | Mtr | RO
4.2 | S & I of trunking same as above but of size 65mm x 38mm x1.6 mm thick for power/data cables. | Mtr | RO
(PROFAB/ASIAN/Approved equivalent)
4.3 | S & I of 1 Run x 25mm dia, MS Conduit in Floor. | Mtr | 100 | 140 | 40 | 18000 | 99 | 180 | 17820 | 99 | 180 | 17820 | -1 | 180 | -180 | 0 | 180 | 0
4.4 | S & I of floor junction boxes similar to above but size 350mm x 350mm x 60 mm | Nos | RO | 800 | 400 |  | 1 | 1200 | 1200 | 1 | 1200 | 1200 | 1 | 1200 | 1200 | 0 | 1200 | 0
4.5 | S & I of floor junction boxes similar to above but size 250mm x 250mm x 60 mm | Nos | RO
4.6 | S & I of floor junction boxes similar to above but size 150mm x 150mm x 60 mm | Nos | 12 | 420 | 120 | 6480 | 12 | 540 | 6480 | 12 | 540 | 6480 | 0 | 540 | 0 | 0 | 540 | 0
4.7 | S & I of GI Pregalvanizd Perforated type Cable Tay
of following sizes suspended from ceiling or fixed
vertically on wall/column as per route directed at site
including all necessary bends, tees, crosses and also
including all necessary supporting arrangement.
All supporting hardware including nuts, bolts etc.
shall be also of galvanised M.S. as approved
(PROFAB/INDIANA/ASIAN/approved equivalent)
4.7.1 | 100mm x 50mm x 1.6mm | Mtr | 50 | 300 | 120 | 21000 | 38 | 420 | 15960 | 27 | 420 | 11340 | -23 | 420 | -9660 | -11 | 420 | -4620
4.7.2 | 150mm x 50mm x 1.6mm | Mtr | 10 | 400 | 140 | 5400 | 4 | 540 | 2160 | 4 | 540 | 2160 | -6 | 540 | -3240 | 0 | 540 | 0
4.7.3 | 300mm x 50mm x 1.6mm | Mtr | 30 | 750 | 180 | 27900 | 49 | 930 | 45570 | 32 | 930 | 29760 | 2 | 930 | 1860 | -17 | 930 | -15810
4.7.4 | 450mm x 50mm x 2.0mm | Mtr | 45 | 1050 | 200 | 56250 | 49 | 1250 | 61250 | 48 | 1250 | 60000 | 3 | 1250 | 3750 | -1 | 1250 | -1250
| Sub Total of 4.0 |  |  |  |  | 135030 |  |  | 150440 |  |  | 128760 |  |  | -6270 | 0 |  | -21680
5 | LIGHT FIXTURES INSTALLATION
5.1 | Installation of lighting fixtures with lamps as per the details below including necessary hardware such as clamps, nuts, bolts, nails screws and suspension rods as required for fixing the fixtures in position as directed by architect / consultant at site.
[12 empty] | 0 |  |  | 0
5.1.1 | SPOT LIGHT (LT1a) | Nos | 12 | 0 | 300 | 3600 | 10 | 300 | 3000 | 10 | 300 | 3000 | -2 | 300 | -600 | 0 | 300 | 0
5.1.2 | SPOT LIGHT (LT1b) | Nos | 10 | 0 | 300 | 3000 | 9 | 300 | 2700 | 9 | 300 | 2700 | -1 | 300 | -300 | 0 | 300 | 0
5.1.3 | SPOT LIGHT (LT2) | Nos | 17 | 0 | 300 | 5100 | 16 | 300 | 4800 | 16 | 300 | 4800 | -1 | 300 | -300 | 0 | 300 | 0
5.1.4 | SUSPENDED LIGHT (LT3) | Nos | 17 | 0 | 200 | 3400 | 16 | 200 | 3200 | 16 | 200 | 3200 | -1 | 200 | -200 | 0 | 200 | 0
5.1.5 | HANGING LIGHT (LT4) | Nos | 6 | 0 | 200 | 1200 | 5 | 200 | 1000 | 5 | 200 | 1000 | -1 | 200 | -200 | 0 | 200 | 0
5.1.6 | HANGING LIGHT (LT5) | Nos | 4 | 0 | 200 | 800 | 3 | 200 | 600 | 3 | 200 | 600 | -1 | 200 | -200 | 0 | 200 | 0
5.1.7 | WALL MOUNTED (LT6) | Nos | 8 | 0 | 200 | 1600 | 7 | 200 | 1400 | 7 | 200 | 1400 | -1 | 200 | -200 | 0 | 200 | 0
5.1.8 | 2 X 2 CEILING MOUNT LIGHT (LT7a) | Nos | 3 | 0 | 350 | 1050 | 4 | 350 | 1400 | 2 | 350 | 700 | -1 | 350 | -350 | -2 | 350 | -700
5.1.9 | 2 X 2 CEILING MOUNT LIGHT (LT7b) | Nos | 14 | 0 | 350 | 4900 | 13 | 350 | 4550 | 13 | 350 | 4550 | -1 | 350 | -350 | 0 | 350 | 0
5.1.10 | BULB LIGHT (LT8) | Nos | 70 | 0 | 350 | 24500 | 81 | 350 | 28350 | 60 | 350 | 21000 | -10 | 350 | -3500 | -21 | 350 | -7350
5.1.11 | LED COVE LIGHT (LT9) | MTR | 10 | 0 | 100 | 1000 | 15 | 100 | 1500 | 15 | 100 | 1500 | 5 | 100 | 500 | 0 | 100 | 0
5.1.12 | TRACK LIGHT-900MM (TL1) | MTR | 6 | 0 | 200 | 1200 | 4 | 200 | 800 | 4 | 200 | 800 | -2 | 200 | -400 | 0 | 200 | 0
5.1.13 | PALM LEAF CEILING FAN (CF1) | Nos | 7 | 0 | 400 | 2800 | 6 | 400 | 2400 | 6 | 400 | 2400 | -1 | 400 | -400 | 0 | 400 | 0
| Sub Total of 5.0 |  |  |  |  | 54150 |  |  | 55700 |  |  | 47650 |  |  | -6500 | 0 |  | -8050
6 | EARTHING :
6.1 | S & I of earth pit comprising of specially designed SEE/Ashlok brand Earth Electrode system 3.00 meter long including necessary materials like side fill compound etc. as required with standard brick masonary chamber with hinged cover and watering arrangement model SEE-60/C with SFC-20/Equivalent ASHLOK MODEL T39 HD (50MM DIA. 3 MTR) | Nos | 2 | 5500 | 2000 | 15000 | [6 empty] | -2 | 7500 | -15000
6.2 | S & I of copper /GI earthing wires/strips in following sizes
6.3 | 8 SWG GI bare wire | Mtr | 100 | 40 | 10 | 5000 | 210 | 50 | 10500 | 165 | 50 | 8250 | 65 | 50 | 3250 | -45 | 50 | -2250
6.4 | 25mm x 3mm thick GI strip welded & painted green | Mtr | 150 | 110 | 20 | 19500 | [6 empty] | -150 | 130 | -19500
6.5 | 25mm x 3mm thick CU strip welded & painted green | Mtr | 10 | 950 | 200 | 11500 | [6 empty] | -10 | 1150 | -11500
6.6 | S & I of isolated/dedicated earthing / grounding system for computers etc.using insulated green-yellow copper earthing wire laid/fixed bare on wall/ceiling from separately made earth pit to the equipment in following sizes The rate shall include termination also.
6.6.1 | 6 Sqmm copper, yellow-green/green insulation | Mtr | 20 | 55 | 15 | 1400 | [6 empty] | -20 | 70 | -1400
6.7 | S & I of Main bus for isolated earth comprising of 300mm x 25 mm x 3mm thick Tinned copper bar fixed on insulated support and having 10 nos of holes and nut bolts studs for clamping the earth leads,all contained in MS/PVC box and having transparent acrylic cover as approved by the consultant | Nos | 1 | 2420 | 300 | 2720 | [6 empty] | -1 | 2720 | -2720
| Sub Total of 6.0 |  |  |  |  | 55120 |  |  | 10500 |  |  | 8250 |  |  | -46870 | 0 |  | -2250
7 | Miscellaneous Item
7.1 | Supply & Install. Of RG 6 TV Cable in 25mm MS Conduit | Mtr. | 30 | 150 | 50 | 6000 | [6 empty] | -30 | 200 | -6000
7.2 | Supply & Laying of RG11 use for Main Cable TV | Mtr. | 50 | 50 | 30 | 4000 | [6 empty] | -50 | 80 | -4000
7.3 | Install. Of TV Stand - Only Installation | Nos. | 1 | 0 | 200 | 200 | [6 empty] | -1 | 200 | -200
7.4 | 4 WAY SPLITTER | Nos. | 1 | 315 | 50 | 365 | [6 empty] | -1 | 365 | -365
| Sub Total of 7.0 |  |  |  |  | 10565
8 | DATA DISTRIBUTION
Supply, Installation, termination & testing of data system:
8.1 | Main SERVER / ROUTER | Nos. | 1 | 22500 | 1500 | 24000 | [6 empty] | -1 | 24000 | -24000
8.2 | ROUTER | Nos. | 1 | 15000 | 1200 | 16200 | [6 empty] | -1 | 16200 | -16200
8.3 | SMART GIGABIT SWITCH 24 PORTS | Nos. | 1 | 12500 | 1200 | 13700 | [6 empty] | -1 | 13700 | -13700
8.4 | Loaded PATCH PANEL for 24 Port | Nos. | 1 | 5500 | 1500 | 7000 | [6 empty] | -1 | 7000 | -7000
8.5 | LIU switch with Accessories. (Optional : if Fibre Optic Cable terminated) | Job | 1 | 9600 | 1550 | 11150 | [6 empty] | -1 | 11150 | -11150
8.6 | Supply & Installation of I/O DATA Outlet (RJ-45) | Nos. | 19 | 300 | 100 | 7600 | [6 empty] | -19 | 400 | -7600
8.7 | S & I of Installation of Wi-Fi ceiling mounted Access Point, managed by controller software | Nos. | 3 | 300 | 120 | 1260 | [6 empty] | -3 | 420 | -1260
8.8 | Supply, installation, termination & testing of all Terminations using Fluke Cable Analyser DTX 1800 for all CAT 6 Information Outlet including Information outlet | Lot | 1 | 30000 | 5000 | 35000 | [6 empty] | -1 | 35000 | -35000
8.9 | CABLES:
8.9.1 | S&I Optical Fiber Cable with 12 fibers, with core dia. 50/125 µm (OM3), suitable for 1GBps Ethernet distance at 850 nm of wavelength, | Mtr. | RO
8.9.2 | S&I Optical Fiber Cable with 6 fibers, with core dia. 50/125 µm (OM3), suitable for 1GBps Ethernet distance at 850 nm of wavelength, | Mtr. | RO
8.9.3 | Supply & providing of CAT 6 UTP cables in the laid raceways / Conduits including terminations | Mtr. | 154 | 50 | 10 | 9240 | 615 | 60 | 36900 | 504 | 60 | 30240 | 350 | 60 | 21000 | -111 | 60 | -6660
8.9.4 | Patch cord (2 mtr-user end) | Each | 19 | 120 | 20 | 2660 | [6 empty] | -19 | 140 | -2660
8.1 | Supply, Installation, Testing & Commissioning of Hardware Packets (20 Nos =1 Pkts) | Pkts | 1 | 500 | 100 | 600 | [6 empty] | -1 | 600 | -600
8.11 | Supply, Installation, Testing & Commissioning of Velcro Ties ( 22 Mtrs = 1 Roll) | Roll | 1 | 150 | 50 | 200 | [6 empty] | -1 | 200 | -200
8.12 | Supply, Installation, Testing & Commissioning of Cable Ties 200mm ( 100 Nos. Pkt) | Pkt. | 1 | 75 | 20 | 95 | [6 empty] | -1 | 95 | -95
8.13 | Project Management including Freight & Forwarding, Cable Bunching, Printed Numbering, tube type Ferruling both sides, Face plate, Patch panel & patch cords both sides, Documentation etc.. | Job | 1 | 35000 | 5000 | 40000 | [6 empty] | -1 | 40000 | -40000
8.14 | Supplying and fixing 15U Rack Aluminium Frame - 600x600mm with 4 x FAN, Dual Split perforated Door at Front and Back Side, 2 x Vertical Cable Basket, 2 x 12 socket 5/15A PDU with MCB, side Panels of 2 nos and Heavy Duty Castors with break, 19" Reduced Channel - Loop Type (DATA+CCTV+PA) | Nos. | 1 | 15000 | 3000 | 18000 | [6 empty] | -1 | 18000 | -18000
8.15 | Supply & installation of MS conduits with junction boxes, reducer etc. complete concealed/surface mounting as required.
8.15.1 | 25 dia conduit | Mtr. | 100 | 140 | 40 | 18000 | 269 | 180 | 48420 | 193 | 180 | 34740 | 93 | 180 | 16740 | -76 | 180 | -13680
| Sub Total of 8.0 |  |  |  |  | 204705 |  |  | 85320 |  |  | 64980 |  |  | -150290 | 0 |  | -20340
9 | SUPPLY & INSTALLATION OF SAFETY ITEMS
9.1 | Sand buckets with stand (set of 3 buckets) | Sets | RO
9.2 | Caution boards (11kV) of standard Size | Nos | RO
9.3 | Caution boards (415V) of std. Size | Nos | 1 | 1500 | 400 | 1900 | [6 empty] | -1 | 1900 | -1900
9.4 | Rubber mat at panel room 12mm thk. 1mtr. Wide | Mtrs | 2 | 2000 | 200 | 4400 | 2 | 2200 | 4400 | 2 | 2200 | 4400 | 0 | 2200 | 0 | 0 | 2200 | 0
9.5 | Shock treatment chart as per electricity board | Nos | 1 | 1500 | 100 | 1600 | [6 empty] | -1 | 1600 | -1600
9.6 | First aid box with standard items | Nos | RO
9.7 | 11 KV rating rubber hand gloves | Sets | 2 | 750 | 50 | 1600 | [6 empty] | -2 | 800 | -1600
9.8 | The contractor to submit all the AS BUILT DRAWINGS after the completion of the project for Electrical & ELV Services executed at site. | Part of Tender
| Sub Total of 9.0 |  |  |  |  | 9500 |  |  | 4400 |  |  | 4400 |  |  | -5100 | 0 |  | 0
10 | UPS/ INVERTER System:
10.1 | Supply /Install of 3 KVA on line Model UPS with inbuilt battery system (1 Phase In & 1 Phase out) Make: Emerson/APC/Consul Neowatt/Vivtar Electronics | set | 1 | 80000 | 5000 | 85000 | 1 | 85000 | 85000 | 1 | 85000 | 85000 | 0 | 85000 | 0 | 0 | 85000 | 0
| Sub Total of 10 |  |  |  |  | 85000 |  |  | 85000 |  |  | 85000 |  |  | 0 | 0 |  | 0
11 | CCTV
11.1 | Supply & Installation of 2 Megapixel IR-20Mtr. IP Indoor Dome + Night vision. Camera Make: CP-PLUS | Nos. | 12 | 3350 | 450 | [7 empty] | -12 | 3800 | -45600
11.2 | Supply & Installation of 2 Megapixel IR-20Mtr. IP Indoor Bullet Camera+ Night vision. Camera Make: CP-PLUS | Nos. | RO
11.3 | Supply & Installation of 2 Megapixel IR-30Mtr. IP Outdoor Bullet Camera + Night vision. Camera Make: CP-PLUS | Nos. | RO
11.4 | Supply & Installation of 16 Channel NVR with 4 Sata Hard Disk Slot (Make: Honeywell/CP PLUS) | Nos. | 1 | 13000 | 1500 | [7 empty] | -1 | 14500 | -14500
11.5 | Supply & Installation of 24 Channel NVR with 4 Sata Hard Disk Slot (Make: Honeywell/CP PLUS) | Nos. | RO
11.6 | Supply & Installation of 8 Channel NVR with 2 Sata Hard Disk Slot (Make: Honeywell/CP PLUS) | Nos. | RO
11.7 | Supply & Installation of 16Port PoE(NVR) Switch (Make: Systimax) | Nos. | 1 | 22500 | 2000 | [7 empty] | -1 | 24500 | -24500
11.8 | 4 TB HDD Hard Disk | Nos. | 4 | 6250 | 650 | [7 empty] | -4 | 6900 | -27600
11.9 | Monitor/PC system | Nos. | 2 | 30000 | 1500 | [7 empty] | -2 | 31500 | -63000
11.1 | Supply & Installation of CAT-6 Cable for Camera Signal | Mtr. | 270 | 50 | 10 | 16200 | 254 | 60 | 15240 | 235 | 60 | 14100 | -35 | 60 | -2100 | -19 | 60 | -1140
| Sub Total of 11 |  |  |  |  | 16200 |  |  | 15240 |  |  | 14100 |  |  | -2100 | 0 |  | -1140
12 | PA SYSTEM
12.1 | Supply & Laying of 2 core 2.5 Sq.mm PVC insulated twisted copper conductor Speaker wires in trunking as required. | RM | 42 | 125 | 60 | 7770 | 82 | 185 | 15170 | 74 | 185 | 13690 | 32 | 185 | 5920 | -8 | 185 | -1480
12.2 | Control Unit (with volume and on/off switch) ( Smooth stepless control, but the control shall be through dimmer switch, the make of which will be same as the make of light control switches ) | Nos. | 1 | 29000 | 5000 | 34000 | [6 empty] | -1 | 34000 | -34000
12.3 | Supply & Installation of 6W Ceiling Speaker with box- Bosch | Nos. | 6 | 3500 | 500 | 24000 | [6 empty] | -6 | 4000 | -24000
12.4 | Voice Alarm Controller with in built 120W Amplifier & Emergency Messaage Manager |  | 1 | 24150 | 1200 | 25350 | [6 empty] | -1 | 25350 | -25350
12.5 | Supply of Voice Command Centre consisting of Electronics for Audio Control and shall include Amplifiers, Audio Message Generator, Microphone, table top mic etc. | Set. | RO
12.6 | Supply & Installation of MS Conduit. | RM | 50 | 140 | 40 | 9000 | 46 | 180 | 8280 | 41 | 180 | 7380 | -9 | 180 | -1620 | -5 | 180 | -900
| Sub Total of 12 |  |  |  |  | 100120 |  |  | 23450 |  |  | 21070 |  |  | -79050 | 0 |  | -2380
13 | FIRE ALARM SYSTEM (MAKE: HONEYWELL/EST)
13.1 | Single Loop Analog Addressable Fire Alarm Control panel (Expandable upto 1 Loop) with battery back up for 4 hours normal operation and 15 minutes alarm operation. The control panel per Loop Capacity 250 Detectrs and Devices, battery charger etc., 8.5" Touch Screen LCD Display, TCP/IP Connectivity, 10000 Event Log, Keyless Log on Using RFID Cards. The panel shall be UL listed and preferably FM approved with response time less than 10sec. Installation of fire alarm system shall be done as per IS 2189 or relevant NFPA standard.The panel shall have the web enabled facility which can able to send or receive e-mails with memory of 1000 events recording.Note:The vendor shall provide panel UL 9th edition listing certificate. (Make: Edwards / Honeywell) | Nos | 1 | 48000 | 10000 | 58000 | 1 | 58000 | 58000 | 1 | 58000 | 58000 | 0 | 58000 | 0 | 0 | 58000 | 0
i) Each loop with Min. 99 Devices + 99 Detectors modules connection capability of Addressable FACP) 1 Loop Pannel.
ii) FACP with all in-built modules & displays.
iii) 240 volts AC power supply, automatic battery charger, 24 volts sealed lead acid batteries sufficient for 4 hours normal working.
iv) Programming & setting up
v) system to be capable of operating the system for 2 hours during an emergency condition including all necessary software for remote programming of fire alarm system through central control station.
vi) As the number of hooters are 43, additional power supplies to be provided as required.
Necessary Integration Facility with BMS for following functions:-
Alarm, Trouble condition,Supervisory alerts to BMS
Share Graphics of Security, Fire and HVAC
13.1.1 | Fire alarm Addressable control panel (1 Loop)
13.2 | Active Repeater Panel with 8.5" Touch Screen TFT display with TCP/IP Eable Repeater Panel shall monitor and control (Scroll, Acknowledge, Reset & Mute) all the events of the FACP to which it is connected and it shall have Port Vectoring / Event Filtering capability of showing only ALARMS, TROUBLES or SUPERVISORY or customized combinations of user selected events. | Nos | RO
13.2.1 | Supply installation and testing of signal loop components in a suitable galvanised steel junction box.
13.3 | Detectors and Devices
13.3.1 | Supply,Installation,Testing & Commissioning of Analogue Addressable Monitor module having Rotary, decimal addressing system for monitoring the field devices & shall be capable of providing DPDTcontact rated at 24V DC, 2A. | Nos | RO
13.3.2 | Supply,Installation,Testing & Commissioning of Analogue Addressable Relay module having Rotary, decimal addressing system for AHU tripping and shall be capable of providing DPDTcontact rated at 24v DC, 2A. | Nos | 1 | 4000 | 550 | 4550 | 1 | 4550 | 4550 | 1 | 4550 | 4550 | 0 | 4550 | 0 | 0 | 4550 | 0
(For all AHU's, Fans & Acess Control)
13.3.3 | Supply,Installation,Testing & Commissioning of Horn / Strobe rated at 82 dBA @ 3m for Audible annunciation and 75cd flashing at 1 Hz for visual indication with Control modules and necessary accessories including back box. | Nos | 3 | 4200 | 400 | 13800 | 3 | 4600 | 13800 | 3 | 4600 | 13800 | 0 | 4600 | 0 | 0 | 4600 | 0
13.3.4 | Supply,Installation,Testing & Commissioning of Analogue Addressable Flash scan Type Photoelectric smoke detectors( Below False Ceiling) having Rotary, decimal addressing system with standard base, built in isolation function and junction box. The detector shall be capable to address in the range of 1-159. The detector shall be with Visible bi-color LEDs for 360 deg viewing and shall blink green every time the detector is addressed, and illuminate steady red on alarm. | Nos | 4 | 3400 | 350 | 15000 | 8 | 3750 | 30000 | 8 | 3750 | 30000 | 4 | 3750 | 15000 | 0 | 3750 | 0
13.3.5 | Supply,Installation,Testing & Commissioning of Analogue Addressable Flash scan Type Photoelectric smoke detectors (Above False Ceiling) having Rotary, decimal addressing system with standard base, built in isolation function and junction box. The detector shall be capable to address in the range of 1-159. The detector shall be with Visible bi-color LEDs for 360 deg viewing and shall blink green every time the detector is addressed, and illuminate steady red on alarm. | Nos | 4 | 3400 | 350 | 15000 | [6 empty] | -4 | 3750 | -15000
13.3.6 | Supply,Installation,Testing & Commissioning of Analogue Addressable Flash scan Type Heat Detector having Rotary, decimal addressing system with standard base, built in isolation function and junction box. The detector shall be capable to address in the range of 1-159. The detector shall be with Visible bi-color LEDs for 360 deg viewing and shall blink green every time the detector is addressed, and illuminate steady red on alarm. | Nos | 3 | 2700 | 265 | 8895 | 3 | 2965 | 8895 | 3 | 2965 | 8895 | 0 | 2965 | 0 | 0 | 2965 | 0
13.3.7 | Supply,Installation,Testing & Commissioning of Addressable Break Glass Manual Call Point having Rotary, decimal addressing system and having an integrally mounted addressable module that monitors and reports contact status. | Nos | 3 | 3250 | 350 | 10800 | 3 | 3600 | 10800 | 3 | 3600 | 10800 | 0 | 3600 | 0 | 0 | 3600 | 0
13.4 | SITC of Fault Isolator. | Nos | 2 | 3750 | 320 | 8140 | 2 | 4070 | 8140 | 2 | 4070 | 8140 | 0 | 4070 | 0 | 0 | 4070 | 0
13.5 | SITC of 2Cx1.5sq.mm multistranded Armoured FRLS RED Colour,Mylan Shielded Screened cable | Mtrs | 75 | 90 | 20 | 8250 | 430 | 110 | 47300 | 430 | 110 | 47300 | 355 | 110 | 39050 | 0 | 110 | 0
13.6 | Response indicator. | Nos | 4 | 105 | 20 | 500 | [6 empty] | -4 | 125 | -500
| Sub Total of 13 |  |  |  |  | 142935 |  |  | 181485 |  |  | 181485 |  |  | 38550 |  |  | 0
| Grand total |  |  |  |  | 1774979 |  |  | 1642391 |  |  | 1476951 |  |  | -298028 |  |  | -165440
z | [17 empty] | 165440

## ELECTRICAL NT
SR. NO. | DESCRIPTION OF ITEM | UNIT | Claimed quantity | Rate | Claimed Amount | Actual Quantity | Certified Rate | Actual Amount | Difference | Remark |  | Purchase remark 08th July
1 | Laying, testing & commissioning of 3.5C x 300 Sq.mm. AL XLPE Cable. | MTR. | 45 | 300 | 13500 | 45 | 200 | 9000 | 4500
[8 empty] | 0 | 0
2 | Supply Laying, testing & commissioning of 4C x 16 Sq.mm. CU XLPE Cable. | MTR. | 45 | 1050 | 47250 | 45 | 800 | 36000 | 11250 | Cable bill required
[8 empty] | 0 | 0
3 | Supply, Installation testing and commission of 4C x 16 Sq.mm. CU XLPE Cable termination | NOS | 2 | 700 | 1400 | 2 | 700 | 1400 | 0
[8 empty] | 0 | 0
4 | Supply Laying, testing & commissioning of 1C x 1.5 Sq.mm. CU wire. | MTR. | 12 | 24 | 288 | 12 | 24 | 288 | 0 | ?
[8 empty] | 0 | 0
5 | Supply, Installation testing and commission of USB SOCKET | NOS | 18 | 900 | 16200 | 18 | 750 | 13500 | 2700
[8 empty] | 0 | 0
6 | Supply, Installation testing and commission of 3 PIN TOP | NOS | 12 | 0 | 0 | 12 |  | 0 | 0
[8 empty] | 0 | 0
7 | Supply, Installation testing and commission of 16A 1SWITCH & 1 SOCKET 3M PVC BACK BOX WITH PLATE. | NOS | 6 | 700 | 4200 | 6 |  | 0 | 4200
[8 empty] | 0 | 0
8 | Supply, Installation testing and commission of 16A 4SWITCH & 4 SOCKET 12M PVC BACK BOX WITH PLATE. | NOS | 1 | 1450 | 1450 | 1 |  | 0 | 1450
[8 empty] | 0 | 0
9 | Supply & Installation of 40A,FP,MCB, in powder coated sheet metal box for terminating power to equipment etc. | NOS | 1 | 5300 | 5300 | 1 |  | 0 | 5300 |  | bill required
[8 empty] | 0 | 0
10 | Supply & Installation of 40A,FP,ELCB, in powder coated sheet metal box for terminating power to equipment etc. | NOS | 1 | 5650 | 5650 | 1 |  | 0 | 5650
[8 empty] | 0 | 0
11 | Removing & refixing of HANGING LIGHT. with flexible | JOB | 1 | 8000 | 8000 | 1 | 3500 | 3500 | 4500
[8 empty] | 0 | 0
12 | Removing & refixing of 4C x 16 Sq.mm. AL XLPE Cable. | JOB | 1 | 1200 | 1200 | 1 |  | 0 | 1200
[8 empty] | 0 | 0
13 | Supply & Installation of AUTOMATION SYSTEM FOR FOH AREA | JOB | 1 | 5500 | 5500 | 1 | 0 | 0 | 5500 |  | done by galaxy automation
[8 empty] | 0 | 0
14 | Supply & Installation of 4FIT 40W LED TUBE LIGHT FIXTURE. | NOS | 6 | 750 | 4500 | 6 | 550 | 3300 | 1200
[8 empty] | 0 | 0
15 | Supply & Installation of 5W/MTR LED STRIP. | MTR. | 25 | 650 | 16250 | 13.75 | 300 | 4125 | 12125
[8 empty] | 0 | 0
16 | Removing of Relay Module | NOS | 1 | 500 | 500 | 1 |  | 0 | 500
[8 empty] | 0 | 0
17 | Removing of Hooter | NOS | 3 | 500 | 1500 | 3 |  | 0 | 1500
[8 empty] | 0 | 0
18 | Removing of Smoke Detector | NOS | 8 | 500 | 4000 | 8 |  | 0 | 4000
[8 empty] | 0 | 0
19 | Removing of Heat Detector | NOS | 3 | 500 | 1500 | 3 |  | 0 | 1500
[8 empty] | 0 | 0
20 | Removing of Manual Call Point | NOS | 3 | 500 | 1500 | 3 |  | 0 | 1500
[8 empty] | 0 | 0
21 | Removing of Fault Isolator | NOS | 2 | 500 | 1000 | 2 |  | 0 | 1000
[8 empty] | 0 | 0
22 | Supply of Addressable single loop Fire Alaram system panel. (Make - Honeybell) Model NFS 320 | NOS | 1 | 268500 | 268500 | 1 | 216000 | 216000 | 52500 | ? | including transportation | Need relay module invoice copy/purchase price
[8 empty] | 0 | 0
23 | Installation, Programming, Testing & Commisioning of Addressable single loop Fire Alaram system panel. (Make - Honeybell) Model NFS 320 | NOS | 1 | 75000 | 75000 | 1 | 15000 | 15000 | 60000 | ? | for installation and programing | Need relay module invoice copy/purchase price
[8 empty] | 0 | 0
24 | Supply, Installation testing and commission of Relay Module UL & FM Approved. (Make - Notifier) | NOS | 11 | 6950 | 76450 | 11 | 4800 | 52800 | 23650 |  | relay module 4400 instalion 400 | Need relay module invoice copy/purchase price
[8 empty] | 0 | 0
25 | Supply, Installation testing and commission of Horn Cum Strober UL & FM Approved. (Make - Notifier) | NOS | 3 | 11360 | 34080 | 3 | 5900 | 17700 | 16380
[8 empty] | 0 | 0
26 | Supply, Installation testing and commission of Smoke Detector UL & FM Approved. (Make - Notifier) | NOS | 8 | 5520 | 44160 | 8 | 5520 | 44160 | 0
[8 empty] | 0 | 0
27 | Supply, Installation testing and commission of Heat Detector UL & FM Approved. (Make - Notifier) | NOS | 3 | 5135 | 15405 | 3 | 5135 | 15405 | 0
[8 empty] | 0 | 0
28 | Supply, Installation testing and commission of Manual call point UL & FM Approved. (Make - Notifier) | NOS | 3 | 5620 | 16860 | 3 | 4550 | 13650 | 3210 |  | Supply rate 4200
[8 empty] | 0 | 0
29 | Supply, Installation testing and commission of Fault Isolator UL & FM Approved. (Make - Notifier) | NOS | 2 | 5910 | 11820 | 2 | 0 | 0 | 11820 | ? | Justification required
[8 empty] | 0 | 0
30 | Supply, Installation testing and commission of Monitor Module UL & FM Approved. (Make - Notifier) | NOS | 1 | 6230 | 6230 | 1 | 5880 | 5880 | 350 | ? | installation charge 350
[8 empty] | 0 | 0
31 | Installation, Integration & commissioning of fire alarm system with all required modules, relays, SMPS with modular Extinguishers. | NOS | 1 | 207500 | 207500 | 1 | 60000 | 60000 | 147500 | ? | 1 SMPS 3 CLEANING AGENT INTEGRATION. / MODULE INSTALATION ABOVE QUOTED | Need supporting document and designer justification as to why this was missed out from BOQ
[8 empty] | 0 | 0
32 | Supply, Installation testing and commission of Fire Exit Signages | NOS | 3 | 6600 | 19800 | 3 | 5800 | 17400 | 2400 | ? | 5500 SUPLY INSTALLATION
[8 empty] | 0 | 0
33 | Supply, Installation testing and commission of Fire Extinguisher Signages | NOS | 8 | 300 | 2400 | 8 | 300 | 2400 | 0
[8 empty] | 0 | 0
34 | Supply, Installation testing and commission of Fire Extinguisher Stand | NOS | 4 | 850 | 3400 | 4 | 700 | 2800 | 600 |  | ITS ONLY STAND WHY ISTLTION CHARGES REQUIRED
[8 empty] | 0 | 0
35 | Supply, Installation testing and commission of Danger Signages | NOS | 4 | 650 | 2600 | 4 | 550 | 2200 | 400
[8 empty] | 0 | 0
36 | Addition & Modification Fire Sprinkler Drain Valve, Pressure Guage, Flow Switch etc. | JOB | 1 | 48000 | 48000 | 1 | 24000 | 48000 | 0 | ? | 25MM 6MTR PIPE PRESURE GUAGE FLOW SWITCH AND LABOUR WORK CONSIDERED WITH PROFIT
[8 empty] | 0 | 0
37 | Supply, Installation testing and commission of Addressable Smoke Detectors (Make - Notifier) | NOS | 4 | 5400 | 21600 | 4 |  | 0 | 21600 | ? |  | Need invoice copy
[8 empty] | 0 | 0
38 | Replacement of hood lights | Nos | 4 | 2700 | 10800 | 4 | 2350 | 9400 | 1400 | Gst Bill also replace the light with flame proof
[8 empty] | 0 | 0
39 | Supply & Installation of wall mount fan in dish wash area | JOB | 1 | 3800 | 3800 | 1 | 3800 | 3800 | 0 | GST Bill Require
[8 empty] | 0 | 0
40 | Load balancing certificate | JOB | 1 | 30000 | 30000 | 1 | 0 | 0 | 30000 | Part of contractor job scope.. Labour charge included | NOT DONE PROPERLY TRIPPING ISSUE IN OUTLET | Supporting invoice of this activity required
[8 empty] | 0 | 0
41 | Replacement of hanging light cable | Nos | 8 | 1400 | 11200 | 8 | 1400 | 11200 | 0 | BILL REQUIRED
[8 empty] | 0 | 0
42 | Supply & Installation 30mA RCCB at main DB in kitchen passage | Nos | 1 | 3500 | 3500 | 1 | 3500 | 3500 | 0 |  |  | site teams call
[8 empty] | 0 | 0
43 | Installation & Commission of UPS & stebilizer for battery | Job | 1 | 10000 | 10000 | 1 | 6000 | 6000 | 4000 | changes in existing UPS |  | site teams call
GRAND TOTAL AMOUNT |  |  |  |  | 1063793 |  |  | 618408 | 445385

## HVAC
COPPER CHIMNEY @ MOM, WAKAD |  |  |  | BOQ |  |  | Claimed |  |  | Approved/ Audited |  |  | As per BOQ |  |  | As Per Audit
HVAC BOQ
Sr. No. | Description Items | Unit | Qty | Supply Rate | Installation Rate | Total Amount | Claimed quantity | Rate | Claimed Amount | Actual Quantity | Rate | Actual Amount | Difference in Qty | Rate | Difference in Amount | Difference in Qty | Rate | Difference in Amount
Note: | Prices shall be based on supply, installation, testing & commissioning (SITC) at site including all taxes, duties, transportation & insurance etc.
1 | CHILLED WATER TYPE CEILING SUSPENDED AHU (AIR HANDLING UNIT) :
1.1 | CEILING SUSPENDED AHU :
Supply and assembly of Ceiling Suspended Double skin cabinet type AHU Integrated (Air handling units) of following specifications:
Frame Structure: It shall consist of 48mm Extruded Aluminium with thermal break profile.
Panel: 45mm +/- 2mm thick double skin sandwich panels with rockwool insulation of density 64 kg/m3 or PUF insulation of 48 kg/m3 , The sheet thickness shall be minimum 0.6 mm for the outer skin precoated and 0.8 mm thickness for the inner skin of plain GI.
Filtration Section: It shall be provided with single stage washable type of prefilter 'MERV 8' first stage which shall be placed before coil section.
Coil Section: Chilled water coil Multi row deep constructed with Aluminium fins of min 0.11mm thick 12 Fins per inch, and copper tubes of min 27 Guage thickness HYRDOPHYLLIC coated fins. Copper tube shall be min 12.5mm diameter. AHRI certified coil.The coil face area velocity shall not exceed 2.5m/sec (500 fpm).
Drain Pan: Condensate drain pan shall be fabricated from 18G SS 304 powder coated, insulated with 13 mm thick closed cell elastomeric(nitrile rubber) insulation.
Fan Section: SISW / DIDW Direct drive backward curved fan. The fan section shall be provided with limt switch for safety to shut off fan during Opening of access door. Fan outlet velocity not to exceed 1600 FPM. The sound level shall not be exceed more than 60dB @ 1m from the source. Vibration isolators, Door Limit switch, UV Lamp as per Technical Specifications, AHU Summary Sheet and drawings. Total static pressue has to calculated by Contractor as per the configuration.
Other Details : AHU to house control box/ terminal box with Auto-Manual switch and incomer power terminal, with SPP, Over/ Undervoltage protection, shortcircuit protection and with no-nc contacts (potential free contact) to be provided for tripping on signal from Fire Dampers / Fire Alarm Panel. Power cable from Terminal box to motor & control cabling of required size upto the thermostat / sensor etc. to be provided. Internal electrical and control wiring of AHU to be provided as factory fitted from AHU supplier. The cost shall include all necessary supports & accessories required for installation.
Contractor shall design the chilled water coil according to the following conditions:
a. Coil air entering temperature - 69.8°F DB
b. Coil air leaving temperature - 54°F DB/ 52.99°F WB
c. Chilled water temperature entering - 6.0°C/ 42.8°F
d. Chilled water temperature leaving - 12.0°C/ 53.6°F
e. Ambient temperature - DB - 96°F / 35.5°C & WB - 78°F / 25.5°C
Make : VTS / Zeco / Citizen
Type Capacity TR ESP No. of
(Cfm) (mm WG) Rows
| CS AHU 4700 15.4 25 4/6 | No. | 1 | 329000 | 25000 | 354000 | 1 | 354000 | 354000 | 1 | 354000 | 354000 | 0 | 354000 | 0 | 0 | 354000 | 0
GENERAL NOTES:
a. | LHS & RHS VALVE station location to be confirmed.
b. | Fan outlet velocity - 1600 FPM
c. | Contractor shall submit static pressure calculation for all above units to Client/Consultant.
d. | Any change in motor HP shall be made at no extra cost to client.
e. | Fan efficiency shall be minimum 75%
f. | The cost shall be included liftting & shifting of each equipment / material with all necesaary arrnagement. Also, it shall be included the cost of scaffloding required for Installation of such material / equipment.
| SUB-TOTAL |  |  |  |  | 354000 | 0 |  | 354000 |  |  | 354000 | 0 |  | 0 | 0 |  | 0
2 | CHILLED WATER PIPING WITH INSULATION:
2.1 | CHW PIPE
SITC of MS Heavy duty class 'C' ERW Chilled Water pipe conforming to IS 1239 - 2004 primer painted including bends, tees, MS supports, PUFF saddles, anchor fasteners, steel angles and any other material required to complete the work. The piping flange connection bolts, washers and nuts should be hot dipped galvanised. Flourscent Plastic Sticker/ paint shall be applied to indicate Water flow directions. Only End flanges to be used for capping of pipes. "Table E" of BS code for flange thickness to be adhered.
Make: Jindal Hissar / TATA
a | Φ 50 mm | Rmt | 30 | 950 | 250 | 36000 | 30 | 1200 | 36000 | 30 | 1200 | 36000 | 0 | 1200 | 0 | 0 | 1200 | 0
2.2 | CHILLED WATER PIPING INSULATION - INTERNAL USE
SITC of insulation for chilled water. piping. For internal pipe - Stick 25mm thick Nitrile rubber class "O" Closed cell nitrile rubber with anti-microbial coating on it. Insulation shall have Thermal conductivity of 0.033 W/(m.K) and water vapor permeance of 0.10. Joints should be sealed with 50 mm wide 3 mm thick self adhesive tape and putting PVC bands at all supports. Further, insulation shall be wrapped with 7 mil cloth with required adhesive on it.
Make: Armaflex & K-flex
a | Φ 50 mm | Rmt | 30 | 320 | 150 | 14100 | 30 | 470 | 14100 | 30 | 470 | 14100 | 0 | 470 | 0 | 0 | 470 | 0
2.3 | BALL VALVE
SITC of following sizes of Ball Valve consist of Cap, Brass Body, Rated for 150 psi SWP, 600 psi WOG Pressure: Two-piece construction; with brass body, regular port, B-16 chrome-plated ball and stem, replaceable “Teflon” or “TFE” seats and seals, blowout-proof stem, vinyl covered steel handle, threaded or soldered ends and extended stem for insulated piping. Same valve shall be used as a Drain valve.
Make: Zoloto / Audco / Kitz
a | Φ 50 mm | Nos. | 3 | 3175 | 200 | 10125 | 3 | 3375 | 10125 | 3 | 3375 | 10125 | 0 | 3375 | 0 | 0 | 3375 | 0
2.4 | BALL VALVE WITH Y-STRAINER
SITC of following sizes of Brass Ball Valve with Y-Strainer consist of Cap, Brass Body, Rated for 150 psi SWP, 600 psi WOG Pressure: Two-piece construction; with brass body, regular port, B-16 chrome-plated ball and stem, replaceable “Teflon” or “TFE” seats and seals, blowout-proof stem, vinyl covered steel handle, threaded or soldered ends and extended stem for insulated piping. Filter element shall be of non magnetic SS sheet with perforation.
Make: Zoloto / Audco / Kitz
a | Φ 50 mm | No. | 1 | 6500 | 200 | 6700 | 1 | 6700 | 6700 | 1 | 6700 | 6700 | 0 | 6700 | 0 | 0 | 6700 | 0
2.5 | PIBCV VALVES
SITC of Pressure Independent Balancing cum Control Valves (PIBCV) including integrated motorised control valve and balancing device for combined flow and water balancing requirement. Valve body to be rated for PN 16. The valve design flow rate should be factory calibrated with +/- 5% flow accuracy. Valve shall have necessary measuring ports, drain port, flanges etc., Valve shall also provide temperature sensor with necessary cabling (min 2mtr length to be considered with each valve). The balancing to be done through microprocessor based hand held terminal / POT and the same results shall be furnished in the water balancing report as part of commissioning report and handing over manual.
Make: Oventrop / Siemens / Danfoss
a | Φ 50 mm | No. | 1 | 41600 | 2500 | 44100 | 1 | 44100 | 44100 | 1 | 44100 | 44100 | 0 | 44100 | 0 | 0 | 44100 | 0
2.6 | Auto Air Vent Valves
Make: Anergy / Flamco
Providing and fitting Auto Vent Valves.
a | SITC of Auto air vent in each risers & common headers & AHU. 3/4" auto vent valves at each coil / riser/ header. | Nos. | 2 | 1465 | 100 | 3130 | 1 | 1565 | 1565 | 1 | 1565 | 1565 | -1 | 1565 | -1565 | 0 | 1565 | 0
2.7 | SITC of Pressure gauges & Thermometers
Make: H Guru / Waree
Necessary pressure gauges and thermometers 4" Dial type.
a | Water Pressure gauges 150mm dial complete with gauge valves, mounting, fittings and copper tubing extension wherever required. Pressure gauges Range 0-10 Kg/CM2 | Nos. | 2 | 1000 | 180 | 2360 | 2 | 1180 | 2360 | 2 | 1180 | 2360 | 0 | 1180 | 0 | 0 | 1180 | 0
b | Thermometers of the mercury in glass stem type and copper separable well complete with guard etc., of industrial grade mounting on water lines. Length 9/12 inches, Thermometer, Range 0-50 deg C | Nos. | 2 | 800 | 180 | 1960 | 2 | 980 | 1960 | 2 | 980 | 1960 | 0 | 980 | 0 | 0 | 980 | 0
c | Thermowells | Nos. | 4 | 350 | 100 | 1800 | 2 | 450 | 900 | 2 | 450 | 900 | -2 | 450 | -900 | 0 | 450 | 0
d | SITC of Brass Test Plug of industrial grade mounting on water | Nos. | RO
2.8 | INSULATED CONDENSATE DRAIN PIPE
SITC of UPVC pipes of following sizes for drain with necessary supports and fittings such as elbows, tees & reducers etc. The insulation line to be insulated with nitrile rubber insulation of thickness 9mm and wrapped by weather proof protection tape. The Pipe wherever concealed should also have a parallel line as a standby arrangement in case of block of primary pipe .
Make: Supreme, Prince, Astral
a | Φ 25 mm | Rmt | RO
b | Φ 32 mm | Rmt | 10 | 80 | 35 | 1150 | 10 | 115 | 1150 | 5 | 115 | 575 | -5 | 115 | -575 | -5 | 115 | -575
NOTES FOR PIPING:
a | Cover all open pipe ends with muslin cloth during construction
b | Pipe cleaning & chemical treatment as per specs shall be included in the piping cost.
c | Unit rates for all indicated sizes of pipes & valves shall be furnished.
d | Cleaning/Painting of pipe before insulation shall be included in piping cost.
e | The piping support should be as per tender specification and additional supports are to be provided Contractor as decided by Consultant.
f | All the valves shall be insulated with the same material as that of Chilled water pipng and cost of insulation for valves shall be considered.
| SUB-TOTAL |  |  |  |  | 121425 | 0 |  | 118960 |  |  | 118385 | -8 |  | -3040 | -5 |  | -575
3 | SHEET METAL WORKS:
3.1 | FACTORY FABRICATED G.I RECTANGULAR DUCT
Supply, Fabrication, Testing, and Commissioning of Factory Fabricated GI Sheet Metal 120GSM Rectangular boxed ducting, Plenums, Cowls, Elbows with turning vanes, Splitters, Reducers, Flanges, Collars etc as per IS and Installaton as per SMACNA standards, The complete ducting shall be provided with MS Supports, Rods, Angles, Flanges, Bracing, Rubber Gaskets, Wooden frames, Canvas Connections, etc. as per drawings and specifications.
GI Sheet Makes : Tata, Jindal, SAIL, Ispat
Make: Rola Star, Zeco & Ductofab
a | 18 Gauge GI Sheet Metal Duct (Above 2251mm & Plenum) | Sq.mtr | RO
b | 20 Gauge GI Sheet Metal Duct (1501-2250mm) | Sq.mtr | RO
c | 22 Gauge GI Sheet Metal Duct (751-1500mm) | Sq.mtr | 30 | 1000 | 350 | 40500 | 28.96 | 1350 | 39096 | 28.96 | 1350 | 39096 | -1.04 | 1350 | -1404 | 0 | 1350 | 0
d | 24 Gauge GI Sheet Metal Duct (0-750mm) | Sq.mtr | 40 | 950 | 350 | 52000 | 24.64 | 1300 | 32032 | 24.02 | 1300 | 31226 | -15.98 | 1300 | -20774 | -0.62 | 1300 | -806
3.2 | FACTORY FABRICATED G.I FLAT OVAL DUCT
Supply, Fabrication, Testing, and Commissioning of Factory Fabricated GI Sheet Metal 120GSM Exposed Flat Oval ducting, Elbows with turning vanes, Splitters, Reducers, Collars etc as per IS and Installaton as per SMACNA standards, The complete ducting shall be provided with MS Supports, Rods, Angles, Flanges, Bracing, Rubber Gaskets, Wooden frames, Canvas Connections, etc. as per drawings and specifications. All exposed ducts has to be powder coated by HVAC contractor, sample and color code to be presented for the validation of Client / Architect.
GI Sheet Makes : Tata, Jindal, SAIL, Ispat
Make: Rola Star, Zeco & Ductofab
a | 22 Gauge GI Sheet Metal Duct (751-1500mm) | Sq.mtr | RO
b | 24 Gauge GI Sheet Metal Duct (0-750mm) | Sq.mtr | 50 | 1064 | 300 | 68200 | 46 | 1364 | 62744 | 46 | 1364 | 62744 | -4 | 1364 | -5456 | 0 | 1364 | 0
3.3 | EXTRUDED ALUMINIUM CEILING GRILLES
Supply, Installation, Testing and Balancing of Powder coated aluminium supply air grilles complete with removable inner core as per approved shop drawing and specifications. The area of grille can be of any geometrical shape (Square/rectangular/Linear). The grilles shall be with 15/30/45° deflections as per requirement. The Colour shall be decided and approved by client and architect.
Make: Cosmos, Air Master & System Air
a | Curve Grille | Sq.mtr | 0.5 | 8500 | 1250 | 4875 | 1.23 | 9750 | 11992.5 | 1.23 | 9750 | 11992.5 | 0.73 | 9750 | 7117.5 | 0 | 9750 | 0
b | Linear / Square / Rectangular Grille | Sq.mtr | 1 | 5500 | 1250 | 6750 | 3.13 | 6750 | 21127.5 | 3.13 | 6750 | 21127.5 | 2.13 | 6750 | 14377.5 | 0 | 6750 | 0
3.4 | OPPOSED BLADE DAMPER
| SITC of Aluminium Opposed blade dampers black powder coated vertical blades type for supply air collar. The damper should be gear operated type. | Sq.mtr | 1.5 | 9500 | 1450 | 16425 | 2.77 | 10950 | 30331.5 | 2.77 | 10950 | 30331.5 | 1.27 | 10950 | 13906.5 | 0 | 10950 | 0
Make: Cosmos, Air Master & System Air
3.5 | MULTI LEAF VOLUME CONTROL DAMPER
| SITC of opposed blade aerofoil type 1.2 mm thick Anodized Aluminium volume control dampers for ducts shall be provided with concealed gears, plastic operator and quadrants for manual control of volume of air flow and for proper balancing of the air distribution system as per the approved shop drawings and specifications. | Sq.mtr | 1 | 6500 | 1450 | 7950 | 1.435 | 7950 | 11408.25 | 1.435 | 7950 | 11408.25 | 0.435 | 7950 | 3458.25 | 0 | 7950 | 0
Make: Cosmos, Air Master & System Air
3.6 | CANVAS CONNECTION
SITC of Flexible connections between mouth piece of Fan and initial piece of ducting with inspection zip. Flexible connections shall be double thickness non-flammable material (Fire retardant type).
a | For AHU | No | 1 | 2000 | 1000 | 3000 | 1 | 3000 | 3000 | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 3000 | 0
NOTES:
The ducting support should be as per tender specification and additional supports are to be provided by Contractor as decided by Consultant.
Muslin cloth cover for all air outlets during construction.
Pressure testing of complete duct work as per DW/ SMACNA standard.
Silicon sealant for longitudinal & transverse joints as per specification.
Diffusers & grilles shall be powder coated as per color approved by Architect.
| SUB-TOTAL |  |  |  |  | 199700 | 0 |  | 211731.75 |  |  | 210925.75 | -16.455 |  | 11225.75 | -0.62 |  | -806
4 | THERMAL & ACOUSTIC INSULATION:
4.1 | THERMAL INSULATION
| Supply & fixing of Thermal insulation for supply air duct using 13mm thick class " O " Closed cell nitrile rubber with anti-microbial coating on it. Insulation shall have Thermal conductivity of 0.033 W/(m.K) and water vapor permeance of 0.10. Joints should be sealed with 50 mm wide 3 mm thick self adhesive tape. The duct shall be stick with recommended adhesive. | Sq.mtr | 110 | 650 | 100 | 82500 | 125 | 750 | 93750 | 124.79 | 750 | 93592.5 | 14.79 | 750 | 11092.5 | -0.21 | 750 | -157.5
Make: Armaflex & K-flex
4.2 | ACOUSTIC INSULATION
| Supply & fixing acoustic insulation for ducting using Class "1" closed cell elastomeric insulation of 10mm thick Nitrile rubber insulation adhesive, longitudinal & transverse joints sealed with adhesive in neat & clean manner. Material shall be processed Nitrile Rubber foam with anti-microbial protection. Insulation shall have thermal conductivity of 0.047 W/(m.K) and density of 140 - 180 kg/m³. | Sq.mtr | 10 | 850 | 150 | 10000 | 10.42 | 1000 | 10420 | 10.42 | 1000 | 10420 | 0.42 | 1000 | 420 | 0 | 1000 | 0
Make: Armaflex & K-flex
Note:
a. | Insulation work to be coordinated with other agencies and repair to be included by contractor as per site requirement.
b. | Vendors to take care of the installation, if any damages takes place the vendor to repair or replace and hand over to clients in good and acceptable condition.
c. | Thermal insulation shall be internal for Elliptical / Expossed ducting.
| SUB-TOTAL |  |  |  |  | 92500 |  |  | 104170 |  |  | 104012.5 | 15.21 |  | 11512.5 | -0.21 |  | -157.5
5 | ELECTRICAL WORKS:
5.1 | STARTER PANEL
SITC of indoor / outdoor, wall mounting type DOL / Delta 3PH, 415V AC MOTOR STARTERS with VFD in CRCA Sheet Steel enclosure with necssary supporting brackets and required accessories, etc., The Enclosure shall be provided with knockouts suitable for cable termination at TOP & BOTTOM for incoming and outgoing power cables of A2XFY type and size specified. The starters shall be complete with suitable MPCB/MCCB, Contactor, Bi-metal O/L relay with SPP, ON/OFF Push buttons, on / off / trip indication Lamp, on off push button, & phase indication Lamp. Selection of relay, contractor, MPCB/MCCB etc. as per Type-2 Coordination. Starter panel shall be BMS compatible.
a | Suitable for DOL Starter Panel without VFD
| CS AHU 4700 CFM, DOL Starter type | No. | 1 | 18500 | 800 | 19300 | 1 | 19300 | 19300 | 1 | 19300 | 19300 | 0 | 19300 | 0 | 0 | 19300 | 0
5.2 | POWER CABLING
Supply, handling, laying effecting proper connections testing and commissioning of following sizes of 1.1 KV grade XLPE insulated FRLS Aluminium /Copper conductor cables laid over MS supports cable racks or fixing on walls including clamping the cable to supports in an approved manner as required complete with Copper earthing as specified for continuous earthing along with cable. All complete as required and as per final instruction as given by Owners/ Consultants and as per Technical specifications. Earthing shall be measured separately and shall be connected in two runs. Power to ELCB to be provided near each ODU by electrical contractor.
a | Suitable Power Cable:
| CS AHU 4700 CFM, DOL Starter type | Rmt | 10 | 300 | 100 | 4000 | 0 | [5 empty] | -10 | 400 | -4000
b | Earthing:
| 8 SWG | Rmt | 20 | 40 | 20 | 1200 | 0 | [5 empty] | -20 | 60 | -1200
5.3 | CABLE TERMINATION :
Supply & Making of Cable termination of armoured / unarmoured cables 1.1 KV grade including installation of cable glands, cable lugs (Aluminium for A2XFY & copper for 2XFY & YY Double compression type), heat shrinkable sleeves on long ends, crimping paste etc. The work includes testing & commissioning of cables, meggaring values & submitting reports of tests. (One set includes termination of all cores of one end only). All crimping tools & dies shall be arranged by contractor.
Suitable for
0 | CS AHU 4700 CFM, DOL Starter type | No. | 2 | 300 | 150 | 900 | 0 | [5 empty] | -2 | 450 | -900
5.4 | CABLE TRAYS
Supplying & Fixing of following sizes of GI cable tray duly painted perforated type of height 50mm along with necessary bends, reducers etc. anchored along the wall / suspended from the ceiling with necessary MS supports.
a | 50mm wide x 1.6mm thick | Rmt | 10 | 250 | 50 | 3000 | 0 | [5 empty] | -10 | 300 | -3000
a | 100mm wide x 1.6mm thick | Rmt | RO
| SUB-TOTAL |  |  |  |  | 28400 |  |  | 19300 |  |  | 19300 | -42 |  | -9100 | 0 |  | 0
| GRAND TOTAL |  |  |  |  | 796025 |  |  | 808161.75 |  |  | 806623.25 |  |  | 10598.25 |  |  | -1538.5
NT Items
1 | Supply & Installation VFD Panel for AC in kitchen passage | [5 empty] | 1 | 45000 | 45000 | 1 | 45000 | 45000 |  |  |  | 0 | 45000 | 0

## VENTILATION
COPPER CHIMNEY @ MOM, WAKAD |  |  |  | Vart Infra offer
VENTILATION BOQ
|  | BOQ |  |  |  |  | Claimed |  |  | Approved |  |  | Difference from claimed bill |  |  | Difference from BOQ
Sr.No. | Item Description | Unit | Qty | Supply Rate | Installation Rate | Total Amount | Claimed quantity | Rate | Claimed Amount | Actual Quantity | Rate | Actual Amount | Difference in Qty | Rate | Difference in Amount | Difference in Qty | Rate | Difference in Amount | Remark
Note: | Prices shall be based on supply, installation, testing & commissioning (SITC) at site including all taxes, duties, transportation & insurance etc.
1 | VENTILATION SYSTEM
1.1 | KITCHEN EXHAUST AIR FAN
SITC of Cabinet type SISW Centrifugal Blower, Direct Drive, Statically & Dynamically Balanced, Backward Curved Impeller fan, Dunlop Anti- Vibration Pads etc. Motor should be outside stream with TEFC squirrel cage, weather protection shield, IP 65 rating with Class H Insulation motor, suitable for 3phase, 415volts, 50hz power supply. Sound level should be 65dB @ 3mtr distance. Fan should be painted with 2 coat of zinc chromate primer and 2 coats Epoxy paint. The quote shall include with MS frame and required accessories. (Vendor to crosscheck static pressure calculation).
Make :Waves / Systems Air / Nicotra
| 10700CFM, 50mm TSP | No. | 1 | 198000 | 20000 | 218000 | 1 | 218000 | 218000 | 1 | 218000 | 218000 | 0 | 218000 | 0 | 0 | 218000 | 0
1.2 | KITCHEN DRY SCRUBBER
SITC of Dry scrubber – Electrostatic Air cleaner with starter panel as per specifications, suitable for following capacities, including electrical starter panel . The Air filtration efficiency should be between 90 to 95% & units shall be staked one above other or side by side as per site requirement, if vendor will propose multiple units.
Finishing - Power coated, Dark Blue
Operating voltage - 220 Vac+/-10%, 50 Hz (Single phase)
Features - Short circuit, arc protection and auto restore power supply, BMS (Building Management System) terminals provided, Auto power cut-off when door is opened, Indicator LEDs for normal or wash indicator, Set of Terminals for remote LED normal or wash indicator
Efficiency - Upto 95%, meets NIOSH 5026 Oil Mist Test
Particle Size - Collects particles as small as 0.01 microns
Motor - Sealead ball bearings UL, single phase.
Cell - Ionizing voltage - 12 KVdc
Collector voltage - 6 KVdc
One cell comprising of 9 ionizing wires and 25 collection plates
Controls - Auto cut-off when door is opened. Indicator lights for fault, normal or wash function.
Pre-filter - Aluminium mesh, washable Dry contact for BMS.
Make: Rydair / Espair
| CFM - 5500 | Nos. | 2 | 210000 | 20000 | 460000 | 2 | 230000 | 460000 | 2 | 230000 | 460000 | 0 | 230000 | 0 | 0 | 230000 | 0
1.3 | KITCHEN AIR-WASHER FAN
SITC of Cabinet type Air-washer fan with Centrifugal Blower, Belt / Direct Drive, Statically & Dynamically Balanced, Backward Curved Impeller, MERV 8 filter, Dunlop Anti- Vibration Pads, filters,Water Circulation Pump, etc. Motor should be TEFC squirrel cage, IP 55 rating with Class F Insulation, suitable for 3phase, 415volts, 50hz power supply. Sound level should be 65dB @ 3mtr distance. Fan should be painted with 2 coat of zinc chromate primer and 2 coats Epoxy paint. MERV 8 / G4 pleated pre-filters should be made of 100% synthetic media to capture common airborne contaminants as per ASHRAE Standard 52.2. (Vendor to crosscheck static pressure calculation) Air Washer will be supplied with Water Circulation Pump, Water Inlet Connection, Overflow, Drain Outlet with 3 / 8” Brass Spray Nozzles, Interconnected Piping for Air Washer.
Make :Waves / Systems Air / Nicotra
a | 9500 CFM, 40mm TSP | No | 1 | 209500 | 20000 | 229500 | 1 | 229500 | 229500 | 1 | 229500 | 229500 | 0 | 229500 | 0 | 0 | 229500 | 0 | Breakup required
1.4 | FRAMEWORK FOR FANS
| Supply, Fabrication and Installation of MS frame using channels/angle iron sections as required for mounting of ventilation fans & scrubber in areas shown in the layout. The frame work shall be applied with red oxide primer and thereafter, two coats of enamel paint of approved colour. The general arrangement drawing for frame work shall be got approved from the Architects/ Structural Engineers prior to commencement of fabrication. | Kg | 200 | 95 | 50 | 29000 | 200 | 145 | 29000 | 200 | 145 | 29000 | 0 | 145 | 0 | 0 | 145 | 0
Note:
a. | Fan outlet velocity - 1600 FPM
b. | All cabinet fans should have plenum section.
c. | Fresh air fan should to have 6mm thick synthetic media washable filter with framework.
d. | Contractor shall submit static pressure calculation for all above units to Client/Consultant for their approval. Also, the total static drops across the systems shall cover the overall length from suction / discharge to grille (inside the outlet).
e. | Any change in motor HP or coil selection shall be made at no extra cost to client.
f. | Fan efficiency shall be minimum 75%
g. | The cost shall be included liftting & shifting of each equipment / material with all necesaary arrnagement. Also, it shall be included the cost of scaffloding required for Installation of such material / equipment.
| SUB-TOTAL |  |  |  |  | 936500 | 0 |  | 936500 |  |  | 936500 |  |  | 0 | 0 |  | 0
2 | SHEET METAL WORKS:
2.1 | FACTORY FABRICATED G.I RECTANGULAR DUCT
| Supply, Fabrication, Testing, and Commissioning of Factory Fabricated GI Sheet Metal 120GSM Rectangular boxed ducting, Plenums, Cowls, Elbows with turning vanes, Splitters, Reducers, Flanges, Collars etc as per IS and Installaton as per SMACNA standards, The complete ducting shall be provided with MS Supports, Rods, Angles, Flanges, Bracing, Rubber Gaskets, Wooden frames, Canvas Connections, etc. as per drawings and specifications. | [17 empty] | Certification & Tc Required
GI Sheet Makes : Tata, Jindal, SAIL, Ispat
Make: Rola Star, Zeco & Ductofab
a | 18 Gauge GI Sheet Metal Duct (Above 2251mm & Plenum) | Sq.mtr | RO
b | 20 Gauge GI Sheet Metal Duct (1501-2250mm) for Kitchen Exhaust Works | Sq.mtr | 80 | 1350 | 350 | 136000 | 59 | 1700 | 100300 | 59 | 1700 | 100300 | 0 | 1700 | 0 | -21 | 1700 | -35700
c | 22 Gauge GI Sheet Metal Duct (751-1500mm) | Sq.mtr | RO | [8 empty] | 0
d | 24 Gauge GI Sheet Metal Duct (0-750mm) | Sq.mtr | 75 | 950 | 350 | 97500 | 130 | 1300 | 169000 | 130 | 1300 | 169000 | 0 | 1300 | 0 | 55 | 1300 | 71500
2.2 | SS EXHAUST AND FRESH AIR GRILLES
SITC of 18G S.S 304 Grills adjustable Double Deflector With S.S Volume Control Dampers. Grills to be of Double Deflection Type for ease of deflection on all sides and to have necessary built in Dampers for adjustable nature.
Make: Carryaire / System Air / Dynacraft / Air Master
a | Linear / Square / Rectangular Grille | Sq.mtr | 1.5 | 8250 | 1250 | 14250 | 0 |  | 0 | [6 empty] | -1.5 | 9500 | -14250
2.3 | EXTRUDED ALUMINIUM LOUVER with BIRD SCREEN
| SITC of Aluminium extruded powder coated Louver with four side flanges, wire mesh bird screen etc. | Sq.mtr | RO
2.4 | OPPOSED BLADE DAMPER
| SITC of Aluminium Opposed blade dampers black powder coated vertical blades type for supply air collar. The damper should be gear operated type. | Sq.mtr | 1.5 | 7500 | 500 | 12000 | 0 | [8 empty] | -1.5 | 8000 | -12000
Make: Cosmos, Air Master & System Air
2.5 | DOOR TRANSFER GRILLE
SITC of Aluminium extruded powder coated Door transfer grills.
| Door transfer grille (Back to Back) | Sq.mtr | 1 | 8000 | 500 | 8500 | 0 | [8 empty] | -1 | 8500 | -8500
Make: Cosmos, Air Master & System Air
2.6 | MULTI LEAF VOLUME CONTROL DAMPER
| SITC of opposed blade aerofoil type 1.2 mm thick Anodized Aluminium volume control dampers for ducts shall be provided with concealed gears, plastic operator and quadrants for manual control of volume of air flow and for proper balancing of the air distribution system as per the approved shop drawings and specifications. | Sq.mtr | 4 | 8050 | 1450 | 38000 | 0 | [8 empty] | -4 | 9500 | -38000
Make: Cosmos, Air Master & System Air
2.7 | CURTAIN TYPE FIRE DAMPER
SITC of curtain type fire dampers consist of 16G GI frame, 20G GI interlocking blades secured with SS springs, blades outside airstream clamped with fusible link UL-555 listed with melting point 165 / 225°F, etc; as per the approved shop drawings and specifications.
Make: Cosmos, Air Master & System Air
a | Bare fire dampers | Sq.mtr | 0.75 | 8000 | 500 | 6375 | 0.35 | 8500 | 2975 | 0.35 | 8500 | 2975 | 0 | 8500 | 0 | -0.4 | 8500 | -3400
b | Fusible link as per specification UL 555 and CBRI approved | Nos. | 2 | 1200 | 200 | 2800 | 0 | [8 empty] | -2 | 1400 | -2800
2.8 | CANVAS CONNECTION
SITC of Flexible connections between mouth piece of Fan and initial piece of ducting with inspection zip. Flexible connections shall be double thickness non-flammable material (Fire retardant type).
a | For Fan | Nos | 2 | 2500 | 750 | 6500 | 2 | 3250 | 6500 | 2 | 3250 | 6500 | 0 | 3250 | 0 | 0 | 3250 | 0
NOTES:
The ducting support should be as per tender specification and additional supports are to be provided by Contractor as decided by Consultant.
Muslin cloth cover for all air outlets during construction.
Pressure testing of complete duct work as per DW/ SMACNA standard.
Silicon sealant for longitudinal & transverse joints as per specification.
Diffusers & grilles shall be powder coated as per color approved by Architect.
| SUB-TOTAL |  |  |  |  | 321925 |  |  | 278775 |  |  | 278775 |  |  | 0 |  |  | -43150
3 | THERMAL & ACOUSTIC INSULATION:
3.1 | THERMAL INSULATION FOR KITCHEN VENTILATION DUCTS
| SITC of Glass Fibre Blanket Insulation material bonded with Thrmosetting Resin, with factory applied laminated aluminium foil of 22 micrns with fibre glass backing. Further, wire mesh along with 7 mil cloth shall be applied on above the insulation with proper adhersive. Nominal density : 32 Kg/CuM. Thermal conductivity, < 0.033 W/m.K at 24 degreeC. All Insuation material and adhesives shall be as per Class I for surface spread and in accordance with BS 476, & Class O for non-combustible grade. | Sq.mtr | 155 | 750 | 150 | 139500 | 330.67 | 900 | 297603 | 330.67 | 900 | 297603 | 0 | 900 | 0 | 175.67 | 900 | 158103
Make: Armaflex & K-flex
Note:
a. | Insulation work to be coordinated with other agencies and repair to be included by contractor as per site requirement.
b. | Vendors to take care of the installation, if any damages takes place the vendor to repair or replace and hand over to clients in good and acceptable condition.
c. | Thermal insulation shall be internal for Elliptical / Expossed ducting.
| SUB-TOTAL |  |  |  |  | 139500 | 0 |  | 297603 |  |  | 297603 |  |  | 0 |  |  | 158103
4 | ELECTRICAL WORKS:
4.1 | STARTER PANEL
SITC of indoor / outdoor, wall mounting type DOL / Delta 3PH, 415V AC MOTOR STARTERS with VFD in CRCA Sheet Steel enclosure with necssary supporting brackets and required accessories, etc., The Enclosure shall be provided with knockouts suitable for cable termination at TOP & BOTTOM for incoming and outgoing power cables of A2XFY type and size specified. The starters shall be complete with suitable MPCB/MCCB, Contactor, Bi-metal O/L relay with SPP, ON/OFF Push buttons, on / off / trip indication Lamp, on off push button, & phase indication Lamp. Selection of relay, contractor, MPCB/MCCB etc. as per Type-2 Coordination. Starter panel shall be BMS compatible. Variable frequency drives shall be provided with necessary sensors and controllers complete with control wiring in all respect as required. VFDs shall be provided with necessary bypass arrangement inside electrical starter panels with IP-55 enclosure.
a | Suitable for Star Delta Panel with VFD
| 10700 CFM Exhaust fan | No. | 1 | 35000 | 3000 | 38000 | 1 | 38000 | 38000 | 1 | 38000 | 38000 | 0 | 38000 | 0 | 0 | 38000 | 0
| 9500 CFM Fresh Air Fan | No. | 1 | 35000 | 3000 | 38000 | 1 | 38000 | 38000 | 1 | 38000 | 38000 | 0 | 38000 | 0 | 0 | 38000 | 0
4.2 | POWER CABLING
Supply, handling, laying effecting proper connections testing and commissioning of following sizes of 1.1 KV grade XLPE insulated FRLS Aluminium /Copper conductor cables laid over MS supports cable racks or fixing on walls including clamping the cable to supports in an approved manner as required complete with Copper earthing as specified for continuous earthing along with cable. All complete as required and as per final instruction as given by Owners/ Consultants and as per Technical specifications. Earthing shall be measured separately and shall be connected in two runs. Power to ELCB to be provided near each ODU by electrical contractor.
a | Suitable Power Cable:
| 10700 CFM Exhaust fan | Rmt | 10 | 300 | 100 | 4000 | 0 | [8 empty] | -10 | 400 | -4000
| 9500 CFM Fresh Air Fan | Rmt | 10 | 300 | 100 | 4000 | 0 | [8 empty] | -10 | 400 | -4000
| 5500 CFM Dry Scrubber | Rmt | 20 | 300 | 100 | 8000 | 0 | [8 empty] | -20 | 400 | -8000
b | Earthing:
| 8 SWG | Rmt | 40 | 40 | 20 | 2400 | 0 | [8 empty] | -40 | 60 | -2400
4.3 | CABLE TERMINATION :
Supply & Making of Cable termination of armoured / unarmoured cables 1.1 KV grade including installation of cable glands, cable lugs (Aluminium for A2XFY & copper for 2XFY & YY Double compression type), heat shrinkable sleeves on long ends, crimping paste etc. The work includes testing & commissioning of cables, meggaring values & submitting reports of tests. (One set includes termination of all cores of one end only). All crimping tools & dies shall be arranged by contractor.
Suitable for
0 | 10700 CFM Exhaust fan | No. | 2 | 350 | 150 | 1000 | 0 | [8 empty] | -2 | 500 | -1000
0 | 9500 CFM Fresh Air Fan | No. | 2 | 350 | 150 | 1000 | 0 | [8 empty] | -2 | 500 | -1000
4.4 | CABLE TRAYS
Supplying & Fixing of following sizes of GI cable tray duly painted perforated type of height 50mm along with necessary bends, reducers etc. anchored along the wall / suspended from the ceiling with necessary MS supports.
a | 50mm wide x 1.6mm thick | Rmt | 20 | 250 | 50 | 6000 | 0 | [8 empty] | -20 | 300 | -6000
a | 100mm wide x 1.6mm thick | Rmt | RO
| SUB-TOTAL |  |  |  |  | 102400 |  |  | 76000 |  |  | 76000 |  |  | 0 |  |  | -26400
| GRAND TOTAL |  |  |  |  | 1500325 |  |  | 1588878 |  |  | 1588878 |  |  | 0 |  |  | 88553

## VENTILATION NT
Sr no | Description | Unit | Claimed quantity | Rate | Claimed Amount | Actual Quantity | Rate | Actual Amount | Difference | Remark
1 | Spring isolator for AHU & Exhaust fan | Nos | 8 | 5500 | 44000 | 8 | 5500 | 44000 | 0 | GST Bill Required
2 | 25mm insulation for kitchen duct | Sqmt | #REF! |  | #REF! |  |  | 0 | #REF!
| Total |  |  |  | 44000 |  |  | 44000 | 0

## FIRE SPRINKLER
COPPWER CHIMNEY -WAKAD
BOQ FOR FIRE FIGHTING SYSTEMS |  |  |  | Vart Infra |  | Target Amount |  | Vart Infra final
|  | BOQ | [7 empty] | Claimed |  |  | Approved / Audited |  |  | From BOQ |  |  | From Claimed
S/NO | DESCRIPTION | QUANTITY | UNIT | Rate | Amount | Rate | Amount | Rate | Amount | Claimed quantity | Rate | Claimed Amount | Actual Quantity | Rate | Actual Amount | Difference in Qty | Rate | Difference In Amount | Difference in Qty | Rate | Difference In Amount
1 | Providing, laying, jointing, testing and commissioning of G.I. `C' Class pipes (IS:1239 (Part-I)-1979) including cutting,threading welding etc providing all malleable galvanized iron fittings conforming to IS 1879, viz. Flanges, bends, tees, elbows,reducers, unions, supporting with G. I. clamps, hangers, M.S. brackets etc. including cutting holes and chases in brick or RCC wall / slabs and making good the same to the Approval of Architect / consultant,complete including painting with one coat of primer and two or more coats of synthetic enamel paint of approved make and shade. ( Note- Rigid/flexible pipe extension from existing line is considered)
i) | 25 mm dia. | 65 | RMT | 950 | 61750 | 750 | 48750 | 770 | 50050 | 64.7 | 770 | 49819 | 62.7 | 770 | 48279 | -2.3 | 770 | -1771 | -2 | 770 | -1540
ii) | 32 mm dia. | 8 | RMT | 1050 | 8400 | 950 | 7600 | 850 | 6800 | 7.1 | 850 | 6035 | 6.65 | 850 | 5652.5 | -1.35 | 850 | -1147.5 | -0.45 | 850 | -382.5
iii) | 40 mm dia. | 5 | RMT | 1150 | 5750 | 1150 | 5750 | 950 | 4750 |  | 950 | 0 |  | 950 | 0 | -5 | 950 | -4750 | 0 | 950 | 0
iv) | 50 mm dia. | 5 | RMT | 1500 | 7500 | 1450 | 7250 | 1250 | 6250 | 3.5 | 1250 | 4375 | 3 | 1250 | 3750 | -2 | 1250 | -2500 | -0.5 | 1250 | -625
v) | 65 mm dia. | 10 | RMT | 1850 | 18500 | 1650 | 16500 | 1550 | 15500 | 10.1 | 1550 | 15655 | 9.1 | 1550 | 14105 | -0.9 | 1550 | -1395 | -1 | 1550 | -1550
vi) | 80 mm dia. | 15 | RMT | 2500 | 37500 | 2050 | 30750 | 1950 | 29250 | 15.9 | 1950 | 31005 | 15.4 | 1950 | 30030 | 0.4 | 1950 | 780 | -0.5 | 1950 | -975
vii) | 100 mm dia. | 0 | RMT | 2800 |  |  |  | 2800 |  | 5.9 | 2800 | 16520 | 5 | 2800 | 14000 | 5 | 2800 | 14000 | -0.9 | 2800 | -2520
0
2 | Providing , fixing testing and commissioning of pendant type sprinkler heads 68 deg. Temp.(Quick response type) | 0 | No. | 850 | [5 empty] | 9 | 0 | 0 | 8 | 0 | 0 |  | 0 | 0 |  | 0
0
3 | Providing , fixing testing and commissioning of concealed type sprinkler heads 68 deg. Temp.(Quick response type) | 21 | No. | 3050 | 64050 | 2050 | 43050 | 2300 | 48300 | 12 | 2300 | 27600 | 12 | 2300 | 27600 | -9 | 2300 | -20700 | 0 | 2300 | 0
4 | Providing , fixing testing and commissioning of upright type sprinkler heads 68 deg. temp(Quick response type)- Optional Subject to liasion team requirements | 0 | No. | 850 | [5 empty] | 25 | 0 | 0 | 25 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
5 | Providing , fixing testing and commissioning of upright type sprinkler heads 79 deg. Temp (Quick response type) | 12 | No. | 900 | 10800 | 900 | 10800 | 750 | 9000 | [6 empty] | -12 | 750 | -9000
6 | Providing & fixing testing and commissioning of braided UL Rated SS Flexible pipe
i) | 1 MT Long | 21 | No. | 3500 | 73500 | 1850 | 38850 | 2250 | 47250 | 21 | 2250 | 47250 | 21 | 2250 | 47250 | 0 | 2250 | 0 | 0 | 2250 | 0
ii) | 1.6 MT Long | 12 | No. | 4000 | 48000 | 2250 | 27000 | 2500 | 30000 | 15 | 2500 | 37500 | 12 | 2500 | 30000 | 0 | 2500 | 0 | -3 | 2500 | -7500
7 | Gun metal chrome finished Ball valves (PN 16) with fittings of screwedend type.
I) | 40 mm dia. | R.O. | No. | 5000
I) | 32 mm dia. (Sprinkler drain-OPTIONAL) | 1 | Nos. | 4500 | 4500 | 2850 | 2850 | 3500 | 3500 | [6 empty] | -1 | 3500 | -3500
8 | Butterfly Valves (PN 16) with CI Body, Black Nitrile Body Liner and Nylon Coated SG Iron Disc with material and labour including hydraulic testing etc. complete as per drawing, specification & to the level of satisfaction of Site- Incharge.
I) | 150 mm dia. | R.O. | No. | 16000
I) | 100 mm dia. (OPTIONAL) | R.O. | No. | 13500
I) | 80 mm dia. | 0 | No. | 12000
9 | 6kg capacity ABC type dry chemical powder fire Extinguishers with wall mounting brackets | 4 | Nos. | 3000 |  | 3000 |  | 3000
10 | 6kg capacity K type fire Extinguishers with wall mounting brackets | 2 | No. | 15500 |  | 12500 |  | 12500
11 | 5kg capacity CO2 type fire Extinguishers with wall mounting brackets | 1 | No. | 6500 |  | 4500 |  | 4500
12 | 9Lit AR-AFFF type fire Extinguishers with wall mounting brackets | R.O. | Nos. | 3500
13 | Flow switch on sprinkler distribution header on each floor with 2 SPDT contacts suitably rated, capable of the high pressure system and connected to fire alarm panel through cable.
i) | 100 mm dia. | 0 | No. | 16500
14 | Ceasefire 5 Kg Ceiling Mounted Fire Extinguisher Clean Agent FE-36, Zero ODP, Stored Pressure Type, Pressure Gauge, Gross Weight 7.7 Kg, empty Weight 2.7 Kg, Can Height 264MM, Diameter 240MM,Discharge Time less than 8 Secs, Auto discharge mechanism on temperature rise, applicable on Class A,B,C and electrically started Fire, Can Construction : Deep drawn & Co2 Mig welded, Valve Construction : Forging & Machining, Internal Coating of Can : Epoxy Powder coating, External Coating of Can : Epoxy Polyster Powder coating, Sheet metal thickness : 2.0MM, Helium Leak Detection Test, 5 Years Warranty-model no 1CH21CF | 0 | No. | 35000
| SUB-TOTAL |  |  |  | 340250 |  | 239150 |  | 250650 |  |  | 235759 |  |  | 220666.5 |  |  | -29983.5 |  |  | -15092.5
Note : | Taxes Extra as applicable.

## FIRE SPRINKLER NT
COPPWER CHIMNEY -WAKAD
BOQ FOR FIRE FIGHTING SYSTEMS
S/NO | DESCRIPTION | UNIT | Claimed quantity | Rate | Claimed Amount | Actual Quantity | Rate | Actual Amount | Difference | Remark
1 | Providing , fixing testing and commissioning of pendant type sprinkler heads 79 deg. Temp.(Quick response type) | No. | 14 | 750 | 10500 | 14 | 750 | 10500 | 0
2 | Providing , fixing testing and commissioning of pendant type sprinkler heads 68 deg. Temp.(Quick response type) | No. | 9 | 710 | 6390 | 9 | 710 | 6390 | 0
3 | Supply, Installation, Testing & Commisioning Of ABC Dry Powder MAP - 50% Moduler Type Fire Extinguishet (Ceiling Mounted) conforming to IS : 15683 : 2018 finish complete. (5KG) | No. | 1 | 5250 | 5250 | 4 | 5250 | 21000 | -15750
4 | Supply, Installation, Testing & Commisioning Of 2KG Firessense Automatic Fire detection and fire fighting system consisting of | No. | 1 | 38900 | 38900 | 2 | 38900 | 77800 | -38900
Cylinder filled with F-K-5-1-12 Clean Agent GAS (UL & FM Approved)
Fitted with Direct Low Pressure Volve
Pressure guage
End of Line Adaptor
Wall bracket
5 | Commisioning of Heat Detection tube (UL & FM Approved) | No. | 50 | 950 | 47500 | 50 | 950 | 47500 | 0
6 | Supply, Installation, Testing & Commisioning Of Pressure Switch | No. | 1 | 13000 | 13000 | 1 | 13000 | 13000 | 0
7 | Supply, Installation, Testing & Commisioning Of Audio Visual Alaram System | No. | 1 | 11000 | 11000 | 1 | 11000 | 11000 | 0
8 | Supply, Installation, Testing & Commisioning Of Sprinkler, K-80 (5.6) QR, SC, 68 deg, 15mm bulb type, Chrome Finish, UL & FM Approved. | No. | 15 | 750 | 11250 | 0 | 750 | 0 | 11250
9 | Supply, Installation, Testing & Commisioning Of Concealed Sprinkler, K-5.6 (80) QR, SC, 68 deg, Pendent Chrome Finish, 15mm with cover plate white finish UL & FM Approved. | No. | 12 | 2100 | 25200 | 0 | 2100 | 0 | 25200
10 | Supply of Smart GAS Detector System. | No. | 6 | 30400 | 182400 | 6 | 30400 | 182400 | 0
MODEL NO. GT-2511-FLP-ATEX
Smart Gas Detector 3 Wire
Make: AMBETRONICS ENGINEERS PVT LTD., INDIA
For GAS LEAKAGE IN AMBIENT MONITORING
Gas to be detected-PNG
Range-0-100% LEL
Sensor Principle:- Catalytic Bead
Standard Output1 : 4-20 mA Output with users settable range
Output 2: Three SDPT Relays of rating '2A'
Output 3: Isolated RS-485 Modbus Communication
4-20mA rated at 470 ohms load driving capacity
programming can be done remote via Fieldbus
Configurable STEL and TWA Set points for Toxic Gases
11 | Supply, Installation, Testing & Commisioning of Monitor Module | No. | 6 | 6850 | 41100 | 6 | 6850 | 41100 | 0
12 | Supply, Installation, Testing & Commisioning of Relay Module | No. | 5 | 5265 | 26325 | 5 | 5265 | 26325 | 0
13 | Testing & commissioning of Smart GAS Detector System. | No. | 1 | 36000 | 36000 | 1 | 36000 | 36000 | 0
14 | Rectification charges for per sprinkler points | No. | 12 | 1050 | 12600 | 11 | 1050 | 11550 | 1050
15 | Form A Certification | Job | 1 | 30000 | 30000 | 1 | 30000 | 0 | 30000
| SUB-TOTAL |  |  |  | 497415 |  |  | 484565 | 12850
Note : | Taxes Extra as applicable.

## PHE
COPPER CHIMNEY WAKAD-PHE BOQ
|  |  |  | BOQ |  |  | Claimed |  |  | Audited |  |  | Difference from BOQ |  |  | From Claimed bill
Item No. | Description | Unit | Qty | Rate | Amount | : | Claimed quantity | Rate | Claimed Amount | Actual Quantity | Rate | Actual Amount | Difference | Rate | Difference | Difference | Rate | Difference | Remark
A | WATER SUPPLY PIPING
1 | CPVC Pipes conforming to ASTM D-2846, SDR-11 grade and CPVC solvent weld fittings like elbows, tees, couplars, brass threaded adaptors, insert ring etc. suitable for (domestic and flushing) cold applications rated, concealed piping within wall / floor including jointing with fittings using solvent cement, brass threaded end fittings for making connection to fixtures. The work shall also include chasing the walls with machine wherever required for concealed piping and making good the same after laying of pipes & necessary pressure testing Chasing finishing shall be done with 1:1 cement mixed mortar, restore the same original condition for internal and shaft piping, including necessary hot deep galvanised supports vertical / horizontal, as per direction of Site incharge direction. [The rate shall include supply of S.S.screws and nut bolts etc.chasing in walls done by machine] (For Domestic and Flushing water-Toilet internal) (Pipe shall be tested with 1.5 times working pressure as covered in specifications)
1.1 | 20 mm Dia | R.mt | 90 | 250 | 22500 |  | 79.27 | 250 | 19817.5 | 46 | 250 | 11500 | -44 | 250 | -11000 | -33.27 | 250 | -8317.5
1.2 | 25 mm Dia | R.mt | 40 | 300 | 12000 |  | 37.04 | 300 | 11112 | 37.04 | 300 | 11112 | -2.96 | 300 | -888 | 0 | 300 | 0
1.3 | 32mm Dia | R.mt | 45 | 350 | 15750 |  | 23.17 | 350 | 8109.5 | 16.7 | 350 | 5845 | -28.3 | 350 | -9905 | -6.47 | 350 | -2264.5
1.4 | 40mm Dia | R.mt | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
2 | Providing & Fixing of gun metal heavy Ball Valves-PN-16 (approved makes as covered in specification) screwed type for water system of the following diameters. Valve shall have with unions. | [5 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
2.1 | 20mm Dia | Nos. | 4 | 930 | 3720 |  | 1 | 930 | 930 | 1 | 930 | 930 | -3 | 930 | -2790 | 0 | 930 | 0
2.2 | 25mm Dia | Nos. | 2 | 1080 | 2160 |  | 4 | 1080 | 4320 | 4 | 1080 | 4320 | 2 | 1080 | 2160 | 0 | 1080 | 0
2.3 | 32mm Dia | Nos. | 1 | 1300 | 1300 |  | 2 | 1300 | 2600 | 2 | 1300 | 2600 | 1 | 1300 | 1300 | 0 | 1300 | 0
2.4 | 40mm Dia | Nos. | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
3 | Providing ,fixing, testing and commissioning capstan make Water Meter including providing & fixing matching Isolation valves ,strainer, non-return valve,complete with all necessary fittings etc screwed type(15Kgs/Sq.cm). Valve shall have with union. | [5 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
3.1 | 25 mm Dia incoming line | Nos. | RO |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
3.2 | 32 mm Dia incoming line | Nos. | 1 | 11200 | 11200 |  | 1 | 11200 | 11200 | 1 | 11200 | 11200 | 0 | 11200 | 0 | 0 | 11200 | 0
3.3 | 40 mm Dia incoming line | Nos. | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
4 | Supply, installation,testing & commissioning of Storage Type Electric Hot Water Generator of mentioned capacity, suitable for 3 KG/cm2 pressure, Wall Mounted / Floor standing type, with Auto Shut-off Thermostat, along with isoltion Valves, Air Release valve, SS flexible connections andall other std accessories | [5 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
4.1 | 5 L Capacity- | Nos. | RO |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
4.2 | 20 L Capacity | Nos. | 2 | 25000 | 50000 |  | 2 | 25000 | 50000 | 2 | 25000 | 50000 | 0 | 25000 | 0 | 0 | 25000 | 0
4.3 | 35 L Capacity- For shower | Nos. | RO |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
5 | Supply, installation,testing & commissioning of Stiebel Type Electric Hot Water Generator of mentioned capacity, suitable for 3 KG/cm2 pressure, Wall Mounted / Floor standing type, with Auto Shut-off Thermostat, along with isoltion Valves, Air Release valve, SS flexible connections andall other std accessories (Optional in pantry) | [5 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
5.1 | 3.5kw in pantry- optional | Nos. | RO |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
5.2 | 8kw | Nos. | RO |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
5.3 | 13kw-3ph- Subject to load permits | Nos. | RO |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
6 | SITC of Eco smart RO-100 with all required accessories | Nos | 1 | 0 | 0 |  | 0 | 0 |  |  | 0 |  | -1 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
7 | SITC of ACO grease trap -model Lipumobil 0.8 -Capacity -48 lit ( 0.8 LPS) with all required accessories ( Order shall be placed as per space available below the counter) | Nos | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
8 | SITC of ACO grease trap -model Lipumobil S -Capacity -32 lit ( 0.5 LPS) with all required accessories | Nos | 1 | 75800 | 75800 |  | 0 | 75800 | 0 | 0 | 75800 | 0 | -1 | 75800 | -75800 | 0 | 75800 | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
A | SUB TOTAL OF A | [5 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
B | DRAINAGE | [5 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
1 | uPVC-SWR pipes conforming to IS 13592/92 including fittings conforming to IS-14935/99 and agri type pipes above 100 mm dia. conforming to IS: 4985, cutting the pipes to required lengths, laying in the position to required grade and level, jointing, supporting with PVC cleat,hot deep galvanised bracket supports,hot deep galvanised nut-bolts, anchor fastners, PVC coated U-clamp, testing and rectifying leakages for piping within vertical shafts / supported on wall / hung below slab etc. with all material & labor complete and as directed. [The Rate shall include supply and fixing of hotdip galvanised bracket nut bolts/ PVC Coated U-Clamp and screws] Vertical line bracket shall be fixed at every 0.8 mtr to 1.00 mtr.] (For Waste, Vent -Internal and vertical shaft ). | [5 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
1.1 | 40mm Dia | R.mt | 10 | 350 | 3500 |  | 0 | 350 | 0 |  | 350 | 0 | -10 | 350 | -3500 | 0 | 350 | 0
1.2 | 50mm Dia | R.mt | 5 | 500 | 2500 |  | 7.32 | 500 | 3660 | 10 | 500 | 5000 | 5 | 500 | 2500 | 2.68 | 500 | 1340
1.3 | 65mm Dia | R.mt | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
1.4 | 75mm Dia | R.mt | 20 | 800 | 16000 |  | 10.67 | 800 | 8536 | 17 | 800 | 13600 | -3 | 800 | -2400 | 6.33 | 800 | 5064
1.5 | 100 mm Dia | R.mt | 40 | 1050 | 42000 |  | 29.73 | 1050 | 31216.5 | 29.73 | 1050 | 31216.5 | -10.27 | 1050 | -10783.5 | 0 | 1050 | 0
1.6 | 150 mm Dia | R.mt | RO |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
2 | Supply, Install PVC Floor Trap for the following pipes including making all approved quality Solvent cement joints with material & labour etc. all complete as per direction of the engineer-in-charge. | Nos. | 4 | 750 | 3000 |  | 4 | 750 | 3000 | 4 | 750 | 3000 | 0 | 750 | 0 | 0 | 750 | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
3 | Supply, Install PVC Multi Floor Trap for the following pipes including making all approved quality Solvent cement joints with material & labour etc. all complete as per direction of the engineer-in-charge. | Nos. | 8 | 1200 | 9600 |  | 8 | 1200 | 9600 | 7 | 1200 | 8400 | -1 | 1200 | -1200 | -1 | 1200 | -1200
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
4 | Supply, Install PVC urinal Traps including fixing with necessary consumables with Circular SS Grating with anti cockroach jali Suitable for 75mm Dia outlet | Nos. | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
5 | Supply, Install PVC P- Traps including fixing with necessary consumables with Circular SS Grating with anti cockroach jali Suitable for 75mm Dia outlet | Nos. | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
| SUB TOTAL OF B | [5 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
C | SANITARY AND C. P. FITTINGS & FIXTURES | [5 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Only installation, testing and commissioning of sanitary and C.P. fittings | [5 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
1.1 | EWC with seat cover | Nos | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
1.2 | Concealed flush tank | Nos | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
1.3 | Concealed flush valve | Nos | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
1.4 | Health Faucet | Nos | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
1.5 | 2 Way Bib-Cock with connection for Health Faucet | Nos | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
1.6 | Bided | Nos | R.O. |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
1.7 | Under Counter Wash Basin including waste Coupling | Nos | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
1.8 | Wash Basin Cock | Nos | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
1.9 | shower and mixer | Nos | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
1.1 | Jet Spray | Nos | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
1.11 | Bath Tub including waste Coupling and nessessary connections | Nos | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
1.12 | Under Counter Sink including waste Coupling | Nos | 8 | 1500 | 12000 |  | 0 | 1500 | 0 |  | 1500 | 0 | -8 | 1500 | -12000 | 0 | 1500 | 0
1.13 | Sink Pillar Cock | Nos | 8 | 250 | 2000 |  | 0 | 250 | 0 |  | 250 | 0 | -8 | 250 | -2000 | 0 | 250 | 0
1.14 | Bottle Trap for WHB/ sink and urinal with all connecting pipes | Nos | 8 | 250 | 2000 |  | 0 | 250 | 0 |  | 250 | 0 | -8 | 250 | -2000 | 0 | 250 | 0
1.15 | Angle Cock with PVC pipe connection upto WHB/sink/Geyser connection /Ro unit | Nos | 22 | 250 | 5500 |  | 0 | 250 | 0 |  | 250 | 0 | -22 | 250 | -5500 | 0 | 250 | 0
1.16 | Urinal | Nos | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
1.17 | Auto Flush Valve & Sensor with connecting piping & spreader for urinal(DC) | Nos | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
| SUB TOTAL -C-SANITARY AND C. P. FITTINGS & FIXTURES ( ONLY INSTALLATIONS) | [5 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
D | S.S. GRATING | [5 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Only installations/ testing and commissioning of S.S.Gratings | [5 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
1 | Making chamber in brick work including internal tiling etc for S.S Grating size, 2200mm x 200mm, in 16 swg 25mm x25mm Square Pipe around the Frame and 20mmX 20mm Square pipe in center of frame with SS perforated tray (304 SWR). Complete as per architectural detail drawing & Site Engineer's instruction. | Nos. | 1 | 49500 | 49500 |  | 1 | 49500 | 49500 | 1 | 49500 | 49500 | 0 | 49500 | 0 | 0 | 49500 | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
2 | Making chamber in brick work including internal tiling etc for S.S Grating size, 1500mm x 200mm, in 16 swg 25mm x25mm Square Pipe around the Frame and 20mmX 20mm Square pipe in center of frame with SS perforated tray (304 SWR). Complete as per architectural detail drawing & Site Engineer's instruction. | Nos. | 1 | 35000 | 35000 |  | 1 | 35000 | 35000 | 1 | 35000 | 35000 | 0 | 35000 | 0 | 0 | 35000 | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
4 | Making chamber in brick work including internal tiling etc for S.S Grating size, 300mm x 300mm, in 16 swg 25mm x25mm Square Pipe around the Frame and 20mmX 20mm Square pipe in center of frame with SS perforated tray (304 SWR). Complete as per architectural detail drawing & Site Engineer's instruction. | Nos. | 9 | 9500 | 85500 |  | 9 | 9500 | 85500 | 9 | 9500 | 85500 | 0 | 9500 | 0 | 0 | 9500 | 0
[7 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
5 | Making chamber in brick work including internal tiling etc for S.S Grating size, 600mm x 300mm, in 16 swg 25mm x25mm Square Pipe around the Frame and 20mmX 20mm Square pipe in center of frame with SS perforated tray (304 SWR). Complete as per architectural detail drawing & Site Engineer's instruction. | Nos. | 2 | 18000 | 36000 |  | 2 | 18000 | 36000 | 2 | 18000 | 36000 | 0 | 18000 | 0 | 0 | 18000 | 0
SUB TOTAL -D-S.S. GRATING INSTALLATION ( ONLY INSTALLATIONS)
| GRAND - TOTAL A , B, C AND D |  |  |  | 498530 |  |  |  | 370101.5 |  |  | 364723.5 |  |  | -133806.5 |  |  | -5378
NOTES :
1. Taxes and duties shall be Extra as actual
2. Supply and installation of Sanitary fixtures and fitting in th kitchen and toilets
3. Supply of S.S. gratings in kitchen

## PHE NT
Sr no | Description | Unit | Claimed quantity | Rate | Claimed Amount | Actual Quantity | Certified Rate | Actual Amount | Difference | Remark
1 | Providing & Fixing of heavy Ball Valves
| 40mm | Nos | 8 | 1550 | 12400 | 8 | 1550 | 12400 | 0
2 | CPVC Pipes conforming to ASTM D-2846, SDR-11 grade - 40mm | Rft | 25 | 125 | 3125 | 25 | 125 | 3125 | 0
3 | Installation of grease trap | Nos | 2 | 5500 | 11000 | 2 | 2000 | 4000 | 7000 | Labour charges
4 | Connection of dish washer,Ice cube & glass washer machine with required materials | Nos | 3 | 2500 | 7500 | 3 |  | 0 | 7500 | installation done by supply vendor
5 | Supply & installation of CP Fiitings |  | 0 | 0 | 0 | 0 |  | 0 | 0
| Sink cock | Nos | 3 | 3050 | 9150 | 2 | 3050 | 6100 | 3050
| Sink mixer | Nos | 4 | 4550 | 18200 | 4 | 4550 | 18200 | 0
| Angle cock | Nos | 22 | 1600 | 35200 | 22 | 1600 | 35200 | 0
| Rinse mixer | Nos | 2 | 30500 | 61000 | 2 | 5000 | 61000 | 0 | Required bill
6 | Supply & Installation of water tank with required pipe & fiitings | Ltr | 500 | 20 | 10000 | 500 | 10 | 10000 | 0 | rate is 5
7 | Supply & Installation of booster pump with required pipe & fittings ( including PRV ) | Job | 1 | 15000 | 45000 | 1 | 45000 | 15000 | 30000 | Required bill
8 | Shifting of sink in kitchen & Bar area as per requirements | Nos | 2 | 3500 | 7000 | 2 | 2500 | 5000 | 2000
9 | Dismantaling of chamber & Drain line in bar area | Job | 1 | 5000 | 5000 | 1 | 0 | 0 | 5000 | Paid in interior works
10 | Installation of RO Machine with required pipe & fittings | Job | 1 | 18500 | 18500 | 1 | 6000 | 6000 | 12500 | agreed by vendor during audit
11 | Installation of water cooler with required pipe & Fittings | Job | 1 | 6500 | 6500 | 1 | 2000 | 2000 | 4500 | agreed by vendor during audit
12 | Supply & Installation of nahani trap jali | Nos | 11 | 1350 | 14850 | 11 | 500 | 5500 | 9350 | agreed by vendor during audit
13 | Pump for glass washer & Ice cube machine | Nos | 2 | 13000 | 26000 | 2 | 5500 | 11000 | 15000 | bill required
14 | Supply & Installation SS Waste coupling for sink | Nos | 3 | 750 | 2250 | 3 | 750 | 2250 | 0
15 | Drain work for cold room ( flexible pipe ) | Job | 1 | 3500 | 3500 | 1 | 2000 | 2000 | 1500
| Total |  |  |  | 296175 |  |  | 198775 | 97400
| Note | Shift the RO to 10 feet for long life

## MUSIC
|  |  | BOQ |  |  | Claimed |  |  | Audited
Sr no | Description | Unit | Quantity | Rate | Amount | Claimed quantity | Rate | Claimed Amount | Actual Quantity | Rate | Actual Amount | Difference from BOQ | Difference from Claimed
1 | Ceiling mounted speaker | Nos | 2 | 3500 | 7000 | 0 | [5 empty] | -7000
2 | Ceiling mounted speaker | Nos | 2 | 3500 | 7000 | 2 | 3500 | 7000 | 2 | 3500 | 7000 | 0 | 0
3 | Slab mounted speaker | Nos | 2 | 3500 | 7000 | 2 | 3500 | 7000 | 3 | 3500 | 10500 | 3500 | -3500
4 | Woofer | Nos | 2 | 5500 | 11000 | 3 | 5500 | 16500 | 2 | 5500 | 11000 | 0 | 5500
5 | 4 Zone Amplifier ( Bluetooth configure ) | Nos | 1 | 35000 | 35000 | 1 | 35000 | 35000 | 1 | 35000 | 35000 | 0 | 0
6 | Connector | Nos | 8 | 450 | 3600 | 8 | 450 | 3600 | 7 | 450 | 3150 | -450 | 450
7 | Installation charges | Nos | 1 | 10000 | 10000 | 1 | 10000 | 10000 | 1 | 10000 | 10000 | 0 | 0
| Total |  |  |  | 80600 |  |  | 79100 |  |  | 76650 | 3050 | 2450

## GAS & GLD
Comp. # : 3 | Comp. # : 3 | Comp. # : 3 | Comp. # : 3 | BOQ |  |  |  | Claimed |  |  | Audited |  |  | Difference from BOQ |  |  | Difference from Claimed
Sr No. | Item Code | Item Name | Item Description | UOM | Qty | Unit Price | Amount | Claimed quantity | Rate | Claimed Amount | Actual Quantity | Rate | Actual Amount | Difference in QTY | Rate | Difference in Amount | Difference in QTY | Rate | Difference in Amount
1 |  | Gas Pipeline Work | Gas pipeline work for Copper Chimney, MOM, Wakad, Pune | Inch | 1 |  | 128100
1 |  | M.S. Piping 40NB seamless SCH40 including fittings and supports MSL / ISMT | M.S. Piping 40NB seamless SCH40 including fittings and supports MSL / ISMT | Rft | 60 | 500 | 30000 | 98 | 500 | 49000 | 100.2 | 500 | 50100 | 40.2 | 500 | 20100 | 2.2 | 500 | 1100
2 |  | Ball valve 25NB fire safe design L T | Ball valve 25NB fire safe design L T | Nos | 1 | 4100 | 4100 | 1 | 4100 | 4100 | 1 | 4100 | 4100 | 0 | 4100 | 0 | 0 | 4100 | 0
3 |  | Pressure gauge all SS 4’ dia 3/8” btm conn with isolation valve range 0-500mbar Pioneer | Pressure gauge all SS 4’ dia 3/8” btm conn with isolation valve range 0-500mbar Pioneer | Nos | 1 | 3500 | 3500 | 3 | 3500 | 10500 | 3 | 3500 | 10500 | 2 | 3500 | 7000 | 0 | 3500 | 0
4 |  | Ball valve 40NB fire safe design L T | Ball valve 40NB fire safe design L T | Nos | 1 | 7500 | 7500 | 2 | 7500 | 15000 | 2 | 7500 | 15000 | 1 | 7500 | 7500 | 0 | 7500 | 0
5 |  | Solenoid valve 24VDC normally open manual reset with brass adapters and union Madas | Solenoid valve 24VDC normally open manual reset with brass adapters and union Madas | Nos | 1 | 17500 | 17500 | 1 | 17500 | 17500 | 1 | 17500 | 17500 | 0 | 17500 | 0 | 0 | 17500 | 0
6 |  | Ball valve ½” screwed Giacomanni (for points) | Ball valve ½” screwed Giacomanni (for points) | Nos | 4 | 900 | 3600 | 8 | 900 | 7200 | 6 | 900 | 5400 | 2 | 900 | 1800 | -2 | 900 | -1800
7 |  | Flexible hose ½” x 1.5mtr with adapters | Flexible hose ½” x 1.5mtr with adapters | Nos | 3 | 1000 | 3000 | 4 | 1000 | 4000 | 6 | 1000 | 6000 | 3 | 1000 | 3000 | 2 | 1000 | 2000
8 |  | Brass adapter 1” x LH with union | Brass adapter 1” x LH with union | Nos | 1 | 700 | 700 | 1 | 700 | 700 | 1 | 700 | 700 | 0 | 700 | 0 | 0 | 700 | 0
9 |  | Isometric drawing | Isometric drawing | Each | 1 | 7000 | 7000 | 1 | 7000 | 7000 | 1 | 7000 | 7000 | 0 | 7000 | 0 | 0 | 7000 | 0
10 |  | Labour charges for installation of the above at your site includes welding, painting and stenciling | Labour charges for installation of the above at your site includes welding, painting and stenciling | Each | 1 | 24000 | 24000 | 1 | 24000 | 24000 | 1 | 24000 | 24000 | 0 | 24000 | 0 | 0 | 24000 | 0
11 |  | Pneumatic pressure testing | Pneumatic pressure testing | Each | 1 | 10200 | 10200 | 1 | 10200 | 10200 | 1 | 10200 | 10200 | 0 | 10200 | 0 | 0 | 10200 | 0
12 |  | Third party inspection and certification as per PNGRB guideline | Third party inspection and certification as per PNGRB guideline | Each | 1 | 17000 | 17000 | 1 | 17000 | 17000 | 1 | 17000 | 17000 | 0 | 17000 | 0 | 0 | 17000 | 0
[7 empty] | 128100 |  |  | 166200 |  |  | 167500 |  |  | 39400 |  |  | 1300