## SUMMARY
| Altitude | Pioneer | Fallow
Civil | 2706168.125 | 1999455 | 2784300
Plumbing | 846591.2 | 441475 | 519575
Electrical | 1378515.81 | 1075550 | 1136105
Total | 4931275.135 | 3516480 | 4439980

## C & I
BILL OF QUANTITIES FOR CIVIL & INTERIOR WORK PROJECT : KFC_FOOD COURT @ AHEMDABAD AIRPORT
[5 empty] | DATE:-29/02/2024 |  | DATE:-29/02/2024 |  | DATE:-29/02/2024
S.NO. | ITEM NAME | ITEM SPECIFICATIONS | UNIT | QUANTITY | RATE | TOTAL | RATE | TOTAL | RATE | TOTAL
1 | DISMENTLING |  |  |  | ALTITUDE |  | PIONEER |  | FALLOW
1.1 | Existing wall and floor Dismantling | Dismantling exisiting brick wall and flooring as per the site | Job | 1 | 78375 | 78375 | 8500 | 8500 | 37500 | 37500
1.2 | Malwa Dumping | Site scrapping/debris Dumping at nearest Dumping yard as/ airport authority rate shall be including loading unloding etc | Per/Trolly | 5 | 11962.5 | 59812.5 | 3500 | 17500 | 8500 | 42500
[6 empty] | 138187.5 |  | 26000 |  | 80000
2 | ANTI TERMITE
2.1 | Anti Termite Treatment | Providing & doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3" in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4' center to center barrier all over as per manufacturer specification and ISI standards. (OR AS APPVD.) including a 1 year guarantee under suitable undertaking on stamp paper etc, complete as directed by Architect. (Mode of measurement is to be carpet area of floor and not the area of surface treated) | Sq.m | 69 | 177.375 | 12238.875 | 145 | 10005 | 250 | 17250
3 | CIVIL WORK
3.1 | 100 MM Thick ACC Siporex block work | Providing and erecting 100 mm thick ACC siporex Block work with Chemical ) in true line, level and plumb for wall compound walls, steps, complete with necessary scaffolding, raking of joints, curing etc., . Rate to include soaking of bricks adequately before construction, complete as directed and specified. (Brick of min strength 100kg./sq.cm.) rate are including all type of scaffolding and required arrangements for making brick wall. | Sq.m | 4 | 2033.625 | 8134.5 | 1450 | 5800 | 2500 | 10000
3.4 | PCC Flooring | Providing and laying plain cement concrete of specified grade, 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20 mm and down gauge) as bed concrete in locations as called for laid, consolidated and cured etc. complete upto maximun 75mm thickness as per specification and drawing including the cost of centering and shuttering. | Sq.m | 70 | 965 | 67550 | 1500 | 105000 | 1500 | 105000
3.5 | Water proofing | Applying and grouting a slurry coat of neat cement using 2.75 kg/sqm. of cement admixed with propeirtary water proofing compound(Davco K10 Polyurethane plus/Dr. Fixit Flexi PU 270-I)conforming to IS : 2645 over the RCC slab including cleaning the surfacebefore treatment cement morter 1:5 (1 cement : 5 coarse sand)admixed with proprietary water proofing compound conforming to IS :2645 over 20 mm thick layer of cement morter of mix 1:5 ( 1 cement : 5coarse sand) admixed with proprietary water proofing compound conforming to IS : 2645 to required slope and treating similary the adjoining walls upto 300 mm height including rounding of junctions of walls and slabs.Finishing the surface with 20 mm thick jointless cement morter of mix1:4 (1 cement : 4 coarse sand) admixed with proprietary water proofing compound conforming to IS : 2645 and finally finishing the surface with trowel with neat cement slurry and making of 300x300 mm square. | Sq.m | 80 | 643.5 | 51480 | 850 | 68000 | 1450 | 116000
|  | TOTAL |  |  |  | 127164.5 |  | 178800 |  | 231000
4 | TILE / STONE WORK
4.01 | KOTA STONE FLOORING BOH AREA | Providing & laying of 25 thk. 560mmX560mm Kota Stone flooring over a bed of 20mm thk. Cement mortar (1:4) jointed with cement slurry mixed with pigment to match the color of kota stone including hole cutting for traps etc. necessary cutting, rubbing, grinding and mirror polishing completed as per the details are provided in drawings or as directed by Architect/Engineer. | Sq.m | 69 | 1876.875 | 129504.375 | 2450 | 169050 | 1900 | 131100
4.02 | KOTA SKIRTING IN BOH AREA | Providing & fixing of 25mm thk. kota stone 4" high over a bed of 20 mm thk. Cement mortar ( 1:4 ) jointed with cement slurry mixed with pigment to match the coloure of KOTA including necessary wastage ,cutting ,grinding & polishing completed as per the details are provided in drawings or as directed by Architect/Engineer. | Rm | 70 | 598.125 | 41868.75 | 450 | 31500 | 400 | 28000
4.04 | Raised floor & Cinder filling | Providing and cinder filing to raised floor as per the drawing and instruction as per site location UPTO 250mm ht. | Sq.m | 69 | 1390.125 | 95918.625 | 1250 | 86250 | 1450 | 100050
4.05 | WALL TILES ( BOH AREA ) | P/fixing glazed ceramic (Kajaria /Johnson Make) White- (200x300mm) Wall tiles as approved, UPTO 2100mm from FFLVL. or BOFC whichever is achieveable, in kitchen over a base of 20-25mm thick plaster with cement mortar 1:3 (1 cement: 3 fine sand) as per approved pattern, setting the tiles in cement slurry, joints filled and finished neat with white cement as/spec.(Basic cost of tile Rs.22/- per sft.) | Sq.m | 110 | 1171.5 | 128865 | 1450 | 159500 | 2200 | 242000
4.06 | WALL TILES ( MOH AREA ) | Providing & Fixing of100x200mm White Bevelled Tile [JOHNSON ] in MOH Area with 12 thk base plaster cement mortar 1:4 and joined with white cement slurry mixed with pigment to match the shade of tile. The tile to be laid as per approved pattern. Completed as per design & details are provided or as directed by Architect. ( Base Rate 85/- Sq.Ft. ) | Sq.m | 15 | 2041.875 | 30628.125 | 2350 | 35250 | 2800 | 42000
4.1 | Granite Work | Providing ,cutting ,and laying 18 mm th. granite, laying over a cement motor ,bedding (1:4) as per the detail draing like thresh hold ,ledge wall top and etc Rate are included with required moulding ,shemfring and polish as per the detail drawing. | Sq.m | 6 | 5500.275 | 33001.65 | 5600 | 33600 | 1800 | 10800
|  | TOTAL |  |  |  | 459786.525 |  | 515150 |  | 553950
5 | MS WORK
5.1 | MS tubular partition | P/F Full Ht partition (75mm above bofc) with single side Framework as per dwg, of MS Box section 50x50mm ,18 gauge at a spacing of 600 mm c/c in both direction to achieve rigidity in the frame of approved sections fixed to floor/soffit/existing ceiling structure with rust-free treatment & enamel paint of colour as specified ready to recieve cladding on top. Rate inclusive of all necessary hardware, wastage, making provision for electrical points and edges with grooves, provision for fixing concealed LED lights, edge finishing as per detailed drawing. Measurement as per elevation | Sq.m | 135 | 2796.75 | 377561.25 | 1500 | 202500 | 3200 | 432000
5.4 | Framing for DMB's | Providing and fixing MS Frame work just below the false ceiling, to hang DMB's in MOH, supported by civil structure with two coats of ms primer etc, complete. | Sq.m | 3 | 7301.25 | 21903.75 | 3500 | 10500 | 3100 | 9300
|  | TOTAL |  |  |  | 399465 |  | 213000 |  | 441300
6 | WOODEN WORK
6.1 | Bison board cladding | Providing and fixing :- 12mm th. Bison board over existing MS framework, ready to take tile finish on top. Rate inculsive of all necessary hardware wastage etc complete in all respects as per drawings/details. Measurement as per elevation. | Sq.m | 220 | 1633.5 | 359370 | 1100 | 242000 | 2250 | 495000
6.2 | Fluted panels on front façade | Providing and fixing :- Fluted WPC panels, Duco painted as per approved shade and make as/elevation. Rate inculsive of all necessary hardware wastage etc complete in all respects as per drawings/details | Sq.m | 22 | 3539.25 | 77863.5 | 3200 | 70400 | 2500 | 55000
6.4 | Duco painted strips on façade | Providing and fixing :- RED Duco painted, approx. 6" wide, 19mm th. FR ply, over existing partition, as per façade/elevation. Rate inculsive of all necessary hardware wastage etc complete in all respects as per drawings/details | Sq.m | 1 | 11851.125 | 11851.125 | 3500 | 3500 | 2250 | 2250
6.6 | Door frame | Providing and fixing :- HARD Wood door frames i.e Sal wood or Equivalent 2.5"X 5"complete with grooves as specified complete polished/painted matching the laminate as specified, with all necessary hardware such as hold fasts etc. completed as per design & details given in drawing/Architect instruction. Door frames to be manufactured with horns minimum 3", 40x12mm rebate size and a temporary wooden strip to retain the shape of the frame etc.including polish of approved shade. | Rm | 15 | 2371.875 | 35578.125 | 1250 | 18750 | 1800 | 27000
6.7 | PUMP ROOM ENTRY | Flush door 38 mm thk ply finished with 1mm thk.laminate on both side & 6" high aluminum powder coated grill at bottom of door. All necessary hardware (i.e. lock, handle, hinges, latch or tower bolt, door stopper, pvc buffer etc ) to be provided. Door held on granite jamb & having open door closer. All to be completed as per the details are provided in drawings or as directed by Architect/Engineer. Door size 1'6" x 7'0" | no | 1 | 41868.75 | 41868.75 | 22000 | 22000 | 22500 | 22500
6.8 | MANAGER CABIN DOOR (WITH VISION PANEL) | Providing & Making of Flush door (38 mm thk ply) finished with 1mm thk. laminate on both side, having vision panel of size 2'-6" x 6" at eye level. All necessary hardware (i.e. lock, handle, hinges, latch or tower bolt, door stopper, door pvc buffer etc ) to be provided. (Door Size: 3'0"x7'0" Incl. Door Frame), completed as per the details are provided in drawings or as directed by Architect/Engineer. | no | 1 | 22646.25 | 22646.25 | 24000 | 24000 | 27500 | 27500
6.9 | BOH ENTRY (VISION PANEL DOOR) | Providing & Making of Flush door (38 mm thk ply) finished with 1mm thk. laminate on inner, BOH side, while outer visible face on facade to be clad with fluted WPC board, DUCO painted as per approved shade, having vision panel of size 9"x9" at eye level. All necessary hardware (i.e. lock, handle, hinges, latch or tower bolt, door stopper, door pvc buffer etc ) to be provided. (Door Size: 3'0"x7'0" Incl. Door Frame), completed as per the details are provided in drawings or as directed by Architect/Engineer. | no | 1 | 30318.75 | 30318.75 | 26000 | 26000 | 28500 | 28500
6.11 | Front Counter Portal | Providing and fixing Of front counter portal with 18 mm thick ply finished with 1mm th. Lamiante on all visible faces as per the detail drawings | Sq.m | 10 | 24585 | 245850 | 2250 | 22500 | 3600 | 36000
6.12 | Main Counter For Order and Picup | Providing & Fixing:- Of 2'-9" deep counter to order & Pick Up made from 19mm thick FR Ply with nosing in front as per detail drawing. Counter top and front fascia to be finished in white corian EM-03 with 150mm wide 3 vertical stripes of Red corian as mentioned, all internal surfaces & under counter storage finished in plain white laminate, niche for KDS, provision for cash till, wire manager etc to completed as per details & design provided or as directed by Architect. Elevation area from MOH side shall be Measured. | Sq.m | 4 | 46700.775 | 186803.1 | 38000 | 152000 | 38000 | 152000
6.14 | OVERHEAD STORAGE (MANAGERS ROOM) | P/Fof 450MM deep overhead storage unit made of 19mm thk. Commercial board.Externally Laminated with laminate of approved shade, off white enamel painted inside.Cost is inclusive of handles, foldable 19mm th. comm. board shelves,partitions etc. and polish complete. Measurement as per elevation | Sq.m | 1.5 | 14759.25 | 22138.875 | 25000 | 37500 | 25000 | 37500
6.15 | MANAGER -O.T. TABLE-LCMS | P/f Table made out of 3/4" thk.commercial board laminated with (LAM -8844 AGED SUEDE ASH FORMICA MAKE). The table to have one drawer unit and key board tray. Cost would include cost of all hardwares likeTelescopic Channels,"C" shaped brushed steel handles, ball catchers,locks etc complete with polish. Measurement as per plan | Sq.m | 1.5 | 31812 | 47718 | 18000 | 27000 | 28500 | 42750
6.16 | SOFT BOARD (MANAGERS ROOM , CREW ROOM & DELIVERY TABLE ) | Providing & fixing of Soft board for Managers Cabin with fabric of approved shade, completed as per the details are provided in drawings or as directed by Architect/Engineer. Basic rate of Fabric as Rs. 100/r.mtr. | Sq.m | 1 | 1600.5 | 1600.5 | 3200 | 3200 | 1950 | 1950
[6 empty] | 1083606.975 |  | 648850 |  | 927950
8 | FALSE CEILING/PAINTING
8.1 | Gypsum False ceiling | Providing and fixing :-in position Saint Gobain Gyproc make, Gypsum Board False Ceiling as per manufacturer's specifications and instructions with 12.5 mm thick `Gypboard' Screw-fixed to the underside Of suspended G.I. grid. G.I. grid should be Constructed and suspended from the main ceiling as per manufacturer's instructions and as per specifications using Original Co. Specified GypRock Framework Sections G.I.24 gauge The Gypboard should be fixed to G.I. grid with 25 mm long Drawali Screws. The `Gypboard ' to be used should be 12.5mm thick FireRated Saint-Gobain make Tapered edge boards. The boards should Be taped and filled from underside to give smooth, seamless ceiling. The rate should include necessary additional ceiling sections and intermediate channels openings for light fixtures, A.C. ducts, vertical drops, offsets. etc. Additional Intermediate channels should be fixed to strap hangers for additional support to prevent strap hangers from buckling/swaying at every 1200 mm. Item to be completed in all respect including necessary sleeves for ducts finishing of joints cut outs supports for A.C. grills, light fixtures, speakers etc. | Sq.m | 69 | 1287 | 88803 | 1600 | 110400 | 2400 | 165600
8.3 | Paint On BOH Ceiling | Providing & applying Of Two or more coats of roller applied premium acrylic emulsion(Asian -0765 MORNING GLORY) paint of interior grade,having VOC (Volatile Organic Compound ) content less than 50 grams/ litre of approved brand and manufacture (Asian Paints applyingTwo coats birla putty to achive smooth surface of BOH area ceiling and one coats primer and two or more coats of paint to achieve even shade and colour as per direction and satisfaction of Architect | Sq.m | 69 | 783.75 | 54078.75 | 450 | 31050 | 750 | 51750
|  | TOTAL |  |  |  | 142881.75 |  | 141450 |  | 217350
9 | MISCELLANEOUS ITEMS
9.1 | SS PARTITION | Providing and fixing of 304 grade stainless steel partition made with 20X20mm tube frame and wrapped with stainless steel sheet and completed as per the details are provided in drawings or as directed by Architect/Engineer. Rate include SS sheet and ss frame and all necessary hardware etc. | Sq.m | 5 | 2840.475 | 14202.375 | 4500 | 22500 | 9200 | 46000
9.2 | Corner Guard For BOH Area | Providing & fixing of 25mm x 25mm SS (202 Grade) Tile Guard in Stainless Steel ( Brushed surface finished 1mm thk.) complete as per approved specification, completed as per the details are provided in drawings or as directed by Architect/Engineer. | Rm | 50 | 1031.25 | 51562.5 | 850 | 42500 | 950 | 47500
9.3 | Trap Door in BOH Area | Providing & fixing Trap door to be made of 19mm BWP ply, finished with laminate or approved paint to match the shade of false ceiling. The trapdoor edges to be finished with 8mm thick teak wood lipping painted to match ceiling color. The item is inclusive of all fittings, fixtures and hardware; providing & fixing all necessary SS hinges (concealed), approved locking system, tied with safety chain, any frames, necessary support structure from the ceiling for fixing the trap door shutters, shadow gap, tools and tackles etc. Rate shall include all wastage, necessary cutting,all leads and lifts at all levels, loading and unloading, transportation and all other incidental charges, cost of materials, providing patterns,as per design, labour, etc.,complete as per specification, design & details,as per the instructions of the Architect/Engineer in charge. Refer to detail drawing | Nos | 2 | 6237 | 12474 | 6000 | 12000 | 6500 | 13000
9.4 | Key box | Providing and making key box as per the design at site | Nos | 1 | 4351.875 | 4351.875 | 3500 | 3500 | 5200 | 5200
9.6 | KICK PLATE ON DOORS | Providing and fixing stainless steel(20 gauge) kick plate on doors on both sides including all necessary screws, nails etc. complete at the bottom of each door.(8" high) | no | 2 | 7713.75 | 15427.5 | 3000 | 6000 | 1850 | 3700
9.9 | Foot rail on façade | Providing and fixing in place, 50mm dia Brushed SS foot rail, in front of façade, made 150mm high with 32mm dia brushed SS pipes fixed at regular intervals, tied to the floor with SS 50mm dia cleats, SS cover etc complete to provide rigidity to the rail, including all necessary hardware wastgae etc complete in all respects. | Rm | 6 | 3506.25 | 21037.5 | 1450 | 8700 | 1850 | 11100
10 | Corian cladding on façade | Providing and fixing of 12mm th. White corian, to match front counter specs. On façade, to be completed as per details & design given in drawing/Architect instruction. | Sq.m | 5 | 16376.25 | 81881.25 | 11000 | 55000 | 1800 | 9000
11 | MS | Total ms platform for RO plant and loft tank | KG | 800 | 177.375 | 141900 | 145 | 116000 | 225 | 180000
|  | TOTAL |  |  |  | 342837 |  | 266200 |  | 315500
|  | SUB-TOTAL |  |  |  | 2706168.125 |  | 1999455 |  | 2784300

## Plumbing
BILL OF QUANTITIES FOR PLUMBING WORK PROJECT : PROJECT : KFC_FOOD COURT @ AHEMDABAD AIRPORT
SR. NO. | MATERIAL | DESCRIPTION | UNIT | QTY. | RATE | AMOUNT |  | RATE | AMOUNT | RATE | AMOUNT | RATE | AMOUNT
[5 empty] | ALTITUDE |  | PIONEER | ALTITUDE |  | PIONEER | FALLOW | FALLOW
1 |  | WATER SUPPLY PIPES
| CPVC Pipes | Supply, laying, testing & commissioning of FOOD GRADE CPVC pipes conforming to CTS (Copper Tube Size) SDR-11 as per (is 15778 ASTM D 2846) with necessary fittings up to the size of 50 mm dia, jointing with CPVC solvent cement of medium body IPS brand or equivalent conform. (Make – SUPREME / KASTA)
1.01 |  | 15mm dia | R.M. | 20 | 218.4 | 4368 |  | 218.4 | 4368 | 550 | 11000 | 225 | 4500
1.02 |  | 20mm dia | R.M. | 45 | 333.76 | 15019.2 |  | 333.76 | 15019.2 | 650 | 29250 | 250 | 11250
| TOTAL |  |  |  | 0 | 19387.2 |  | 0 | 19387.2 |  | 40250 |  | 15750
2 |  | WATER DRAIN PIPES |  |  | 0 |  |  | 0
| PVC WASTE PIPE | PVC Plastic Pipe for Drainage (Make – SUPREME / KASTA) |  |  | 0 |  |  | 0
2.01 |  | 100mm dia | R.M. | 50 | 700 | 35000 |  | 700 | 35000 | 650 | 32500 | 450 | 22500
2.02 |  | 50mm dia | R.M. | 15 | 420 | 6300 |  | 420 | 6300 | 455 | 6825 | 225 | 3375
| TOTAL |  |  |  | 0 | 41300 |  | 0 | 41300 |  | 39325 |  | 25875
3 |  | CHAMBER & GRATING |  |  | 0 |  |  | 0
3.01 | INSPECTION CHAMBER | Supply, Laying, Testing & Commissioning of Approved SS Inspection Chamber along of Size- 300mmx300mm with SS Cover & SS Grating over it. Make Jaquar / Ozone. | Nos. | 7 | 16240 | 113680 |  | 16240 | 113680 | 7500 | 52500 | 5000 | 35000
| TOTAL |  |  |  | 0 | 113680 |  | 0 | 113680 |  | 52500 |  | 35000
4 |  | FLOOR TRAP |  |  | 0 |  |  | 0
4.01 | FLOOR TRAP | Supply, Laying, Testing & Commissioning of 100x100mm Floor Trap with Approved Make heavy duty round or Square. | Nos. | 8 | 1344 | 10752 |  | 1344 | 10752 | 1700 | 13600 | 2000 | 16000
| TOTAL |  |  |  | 0 | 10752 |  | 0 | 10752 |  | 13600 |  | 16000
5 |  | VALVE AND TAP |  |  | 0 |  |  | 0
5.01 | ANGLE VALVE | Providing & Fixing Angle Valve. | Nos. | 14 | 1512 | 21168 |  | 1512 | 21168 | 2600 | 36400 | 2000 | 28000
5.02 | LONG BODY TAP | Providing & Fixing Sink Cock. (Make – JAQUAR / OZONE) | Nos. | 12 | 2016 | 24192 |  | 2016 | 24192 | 3200 | 38400 | 3500 | 42000
5.04 | Gate Valves | Providing & Fixing CPVC Ball Valve ISI mark. (For Inlet) (Make – KITZ / ZOLOTO / AUDCO) 20mm Dia | Nos. | 2 | 952 | 1904 |  | 952 | 1904 | 1750 | 3500 | 1350 | 2700
5.05 | Single Lever Mixer | Providing and fixing 15mm C.P. Single lever wall mixer for 3 Bowl Sink. (Jaguar-Continental make.) | Nos. | 1 | 3920 | 3920 |  | 3920 | 3920 | 4200 | 4200 | 3500 | 3500
| TOTAL |  |  |  | 0 | 51184 |  | 0 | 51184 |  | 82500 |  | 76200
6 |  | ACCESSORIES |  |  | 0 |  |  | 0
6.01 | Grease Trap | Providing & Fixing of portable grease trap NGT-8,14,50 from Nugreen | Nos. | 5 | 68320 | 341600 |  | 68320 | 341600 | 22000 | 110000 | 22500 | 112500
6.03 | Bottle Trap | Providing & fixing 32mm CP finished Bottle Trap with wall flanges. (Make – JAQUAR / OZONE) | Nos. | 2 | 1960 | 3920 |  | 1960 | 3920 | 4200 | 8400 | 2000 | 4000
6.04 | S.S. GRATING | Providing & Fixingof S.S. triple layer grating for the drain as per drawings. | Nos. | 3 | 9520 |  |  | 9520 |  | 8500 |  | 2200
6.05 | Waste Coupling | Providing Waste Coupling 32mm size full thread waste coupling to be use for 3-bowl sink. (Make – JAQUAR / OZONE) | Nos. | 1 | 2800 | 2800 |  | 2800 | 2800 | 1700 | 1700 | 1250 | 1250
6.06 | GEYSER STORAGE | Geyser(Providing & fixing)RECOLD MAKE |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0
|  | 35 LTR | each | 1 | 16240 | 16240 |  | 16240 | 16240 | 3500 | 3500 | 16500 | 16500
|  | 15 LTR | each |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0
|  | 6LTR (INSTANT GEYSER) | each | 2 | 9520 | 19040 |  | 9520 | 19040 | 9500 | 19000 | 7500 | 15000
6.07 | PVC WATER TANK | Providing & Fixing of PVC water, vertical type storage tanks of the approved quality Make Sintex, including making solid supported flat base as per instruction but in masonary work, and doing all connections as required. Item also inculding the lockable system require for food safety. |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0
|  | 5000 LTR. | Each |  | 66976 | 0 |  | 66976 | 0 |  | 0 |  | 0
|  | 2000 LTR. | Each |  | 35280 | 0 |  | 35280 | 0 |  | 0 |  | 0
|  | 500 LTR | each | 1 | 9520 | 9520 | LOFT TANK placed over MS platform refer general arrangement plan | 9520 | 9520 | 5000 | 5000 | 10000 | 10000
|  | 200 ltr | each |  | 6720 | 0 |  | 6720 | 0 |  | 0 |  | 0
|  | SUB TOTAL OF WATER SUPPLY |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0
6.08 | WATER MOTOR | P/f of 1HP water motor. | No | 1 | 18816 | 18816 | For Ro Water supply | 18816 | 18816 | 13500 | 13500 | 11500 | 11500
6.09 | 03 BOWL SINK CONNECTION | Providing and fixing 3-Bowl Sink Drain outlet connection with valve & Drain pipe complete with all necessary fittings. | No | 1 | 6720 | 6720 |  | 6720 | 6720 | 3200 | 3200 | 5000 | 5000
6.1 | SINK CONNECTION | Fixing Hand Wash Sink Drain outlet connection with valve & Drain pipe complete with all necessary fittings. | No | 1 | 3360 | 3360 |  | 3360 | 3360 | 3500 | 3500 | 2500 | 2500
6.11 | SINK CONNECTION | Providing and fixing Veg. Prep. Sink Drain outlet connection with valve & Drain pipe complete with all necessary fittings. | No | 1 | 3360 | 3360 |  | 3360 | 3360 | 3500 | 3500 | 2500 | 2500
6.12 | FRESH AIR MACHINE CONNECTION | Connection of fresh air overflow. Complete in all respects. | No | 1 | 3360 | 3360 |  | 3360 | 3360 | 3500 | 3500 | 2000 | 2000
6.13 | MAIN CONNECTION with airport drain line | Making connection to existing sewer/storm water drains including excavation,cutting of manhole walls and making good the same,modifying drain channels etc.complete in all respects. A)150 to 300 mm dia connection. | No | 1 | 8400 | 8400 |  | 8400 | 8400 | 3500 | 3500 | 6000 | 6000
6.14 | PVC 50MM DIA PIPE | Providing, laying and jointing 50mm dia. PVC pipes complete (PRINCE) with PVC fittings and clamps, including cutting and making good the walls and floors, wherever necessary etc., complete. | Rm | 10 | 330.4 | 3304 |  | 330.4 | 3304 | 650 | 6500 | 250 | 2500
6.16 | Pressure Pump | 0.5 HP Crompton Make Pressure Pump | Nos | 1 | 17696 | 17696 | For Raw water supply | 17696 | 17696 | 12500 | 12500 | 9500 | 9500
6.17 | Ro Plant | 150LPH | Nos | 1 | 152152 | 152152 | As per KFC operations requirement ,placed over MS platform refer general arrangement plan | 152152 | 152152 | 16000 | 16000 | 150000 | 150000
| TOTAL |  |  |  |  | 348320 |  |  | 610288 |  | 213300 |  | 350750
| GRAND TOTAL |  |  |  |  | 584623.2 |  |  | 846591.2 |  | 441475 |  | 519575

## ELECTRICAL
KFC Food Court Ahmedabad Airport.
Schedule of quantities - Electrical Works Dated 29th Feb. 2024
The prices are to be quoted in the section mentioned below and shall include the supply, Installation, Testing and commissioning at site of all the equipments, ancillary materials as specified and all such items what so ever required to fulfill the intent and purpose as laid down in the specifications and/or drawings and shall include all taxes and duties on works contract basis.
S. No. | Description | Unit | Qty. | Rate | Amount | Rate | Amount | Rate | Amount
|  |  |  | (Rs.) | (Rs.) | (Rs.) | (Rs.) | (Rs.) | (Rs.)
|  |  |  | ATITUDE |  | PIONEER |  | FALLOW
Design, fabrication, assembling, wiring , supply , Erection , Installation , testing and commissioning of MDB Panels fabricated out of 2mm thick for structural members (Load bearing members) and 1.6mm thick for door and covers (Non load bearing members) CRCA painted sheet steel in cubicle formation with reinforcement of suitable size angle iron, channels, T irons, flats wherever necessary for large meter boards. Cable gland plates shall be provided at top and bottom both and windows for meter reading, locking arrangement (pad-lock & seal) with wiring upto KWH meter & meter to MCB shall be done by using adequately rated flexible single core copper wire. The boards shall be treated with all anticorrosive process before painting as per standards with final approved shade of powder coated as approved, 2 nos. earthing terminals shall be provided for all panels. The boards shall be suitable for 415 V, 3 phase, 4 wire, 50 Hz supply system. Boards shall be fabricated in length, height, depth etc to match with site conditions.
An approval shall be taken for each panel before manufacturing. Galvanised hardwares with zinc passivation shall be used in fabrication of boards.
Note: The following provisions shall be required to be made in the switchboard detailed below
The Switchboard shall have provision for entry of all PVCA cables from the top/bottom as required.
All live accessible parts shall be shrouded and all equipment shall be finger touch proof. The busbar insulation shall be with heat shrinkable sleeves. SMC/DMC shrouds and busbar supports shall be used.
Suitable tinned copper extension links for incoming/outgoing cables shall be provided wherever required
Control circuits includes breaker control switch, auto manual selector switch, anti pumping relay, spring charging trip indication, TIMER, control wiring, Auxiliary contactors MCB’s as required at site.
Positive isolation of all breakers.
All fault level breaking capacity indicates shall be ICS value at 415 volts (ICS = ICU = ICW = 100%).
Space Heater/ light/air filter shall be provided for each vertical compartment
Link and drops from MCCB shall be designed for full rated current of MCCB ratings at same current density as of Main Bus Bar
2 nos. GI earth strip throughout the panel.
1 | MAIN Panel
A | Incoming
1 No. 160 amps 16 kA 440 volt FP MCCB with Thermal Magnetic overcurrent and short circuit and with following
B | Metering, Indication & Protection:
a | 1 Nos. 6 Parameter Multi Function Mater with 3 Nos. Cast Resin CTs and MCBs
b | Breaker ON OFF indication Lamps
c | R-Y-B indication lamps with MCBs
d | ELR with CBCT
C | Bus Bar:
200 A, TPN Al. Bus Bar of suitable length having Current density 1Amp/sq.mm & having high conductivity electrical grade suitable to withstand symmetrical fault level of 25 kA. Neutral busbar shall be of 100% capacity.
D | Outgoings:
a | 3 No. 63 amps 4P MCB ( Type C)
b | 5 No. 25 amps 4P MCB ( Type C)
c | 7 No. 32 amps 2P MCB ( Type C)
d | 1 No. 25 amps 2P MCB ( Type C)
| Main MDB as described above | 1 | Set | 60030 | 60030 | 115000 | 115000 | 200000 | 200000
[5 empty] | 0 |  | 0 |  | 0
1.1 | DISTRIBUTION BOARDS |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
| Supply, erection, testing and commissioning of the following sheet steel clad wall recess mounting dust and vermin proof double door type distribution boards constructed from 16 SWG sheet steel IP 42 construction, finished with rust proof duly powder coated in approved shade with hinged gasketed door and housing the following complete with P.V.C. insulated copper busbars rated 200 amp with interconnections, neutral and earth bar assembly per phase, earthing terminals complete as approved by Architects. |  |  |  | 0 |  | 0 |  | 0
| Note : All MCBs in distribuition board for power circuits shall be of C curve |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
i | Type A |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
| 1-63 amp FP MCB with 3 single phase banks each comprising of 63A DP RCCB(100 mA) and 6 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 2 | Set | 6576.62 | 13153.24 | 22000 | 44000 | 24000 | 48000
[5 empty] | 0 |  | 0 |  | 0
ii | Type B |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
| 1-32 amp DP MCB + DP RCCB ( 100mA) and 12 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 1 | Set | 9418.04 | 9418.04 | 16000 | 16000 | 15000 | 15000
[5 empty] | 0 |  | 0 |  | 0
ii | Type C |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
| 1-32 amp DP MCB + DP RCCB ( 100mA) and 8 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 2 | Set | 8457.56 | 16915.12 | 15000 | 30000 | 13500 | 27000
[5 empty] | 0 |  | 0 |  | 0
iv | Type D |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
2 | Supply installation testing and commisioning 3.0 kVA online ( 1ph input and 1ph output) UPS with 15 Min power back up complete with in buit Static by pass switch , Mannual external maintenance by pass switch , Rectifiers , Sealed MF batteries etc as required | 2 | No. | 35351 | 70702 | 62000 | 124000 | 65000 | 130000
[5 empty] | 0 |  | 0 |  | 0
3 | Supply, laying, testing & commissioning of following sizes of Al/Cu. conductor 1.1 kV grade, armoured, XLPE insulated FRLS LT Cables/ Control Cables including necessary cleats, clamps etc. (Cables shall be partly laid in Pipes, O/H cable tray, on wall as required ) |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
3.1 | 3.5C – 70.0 (Al.) FRLS Armoured XLPE Cable * | 40 | Mtrs | 780.39 | 31215.6 | 650 | 26000 | 1200 | 48000
[5 empty] | 0 |  | 0 |  | 0
3.2 | 4C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 70 | Mtrs | 350.842 | 24558.94 | 550 | 38500 | 600 | 42000
3.3 | 3C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 30 | Mtrs | 170.752 | 5122.56 | 450 | 13500 | 350 | 10500
[5 empty] | 0 |  | 0 |  | 0
| * Approximate and shall be as per point of supply from Airport Panel/ Isolator |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
4 | Supply, erection, testing & commissioning of following sizes of cable end terminations with Single compression gland for 1.1 kV grade, XLPE insulated, Al/Cu Conductor cable |  |  |  | 0 |  | 0 |  | 0
4.1 | 3.5C – 70.0 (Al.) FRLS Armoured XLPE Cable *(Double Compression) | 2 | Nos. | 780.39 | 1560.78 | 1200 | 2400 | 2500 | 5000
[5 empty] | 0 |  | 0 |  | 0
4.2 | 4C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 6 | Nos. | 350.842 | 2105.052 | 750 | 4500 | 1250 | 7500
4.3 | 3C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 4 | Nos. | 170.752 | 683.008 | 750 | 3000 | 550 | 2200
[5 empty] | 0 |  | 0 |  | 0
5 | Wiring for DB Submains with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in surface/concealed MS surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and making suitable end termination with copper lugs complete as required and as below |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
5.1 | 4 x 16 sq.mm + 2 No. 6.0 Sq. mm in 40 mm dia MS Conduit | 35 | Mtrs | 1680.84 | 58829.4 | 950 | 33250 | 1250 | 43750
5.2 | 4 x 6 sq.mm + 2 No. 4.0 Sq. mm in 32 mm dia MS Conduit | 10 | Mtrs | 1093.88 | 10938.8 | 750 | 7500 | 950 | 9500
[5 empty] | 0 |  | 0 |  | 0
5.3 | 2 x 6 sq.mm + 1 No. 4 Sq. mm in 25 mm dia MS Conduit | 75 | Mtrs | 713.69 | 53526.75 | 450 | 33750 | 550 | 41250
5.4 | 2 x 4 sq.mm + 1 No. 2.5 Sq. mm in 25 mm dia MS Conduit | 280 | Mtrs | 633.65 | 177422 | 325 | 91000 | 450 | 126000
[5 empty] | 0 |  | 0 |  | 0
6 | Supplying and laying of the following earthing clamped to wall with suitable clamps saddles and fixing bolts/ in ground including the cost of digging and back filling as required and complete as required to comply with IS 3043:1987. All copper joints shall be tinned. The rates shall be inclusive of making test joints where ever required |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
6.1 | 50X6 mm GI Strip | 15 | Mtrs | 90.712 | 1360.68 | 550 | 8250 | 450 | 6750
6.2 | 25X6 mm GI Strip | 20 | Mtrs | 88.044 | 1760.88 | 400 | 8000 | 325 | 6500
[5 empty] | 0 |  | 0 |  | 0
6.3 | 25X3 mm GI Strip | 30 | Mtrs | 73.37 | 2201.1 | 350 | 10500 | 200 | 6000
6.4 | 8 SWG Copper Wire | 70 | Mtrs | 160.08 | 11205.6 | 95 | 6650 | 90 | 6300
6.5 | 8 SWG GI Wire | 100 | Mtrs | 106.72 | 10672 | 85 | 8500 | 90 | 9000
6.6 | 1 Core 6.0 Sq. Mm FRLS Green Wire | 60 | Mtrs | 113.39 | 6803.4 | 110 | 6600 | 75 | 4500
[5 empty] | 0 |  | 0 |  | 0
7 | Supply, erection, testing & commissioning of prefabricated GI Perforated type cable trays including Tees / Bends / Crossing / Reducers / Couping to be laid in cable trench, overhead on wall or hanged from ceiling complete with all accessories as required including support at every 1500mm as required |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
7.1 | 150 mm x 40 x 40 x 2 mm thick with 2 Nos. 25X3mm GI Earth Strip | 30 | Mtrs | 1534.1 | 46023 | 1150 | 34500 | 475 | 14250
7.2 | 300 mm x 40 x 40 x 2 mm thick with 2 Nos. 25X3mm GI Earth Strip | 15 | Mtrs | 1800.9 | 27013.5 | 1350 | 20250 | 675 | 10125
7.3 | 450 mm x 40 x 40 x 2 mm thick with 2 Nos. 25X3mm GI Earth Strip | 10 | Mtrs | 2067.7 | 20677 | 1650 | 16500 | 758 | 7580
[5 empty] | 0 |  | 0 |  | 0
8 | Wiring for MCB controlled normal primary light points/ Wall Point/ Floor Point with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq. mm PVC insulated copper conductor wire for loop earthing etc. complete as required. (Cost of MCB included in the item for per DB). | 4 | Pt | 4669 | 18676 | 2150 | 8600 | 1250 | 5000
[5 empty] | 0 |  | 0 |  | 0
9 | Wiring for secondary MCB controlled normal light points/ Wall Point/ Floor Point( Looped from above point) with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | 10 | Pt | 4669 | 46690 | 1550 | 15500 | 1000 | 10000
[5 empty] | 0 |  | 0 |  | 0
10 | Wiring for MCB controlled Emergency primary light points/ Wall Point/ Floor Point with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq. mm PVC insulated copper conductor wire for loop earthing etc. complete as required. (Cost of MCB included in the item for per DB). | 1 | Pt | 3335 | 3335 | 2450 | 2450 | 1850 | 1850
[5 empty] | 0 |  | 0 |  | 0
11 | Wiring for secondary MCB controlled Emergency light points/ Wall Point/ Floor Point( Looped from above point) with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | 6 | Pt | 3335 | 20010 | 1600 | 9600 | 1850 | 11100
[5 empty] | 0 |  | 0 |  | 0
12 | Wiring for a 5 pin 240 volt 6 amp single phase and neutral switch socket outlet with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / ceiling including cost of providing circuit wiring with 2.5 sq mm PVC insulated stranded copper conductor 1100 volt grade wires and including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and providing and fixing of a combined 5 pin 240 volt 6 amp socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires complete as requied( Switch and socket shall be as approved by the architect / Client) | 8 | Pt. | 7337 | 58696 | 3050 | 24400 | 950 | 7600
[5 empty] | 0 |  | 0 |  | 0
13 | Wiring same as in Item 12 above looped from an adjacent 6 amp switch socket outlet as required and providing and fixing of a modular type 5 pin 240 Volt 6 amp shuttered socket outlet and a modular type 6 amp 240 Volt single pole switch in a recessed GI boxes with internal wiring and moulded front plates complete as required. ( Switch and socket shall be as approved by the architect / Client) | 12 | Pt. | 4669 | 56028 | 1250 | 15000 | 925 | 11100
[5 empty] | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
15 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (1 outlet wired on 1 circuit) with 2.5 sq. mm PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / Ceiling including the cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including providing and fixing 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted modular type switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires and complete as requied( Switch and socket shall be as approved by the architect / Client) | 6 | Pt. | 6670 | 40020 | 3150 | 18900 | 1250 | 7500
[5 empty] | 0 |  | 0 |  | 0
16 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (1 outlet wired on 1 circuit) with 4.0 sq. mm PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / Ceiling including the cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including providing and fixing 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted modular type switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires and complete as requied( Switch and socket shall be as approved by the architect / Client) | 5 | Pt. | 7337 | 36685 | 3200 | 16000 | 1250 | 6250
[5 empty] | 0 |  | 0 |  | 0
17 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (2 outlets wired on 1 circuit) with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS), 4.0 sq mm upto the first outlet and 2.5 sq mm from first to the second outlet in 25mm dia 16 SWG MS conduit in wall / Ceiling including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases and including providing and fixing of two sets of 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted switches with moulded cover plate in a recessed GI box including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wire complete as required. (Switch/Socket Shall be as per approved sample by Architect) | 4 | Pt. | 6670 | 26680 | 3400 | 13600 | 1400 | 5600
[5 empty] | 0 |  | 0 |  | 0
18 | Wiring for primary switch board consisting of 3 Nos. 5 pin 240 volt 6 amp single phase and neutral switch socket outlets with 3 Nos. 6A switch with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS), 2.5 sq FRLS copper wire mm in 25mm dia 16 SWG MS conduit in wall / Ceiling including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases and including providing and fixing prewired switch board each consisting of 3 Nos. 5 pin 240 volt 6 amp single phase and neutral switch socket outlets with 3 Nos. 6A modular switch , safety shutters in a recessed/surface GI box including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wire complete as required. (Switch/Socket Shall be as per approved sample by Architect) Note- Conduits shall be 16 SWG MS on surface and FRLS PVC for wall concealed | 5 | Pt. | 6670 | 33350 | 3600 | 18000 | 1500 | 7500
[5 empty] | 0 |  | 0 |  | 0
19 | Supply installation testing and fixing 3 pin 16A/20A , 240V , single Phase metal Clad industrial socket outlet with 16A/20A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | 21 | Nos. | 3401.7 | 71435.7 | 3200 | 67200 | 4000 | 84000
[5 empty] | 0 |  | 0 |  | 0
20 | Supply installation testing and fixing 3 pin 25A/32A , 240V , single Phase metal Clad industrial socket outlet with 25A/32A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | 6 | Nos. | 3401.7 | 20410.2 | 3600 | 21600 | 4000 | 24000
[5 empty] | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
22 | Supply installation testing and fixing 5 pin 32A , 415V , single Phase metal Clad industrial socket outlet with 32A FP MCB and complete in all respects( Wiring Excluded from scope of this item) | 1 | Nos. | 4735.7 | 4735.7 | 3800 | 3800 | 2000 | 2000
[5 empty] | 0 |  | 0 |  | 0
23 | Supply , fixing & Laying 2.0mm Thick FRLS PVC conduits on surface or concealed complete with PVC junction boxes, cover plates, PVC bends, PVC saddles, base and other accessories all made in PVC with GI screws as required to complete the job. . |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
i | 25 mm dia FRLS PVC conduit | 30 | Mtrs | 133.4 | 4002 | 110 | 3300 | 250 | 7500
ii | 20 mm dia FRLS PVC conduit | 60 | Mtrs | 106.72 | 6403.2 | 95 | 5700 | 185 | 11100
[5 empty] | 0 |  | 0 |  | 0
24 | Supply , fixing & Laying 16 SWG MS conduits on surface or concealed complete with PVC junction boxes, cover plates, bends, saddles, base and other accessories all made in PVC with GI screws as required to complete the job. . |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
25 | Supply and Installation of following in wall mounted MS enclosure |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
i | 32A/25A FP RCBO | 2 | Nos | 5135.9 | 10271.8 | 9500 | 19000 | 2500 | 5000
ii | 32A/25A DP RCBO | 5 | Nos | 3801.9 | 19009.5 | 5000 | 25000 | 3500 | 17500
[5 empty] | 0 |  | 0 |  | 0
26 | Supply and installation of flush mounted (Enhanced Category 6T 568 A or B) outlets with 2 mm thick GI box complete including cutting, chases, fixing of GI boxes and making good. The plastic shall be high impact, flame-retardant, UL rate thermoplastic. Dust cover / blank shall be provided to protect unused faceplate openings. Termination caps and plastic cover shall be provided to protect jack wiring. |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
i | Single outlet face plate with RJ-45 Jack with information outlet | 16 | Nos. | 33.35 | 533.6 | 950 | 15200 | 800 | 12800
ii | Duplex outlet face plate with RJ-45 Jack with information outlet | 4 | Nos. | 40.02 | 160.08 | 1150 | 4600 | 1500 | 6000
[5 empty] | 0 |  | 0 |  | 0
27 | Supply,installtion testing and commisioning of Cat-6A UTP cables in existing Conduit complete as required for Telephone and Data System | 200 | Mtrs | 372.186 | 74437.2 | 135 | 27000 | 65 | 13000
[5 empty] | 0 |  | 0 |  | 0
28 | Supplying,installation and commisioning of CAT-6A patch cords 2 mtrs. | 22 | Nos | 333.5 | 7337 | 650 | 14300 | 800 | 17600
[5 empty] | 0 |  | 0 |  | 0
29 | Supplying,installation and commisioning of CAT-6A patch cords 1 mtr. | 22 | Nos | 246.79 | 5429.38 | 550 | 12100 | 450 | 9900
[5 empty] | 0 |  | 0 |  | 0
30 | Installation of following light fixtures including connections and complete in all respects |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
i | 25/15/12Watt Recessed Down Lighter | 7 | No. | 3335 | 23345 | 450 | 3150 | 1750 | 12250
ii | Signage | 2 | No. | 59800 | 119600 | 2500 | 5000 | 2500 | 5000
iii | 2X20W FTL LED | 11 | No. | 667 | 7337 | 400 | 4400 | 750 | 8250
Total For Electrical Works - INR |  |  |  |  | 1378515.81 |  | 1075550 |  | 1136105
THE ABOVE EXCLUDES THE FOLLOWING:-
1 | Equipment ( Server , Ports etc) for networking / LAN system / EPABX and Centrex system , however infrastructure like Conduits / Pipes /RJ-45 sockets have been considered
2 | Fire Alarm System
3 | Supply of light fixtures. However installation and Wiring considered

## CIVIL INTERIOR MAKE LIST
APPROVED LIST OF MAKES/BRANDS FOR CIVIL INTERIOR & PLUMBING WORKS
NOTES
1 | No deviations shall be permitted.
2 | All materials to be used shall be of first quality unless otherwise specified
3 | All sizes of materials mentioned shall be finished sizes.
4 | All materials used shall be of ISI grade wherever applicable
5 | Wherever there is a proposal to use "equivalent " makes(other than the specified makes mentioned in BOQ)the same shall be done only after the prior approval of engineer incharge.
S.NO | ITEM DESCRIPTION | MAKE
1 | ADHESIVE | FEVICOL/3M/KITCOL/VAMICOL/ARALDITE
2 | ALUMINIUM COMPOSITE PANELS(ACP) | ALUCOBOND/DUROBOND/DURABUILD
3 | ALUMINIUM SECTIONS | JINDAL
4 | BOARDS(COMMERCIAL & WATER PROOF)ALL SIZES AND THICKNESS | ISI MARK
5 | CAST IRON PIPES | NECO/BIC/BLC
6 | CEMENT (NORMAL) | ACC/AMBUJA/BIRLA/ULTRATECH/JK
7 | CEMENT BOARDS | BISON/EVEREST
8 | CERAMIC TILES | KAJARIA/BELL/SOMANY/NITCO/JOHNSON/ORIENT
9 | COREAN | DUPONT/LG/SAMSUNG
10 | DOOR CLOSERS | DORSET/GODREJ/DORMA
11 | DRAWER CHANNELS | HETTICH/HAFFELE/EBCO/INGERSOL RAND
12 | EXTERIOR PAINT ACRYLIC BASED | WETHERSHIELD,ASIAN
13 | EXTERIOR PAINT CEMENT BASED | SNOWCEM/NITCO
14 | FILM | 3M
15 | FIRE RETARDANT PAINT | FIRE TARD/PROMAT
16 | FLEXIBLE PLY ALL SIZES AND THICKNESS | ISI MARK
17 | FLOOR SPRING AND FITTINGS | OZONE/DORMA/HAFFELE
18 | FLUSH DOORS ALL SIZES | ISI MARK
19 | GALVANIZED IRON(G.I.) PIPES | TATA/JINDAL
20 | GLASS | ASAHI/MODIGAURD/SAINT GOBAIN
21 | GLASS MOSAIC TILES | BISSAZA/GLASS ITALIA
22 | GYPSUM BOARDS | SAINT GOBAIN-INDIA GYPSUM/FIRE LINE BOARD
23 | HAND DRYERS | KIMBERLEY CLERK
24 | HANDLES(AS APPROVED) | NEKI/D-LINE/DORMA
25 | HARD WOOD FOR FRAMEWORK | MIRANDI OR EQUIVALENT
26 | HIGH DENSITY FIBRE BOARD | NOVOPAN/DURATUFF
27 | HINGES | MAGNUM/GARD/UNION/DORMA/HAFFELE
28 | INTERIOR PAINT ACRYLIC,LUSTURE,ENAMEL | ICI/DULUX/NEROLAC/BERGER/ASIAN/OIKOS/ASIAN
29 | LAMINATES(AS APPROVED) | GREENLAM/FORMICA/KITLAM/VIRGO/MERINO
30 | LOCKERS/SAFE | GODREJ
31 | LOCKS (AS APPROVED) | DORSET/GODREJ
32 | MAGNETIC BALL CATCHERS | GODREJ/EBCO/INGERSOL RAND/HETTICH
33 | METAL FALSE CEILING | ARMSTRONG/LUXALON/TRACDEK/USG
34 | MINERAL FIBRE CEILING | ARMSTRONG/AMF/NITTOBO/INSULA
35 | PARTICLE BOARD | NOVOPAN/ECO BOARD
36 | PLY(COMMERCIAL & WATER PROOF) ALL SIZES AND THICKNESS | ISI MARK
37 | PPR PIPES & FITTINGS | PRINCE
38 | PRE LAMINATED PARTICLE BOARD | NOVOPAN/GREEN LAMIBOARD
39 | PVC PIPES | PRAKASH/SUPREME/PRINCE
40 | SANITORY FITTINGS | JAQUAR/MARC/AMERICAN STANDARDS
41 | SANITORY FIXTURES | CERA/HINDWARE/NEYCER/PARRYWARE/AMERICAN STANDARDS
42 | SCREWS | PHILLIPS/GKW
43 | SENSORS FOR URINAL | AOS/TECHNOCRAT/D-LINE
44 | SILICON SEALANTS | DOW CORNING
45 | SINKS | NARALI/SS UTILITIES
46 | SOAP DISH HOLDERS | JAQUAR/NEKI/MARC/AMERICAN STANDARDS/D-LINE
47 | SOAP DISPENSERS | JAQUAR/NEKI/MARC/AMERICAN STANDARDS/D-LINE
48 | SOFT BOARD | JOLLY BOARD
49 | SOUND PROOF PANELS | ANUTONE/ARMSTRONG/NITTOBO
50 | STAINLESS STEEL SHEETS | JINDAL
51 | STONE GRANITE PRESERVATIVES | DUPONT
52 | TEAK WOOD | TEAK WOOD AS PER BASIC COST
53 | TEXTURE PAINT | SPECTRUM/OIKOS
54 | TOILET PAPER HOLDER | JAQUAR/NEKI/MARC/D-LINE
55 | TOWEL RAIL
56 | TOWER BOLT/STOPPERS
57 | VENEERS(AS APPROVED) | CENTURY/GREEN/GARNET
58 | VENETIAN,VERTICAL ROLLERS | VIESTA/MAC/AEROLAX/HUNTER DOUGLAS
59 | VINYL FLOORING | ARMSTRONG/WONDER FLOOR/HANWA
60 | VITRIFIED TILES | JOHNSON/BELL/MARBONITE/EURO/ASIAN/NITCO/KAJARIA
61 | WATER PROOFING COMPOUND | DR.FIXIT/ROFFE/FOSROC/CIKO/SIKA
62 | WHITE BOARD | WHITE MARK/ALKON/ALTOP/FIXOGRAPH
63 | WHITE CEMENT | BIRLA/JK
64 | WOOD PRESERVATIVES | WOODGAURD/TERMISEAL
65 | WATER TANK | SINTEX
66 | WOODEN FLOORING | PERGO/KRONOTEX/ARMSTRONG
JAQUAR/NEKI/MARC/D-LINE
GODREJ/UNION/EBCO/DORMA/D-LINE