## Working sheet
FEBRUARY 2020
TRAVEL FOOD SERVICES
BOQ STANDARDISATION, IMPLEMENTATION AND COST CONSULTANCY |  |  |  |  | CIVIL MASONRY BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU
M&A final bill
SR. NO. | WBS | WBS Level1 | WBS Level 2 | SHORT ITEM DESCRIPTION | PARTICULARS | UOM | QTY. | Final Rate | Amount | Qty | Amount |  | Remark | DEVIATION AMOUNT | Difference Rate | Amount
[5 empty] | GENERAL NOTES | [8 empty] | Plus / Minus
4.4 | CIVIL | waterproofing | chemical water proofing system | Laying proprietary chemical water proofing system ON THE MOTHER SLAB | Providing and laying proprietary chemical water proofing system consisting of polymer modified acrylic base coating in two coats in form of slurry (total consumption of 1.5 Kg/Sqm) as approved by the PM and as directed by the approved manufacturer of waterproofing coating, with sandwiched fibre mesh and protective screed. The work shall include cleaning of surface, grouting porous surfaces including making ‘V’ grooves at junctions, cracks with non shrink crystalline base cementitious grout etc. Further including horizontal and vertical surfaces protected with 20mm screeding in 1:4 mortar (1 cement : 4 sand), finished in ready to receive Architectural finish, in correct line, level and plumb, curing, grouting, testing, etc. all complete to entire satisfaction of the PM, contractor to provide guarantee for 10 years Rs.100/- stamp paper in approved proforma. MAKE: WPM 002-AROEX ENDURA. CONTRCTING HAS TO FOLLOW THE DETAILED METHODOLOGY OF THE MANUFCATURERS INSTRUCTION. ONLY FOR WET AREA. | Sq m | 36 | 1614 | 58104 | 32.58 | 52584.12 | as certify |  | 5519.88
4.4.A | CIVIL | waterproofing | chemical water proofing system | Laying proprietary chemical water proofing system ON THE VERTICAL SURFACES UPT0 900MM HEIGHT. | Providing and laying proprietary chemical water proofing system consisting of polymer modified acrylic base coating in two coats in form of slurry (total consumption of 1.5 Kg/Sqm) as approved by the PM and as directed by the approved manufacturer of waterproofing coating, with sandwiched fibre mesh and protective screed. The work shall include cleaning of surface, grouting porous surfaces including making ‘V’ grooves at junctions, cracks with non shrink crystalline base cementitious grout etc. Further including horizontal and vertical surfaces protected with 20mm screeding in 1:4 mortar (1 cement : 4 sand), finished in ready to receive Architectural finish, in correct line, level and plumb, curing, grouting, testing, etc. all complete to entire satisfaction of the PM, contractor to provide guarantee for 10 years Rs.100/- stamp paper in approved proforma. MAKE: WPM 002-AROEX ENDURA. CONTRCTING HAS TO FOLLOW THE DETAILED METHODOLOGY OF THE MANUFCATURER"S INSTRUCTION. ONLY FOR WET AREA. | Sq m | 27.9 | 1614 | 45030.6 | 38.124 | 61532.136 | as certify |  | -16501.536
4.4.A | CIVIL | waterproofing | Block bat coba | Filling light weight block bats (50 mm thick) | Providing and filling light weight block bats 40-60mm mm thick with cement mortar mixed in ratio 1:3:6 (1 cement : 3 sand : 6 block bats) including mixing of water proofing compound 4 % by weight of cement to sunk portions of toilets, deck etc. complete to the entire satisfaction of the PM. Further surfaces shall be screeded with (1:1.5:3) cement concrete mix with 4% by weight of cement approved waterproofing compound about 20-30mm thick and finished smooth or ready to receive finish material as specified. Care shall be taken prior to filling all pipes passing through sunk portion are pressure tested by maintaining pressure for 24 hours and junctions of pipes passing through walls, slabs are well grouted and sealed. This shall be tested by ponding water for 100mm thickness and maintaining for 72 hours. FOH AREA. | Cu m | 5.55 | 5500 | 30525 | 5.2797 | 29038.1586 | as certify | 150mm rate change | 1486.8414
4.6.A | CIVIL | waterproofing | Brick bats coba | Filling brick bats coba (.... mm thick) | Providing and filling brick bats coba 150mm thick) with cement mortar mixed in ratio 1:3:6 (1 cement : 3 sand : 6 block bats) including mixing of water proofing compound 4 % by weight of cement to sunk portions of toilets, deck etc. complete to the entire satisfaction of the PM. Further surfaces shall be screeded with (1:1.5:3) cement concrete mix with 4% by weight of cement approved waterproofing compound about 20-30mm thick and finished smooth or ready to receive finish material as specified. Care shall be taken prior to filling all pipes passing through sunk portion are pressure tested by maintaining pressure for 24 hours and junctions of pipes passing through walls, slabs are well grouted and sealed. This shall be tested by ponding water for 100mm thickness and maintaining for 72 hours. WITH LIGHT WEIGHT SIPOREX BLOCK. | Cu m | 5.055 | 9500 | 48022.5 | 5.2454 | 49831.395 | as certify | 225mm hight rate change | -1808.895
4.8.2 |  |  | Water proof screed | Membrane protected by 18/20 mm thick water proof screed in CM mix ratio (1:4) | Membrane protected by 18/20mm thick water proof screed in CM mix ratio (1:4) spread over entire terrace area and finished to receive Architectural finish. Walls plastered with 12 mm thick CM 1:4. Work to include adding Polypropylene Fibermesh fibres with Microban to mortar in proportion recommended by the manufacturer with use of approved products and work carried out as per approved shop drawings, instructions and specifications of the manufacturer of product. Also include required preparation of the surface, etc. testing by pounding water for 72 hours and giving guarantee for 10 years on Rs.100/- Stamp paper in approved proforma. FOR WET AREA. | Sq m | 36 | 591 | 21276 | 35.8194 | 21169.2654 |  |  | 106.7346
[5 empty] | TOTAL OF WATERPROOFING WORK |  |  |  | 202958.1 |  | 214155.075 |  |  | -11196.975
6 |  |  |  |  | MASONRY WORK | [6 empty] | Certify qty
6.1 | CIVIL | Masonry | AAC concrete blocks | For 300mm or 200mm thick concrete block masonry | Providing and constructing 300mm /200mm thick concrete block masonry made out from AAC concrete blocks conforming to IS 2185 (Part-III) having minimum crushing strength 30 Kg/Sq. cm and maximum water absorption 10%, in cement sand mortar CM 1:5 (1 cement : 5 sand) mixed with approved non-shrinking compound as per manufacturer’s instructions complete with required raking out joints, curing, doing independent double legged scaffolding etc. as per specification at all heights, depths and leads to entire satisfaction of the PM.
6.1.1 |  |  |  | 300mm thick wall | for 300mm thick concrete block masonry | Sq. m
6.1.2 |  |  |  | 200mm thick wall | for 200mm thick concrete block masonry | Sq. m
6.2 | CIVIL | Masonry | AAC concrete blocks | 150mm or 100mm thick concrete block masonry | Providing and constructing 150mm /100mm thick concrete block masonry made out from AAC concrete blocks conforming to IS 2185 (Part-III) having minimum crushing strength 30 Kg/Sq. cm and maximum water absorption 10%, in cement mortar CM 1:4 (1 cement : 4 sand) mixed with approved non-shrinking compound as per manufacturer’s instructions, including providing RCC patli beam of 150mm x 100mm at every 1.00m C/C with 2 nos. 8 mm dia Tor bars and 6 mm dia links at 300 c/c in cement concrete of mix M 20, required formwork complete with raking out joints, curing, doing independent double legged scaffolding as per specifications etc. at all heights, depths and leads as directed by the PM to his entire satisfaction. (Patli beam is including reinforcement part of the item)
6.2.1 |  |  |  | 150mm thick wall | for 150mm thick concrete block masonry (UPTO TRUE CEILING LEVEL OF 6000MM HEIGHT) | Sq. m | 66.906 | 1614 | 107986.284 | 51.5415 | 83187.981 |  |  | 24798.303
6.2.1.A |  |  |  | 150mm thick wall | for 150mm thick concrete block masonry (UPTO 3000MM HEIGHT) | Sq. m | 5.55 | 1500 | 8325 | 6.138 | 9207 |  |  | -882
6.2.2 |  |  |  | 100mm thick wall | for 100mm thick concrete block masonry (UPTO 1200MM HEIGHT) | Sq. m | 2.01 | 1360 | 2733.6 | 11.747 | 15975.92 | as certify |  | -13242.32
6.3 | CIVIL | Masonry | Solid concrete block masonry | 1) 200mm/150mm/100mm thick solid concrete block masonry | Providing and constructing 200mm/150mm/100mm thick solid concrete block masonry in superstructure with approved factory made blocks having minimum crushing strength 100 Kg/Sq. cm and maximum water absorption 10%, in cement mortar mix ratio CM 1:5 (1 cement: 5 Sand) mixed with approved non-shrinking compound, doing masonry in specified courses, complete with raking out joints, curing, doing independent double legged scaffolding, complete as per specifications etc. at all heights, depths and leads and as directed by PM to his entire satisfaction. | [5 empty] | 0 |  |  | 0
6.3.1 |  |  |  | 200mm thick wall | 200mm thick solid concrete block masonry in CM 1:5 | Sq. m |  |  |  |  | 0 |  |  | 0
6.3.2 |  |  |  | 150mm thick wall | 150mm thick solid concrete block masonry in CM 1:4 | Sq. m |  |  |  |  | 0 |  |  | 0
6.3.3 |  |  |  | 100mm thick wall | 100mm thick solid concrete block masonry in CM 1:4 | Sq. m |  |  |  |  | 0 |  |  | 0
6.4 | CIVIL | Masonry | Bricks Masonry | 1) 230mm or more/half brick (115mm) thick masonry | Providing and constructing 230mm or more/115mm thick masonry with locally available approved quality bricks having minimum crushing strength 35 Kg/Sq. cm and water absorption maximum 20% in cement sand mortar CM 1:6 (1 cement : 6 Sand) mixed with approved non-shrinking compound as per manufacturer’s instruction in specified courses of approved bond and including raking out joints, curing, doing independent double legged scaffolding, all complete as per specifications etc. at all heights, depths and leads, dewatering area where required complete as per specifications etc. all as directed by PM to his entire satisfaction. | [5 empty] | 0 |  |  | 0
6.4.1 |  |  |  | 230mm or more thick wall | 230mm or more thick masonry in CM 1:6 (1 cement : 6 Sand) | Sq. m |  |  |  |  | 0 |  |  | 0
6.4.2 |  |  |  | 115mm thick wall | half brick (115mm thick) masonry in CM 1:4 (1 cement : 4 Sand) | Sq. m |  |  |  |  | 0 |  |  | 0
6.5.1 | CIVIL | Masonry | Rubble masonry | Random Rubble masonry | Providing and constructing Random Rubble masonry using cement mortar (1:4), including providing Header stones / Bond stones for every 0.50 Sq.m of masonry surface, corner stones/ quoin stones at corners not less than 0.03 Cum., hammer dressing on face, sides and bed with bushing on the exposed face not more than 20mm and face joints not more than 20mm, erecting and removal of scaffolding, raking out joints, flush pointing in CM (1:4), cleaning, wetting, filling with mortar, watering and providing weep holes as directed by PM etc. Complete to entire satisfaction of the PM. | Cu m |  |  |  |  | 0 |  |  | 0
6.5.2 | Civil | Masonry | Rubble masonry | Uncoursed Rubble masonry | Providing and laying Uncoursed Rubble masonry of trap / granite / quartzite / gneiss stones in foundations, plinth, superstructure in 1:6 cement mortar including raking out joints, staging, scaffolding and curing, etc. complete as directed by Engineer-In-Charge. | Cum |  |  |  |  | 0 |  |  | 0
6.6 | CIVIL | Masonry | Solid concrete block masonry | Bund wall with concrete block masonry | Providing and constructing 200mm thick solid concrete block masonry as Bund wall upto height of 450mm with approved factory made blocks having minimum crushing strength 100 Kg/Sq. cm and maximum water absorption 10%, in cement mortar mix ratio CM 1:5 (1 cement: 5 Sand) mixed with approved non-shrinking compound, doing masonry in specified courses, complete with raking out joints, curing, complete as per specifications etc. at all depths and leads and as directed by PM to his entire satisfaction. [ cement consumption= 0.12 Bag / Sqm ] | Sq. m |  |  |  |  | 0 |  |  | 0
6.7 | Civil | Masonry | Chamber | Brick masonry chamber | Providing and constructing Brick masonry chambers with C.M. 1:4, 600mm heavy duty D.I. cover each including necessary scaffolding, finishing, curing etc. complete. with good quality bricks as directed by Engineer-In-Charge. | [5 empty] | 0 |  |  | 0
6.7.3 |  |  |  |  | 700 x 400 x 150mm D avg. depth(for effluent drain) | Nos. | 1 | 16000 | 16000 | 2 | 32000 |  | discuss sir | -16000
6.7.4 |  |  |  |  | 400 x 400 x 150mm D avg. depth(for effluent drain) | Nos. | 5 | 11000 | 55000 | 4 | 44000 |  | discuss sir | 11000
7 |  |  |  |  | PLASTERING WORK | [5 empty] | 0 |  |  | 0
7.1 | CIVIL | Plaster | Plaster by premix mortar | 12mm thick plaster with premix mortar | Providing and applying 12mm thick plaster with premix mortar mix of ratio CM 1:4 (1 cement : 4 sand) with air entraining agent Cebex 112, 150ml per bag of cement, to internal surfaces of concrete and masonry work; including raking out joints, hacking concrete surfaces and applying approved chemical bonding agent for receiving cement finished / dash coat plaster and applying a scratch coat over concrete surfaces by bonding / adhesive chemical coat as directed by approved manufacturer to create a key, cleaning / grooving deep junctions of concrete & masonry, grouting then back by mortar mixed with non shrinking compound along with packing of clean, fresh square cut aggregate; also providing and fixing 20 gauge PVC mesh @ 150 mm wide to junctions of concrete and masonry, preparing jambs, sills, grooves, pattas, wattas, rounding of corners, all complete as per architectural drawings, specifications and finished smooth with wooden rundha or as specified by the PM at all leads, depth and lifts, doing independent double-legged scaffolding, cleaning of surfaces, curing, complete as per specification and to the approval of the PM. (Location : Vertical wall / partition wall of any type) | Sq m |  |  |  |  | 0 |  |  | 0
7.1.A |  |  |  |  | FOR THE BOTH SIDES OF NEW CONSTRUCTED BLOCK MASONRY UPTO 4300MM HEIGHT. | Sq. m | 91.091 | 914 | 83257.174 | 189.559 | 173256.926 | as certify |  | -89999.752
7.1.B |  |  |  |  | FOR THE BOTH SIDES OF NEW CONSTRUCTED BLOCK MASONRY UPTO 3000MM HEIGHT. | Sq. m | 11.1 | 914 | 10145.4 |  | 0 |  |  | 10145.4
7.1.C |  |  |  |  | FOR THE BOTH SIDES OF NEW CONSTRUCTED BLOCK MASONRY UPTO 1200MM HEIGHT. | Sq. m | 4.02 | 914 | 3674.28 |  | 0 |  |  | 3674.28
7.1.D |  |  |  |  | FOR THE ONE SIDE OF EXISING BLOCK MASONRY / COLUMNS UPTO 4300MM HEIGHT. | Sq. m | 132.44 | 914 | 121050.16 |  | 0 |  |  | 121050.16
7.1.E |  |  |  |  | FOR THE ONE SIDE OF EXISING BLOCK MASONRY / COLUMNS UPTO 3000MM HEIGHT. | Sq. m | 51.9 | 914 | 47436.6 |  | 0 |  |  | 47436.6
7.1.1 |  | common Plaster | Plaster by Ready mix cement mortar | 12mm thick plaster with Ready mix cement mortar | Providing and applying 12mm thick plaster with Ready mix cement mortar mix of CM 1:4 (1 cement : 4 sand) with air entraining agent Cebex 112, 150ml per bag of cement, to internal surfaces of concrete work; including hacking concrete surfaces then applying approved chemical bonding agent and applying a scratch coat over concrete surfaces by bonding / adhesive chemical coat as directed by approved manufacturer to create a key, cleaning / grooving deep junctions of concrete & masonry, grouting then back by mortar mixed with non shrinking compound along with packing of clean, fresh square cut aggregate, preparing grooves, pattas, wattas, rounding of corners, all complete as per architectural drawings, specifications and finished smooth with wooden rundha or as specified; at all leads, depth and lifts, doing independent double-legged scaffolding, cleaning of surfaces, curing, complete as per specification and to the approval of the PM. | Sq m | [7 empty] | 0
7.2 | CIVIL | Plaster | Gypsum plaster | Gypsum plaster to internal walls and ceilings | Providing, preparing and plastering readymade proprietary Gypsum plaster to internal walls and ceilings average 12mm thick, wall surfaces of concrete, masonry work, including doing jambs, sills, grooves, wattas, rounding of corners etc. all complete as per architectural drawing, specification and directed by PM, at all lift, lead and depth, doing independent double legged scaffolding, making gypsum plaster mix as per approved manufacturer’s instruction, providing and fixing 20 gauge GI chicken mesh 150 mm wide to junctions of concrete and masonry, hacking closely concrete surfaces, apply chemical adhesive coating on concrete surfaces and apply scratch coat plaster etc. complete as approved by PM. Plastering shall be to correct line, levels and plumb including curing, cleaning etc. complete to entire satisfaction of PM. | Sq m | [7 empty] | 0
7.3 | CIVIL | Plaster | Gypsum plaster | Gypsum plaster to walls / ceilings of ducts and inside the boxing masonry | - Do - as per Item No. 8.2 but to walls / ceilings of ducts and inside the boxing masonry including adding approved waterproofing compound 2% by weight of cement or as directed by the PM to his entire satisfaction. | Sq m | [7 empty] | 0
7.4 | CIVIL | Plaster | Double coat cement sand plaster | 25 mm thick double coat cement sand plaster | Providing and applying minimum 25 mm thick double coat cement sand plaster; first coat to be 15 mm thick Ready mix cement sand mortar of mix ratio CM 1:4 (1 cement : 4 sand) including adding 2% by weight of cement approved waterproofing compound of approved manufacturer, second coat to be 10 mm thick Ready mix cement sand mortar of mix ratio CM 1:3 (1 cement : 3 sand), finished sand face or as required to receive specified architectural external finish to correct line, plumb and level to external faces of walls, soffits/ceiling if any, including hacking concrete surfaces then applying chemical adhesive coating and a scratch/dash coat as a positive bond, curing the same, racking out junctions of masonry and concrete, then pointing and grouting using non-shrinking compound, joints grouted by pressing square crushed stone, further providing 150mm wide 20 gauge GI chicken mesh at junctions of concrete and masonry work, doing independent double legged scaffolding; at all levels and locations and leads. Item also include plastering to window sills, RCC cornices, making wattas, drip-moulds, pattas, grooves, doing curing, cleaning, all complete to the approval of the PM. (To External Surfaces) | Sq. m | [7 empty] | 0
7.5 | CIVIL | Plaster | Skimming plaster | Skimming plaster of approved make to internal dry wall surfaces. | Providing and applying Skimming plaster of approved make to internal dry wall surfaces as specified by the PM at all leads, depth and lifts, doing independent double-legged scaffolding, cleaning of surfaces, curing, complete as per specification and to the approval of the PM. (Location : Plaster to Internal dry walls) | Sq. m | [7 empty] | 0
7.6 | CIVIL | Plaster | White cement based putty | White cement based putty of average thickness 1 mm | Providing and applying white cement based putty of average thickness 1 mm, of approved brand and manufacturer, over the plastered wall surface to prepare the surface even and smooth complete. | Sq. m | [7 empty] | 0
7.7 | CIVIL | Plaster | Putty | Applying of Alltek / Birla or equivalent Putty to wall surfaces | Providing and applying of Alltek / Birla or equivalent Putty to wall surfaces. Putty not to be applied on those surfaces which are getting panelled. All wall surfaces to be marked for putty work and approval taken, etc. complete. As directed by Engineer-In-Charge. | Sq. m | [7 empty] | 0
7.8 | CIVIL | Plaster | Water Proofing | 2 Coat T20MM Water proofing of Ratio 1:4 CM | Providing and applying of 2 Coat T20MM Water proofing of Ratio 1:4 CM . Having 3m and 6 m height . | Sq. m | [7 empty] | 0
7.9 | CIVIL | Plaster | POP over Cement plaster | 6 to 8mm thick POP over Cement plaster | Providing and applying of 6 to 8mm thick POP over Cement plaster, etc. complete, as directed by Engineer-In-Charge. Having 3m and 6 m height . | Sq. m | [7 empty] | 0
[5 empty] | TOTAL OF PLASTERING WORK |  |  |  | 455608.498 |  | 357627.827
9.23 | CIVIL | Flooring | Kota stone flooring | 25mm thick Kota stone flooring - BOH AREA. | laying machine cut, machine polished approved 25mm thick Kota stone flooring, stone to be machine cut, machine polished, laid in pattern and sizes as detailed in drawing or as directed by PM, bedded over cement sand mortar of mix ratio of 1:6 (1 cement : 6 sand) including cleaning and preparing the surface for bedding, spreading neat cement slurry by using minimum cement about 2 kg/ sqm prior to bedding and spreading cement paste using minimum cement about 4.5 kg/sqm over bedding, joints to be cleaned and grouted with matching colour approved quality polymer based readymade grout, curing, machine polishing, cleaning, etc. to required line, level, etc. all complete at all depths, heights and leads to the satisfaction of the PM. | Sq m | 34 | 1721 | 58514 | 32.496 | 55925.616 |  |  | 2588.384
9.27.A | CIVIL | Strip | Kota Strip in Ramp -100mm | Kota Strip in Ramp -100mm - BOH AREA. | CP128;P&L Kota Strip in Ramp,-150mm.wide Providing and fixing 20-25mm thick 150mm wide Kota stone strip in ramp, including cost of 20-30mm thick cement bedding, mirror polishing, making V-Grooves, matching colour pigments in joints etc. complete as directed by Engineer-in-charge. | Rmt | 10 | 450 | 4500 | 15.4 | 6930 | as certify |  | -2430
9.37 | CIVIL | Flooring | Vitrified tile flooring | Vitrified tile flooring | Providing and laying Vitrified tiles as specified below conforming to I.S.15622-2006 with water absorbtion less than 0.08% for flooring of an approved, quality, make and pattern /design for flooring including cement mortar bedding of 25 mm thick in 1:4 proportion, cutting, levelling, jointing, filling the joints by neat cement slurry or approved colour grout, curing, finishing etc. complete as directed by Engineer In Charge |  |  |  | 0 |  | 0 |  |  | 0
9.37.2 |  |  |  | Tile size of 600 x 600mm | Tile size of 600 x 600mm |  |  |  | 0 |  | 0 |  |  | 0
9.37.2.b |  |  |  | Printed - FOH AREA. | Anti Skid Vitrified Tile Flooring 600 x 600mm (Basic Cost INR. 2690.00/SM) | Sq m | 27.5 | 4750 | 130625 | 30.6665 | 145665.875 |  |  | -15040.875
9.37.4 |  |  |  | Tile size of 1200 x 600mm | Tile size of 600 x 600mm |  |  |  | 0 |  | 0 |  |  | 0
9.37.4,b |  |  |  | Cemented Finished - FOH AREA. | Anti Skid Vitrified Tile Flooring 1200 x 600mm (Basic Cost INR. 1345.00/SM) | Sq m | 73 | 3290 | 240170 | 73.7495 | 242635.8945 |  |  | -2465.8945
9.39 | CIVIL | Skirting | Vitrified tile Skirting, | Vitrified tile Skirting, | Providing and fixing vitrified tiles as specified below conforming to I.S. 15622-2006 of approved quality, pattern and colour for flush/projected skirting / riser including preparing the surface and levelling in the desired line, backing of 20 thk. cement mortar in proportion 1:3, square cut top edge or chamfered top edge in cement mortar 1:3,cement float, machine cutting, levelling, jointing, filling the joints with neat cement slurry or pigments mixed with cement, finishing, curing etc. complete as directed by Engineer in charge. |  |  |  | 0 |  | 0 |  |  | 0
9.39.2 |  |  |  | 10mm thick | For 10mm Thk |  |  |  | 0 |  | 0 |  |  | 0
9.39.2.e |  |  |  | Cemented Finished - FOH AREA. | antiskid / matt vitrified tiles for height up to 100mm of 10mm Thk (Basic Cost INR. 1345.00/SM) | Rmt | 41.05 | 456 | 18718.8 | 41.98 | 19142.88 |  |  | -424.08
9.41.a | CIVIL | Strips in ramps | Granite Strip | 150MM WIDE JET BLACKGRANITE STRIP-FOH AREA's Floor. | Providing and Fixing 150 mm wide granite strips on sloping portions of entrance I ramps etc. using 19mm thk prepolished jet black granite on mortar bed (CM -1:4) with neat cement paste in overlapping fashion as per drawing so as to achieve the antis kid effect and to the complete satisfaction of engineer in charge. | Rmt | 20.6 | 810 | 16686 | 35.85 | 29038.5 | as certify qty revised from 20.60 to 35.85 |  | -12352.5
9.41.b | CIVIL | Strips in ramps | Curved Granite Strip | 150MM WIDE CURVED JET BLACKGRANITE STRIP, FOH AREA'S FLOOR. | Providing and Fixing 150 mm wide granite strips on sloping portions of entrance I ramps etc. using 19mm thk prepolished jet black granite on mortar bed (CM -1:4) with neat cement paste in overlapping fashion as per drawing so as to achieve the antis kid effect and to the complete satisfaction of engineer in charge. | Rmt | 9.7 | 1000 | 9700 | 8.76 | 8760 | as certify |  | 940
9.41.c | CIVIL | Strips in ramps | Curved Granite Strip | 300MM WIDE CURVED JET BLACKGRANITE STRIP-FOH AREA at BANQUET SIDE. | Providing and Fixing 300 mm wide granite strips on sloping portions of entrance I ramps etc. using 19mm thk prepolished jet black granite on mortar bed (CM -1:4) with neat cement paste in overlapping fashion as per drawing so as to achieve the antis kid effect and to the complete satisfaction of engineer in charge. | Rmt | 12.6 | 2000 | 25200 |  | 0 |  |  | 25200
9.42 | CIVIL | Strip | Granite Slab | STN CIL 250MM JET BLACK GRANTE - AT ENTRANCE TO POS SECTION. | Providing and Fixing Stone (Type of stone and thickness of stone to be mentioned) sill (250 wide) with half round edges to RCC /Masonry surface using cement mortar 1: 4 closely jointed and pointed with matching colour grout. Rate to include cost of hand machine polishing if required. | Sq m |  | 5000 | 0 |  | 0 |  |  | 0
9.42.a | CIVIL | Strip | Granite Slab | STN CIL 200MM JET BLACK GRANTE-GLASS WINDOW AREA. | Providing and Fixing Stone (Type of stone and thickness of stone to be mentioned) sill (200 wide) with half round edges to RCC /Masonry surface using cement mortar 1: 4 closely jointed and pointed with matching colour grout. Rate to include cost of hand machine polishing if required. | Sq m | 3.3 | 4500 | 14850 | 1.848 | 8316 | as certify |  | 6534
9.42.b | CIVIL | Strip | Granite Slab | STN CIL 175MM JET BLACK GRANTE - POT WASH | Providing and Fixing Stone (Type of stone and thickness of stone to be mentioned) sill (175 wide) with half round edges to RCC /Masonry surface using cement mortar 1: 4 closely jointed and pointed with matching colour grout. Rate to include cost of hand machine polishing if required. | Sq m | 0.63 | 4200 | 2646 | 0 | 0 |  |  | 2646
9.42.c | CIVIL | Strip | Granite Slab | STN CIL 100MM JET BLACK GRANTE-GLASS WINDOW AREA. | Providing and Fixing Stone (Type of stone and thickness of stone to be mentioned) sill (100 wide) with half round edges to RCC /Masonry surface using cement mortar 1: 4 closely jointed and pointed with matching colour grout. Rate to include cost of hand machine polishing if required. | Sq m | 1.65 | 4000 | 6600 |  | 0 | as certify |  | 6600
9.55.01 | C & I | Skirting | SS Skirting | SS Rose Gold Skirting with 6mm plywood (bwr, fire rated) backing. | Providing & fixing SS Rose Gold finished skirting 100mm height & 1mm thickness with 6mm edge bending approved machine cut, as detailed in drawing and to the entire satisfaction of Engineer-In-Charge. | RMT | 41.05 | 1925 | 79021.25 | 40.661 | 78272.425 |  |  | 748.825
[5 empty] | TOTAL OF FLOORING WORK |  |  |  | 607231.05 |  | 594687.1905
10.1.01 | CIVIL | Dado | Marble stone Dado. | 19mm thick Terrazzo Marble stone Dado. Basic Cost INR.4035.00 | Laying 19mm thick machine cut, machine polished Terrazzo Marble stone Dado of approved quality, colour, shade and pattern, laid in pattern and sizes as shown in drawing. Joints to be well cleaned and grouted with matching colour approved quality polymer based readymade grout, curing, machine polishing, cleaning, protecting till handing over etc. to required line, level, etc., at all levels and locations, complete to the entire satisfaction of the PM. Back Wall of the POS Section. | Sq m | 19 | 8148 | 154812 | 17.82 | 145197.36 | certify |  | 31889.64 | 1250 | 22275
10.4 | C & I | Cladding | Vitrified Tiles | Vitrified Tile | Providing & fixing Vitrified tile dado of approved make & shade in required position including backing coat plaster in CM:1:4 including neat cement paste curing ,filling the joints with white cement & colour pigment to match the shade of cladding and cleaning etc. Complete. Light coloured glazed vitrified tiles/ Dark coloured glazed vitrified tiles/matt vitrified tiles/ Dark coloured antiskid / matt vitrified tiles. |  |  |  | 0 |  | 0
10.4.3 |  |  |  | 600mm x 600mm Off White, Kajaria make, basic cost INR. 538.00/SM. | Providing & fixing Vitrified Tiles at Back Kitchen Area up to 2700mm Height. At Back Kitchen area. | Sq m | 51.435 | 2421 | 124524.135 | 87.46 | 211740.66 |  |  | -87216.525
10.4.4 |  |  |  | 600mm x 600mm Off White, Kajaria make, basic cost INR. 538.00/SM. | Providing & fixing Vitrified Tiles at Back Kitchen Area up to 1350mm Height. At Back Kitchen area. | Sq m | 4.59 | 2421 | 11112.39 | 6.04 | 14622.84 |  |  | -3510.45
10.4.5 |  |  |  | 600mm x 600mm Light Grey, Kajaria / other approved make, basic cost INR. 1345.00/SM. | Providing & fixing Vitrified Tiles at Display Kitchen Area up to 2700mm Height. At Back Kitchen area. | Sq m | 36.45 | 3390 | 123565.5 | 25.087 | 85044.93 |  |  | 38520.57
| C & I | Wall Window | Glass Window | GLASS WINDOW 12MM TOUGHEN GLASS @ DISPLAY KITCHEN. | Providing and fixing Glass Facade made out of 12mm thick clear float, toughened glass (manufactured by AISI / Modi Guard / Sainte.Gobainorequivalent) fixed to the wooden/ RCC member at top and channel edge grooving floor as shown in the standard detailed drawing with necessary screws/ hold fasts. The glass shall be edge polished on all sides. (For the display kitchen area, Heatproof & Clear Toughened ) | Sq m | 7.3438 | 5111 | 37533.9062 | 7.32 | 37412.52 |  |  | 121.3863
10.19 | C & I | Cladding | wooden paneling | Veneer finished wooden paneling | S/I of 50mm Thk Veneer finished paneling in 12mm thk Ply, supported on aluminium frame work as per design and detailing | Sq m |  |  | 0 |  | 0 |  |  | 0
10.19.01 | C & I | Cladding | wooden paneling | Veneer finished wooden paneling | S/I of Veneer finished paneling over existing 12mm thk Ply Paneling supported on aluminium frame work as per design and detailing. Veneer finished with fire rated PU Polish. As per Elevation AA. | Sq m | 22.867 | 5100 | 116621.5776 | 22.8005 | 116282.55 |  |  | 339.0276
10.19.02 | C & I | Cladding | wooden paneling | Veneer finished wooden paneling | S/I of Veneer finished paneling over existing 12mm thk Ply Paneling supported on aluminium frame work as per design and detailing. Veneer finished with fire rated PU Polish. As per Elevation BB. | Sq m | 11.8875 | 5100 | 60626.25 | 11.875 | 60562.5 |  | not acceptable qty 5.94 | 63.75
10.19.03 | C & I | Cladding | wooden paneling | Solid wooden paneling for artist's work.. | S/I of 19mm thick (red oak / ash wood) sold wooden paneling with 12mm thk Ply backing supported on aluminium frame work / wall as per design and detailing. Wood finished with fire rated PU Polish. As per Elevation AA. 1125mm x 400mm x 5 nos. | Sq m | 2.25 | 8900 | 20025 | 2.5 | 22250 |  |  | -2225
10.23 | C & I | Finishing | wooden beading | wooden beading with paint finish | Providing and fixing of 1"x1/2" wooden beading patty screwed to wall at intervals and flat oil paint finished same as wall shade. | Rmt |  |  | 0 |  | 0 |  |  | 0
10.23.01 | C & I | Finishing | wooden beading | wooden beading with PU Polish finish | Providing and fixing of 1"x1/2" wooden (seasoned red oak / ash wood) beading patty screwed / nailed to wall at intervals and PU Polish finished same as wall shade. As per Elevation BB over Veneer Paneling. | Rmt | 62.5 | 700 | 43750 | 57.5 | 40250 | certify |  | 3500
10.23.02 | C & I | Finishing | wooden beading | wooden beading with PU Polish finish | Providing and fixing of 1"x1/2" wooden (seasoned red oak / ash wood) beading patty screwed / nailed to wall at intervals and PU Polish finished same as wall shade. On the façade paneling. | Rmt | 198 | 700 | 138600 | 358.55 | 250985 | certify |  | -112385
10.23.03 | C & I | Finishing | wooden beading | wooden beading with PU Polish finish | Providing and fixing of 4"x3/4" wooden (seasoned red oak / ash wood) beading patty screwed / nailed to wall at intervals and PU Polish finished same as wall shade. As per Elevation BB + C1C1, for glass beading. | Rmt | 16.5 | 2450 | 40425 | 16.5 | 40425 |  |  | 0
10.23.04 | C & I | Finishing | wooden beading | wooden beading with PU Polish finish | Providing and fixing of 4"x3/4" wooden (seasoned red oak / ash wood) beading patty screwed / nailed to wall at intervals and PU Polish finished same as wall shade. As per Elevation BB + C1C1, for glass beading. | Rmt | 16.9 | 2450 | 41405 | 16.7 | 40915 |  |  | 490
10.23.05 | C & I | Finishing | wooden beading | wooden beading with PU Polish finish | Providing and fixing of 2"x3/4" wooden (seasoned red oak / ash wood) beading patty screwed / nailed to wall at intervals and PU Polish finished same as wall shade. As per Elevation BB at the divider partition fascia at Open Deck Units area. | Rmt | 7.6 | 1325 | 10070 | 7.6 | 10070 |  | chk mb 3+1 | 0
| C & I | Finishing | wooden beading | wooden beading with PU Polish finish | Providing and fixing of 6"x3/4" wooden (seasoned red oak / ash wood) beading patty screwed / nailed to wall at intervals and PU Polish finished same as wall shade. As per Elevation BB at the top of the Open Deck Units area. | Rmt | 3.4 | 3400 | 11560 | 3.4 | 11560 |  |  | 0
10.23.07 | C & I | Finishing | wooden baffle panel | Linear Wooden Baffle Panel - in PU Polish finish. | Linear Wooden Baffle Panel (Birch Plywood of 25mm thick in fire rated PU Polish), with supply & installation of Vertical Linear Wooden Baffle/Rafter Panel system consist of approved shade of 25mm thick birch plywood sections of specified size 25mm thick x 22mm to 250mm height or as per drawing with a centre to centre spacing of 75mm with complete standard installation system and necessary supports as per manufacturer's specifications / site condition. The baffle units are then attached on the existing plywood backing panel as per approval of the architect & detail drawings complete in all respect. Wood Grain Finish-Design as specified in drawing and in line with Architect approved. This item is for the front facade panel. | Sq.m | 4.38 | 7000 | 30660 |  | 0 |  |  | 30660
10.28.01 | C & I | Cladding | Wall Paneling | BOX PANELNG OF 200MM THICK 19MM PLY WOOD FRAME | Providing and fixing in 200mm box wall paneling using 19mm thick ply wood framework on the wall at 600mm C/C, fixing with 12mm thick ply wood finished good to receive directly painting over the exposed surfaces etc., complete all as per drawings and as directed by Engineer-In-charge. | Sq m | 11.34 | 4600 | 52164 | 7.56 | 34776 | certify |  | 17388
10.34.01 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Wall Paneling of 37mm thick. | Aluminium section of 2"x1" framework (out of vertical members at 600 mm c/c & with horizontal members at 600 mm c/c) for wall paneling in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling paneling framework,12 mm thk FR plywood fixed to framework with flat head, full thread, sheet metal screws without any finish. As per Elevation AA, above banquet Seating up to false ceiling level. | Sq m | 39.564 | 4100 | 162212.4 | 40.32 | 165312 |  |  | -3099.6
10.34.02 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Wall Paneling of 37mm thick. | Aluminium section of 2"x1" framework (out of vertical members at 600 mm c/c & with horizontal members at 600 mm c/c) for wall paneling in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling paneling framework,12 mm thk FR plywood fixed to framework with flat head, full thread, sheet metal screws without any finish. As per Elevation BB, at glass display window wall up to false ceiling level, less glass opening area. | Sq m | 13.49 | 4100 | 55309 | 15.12 | 61992 |  |  | -6683
10.34.03 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Wall Paneling of 37mm thick. | Aluminium section of 2"x1" framework (out of vertical members at 600 mm c/c & with horizontal members at 600 mm c/c) for wall paneling in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling paneling framework,12 mm thk FR plywood fixed to framework with flat head, full thread, sheet metal screws without any finish. Facade Paneling. | Sq m | 14.985 | 4100 | 61438.5 | 56.5545 | 231873.45 |  |  | -170434.95
10.34.04 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Round Column Paneling of 37mm thick. | Aluminium section of 2"x1" framework + 19mm thick plywood framing horizontally (out of vertical members at 450 mm c/c & with horizontal members at 600 mm c/c) for round column paneling in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling paneling framework,12 mm thk FR plywood fixed to framework with flat head, full thread, sheet metal screws without any finish. As per Elevation BB, from ffl to false ceiling level. | Sq m | 11.5825 | 5500 | 63703.75 | 16.4 | 90200 |  |  | -26496.25
10.34.05 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Wall Paneling of 50mm thick with Cove Light Provision. | Aluminium section of 1.5"x1.5" framework (out of vertical members at 400 mm c/c & with horizontal members at 600 mm c/c) for wall paneling in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling paneling framework,12 mm thk FR plywood fixed to framework with flat head, full thread, sheet metal screws with another layer of 4mm thick plywood finish to get the even surfaces and edges for stucco / selected paint finish. As per Elevation DD, 482mm W x 3650mm H x 54mm D x 8 Nos. | Sq m | 14.0744 | 4850 | 68260.84 | 13.8816 | 67325.76 |  |  | 935.08
10.34.06 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Wall Paneling of 74mm thick. | Aluminium section of 2"x1" framework (out of vertical members at 600 mm c/c & with horizontal members at 600 mm c/c) for wall paneling in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling paneling framework,12 mm thk FR plywood fixed to framework with flat head on both the surfaces, full thread, sheet metal screws without any finish. As per Elevation BB, at open display unit, up to the false ceiling level, the front partition to create the niches. | Sq m | 10.417 | 4850 | 50522.45 | 10.987 | 53286.95 |  |  | -2764.5
10.34.07 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Top + Horizontal Wooden Shelve of 74mm thick. | Aluminium section of 2"x1" framework (out of vertical members at 600 mm c/c & with horizontal members at 400 mm c/c) for top / shelves in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling paneling framework,12 mm thk FR plywood fixed to framework with flat head on both the surfaces, full thread, sheet metal screws without any finish. As per Elevation BB, top and shelves above the open display unit. | Sq m | 5.94 | 5000 | 29700 | 6.408 | 32040 |  |  | -2340
10.34.08 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Partition of 50mm thick. | Aluminium section of 2"x1" framework (out of vertical members at 400 mm c/c & with horizontal members at 600 mm c/c) for top / shelves in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling partition framework,12 mm thk FR plywood fixed to framework with flat head on both the surfaces, full thread, sheet metal screws with 1mm thick laminate finish. As per Elevation BB, divider partition at the display unit area with both surfaces in laminate finish. | Sq m | 3.42 | 4900 | 16758 | 3.822 | 18727.8 |  | to be clarify | -1969.8
10.34.09 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Partition of 50mm thick. | Aluminium section of 2"x1" framework (out of vertical members at 400 mm c/c & with horizontal members at 600 mm c/c) for top / shelves in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling partition framework,12 mm thk FR plywood fixed to framework with flat head, full thread, sheet metal screws with 1mm thick laminate finish. As per Elevation BB, both the sides panel at the display unit area with one surface in laminate finish. | Sq m | 3.42 | 4900 | 16758 | 3.822 | 18727.8 |  | to be clarify | -1969.8
10.34.10 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Bulkhead of 75mm thick. | Aluminium section of 2"x1" framework (out of vertical members at 400 mm c/c & with horizontal members at 600 mm c/c) for top / shelves in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling partition framework,12 mm thk FR plywood fixed to framework with flat head, full thread, sheet metal screws with 1mm thick laminate finish. As per the front facade elevation with one surface in laminate finish. | Sq m | 5.899 | 5800 | 34214.2 | 3.24 | 18792 |  | to be clarify | 15422.2
10.58 | C & I | Cladding | Subway tile cladding | Subway tile cladding | Providing and fixing of app. Subway tile with appropriate proportion of cement and water to be align in plumb. | Sq m |  |  | 0 |  | 0 |  |  | 0
10.58.01 | C & I | Cladding | Subway tile cladding | Subway tile cladding. 75mm x 275mm, Basic Cost INR. 3120.00 | Providing and fixing of app. Subway tile with appropriate proportion of cement and water to be align in plumb. As per Elevation BB with selected & approved grouting. | Sq m | 11.38 | 5500 | 62590 | 11.38 | 62590 |  |  | 0
10.58.02 | C & I | Cladding | Subway tile cladding | Subway tile cladding over ply wood base. 75mm x 275mm, Basic Cost INR. 3120.00 | Providing and fixing of app. Subway tile with appropriate proportion of adhesive to be align in plumb over ply wood base. As per Elevation AA with selected & approved grouting. | Sq m | 16.3525 | 5500 | 89938.75 | 16.3742 | 90058.1 |  |  | -119.35
10.58.03 | C & I | Cladding | Subway tile cladding | Subway tile cladding over ply wood base. 75mm x 275mm, Basic Cost INR. 3120.00 | Providing and fixing of app. Subway tile with appropriate proportion of adhesive to be align in plumb over ply wood base. As per Elevation BB with selected & approved grouting. | Sq m | 13.6385 | 5500 | 75011.75 | 13.366 | 73513 |  |  | 1498.75
10.59.01 | C & I | Cladding | Ceramics Mosaic Tile Cladding. | Aqua Ceramic Mosaic (0.5"X0.5" on sheet)Tile Cladding on existing ply base. Basic Cost INR. 4304.00 | S/I of 3/4mm Thick Aqua Ceramic Mosaic (0.5"X0.5" on sheet)Tile Cladding on existing ply base raised flooring as per selection by client. As per Elevation BB, over the round column cladding area. | Sq m | 11.3 | 6600 | 74580 | 10.96 | 72336 | certify |  | 2244
10.64 | CIVIL | POP Punning | P&F of POP Punning | P&F of POP Punning | Providing and applying average 12 mm thk. POP mirror smooth punning to walls and existing ceiling including scraping and cleaning wherever required, to proper angle, line, level and plumb, ready to receive paint. Including protective, external corners of 20/25 SWG GI [India Gypsum or equivalent make], making all grooves, required scaffolding and protecting the surrounding areas and cleaning finished complete. | Sq m |  |  | 0 |  | 0 |  |  | 0
10.64.01 | CIVIL | POP Punning | P&F of POP Punning | P&F of POP Punning | Specifications same as above, for Elevation AA. | Sq m | 13.53 | 400 | 5412 | 15.17 | 6068 |  |  | -656
10.64.02 | CIVIL | POP Punning | P&F of POP Punning | P&F of POP Punning | Specifications same as above, for Elevation BB. | Sq m | 16.687 | 400 | 6674.8 | 7.56 | 3024 |  |  | 3650.8
10.64.03 | CIVIL | POP Punning | P&F of POP Punning | P&F of POP Punning | Specifications same as above, for Elevation CC. | Sq m | 20.5 | 400 | 8200 | 20.5 | 8200 |  |  | 0
[5 empty] | TOTAL OF CLADDING WORK |  |  |  | 1898739.1989 |  | 2196161.22
20 |  |  |  |  | COMPLETE COUNTER WORKS
20.1.01 |  | C & I | Flap door-Carpentry | Flap Door, Front Fascia with Veneer along with Corian finish. | P&F of Flap door in Curved Shape with 19mm thick plywood framing and 6mm flexible plywood cladding on it (bwr fire retardant bwr grade plywood - Archid / Kenwood make with pesticide treatment). Flap door's back of the surfaces and part of the front to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM) in 2 Hrs. fire rated PU polish. Top and rest part of the front fascia to be finished with 12mm thick Corian (ICE Queen W001 - DuPont make, basic rate INR. 10760.00/SM) with complete buffing / polish up to the mark. Includes 100mm ht. 1mm thick 304 grade SS (with selected and approved rose gold coating finished) skirting from inside. Rate including all necessary hardware fittings, heavy duty hinges, tower bolt, etc. Complete as per architectural detail drawing & site engineer's instruction. Size: 900mm L x 850mm H x 75mm thick. At the POS Area. | Nos. | 1 | 18500 | 18500 | 0.5 | 9250 |  |  | 9250
20.1.02 |  | C & I | Foldable Shutter-Carpentry | Foldable Counter Top, Top & both Fascia with Corian finish. | P&F of Foldable Counter Top in Curved Shape with 19mm thick plywood (bwr fire retardant bwr grade plywood - Archid / Kenwood make with pesticide treatment). Foldable top and both fascia with 50mm edges to be finished with 12mm thick Corian (ICE Queen W001 - DuPont make, basic rate INR. 10760.00/SM) with complete buffing / polishing up to the mark. Bottom of the surface to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM) in 2 Hrs. fire rated PU polish. Rate including all necessary hardware fittings, heavy duty hinges, tower bolt, etc. Complete as per architectural detail drawing & site engineer's instruction. Size: 900mm L x 900mm D x 50mm thick. At the POS Area. | Nos. | 1 | 31500 | 31500 | 0.5 | 15750 |  |  | 15750
20.1.03 |  | C & I | POS Counter-Carpentry | POS Counter Section with Corian Top & Fascia, fascia along with Veneer in PU Polish finish. | P&F of Curved Shape POS Counter with 19mm thick plywood structure & 12mm thick flexible plywood for front fascia (in two layers 12mm thick plywood to get the dual layer of the front fascia to make the necessary provision for the cove lighting and boxing for switch-socket installation) to get the curved shape and to make the dual layer of the front fascia (fire retardant plywood, Archid / Kenwood make with pesticide treatment). Counter's top and part of the fascia with internal edge of 50mm thick to be finished with 12mm thick Corian (ICE Queen W001 - DuPont make, basic rate INR. 10760.00/SM) with complete buffing / polish up to the mark. Counter's rest front fascia (the balance surfaces of Corian finish) other external surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Inside of the unit to be finished 1mm thick laminate (Formica / Heritage make, basic rate INR. 1325.00 / Sheet). Counter will be having five nos. of compartments. Three of the compartments will be having one no. of open space for cash machine provision, one no. of drawer with necessary draw compartment, one no. of open able shutter. And other four the compartments will be having one nos. of open able shutter with two nos. of wooden shelves (in 19mm thick plywood) on working side of the unit. Includes 100mm ht. 1mm thick 304 grade SS (with selected and approved rose gold coating finished) skirting from working side. Counter front fascia will having cove light provision as per details shown. Rate inclusive of all the necessary hardware fittings as required (like - heavy duty auto closing hinges, lock, grooves as handle, SS wire managers, etc. branded make) & necessary cut out for the services requirement. Complete as per architectural detail drawing & site engineer's instruction. Size: 5700mm Curved L (front fascia) x 900mm D x 900mm H x 1 no. | Sq. M. | 5.13 | 59180 | 303593.4 | 5.13 | 303593.4 |  |  | 0
20.1.04 |  | C & I | Dispenser Box-Carpentry | Dispenser Box with Corian finish. | P&F of Dispenser box with 12mm thick plywood structure (fire retardant plywood, Archid / Kenwood make with pesticide treatment), all surfaces of the dispenser box with 12mm thick Corian (ICE Queen W001 - DuPont make, basic rate INR. 10760.00/SM) with complete buffing / polish up to the mark, having provision of 100mm dia 4 nos. of SS containers, provisions for the mug container in said Corian finished. Rate including all necessary hardware fittings (branded make) & SS containers. Complete as per architectural detail drawing & site engineer's instruction. Size: 500mm L x 350mm H x 200mm D x 1 no. At the POS Area. | Nos. | 1 | 12500 | 12500 | 1 | 12500 |  |  | 0
20.1.05 |  | C & I | Back Counter-Carpentry | Back Counter with Corian Top & Fascia, front fascia with Veneer in PU Polish finish. | P&F of Back Working Counter with 19mm thick plywood structure & 12mm thick plywood back (fire retardant plywood, Archid / Kenwood make with pesticide treatment). Counter's top and edge of 50mm thick to be finished with 12mm thick Corian (ICE Queen W001 - DuPont make, basic rate INR. 10760.00/SM) with complete buffing / polish up to the mark. Counter front fascia external surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Inside of the unit to be finished 1mm thick laminate (Formica / Heritage make, basic rate INR. 1325.00 / Sheet). Counter will be having three nos of compartments. Counter's one of the compartments will be having one no. of open able shutter with two nos. wooden shelves (in 19mm thick plywood), the 2nd compartment will be having open space for kitchen equipment. Includes 100mm ht. 1mm thick 304 grade SS (with selected and approved rose gold coating finished) skirting from working side. Rate inclusive of all the necessary hardware fittings as required (like - heavy duty auto closing hinges, lock, handle, SS wire managers, etc. branded make) & necessary cut out for the services requirement. Complete as per architectural detail drawing & site engineer's instruction. Size: 2975mm L x 750mm D x 950mm H x 1 no. At the POS Area. | Sq. M. | 8.8506 | 43040 | 380930.9 | 3 | 129120 |  |  | 251810.9
20.1.06 |  | C & I | Back Display Rack-Carpentry | Back Display with MS Framing in metal primer with Veneer in PU Polish finish. | P&F of Wooden Shelves with MS Framing in Veneer finish, with 12mm x 20mm x 1.35mm thick C-Class MS tube framing as the detailed drawings. MS framing to be treated with antirust red oxide metal primer with selected and approved fire rated. Outer surfaces of the framing to be cladded with 6mm thick plywood to get the even surfaces to finish with 4mm thick selected and approved make red oak veneer as per the detailed patterns (Basic rate INR. 1614.00/SM) in 2 Hrs. fire rated PU polish. Rate including ms welding works with necessary fire protection, all necessary hardware fittings to install the framing, including all necessary supports from the columns / walls / connecting supports, etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing & site engineer's instruction. Size: 3900mm L x 300mm W x 25mm thick x 2 nos. At the POS Area. | R.M. | 7.8 | 12912 | 100713.6 | 7.8 | 100713.6 |  |  | 0
20.1.07 |  | C & I | MS Framing-Carpentry | MS Framing in PU Paint for LED Screens Back. | P&F of MS Framing in PU Paint finish, with 25mm x 25mm x 2mm thick C-Class MS tube framing out of vertical members (two nos.) at 1920 mm c/c & with horizontal members (two nos.) at 440 mm c/c) as the detailed drawings. MS framing to be treated with antirust red oxide metal primer with selected and approved fire rated and to be finished with selected and approved PU Paint. Rate including ms welding works with necessary fire protection, all necessary hardware fittings to install the framing, including all necessary supports from the columns / walls / ceiling connecting supports, etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing & site engineer's instruction. Size: 1920mm L x 300mm W x 25mm thick x 1 no. At the POS Area. | Nos. | 1 | 15500 | 15500 |  | 0 |  |  | 15500
20.1.08 |  | C & I | MS Framing-Carpentry | MS Framing in PU Paint to hold the Planter. | P&F of MS Framing in PU Paint finish, with 25mm x 25mm x 2mm thick C-Class MS tube framing out of vertical members (four nos.) at 200 mm c/c & with horizontal members (eight nos.) at top and bottom, with 25mm X 25mm x 2mm 'L' angel of 6 x nos to make the provision to install the wooden shelves as the detailed drawings. MS framing to be treated with antirust red oxide metal primer with selected and approved fire rated and to be finished with selected and approved PU Paint. Rate including ms welding works with necessary fire protection, all necessary hardware fittings to install the framing, including all necessary supports from the columns / walls / ceiling connecting supports, etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing & site engineer's instruction. Size: 7650mm L (in 'L' shape) x 200mm W x 200mm D x 12 nos. As per elevation AA, above banquet seating back. | R.M. | 91.8 | 405 | 37179 | 43.6248 | 17668.044 |  | CHK qty Certify 43.62 actual qty 91.8 | 19510.956
20.1.09 |  | C & I | Wooden Shelves-Carpentry | Wooden Shelves Veneer in PU Polish finish. | P&F of Wooden Shelves, using 12mm thick plywood structure (fire retardant plywood, Archid / Kenwood make with pesticide treatment). Shelves top, bottom and edges of 50mm thick and 20mm thick to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Rate including ms welding works with necessary fire protection within the existing ms structure, all necessary hardware fittings to install the framing, including all necessary supports from the columns / walls / connecting supports, etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing & site engineer's instruction. Size: 2500mm L x 200mm W x 50mm thick x 6 nos. As per elevation AA, above banquet seating back. | R.M. | 15 | 3000 | 45000 | 15 | 45000 |  |  | 0
20.1.10 |  | C & I | Wooden Shelves-Carpentry | Wooden Shelves Veneer in PU Polish finish. | P&F of Wooden Shelves, using 12mm thick plywood structure (fire retardant plywood, Archid / Kenwood make with pesticide treatment). Shelves top, bottom and edges of 50mm thick and 20mm thick to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Rate including ms welding works with necessary fire protection within the existing ms structure, all necessary hardware fittings to install the framing, including all necessary supports from the columns / walls / connecting supports, etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing & site engineer's instruction. Size: 1425mm L x 200mm W x 50mm thick x 3 nos. As per elevation AA, above banquet seating back. | R.M. | 4.275 | 3000 | 12825 | 4.275 | 12825 |  |  | 0
20.1.11 |  | C & I | Wooden Shelves-Carpentry | Wooden Shelves Veneer in PU Polish finish. | P&F of Wooden Shelves, using 12mm thick plywood structure (fire retardant plywood, Archid / Kenwood make with pesticide treatment). Shelves top, bottom and edges of 50mm thick and 20mm thick to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Rate including ms welding works with necessary fire protection within the existing ms structure, all necessary hardware fittings to install the framing, including all necessary supports from the columns / walls / connecting supports, etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing & site engineer's instruction. Size: 200mm L x 200mm W x 50mm thick x 16 nos. As per elevation AA, above banquet seating back. | R.M. | 3.2 | 3500 | 11200 | 4.8 | 16800 | certify qty revised from 3.20 to 4.80 |  | -5600
20.1.12 |  | C & I | Wooden Shelves-Carpentry | Wooden Shelves Veneer in PU Polish finish. | P&F of Wooden Shelves, using 12mm thick plywood structure (fire retardant plywood, Archid / Kenwood make with pesticide treatment). Shelves top, bottom and both edges of 50mm thick to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Rate including ms welding works with necessary fire protection within the existing ms structure, all necessary hardware fittings to install the framing, including all necessary supports from the columns / walls / connecting supports, etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing & site engineer's instruction. Size: 12600mm L x 275mm W x 50mm thick x 16 nos. As per elevation AA, above banquet seating back. | R.M. | 25.2 | 3000 | 75600 | 25.2 | 75600 |  |  | 0
20.1.13 |  | C & I | Wooden Shelves-Carpentry | Wooden Shelves Veneer in PU Polish finish. | P&F of Wooden Shelves, using 12mm thick plywood structure (fire retardant plywood, Archid / Kenwood make with pesticide treatment). Shelves top, bottom and edges of 50mm thick and 20mm thick to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Rate including ms welding works with necessary fire protection within the existing ms structure, all necessary hardware fittings to install the framing, including all necessary supports from the columns / walls / connecting supports, etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing & site engineer's instruction. Size: 5400mm L x 200mm W x 50mm thick x 1 no. As per elevation BB above the display glass area. | R.M. | 5.4 | 3000 | 16200 | 5.3 | 15900 |  |  | 300
20.1.14 |  | C & I | Counter-Carpentry | Condiment Counter with Corian Top & Edges, Front Fascia with Veneer in PU Polish finish. | P&F of Condiment Counter with 19mm thick plywood structure (fire retardant plywood, Archid / Kenwood make with pesticide treatment). Counter's top and edges of 38mm thick to be finished with 12mm thick Corian (ICE Queen W001 - DuPont make, basic rate INR. 10760.00/SM) with complete buffing / polish up to the mark. Counter will be having two nos. of compartments. Counter's all surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Inside of the unit to be finished 1mm thick laminate (Formica / Heritage make, basic rate INR. 1325.00 / Sheet). Counter will be having one no. of flap door (at the top of the counter with 300mm dia round ring of 25mm W x 25mm H in 3mm thick 304 grade matt finished SS sheet and flap door with same SS sheet. One of the compartments will be having one no. of open able shutter (in 19mm thick plywood and other part with two nos. of 25mm thick adjustable wooden shelves. Includes 150mm ht. 1mm thick 304 grade SS (with selected and approved rose gold coating finished) skirting for all the sides external surfaces. Rate inclusive of all the necessary hardware fittings as required (like - heavy duty auto closing hinges, lock, grooves as handle, SS wire managers, etc. branded make) & necessary cut out for the services requirement. Complete as per architectural detail drawing & site engineer's instruction. Size: 975mm L x 600mm D x 1050mm H x 1 no. At the entrance area. | Sq. M. | 1.0237 | 35000 | 35831.25 | 1.0237 | 35831.25 |  |  | 0
20.1.15 |  | C & I | Counter-Carpentry | Service Station with Veneer in PU Polish finish. | P&F of Service Station with 19mm thick plywood structure (fire retardant plywood, Archid / Kenwood make with pesticide treatment). Counter's all surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Inside of the unit to be finished 1mm thick laminate (Formica / Heritage make, basic rate INR. 1325.00 / Sheet). Counter will be having two nos. of open able shutter (in 19mm thick plywood with one nos. of 25mm thick adjustable wooden shelves and 150mm flush band as shown details. Includes 150mm ht. 1mm thick 304 grade SS (with selected and approved rose gold coating finished) skirting for all the sides external surfaces. Rate inclusive of all the necessary hardware fittings as required (like - heavy duty auto closing hinges, lock, grooves as handle, SS wire managers, etc. branded make) & necessary cut out for the services requirement. Complete as per architectural detail drawing & site engineer's instruction. Size: 1025mm L x 600mm D x 900mm H x 1 no. As per elevation AA, in-between the two banquet seating. | Sq. M. | 0.8775 | 35000 | 30712.5 | 0.882 | 30870 |  |  | -157.5
20.1.16 |  | C & I | Counter-Carpentry | Banquet Seating with Veneer in PU Polish finish. | P&F of Banquet Seating, having 600mm width x 350mm ht. slanted boxing with 19mm thick plywood framing and 19mm thick of the boxing (selected & approved make, fire-retardant bwr grade) for seating, having 75mm to 125mm thick. slanted back of 900mm ht with 19mm thick plywood framing & upholstery work (selected & approved density foam, fatherlite make) finished with selected & approved make fabrics / leatherette (basic cost INR. 1800.00 /Mtr. for both slanted back and seat). Banquet's all front surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Includes 150mm ht. 1mm thick 304 grade SS (with selected and approved rose gold coating finished) skirting for all the sides external surfaces. Rate including all necessary hardware fittings. Complete as per architectural detail drawing. Size: (5775+5800)mm L x 600mm W x 900mm height. | R. M. | 11.575 | 14580 | 168763.5 | 7.75 | 112995 |  |  | 55768.5
20.1.17 |  | C & I | Carpentry | SS Foot Rail | P&F of 25mm dia 2mm thick 304 grade Round SS Foot Rail of 100mm Ht. with 20mm dia stands (matt hairline finish) at Counter's front fascia. The stand to be fixed on the existing flooring with necessary anchor / bolting / screwing system. Rate including all necessary hardware fittings. Complete as per architectural detail drawing & site engineer's instruction. Size: 5700mm Curved L x 100mm H. At the POS Counter. | R. M. | 5.7 | 3402 | 19391.4 |  | 0 |  |  | 19391.4
[5 empty] | TOTAL OF COUNTER WORK |  |  |  | 1315940.55 |  | 934416.294
11.1 | C & I | Ceiling | False Ceiling | 12mm thick Gypsum False Ceiling-FOH Area | Providing and fixing 12mm thick Gypsum False Ceiling manufactured by India Gypsum or equivalent approved on G.I. frame work, in G.I. vertical supports at every 450mm c/c and horizontal runners at every 900mm c/c in brass screws to proper line and level. G.I. metal frame to be of 22 gauge folded strip of 50mm width to be used. All complete as per PM's instructions and specifications. The grid of frame work to be supported at every 1500mmx1500mm interval by MS rod anchored to the slab to support the G.I. framework. All vertical G.I. framework to be anchored to the slab by means of anchor fasteners including cornices and making holes/cutting and fixing with required framing for electrical fixtures, A.C. grills etc. Area of electrical fixtures will be paid full with ply on top of ceiling fixed to G.I. supports to receive spotlights etc. all other related works, at all levels and locations. Rate to include finishing with two or more coats of lustre paint in approved shade, colour and make. | Sq. m | 110 | 1345 | 147950 | 102.6234 | 138028.4407 |  |  | 86889.0913 | 750 | 76967.532
11..1.a | C & I | Ceiling | False Ceiling | 12mm thick Ply wood backing for the Gypsum False Ceiling-FOH Area | Providing & Fixing of 12mm thick ply wood on the existing GI framing, before installation the 12mm thicj Gypsum board. | Sq. m | 110 | 1650 | 181500 | 102.6234 | 169328.5704 |  |  | 12171.4296
11.2.a | C & I | Ceiling | Access doors | Trap door/access doors (assumed 1600mm x 990mm size) | Providing and creating trap door/access doors (assumed 1600mm x 990mm size), Aluminium section of 2"x1" framework (out of vertical members at 425 mm c/c & with horizontal members at 52 mm c/c) for shutter framing in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling paneling framework,6 mm thk FR plywood fixed to framework with flat head, full thread, sheet metal screws on both the surfaces with another layer of 4mm thick plywood finish to the bottom surface to get the even surfaces and edges for selected acrylic paint finish in Gypsum false ceiling including cutting to required size, recycled wood beading, creating grooves, required double legged scaffolding/staging etc. all complete as per reflected ceiling plan, at all levels and locations, and to the entire satisfaction of the PM/Architect. Bottom surfaces in selected acrylic paint finish and internal surfaces to be finished in selected and approved 1mm thick laminate finish. With all standard amd branded hardware fittings. Size: 1600mm L x 990mm W x 2 nos. | Sq m | 3.168 | 3766 | 11930.688 | 1.44 | 5423.04 |  |  | 6507.648
11.4 | C & I | Ceiling | Metal Ceiling | Micro Perforation Metal Ceiling of white colour with Black acoustic fleece. | Providing and fixing random Micro Perforation Metal Ceiling of white colour with Black acoustic fleece above with following specifications- Supply Laying micro perforated Tiles with 15mm Grid: Supply of GI 1800mmx600mmx0.5mm ceiling white tiles (random) perforated to 20mm dia holes with 15mm grid suspension system as per manufacturer's specifications. L shape Wall trim 19x19mm & T Grid 15mm(W)x38mm(H) included. Make- Armstrong/Fame line or equivalent. | Sq.m | 32.5 | 1775 | 57687.5 | 25.56 | 45369 |  |  | 12318.5
11.5.1 | C & I | Ceiling | Baffle Ceiling | Linear Wooden Baffle Ceiling - in PU Polish finish. | Linear Wooden Baffle Ceiling (Birch Plywood of 25mm thick in fire rated PU Polish), with supply & installation of Vertical Linear Wooden Baffle/Rafter ceiling system consist of approved shade of 25mm thick birch plywood sections of specified size 25mm thick x 200mm to 300mm height or as per drawing with a centre to centre spacing of 200mm with complete standard suspension system and necessary supports as per manufacturer's specifications / site condition. The baffle units are then attached to L- channel carriers spaced at 1200mm c.c. and suspended with M6 threaded rod hangers spaced 1200mm c.c. and to installed on the existing plywood backing gypbard ceiling as per approval of the architect & detail drawings complete in all respect. Note-The Baffle details to be coordinated and consulted with lighting consultant. Wood Grain Finish-Design as specified in drawing and in line with Architect approved. This item is for the POS Counter area and next the proposed AHU Unit. | Sq.m | 15.8 | 5000 | 79000 | 8.7 | 43500 | certify | rate will be change | 35500
11.5.2 | C & I | Ceiling | Baffle Ceiling | Linear Wooden Baffle Ceiling - in PU Polish finish. | Linear Wooden Baffle Ceiling (Birch Plywood of 25mm thick in fire rated PU Polish), with supply & installation of Vertical Linear Wooden Baffle/Rafter ceiling system consist of approved shade of 25mm thick birch plywood sections of specified size 25mm thick x 200mm to 300mm height or as per drawing with a centre to centre spacing of starting point from 175mm to end point 800mm with complete standard suspension system and necessary supports as per manufacturer's specifications / site condition. The baffle units are then attached to L- channel carriers spaced at 1200mm c.c. and suspended with M6 threaded rod hangers spaced 1200mm c.c. and to installed on the existing plywood backing gypbard ceiling as per approval of the architect & detail drawings complete in all respect. Note-The Baffle details to be coordinated and consulted with lighting consultant. Wood Grain Finish-Design as specified in drawing and in line with Architect approved. This item is for the FOH area. | Sq.m | 54 | 5000 | 270000 | 32.7498 | 163749 | certify | rate will be change | 106251
11.22 | C & I | Ceiling | Ceiling panel | Bison board panelling | Providing and fixing in position 12 mm thick Bison board panelling, with framework fabricated from, 50x35 hardwood 600 C/C, both ways, fixed to wall/ ceiling necessary supporting frame work, Supports, hardware.Consurnables as directed by EIC | Sq m
[5 empty] | TOTAL OF FALSE CEILING WORK |  |  |  | 748068.188 |  | 565398.0511
12.2.4 | Civil | Door | solid core flush shutter | Single Leaf Door - 50mm thick solid core flush shutter in laminate finish. | P&F of Single Leaf Door with door frame at the back entrance to the kitchen, over all size 1000mm x 2400mm, the back entrance to the kitchen. Using 50mm thick readymade fireproof block board shutter (selected & approved make, fire retardant bwr grade). Both the surfaces and edges of the door to be finished with 1mm thick laminate (basic cost INR. 1345.00 / SM). Rate inclusive of all hardware fittings like- heavy duty ball bearing butt hinges (code:9268610 - Hettich make), 300mm ht. x 25 mm dia SS 'H' handle (Hettich make- 2310, code:9228560O /zone make - OGH-55-25X300MM SSS - H Type Handle / Equivalent make) on shutters, heavy duty SS door stopper (Hettich-code:9250600), single type dead lock, tower bolt, Open type door closure (Hettich make- Item code:9227816), all necessary hardware fittings, etc. (all the hardware fittings should be Hettich / Dorset / Dorma / Ozone make / Equivalent make and to be approved by architect / site engineer), including 8mm thick clear glass vision panel (300mm L x 500mm H) to be fixed with the wooden beading and to be finished in said in polish. Having 304 grade 900mm height x 2mm thick SS Matte hairline finished kick plate on the both surfaces of the shutter. With doorframe out of 200mm W x 60mm thickness made out of approved quality, chemically treated, Kiln-seasoned, antitermite treated approved quality red oak / ash wood with shaped, grooved, metered joint arrangement, moldings, rebates, including use of approved water repellent adhesive, GI screws, pins, etc. all exposed surfaces to be melamine polished in approved colour and shade, surfaces of frame in contact with masonry / concrete surfaces shall be painted with one coat of hot bitumen of approved quality, 3 nos. GI holdfast (split and 225 x 75 x 2 mm thick) / bolts on each side of frame well-grouted with cement concrete mix in a ratio of 1:2:4 (1 cement : 2 sand : 4 aggregate), etc., at all levels and locations, complete to the entire satisfaction of the PM.Complete as per architectural detail drawing & site engineer's instruction. Size: 1000mm L x 2400mm H x 1 no. As per D3. | No | 1 | 38000 | 38000 |  | 0 |  |  | 38000
12.2.5 | Civil | Door | solid core flush shutter | Single Leaf Door - 50mm thick solid core flush shutter in laminate finish. | P&F of Single Leaf Door with door frame at the divider to the display kitchen and prep. section, over all size 1000mm x 2400mm, the back entrance to the kitchen. Using 50mm thick readymade fireproof block board shutter (selected & approved make, fire retardant bwr grade). Both the surfaces and edges of the door to be finished with 1mm thick laminate (basic cost INR. 1345.00 / SM). Rate inclusive of all hardware fittings like- heavy duty ball bearing butt hinges (code:9268610 - Hettich make), 300mm ht. x 25 mm dia SS 'H' handle (Hettich make- 2310, code:9228560O /zone make - OGH-55-25X300MM SSS - H Type Handle / Equivalent make) on shutters, heavy duty SS door stopper (Hettich-code:9250600), single type dead lock, tower bolt, Open type door closure (Hettich make- Item code:9227816), all necessary hardware fittings, etc. (all the hardware fittings should be Hettich / Dorset / Dorma / Ozone make / Equivalent make and to be approved by architect / site engineer), including 8mm thick clear glass vision panel (300mm L x 500mm H) to be fixed with the wooden beading and to be finished in said polish. Having 304 grade 900mm height x 2mm thick SS Matte hairline finished kick plate on the both surfaces of the shutter. With doorframe out of 200mm W x 60mm thickness made out of approved quality, chemically treated, Kiln-seasoned, antitermite treated approved quality red oak / ash wood with shaped, grooved, metered joint arrangement, moldings, rebates, including use of approved water repellent adhesive, GI screws, pins, etc. all exposed surfaces to be melamine polished in approved colour and shade, surfaces of frame in contact with masonry / concrete surfaces shall be painted with one coat of hot bitumen of approved quality, 3 nos. GI holdfast (split and 225 x 75 x 2 mm thick) / bolts on each side of frame well-grouted with cement concrete mix in a ratio of 1:2:4 (1 cement : 2 sand : 4 aggregate), etc., at all levels and locations, complete to the entire satisfaction of the PM.Complete as per architectural detail drawing & site engineer's instruction. Size: 950mm L x 2200mm H x 1 no. As per D2. | No | 1 | 38000 | 38000 | 1 | 38000 |  |  | 0
12.2.6 | Civil | Door | solid core flush shutter | Single Leaf Door - 38mm thick solid core flush shutter in subway tile finish (tile to be considered separatly). | P&F of Single Leaf Door without door frame at the storage unit, over all size 900mm x 2100mm for storage unit. Using 38mm thick readymade fireproof block board shutter (selected & approved make, fire retardant bwr grade). Back of the surface and edges of the door to be finished with 1mm thick laminate (basic cost INR. 1345.00 / SM). Rate inclusive of all hardware fittings like- heavy duty ball bearing butt hinges (code:9268610 - Hettich make), heavy duty SS door stopper (Hettich-code:9250600), single type dead lock, tower bolt, all necessary hardware fittings, etc. (all the hardware fittings should be Hettich / Dorset / Dorma / Ozone make / Equivalent make and to be approved by architect / site engineer). complete to the entire satisfaction of the PM.Complete as per architectural detail drawing & site engineer's instruction. Size: 900mm L x 2100mm H x 1 no. As per Section ZZ. | No | 1 | 28000 | 28000 |  | 0 |  |  | 28000
12.16.1 | Civil | Glass Door | Glass Door | Entrance single leaf glass door 12mm thick Glass, with wooden doorframe. | P&F of Single Leaf Glass Door with Doorframe, over all size 900mm x 2400mm @ Entrance to POS Section from display kitchen, with 200mm x 50mm thick seasoned red oak / ash wooden doorframe. Doors in 12mm thick (Heat Proof Toughened Glass in two parts, with service window provision of 450mm height) thick clear toughened glass. Using 75mm x 50mm thick seasoned red oak / ash wooden framing to be polished with Fire-Retardant pu polish. Rate inclusive of all hardware fittings like- door spring (BTS80F-Dorma make), 600mm Ht. 'H' handle (Dorma make) in metal Fire-Retardant rose gold colour in chrome finished. Rate includes all necessary hardware fittings, etc. (all the fittings should be approved by architect / site engineer) . Complete as per architectural detail drawing & site engineer's instruction. Size: 900mm L x 2400mm H x 1 no. | No. | 1 | 37500 | 37500 | 1 | 37500 |  |  | 0
[9 empty] | 141500 |  | 75500
14 |  |  |  |  | PAINTING WORK
14.24 | C & I | Painting | Interior Emulsion Velvet Touch Paint - Wall | One coat approved primer and Two Coat of Interior Emulsion Velvet Touch Paint Finish | P&A of Matte Velvet Touch Fire Retardant Paint (Apcolite Premium Matte - Royal Ivory 0331-Asian Paint / equivalent) on Birla Putty / POP Punning finished walls with removing loose particles and paint flakes, scraping with sandpaper to ensure that the surface is dry and free from dust, dirt or grease. Apply a coat of wall primer, using deco prime wall primer (solvent thinnable) on wall surfaces with fill and level the minor undulations of wall by applying Asian paint enamel / oil wall putty and ensure that the surface is uniformly smooth by sanding, after putty work. One liberal coat of deco prime wall primer (solvent thinned) is recommended on puttied areas before applying the top coat. The primer should be allowed to dry for 10 to 12 hours, there after painting the surface in two finishing coats over base primer coat to achieve even finish. Allow the first coat to dry completely for a minimum of 10 to 12 hours. Once the first coat is dry, just rub the surface gently with sandpaper in order to remove the loose and small particles. After finishing the first coat, start applying the second coat of paint and leave the surface to dry completely for a minimum 10 to 12 hours. All these process and application to be done as per the manufactures' instruction with high quality tools to get the best quality of the paint finish. Complete up to the mark & site engineer's instruction. It is up to 4000mm height walls. | Sqm | 0 | 430 | 0 | #VALUE! | 18588.9 |  |  | -18588.9
14.25 | C & I | Painting | Interior Emulsion Velvet Touch Paint - Wall | One coat approved primer and Two Coat of Interior Emulsion Acrylic Paint Finish | P&A of Fire Retardant Acrylic Paint (Ivory 0331-Asian Paint / Equivalent) on Gypboard finished false ceiling with removing loose particles and paint flakes, scraping with sandpaper to ensure that the surface is dry and free from dust, dirt or grease. Apply a coat of wall primer, using deco prime primer on the surfaces with fill and level the minor undulations of true ceiling by applying Asian paint wall putty and ensure that the surface is uniformly smooth by sanding, after putty work. One liberal coat of deco prime wall primer (solvent thinned) is recommended on puttied areas before applying the top coat. The primer should be allowed to dry for 6 to 8 hours, there after painting the surface in two finishing coats over base primer coat to achieve even finish. Allow the first coat to dry completely for a minimum of 6 to 8 hours. Once the first coat is dry, just rub the surface gently with sandpaper in order to remove the loose and small particles. After finishing the first coat, start applying the second coat of paint and leave the surface to dry completely for a minimum 6 to 8 hours. All these process and application to be done as per the manufactures' instruction with high quality tools to get the best quality of the paint finish. Complete up to the mark & site engineer's instruction. | Sqm | 110 | 396 | 43560 | 102.6234 | 40638.8569 |  |  | 2921.1431
[9 empty] | 43560 |  | 59227.7569
TOTAL OF PAINTING WORK
17 |  |  |  |  | MISCELLANEOUS & JOINERY WORK
17.1.1 | Civil | Front Railing | Wooden Railing | Wooden Railing in PU Polish finish @ 900mm high above finish floor level at the front façade of the unit. | Providing, fixing, Wooden railing @ 900mm high above finish floor level, out of 75mm x 50mm seasoned red oak / ash wood framing uprights and 50mm x 50mm vertical grids at about 225mm c/c, 16 nos. and 25mm x 25mm ms tube grids of 10 nos in PU matt paint finish. With 5 nos of seasoned red oak / ash wooden panel of 355mm x 355mm x 38mm thick. All wooden surfaces tobe finished in fire rtaed PU polish. Including required jointing and sealing with approved quality silicon sealant etc, at all levels and locations, all complete as per detail drawing, specification to entire satisfaction of PM. Work includes preparing shop drawings to scale with joinery and fixing details and further includes providing samples and preparing full scale mock-up samples for approval. As per site measurement correction to dimension with approval of the PM shall be made. Size: 5000mm L x 900mm H x 1 no. | Rmt | 5 | 8200 | 41000 | 5 | 41000 | Not acceptable as per drawing made |  | 0
17.1.1 | Civil | Front Wooden Framing | Vertical Wooden Framing | Wooden Railing in PU Polish finish @ 900mm high above finish floor level at the front façade of the unit. | Providing, fixing, Vertical wooden framing, out of 50mm x 50mm seasoned red oak / ash wood framing both vertical sides and 75mm x 50mm vertical grids at about 400mm c/c, 5 nos. All wooden surfaces to be finished in fire rated PU polish. Including required jointing and sealing with approved quality silicon sealant etc., at all levels and locations, all complete as per detail drawing, specification to entire satisfaction of PM. Work includes preparing shop drawings to scale with joinery and fixing details and further includes providing samples and preparing full scale mock-up samples for approval. As per site measurement correction to dimension with approval of the PM shall be made. Size: 2750mm H x 600mm W x 1 no. | Rmt | 2.75 | 8200 | 22550 | 3.6 | 29520 |  |  | -6970
17.1.3 | Civil | Front Planter Box | Wooden Planter Box | Wooden Planter Box in PU Polish finish @ 900mm high above finish floor level at the front façade of the unit. | Providing, fixing, Wooden Planter Box, Using 12mm thick plywood for the planter box (fire retardant plywood, Archid / Kenwood make with pesticide treatment) and all surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish.. Including required jointing and sealing with approved quality silicon sealant etc., at all levels and locations, all complete as per detail drawing, specification to entire satisfaction of PM. Work includes preparing shop drawings to scale with joinery and fixing details and further includes providing samples and preparing full scale mock-up samples for approval. As per site measurement correction to dimension with approval of the PM shall be made. Size: 600mm L x 125mm D x 125mm H x 5 nos. | No. | 5 | 4300 | 21500 | 5 | 21500 |  |  | 0
17.2 | Civil | Staircase/ Ramps | SS Railing over Staircase Pardi | 50 mm dia SS pipe (304 grade) matt finish as hand rail | Providing and fixing 50 mm dia SS pipe (304 grade) matt finish as hand rail over staircase pardi supported on 20mm x 20mm SS (304 grade) uprights at required intervals fixed with SS pins, dowels, clamps, rubber, screws, gaskets etc. including welding, required jointing and sealing with approved quality silicon sealant etc, at all levels and locations, all complete as per detail drawing, specification to entire satisfaction of PM. (Residential floors) | Rmt |  |  | 0 |  | 0 |  |  | 0
17.3 | Civil | Staircase/ Ramps | MS Railing | M. S. railing @ 900mm high above finish floor level, in profile made out of 50mm x 40mm uprights | Providing, fixing, fabricating M. S. railing @ 900mm high above finish floor level, in profile made out of 50mm x 40mm uprights (end and intermediate), runners, and 50 mm dia pipe as hand rail, rosette cover fixed with pins, dowels, clamps, rubber, screws, gaskets etc. including required jointing and sealing with approved quality silicon sealant etc, at all levels and locations, all complete as per detail drawing, specification to entire satisfaction of PM. Work includes preparing shop drawings to scale with joinery and fixing details and further includes providing samples and preparing full scale mock-up samples for approval. As per site measurement correction to dimension with approval of the PM shall be made. |  |  |  | 0 |  | 0 |  |  | 0
17.3.1 |  |  |  |  | MS Handrail-Wall | Rmt |  |  | 0 |  | 0 |  |  | 0
17.3.2 |  |  |  |  | MS Handrail- Over RCC Pardi as per design as specified by consultants | Rmt |  |  | 0 |  | 0 |  |  | 0
17.4 | C & I | Stainless steel railing | SS RAILING 304G 50MM DIA | 50mm dia.SS pipe handrail fixed on 38mm dia.SS vertical members | Providing and fixing in position Stainless steel railing of 304 Grade as per the architectural design,drawings,includes 50mm dia.SS pipe handrail fixed on 38mm dia.SS vertical members (at suitable positions) and 20mm dia horizontal members(3No.), fixing to the 12mm dia S.S.member and specifications including necessary anchor fasteners, etc. complete as per drawing with all lead and lift of all levels, loading and unloading, transportation, curing etc, and all other incidental charges etc. complete and as directed by Engineer-in-charge.as per drawing. | RMT |  |  | 0 |  | 0 |  |  | 0
17.5 | C & I | Stainless steel hand rail | SS HAND RAIL 304 GRADE 50MM DIA | 50mm dia. S.S. pipe handrail fixed with 2mm thk. and 12mm dia S.S.plate, | Providing and fixing in position Stainless steel hand rail of 304Grade as per architectural design, drawings includes 50mm dia. S.S. pipe handrail fixed with 2mm thk. and 12mm dia S.S.plate, including necessary anchor fasteners, fittings and SS plates as per drawing with all leads and lifts of all levels, loading and unloading, transportation, curing, etc. and all other incidental charges etc. complete and as directed by Engineer-in·charge.(Only Hand rail with Bracket support). | RMT |  |  | 0 |  | 0 |  |  | 0
17.6 | C & I | Column guards | MS column guards at corner | MS column guards at corners made out of 25x25x6mm thick MS angle section | Providing and fixing MS column guards at corners made out of 25x25x6mm thick MS angle section about 1500 mm high fixed in floor by grouting about 150 mm deep as per detail drawings, MS section to be finished with two coats of primer, two under coats and one finished coat of approved synthetic enamel paint all as per instruction and entire satisfaction the of the PM / Architect, at all levels and locations. | Kg |  |  | 0 |  | 0 |  |  | 0
17.7 | C & I | Column guards | POWDER COATED ALU ANGLE 25x25x2 mm | Aluminium angle of size 25x25x2 mm thick powder coated to match the approved colour | Providing & fixing aluminium angle of size 25x25x2 mm thick powder coated to match the approved colour at the edge of column cladding to protect column edge, with high bond adhesive. Work including material,labor,tools,tackles,transportation,lead,lift,hardware,consumables etc. Complete as directed by EIC. | RMT |  |  | 0 |  | 0 |  |  | 0
17.9 | C & I | Column guards | Column edge protection | Aluminium angle of size 38x38x2mm and finished with 50 to 60-micron powder coating of approved colour | Providing & fixing Jindal Hindalco make Aluminium angle of size 38x38x2mm and finished with 50 to 60-micron powder coating of approved colour. Aluminium angle to be pasted with hi bond epoxy adhesive, on the existing vitrified tile edge column edge as edge protection, Edge gaps of the aluminium angle to be finished with clear silicon sealant after pasting. Work including all material, labour, tools, tackles, transportation, lead, lift,hardware,consumables etc. Complete as directed by EIC. | RMT | 21.6 | 485 | 10476 | 12 | 5820 |  |  | 4656
17.19 | C & I | Laminated sheet | Laminated sheet of 1.0 mm thk. | Laminated sheet of 1.0 mm thk. of approved shade and brand such as sun mica/ Formica /decolam or any other | Providing & Fixing Laminated sheet of 1.0 mm thk. of approved shade and brand such as sun mica/ Formica /decolam or any other equivalent quality for the places such as table top wooden partition, doors, etc. complete. As directed by the Engineer in charge. | Sq m | 0 | 1245 | 0 | 4.5 | 5602.5 |  |  | -5602.5
17.24 | C & I | Flex | Temporary Flex | Temporary Flex for Cordoning of area by using wooden framework | Providing and erecting Temporary Flex for Cordoning of area by using wooden framework of hard wood of size 50mm x 50mm at spacing of 1200mm centre to centre, both horizontally and vertically, for height up to 3.5 mts, with one face covered with Chinese flex sheet, double skinned, 10 ounce thick Media, Print Medium solvent printing, fixed by use of approved adhesive, etc. complete. The Artwork for printing will be given by Engineer-In-Charge. | Sq m | 48 | 1883 | 90384 | 19.28 | 36304.24 |  |  | 54079.76
[5 empty] | MISCELLANEOUS & JOINERY WORK |  |  |  | #VALUE! |  | 139746.74
[5 empty] | Total Amount | [5 empty] | 5136920.1545
NT ITEMS
Remarks
|  |  |  | marble | 19mm thick Terrazzo Marble stone Dado. | Sqmt |  |  |  | 17.82 |  |  |  |  | 1250 |  | taken above in code 10.1.01 | Difference Rate
|  |  |  | Floor Protection | P&L of 6mm thick Commercial Plywood with base clear plastic and 4mm thick hollow PVC Sheet. Protection to the tiles flooring / others soft flooring with 50 micron plastic sheet and 4mm thick hollow spaced floor protection sheet and then 6mm thick commercial plywood to be laid over the PVC sheet. All the joints to be covered with 50mm width brown tape. After competition of all Interiors works the same has to be removed from the floor with proper cleaning of the flooring & debris' to be removed from the compound. Complete as per site engineer's instruction. | Sqmt |  |  |  | 138.4314 |  |  |  |  | 807 | 111714.1204 | As per James Martin PO Number HO/PO/22-23/000055 | as per james martin po
|  |  |  | Metal door | P&F of Single Leaf Door with door frame (size 2200 x 1000 mm) | Nos |  |  |  | 1 |  |  |  |  | 77150 | 77150 | mail confirmation attached sheet | as per bial & tfs requirement
|  |  |  | DMB/ menu board | P&F of MS Pipe for DMB/ menu board with 18 ply with venner size 5000X300X1 (P&F of menu board with MS Framing in PU Paint & Polish finish, using 12mm thick plywood structure (fire retardant plywood, Archid / Kenwood make with pesticide with 50mm x 50mm x 1.6mm thick bright MS tube framing as per the detailed drawings. 900mm width and both 100mm edges of the ledge to be finished with seasoned ash wood venners of 12mm PLY finished in 1mm thick lvenners . MS framing to be treated with antirust red oxide metal primer with selected and approved fire rated and to be finished with metal PU Paint in 2 Hrs. fire rated. Rate including ms welding works with necessary fire protection, all necessary hardware fittings to install the framing, including all necessary supports from the mother slab / floor / columns / railing connecting supports, etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing & site engineer's instruction. Size: 3300mm L x 2000mm W x 100mm thick. At one of the front TV area. | Nos |  |  |  | 1 |  |  |  |  | 15000 | 15000 | mail confirmation attached sheet | as per tfs requirement
[5 empty] | P&F of aluminium frame both side with bison board and filling of glass wool both side | Sqmt |  |  |  | 39.145 |  |  |  |  | 5500 | 215297.5 | mail confirmation attached sheet | rate approval Sir
|  |  |  | demolishing brick | Dismantling and demolishing brick/ block work in lime or cement mortar including plaster, paint, etc. manually/ by mechanical means including stacking of serviceable material and disposal of unserviceable material within 250 metres lead as per direction of Engineer-in-charge. | Sqmt |  |  |  | 6.16 |  |  |  |  | 1150 | 7084 | mail confirmation attached sheet | as per tfs requirement
|  |  |  | Fire Rated Gysum Board | Providing and fixing 12mm thick Gypsum False Ceiling manufactured by India Gypsum or equivalent approved on G.I. frame work, in G.I. vertical supports at every 450mm c/c and horizontal runners at every 900mm c/c in brass screws to proper line and level. G.I. metal frame to be of 22 gauge folded strip of 50mm width to be used. All complete as per PM's instructions and specifications. The grid of frame work to be supported at every 1500mmx1500mm interval by MS rod anchored to the slab to support the G.I. framework. All vertical G.I. framework to be anchored to the slab by means of anchor fasteners including cornices and making holes/cutting and fixing with required framing for electrical fixtures, A.C. grills etc. Area of electrical fixtures will be paid full with ply on top of ceiling fixed to G.I. supports to receive spotlights etc. all other related works, at all levels and locations. Rate to include finishing with two or more coats of lustre paint in approved shade, colour and make. | Sqmt |  |  |  | 102.9834 |  |  |  |  | 750 |  | mail confirmation attached sheet | Difference Fire Rated Gypsum
[5 empty] | P&F of new MS frame platform size 2000X1200mm for water tank | Nos |  |  |  | 1 |  |  |  |  | 75000 | 75000 | mail confirmation attached sheet | as per tfs requirement
[5 empty] | Range: Medi Series Code: FLR-CHR-5031N Description: Florentine Pillar Cock with Extended Lever Handle | Nos |  |  |  | 1 |  |  |  |  | 5500 | 5500 | mail confirmation attached sheet | as per tfs requirement
[5 empty] | SS SINK FOR BACK COUNTER OVERALL SIZE:- 355 x 305 x 150 MM ( Desginer has mailed and instruted by ranjandas ) | Nos |  |  |  | 1 |  |  |  |  | 8000 | 8000 | mail confirmation attached sheet | as per tfs requirement
0
[5 empty] | Providing ,fixing, testing and commissioning Electromagnetic flow meter-flow (30 GPM-1.89 LPS) including providing & fixing matching with required accessories 16Kgs/Sq.cm). - Contractor to check existing make in BILA airport and provide that. (Difference) 40 mm Dia incoming line | Nos |  |  |  | 1 |  |  |  |  | 67500 | 67500 | (diff- 110000-42500 claimedin plumbing bill po no. Order Number BLR/PO/22-23/000073 | diff as per tfs requirement
[5 empty] | Providing & Fixing of MS angle frame work size 2"x 2" thickness 5 mm for hanging false ceiling as per drawing. | KG |  |  |  | 1125.1665 |  |  |  |  | 225 | 253162.4625 | rate revised from 250 to 225 as per meeting | rate aprove in mail
[5 empty] | Demolishing of gypsum partition in facade (Demolition and dismantling work at any level, including providing double scaffolding, props, runners, covering the glass panels, panneling, weather sheds with plywood or tin sheets including hessian cloth stiched to external face of scaffolding, all tools and tackles.(removing the material 3 km away from site as approved by site incharge) | Sqmt |  |  |  | 38.35 |  |  |  |  | 1150 | 44102.5 | mail confirmation attached sheet
[5 empty] | Duco paint for wooden panelling | Sqmt |  |  |  | 51.55 |  |  |  |  | 3766 | 194137.3
[5 empty] | Making Of wooden frame for TV unit ( as per drawing we have made the unit and later on the size was change in front Amol & Ranjandas Sir the TV unit was broken & re made. | Nos |  |  |  | 1 |  |  |  |  | 10300 | 10300
[5 empty] | Modification of service station ( as per drawing we have made the service station later on the sofa size came big so we have to modify the service station as ranjandas has send the images in whatsup group.) | nos |  |  |  | 1 |  |  |  |  | 15000 | 15000
[5 empty] | Metel ceiling re work 3 time ( as per drawing we have made the ceiling work but due to sprinkler, hvac, and hvac hood connection was done later on as per ranjandas instruction ( APROX 65 SQMTS OF WORKS DONE @ 184 PER SQ MTRS ) | nos |  |  |  | 1 |  |  |  |  | 12000 | 12000
[5 empty] | Providing of safety officers | Months |  |  |  | 4 |  |  |  |  | 42000 | 168000
[5 empty] | Providing of aluminum scafolding on rental per month | Months |  |  |  | 5 |  |  |  |  | 9000 | 45000 | attached bill
[5 empty] | Installation of kitchen equipment and shelf (Providing labours during the course of the project to carry out minor jobs also for fixing of following items including making necessary hole, adhesive, nails etc. complete as directed by Architect and Engineer - in - charge TOTAL ABOUT 19 LABOUR @ 900/- | Ls |  |  | oiy\\ | 1 |  |  |  |  | 17000 | 17000
[5 empty] | Providing & fixing of T profile | Rft |  |  |  | 250 |  |  |  |  | 350 | 87500
[5 empty] | Mobilization & demobilization charges due to stop of work ( CISF visit work closed dated 6 Nov 2022 to 14 Nov 2022, later PM visit at site 1 week closed, BIAL party for inaugaration site closed for 3 days) | Ls |  |  |  | 1 |  |  |  |  | 100000 | 100000
[5 empty] | TOTAL | [5 empty] | 0 |  |  |  |  | 1627690.4149

## Extra Mb
MB Sheet CIVIL MASONRY BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU
SR.NO | Item Description | Unit | No | Length | Breadth | Total Quantity
1 | 19mm thick Terrazzo Marble stone Dado
| kitchen above window | Sqmt | 1 | 2.1 | 1.5 | 3.15
| wall | Sqmt | 1 | 2 | 3 | 6
| wall | Sqmt | 1 | 2.1 | 4 | 8.4
| wall | Sqmt | 1 | 0.9 | 0.3 | 0.27
| Total | Sqmt |  |  |  | 17.82
2 | 12mm thick Ply wood backing for the Gypsum False Ceiling-FOH Area
| sofa side live kitchen cold and hot wall ellevayin bb | Sqmt | 1 | 9.886 | 8.664 | 85.6523
| less column | Sqmt | -1 | 2.048 | 1.186 | -2.4289
| sofa side live kitchen wall elevation bb | Sqmt | 1 | 4.6 | 5 | 23
Micro Perforation Metal Ceiling of white colour with Black acoustic fleece.
| live kitchen area | Sqmt | 1 | 4.8 | 2.78 | 13.344
| kitchen area | Sqmt | 1 | 7.86 | 2.4 | 18.864
| Total | Sqmt |  |  |  | 138.4314
3 | Metal door | Nos | 1 |  |  | 1
| Total | Nos |  |  |  | 1
4 | P&F of MS Pipe for DNB with 18 ply with venner size 5000X300X1 | Nos | 1 |  |  | 1
| Total | Nos |  |  |  | 1
5 | P&F of aluminium frame both side with bison board and filling of glass wool both side 200mm wide
| above glass | Sqmt | 1 | 5.2 | 5.1 | 26.52
| above glass | Sqmt | 1 | 2.5 | 2.5 | 6.25
| above glass | Sqmt | 1 | 1.25 | 5.1 | 6.375
| Total | Sqmt |  |  |  | 39.145
6 | demolishing brick entrance back door | Sqmt | 1 | 1.5 | 2.8 | 4.2
| floor | Sqmt | 1 | 0.3 | 6 | 1.8
| hole gas line | Sqmt | 4 | 0.2 | 0.2 | 0.16
| Total | Sqmt |  |  |  | 6.16
7 | Fire Rated Gypsum Board
12mm thick Ply wood backing for the Gypsum False Ceiling-FOH Area
| sofa side live kitchen cold and hot wall ellevayin bb | Sqmt | 1 | 9.886 | 8.664 | 85.6523
| less column | Sqmt | -1 | 2.048 | 1.186 | -2.4289
| sofa side live kitchen wall elevation bb | Sqmt | 1 | 4.6 | 5 | 23
| less boxing | Sqmt | -1 | 0.9 | 3.6 | -3.24
| Total | Sqmt |  |  |  | 102.9834
8 | P&F of new MS frame platform size 2000X1200mm for water tank | Nos | 1 |  |  | 1
| Total | Nos |  |  |  | 1
9 | Range: Medi Series Code: FLR-CHR-5031N Description: Florentine Pillar Cock with Extended Lever Handle | Nos | 1 |  |  | 1
| Total | Nos |  |  |  | 1
10 | SS SINK FOR BACK COUNTER OVERALL SIZE:- 355 x 305 x 150 MM | Nos | 1 |  |  | 1
| Total | Nos |  |  |  | 1
11 | Providing ,fixing, testing and commissioning Electromagnetic flow meter-flow (30 GPM-1.89 LPS) including providing & fixing matching with required accessories 16Kgs/Sq.cm). - Contractor to check existing make in BILA airport and provide that.
A | 40 mm Dia incoming line (rate difference) | NO | 1 |  |  | 1
| Total | Nos |  |  |  | 1
12 | MS angle frame work size 2"x 2" thickness 5 mm for | Rmt | 25 | 2.96 |  | 74
| CEILING | Rmt | 4 | 1.75 |  | 7
|  | Rmt | 5 | 0.6 |  | 3
|  | Rmt | 2 | 12.637 |  | 25.274
|  | Rmt | 2 | 4.93 |  | 9.86
|  | Rmt | 3 | 14.137 |  | 42.411
|  | Rmt | 1 | 8.664 |  | 8.664
|  | Rmt | 2 | 5 |  | 10
|  | Rmt | 1 | 6 |  | 6
|  | Rmt | 3 | 11.476 |  | 34.428
|  | Rmt | 1 | 4 |  | 4
| KITCHEN LIVE | Rmt | 1 | 5 |  | 5
| KITCHEN LIVE | Rmt | 2 | 2.4 |  | 4.8
| INSIDE KITCHEN | Rmt | 1 | 6 |  | 6
| INSIDE KITCHEN | Rmt | 4 | 2.4 |  | 9.6
250.037
| Total | Kg | 0.05 | 0.05 | 5 | 1125.1665
13 | Demolishing of gypsum partition in facade
| façade | Sqmt | 1 | 6.5 | 3.5 | 22.75
| façade | Sqmt | 1 | 6.5 | 2.4 | 15.6
| Total | Sqmt |  |  |  | 38.35
14 | Duco paint for wooden panelling
10.34.03 | Aluminium Frame + Wooden Wall Paneling of 37mm thick.
| fasad RHS | Sqmt | 1 | 2.4 | 7.5 | 18
| fasad LHS | Sqmt | 1 | 1.3 | 7.5 | 9.75
| above opining entrance | Sqmt | 1 | 7 | 3.4 | 23.8
| Total | Sqmt |  |  |  | 51.55
15 | Making Of wooden frame for TV unit | Nos | 1 |  |  | 1
| Total | Nos |  |  |  | 1
16 | Modification of service station | Nos | 1 |  |  | 1
| Total | Nos |  |  |  | 1
17 | Metel ceiling re work 3 time | Nos | 1 |  |  | 1
| Total | Nos |  |  |  | 1
18 | Providing of safety officers | Months | 4 |  |  | 4
| Total | Months |  |  |  | 4
19 | Providing of aluminum scafolding on rental per month | Months | 5 |  |  | 5
| Total | Months |  |  |  | 5
20 | Installation of kitchen equipment and shelf | Ls | 1 |  |  | 1
| Total | Ls |  |  |  | 1
21 | Providing & fixing of T profile | Rft | 250 |  |  | 250
| Total | Rft |  |  |  | 250
22 | Mobilization & demobilization charges due to stop of work by prime minister visit . | Ls | 1 |  |  | 1
| Total | Ls |  |  |  | 1

## SUMMARY
Summary Sheet For Bill @ TFS Gully Kitchen Banglore
|  | TFS | Actual Bill (Mailed) | Certify Bill
Sr.no | Description | PO Amount | Amount | Amount
1 | Water Proofing Work | 202958.1 | 231518.94 | 214155.075
2 | Masonry & Plaster | 455608.498 | 351529.99 | 357627.827
3 | Gr Flooring | 607231.05 | 661763.69 | 594687.1905
4 | Wall finishes | 1898739.1989 | 2236004.46 | 2196161.22
5 | Counter & Others | 1315940.55 | 948327.25 | 934416.294
6 | I. Ceiling | 748068.188 | 605961.05 | 565398.0511
7 | J. Doors | 141500 | 75500 | 75500
8 | L.Painting | 77863.852 | 59227.76 | 59227.7569
9 | N. Miscellaneous | 206274.465 | 139746.74 | 139746.74
| Total | 5654183.9019 | 5309579.88 | 5136920.1545
| Less Discount | 243780 | 228923 | 221478.3125
| Total Amount | 5410403.9019 | 5080656.88 | 4915441.842

## D. Waterproofing
FEBRUARY 2020
TRAVEL FOOD SERVICES
BOQ STANDARDISATION, IMPLEMENTATION AND COST CONSULTANCY |  |  |  |  | CIVIL MASONRY BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU
M&A final bill
SR. NO. | WBS | WBS Level1 | WBS Level 2 | SHORT ITEM DESCRIPTION | PARTICULARS | UOM | QTY. | Final Rate | Amount | Qty | Amount |  | Remark
GENERAL NOTES
4.4 | CIVIL | waterproofing | chemical water proofing system | Laying proprietary chemical water proofing system ON THE MOTHER SLAB | Providing and laying proprietary chemical water proofing system consisting of polymer modified acrylic base coating in two coats in form of slurry (total consumption of 1.5 Kg/Sqm) as approved by the PM and as directed by the approved manufacturer of waterproofing coating, with sandwiched fibre mesh and protective screed. The work shall include cleaning of surface, grouting porous surfaces including making ‘V’ grooves at junctions, cracks with non shrink crystalline base cementitious grout etc. Further including horizontal and vertical surfaces protected with 20mm screeding in 1:4 mortar (1 cement : 4 sand), finished in ready to receive Architectural finish, in correct line, level and plumb, curing, grouting, testing, etc. all complete to entire satisfaction of the PM, contractor to provide guarantee for 10 years Rs.100/- stamp paper in approved proforma. MAKE: WPM 002-AROEX ENDURA. CONTRCTING HAS TO FOLLOW THE DETAILED METHODOLOGY OF THE MANUFCATURERS INSTRUCTION. ONLY FOR WET AREA. | Sq m | 36 | 1614 | 58104 | 32.58 | 52584.12 | as certify
4.4.A | CIVIL | waterproofing | chemical water proofing system | Laying proprietary chemical water proofing system ON THE VERTICAL SURFACES UPT0 900MM HEIGHT. | Providing and laying proprietary chemical water proofing system consisting of polymer modified acrylic base coating in two coats in form of slurry (total consumption of 1.5 Kg/Sqm) as approved by the PM and as directed by the approved manufacturer of waterproofing coating, with sandwiched fibre mesh and protective screed. The work shall include cleaning of surface, grouting porous surfaces including making ‘V’ grooves at junctions, cracks with non shrink crystalline base cementitious grout etc. Further including horizontal and vertical surfaces protected with 20mm screeding in 1:4 mortar (1 cement : 4 sand), finished in ready to receive Architectural finish, in correct line, level and plumb, curing, grouting, testing, etc. all complete to entire satisfaction of the PM, contractor to provide guarantee for 10 years Rs.100/- stamp paper in approved proforma. MAKE: WPM 002-AROEX ENDURA. CONTRCTING HAS TO FOLLOW THE DETAILED METHODOLOGY OF THE MANUFCATURER"S INSTRUCTION. ONLY FOR WET AREA. | Sq m | 27.9 | 1614 | 45030.6 | 38.124 | 61532.136 | as certify
4.4.A | CIVIL | waterproofing | Block bat coba | Filling light weight block bats (50 mm thick) | Providing and filling light weight block bats 40-60mm mm thick with cement mortar mixed in ratio 1:3:6 (1 cement : 3 sand : 6 block bats) including mixing of water proofing compound 4 % by weight of cement to sunk portions of toilets, deck etc. complete to the entire satisfaction of the PM. Further surfaces shall be screeded with (1:1.5:3) cement concrete mix with 4% by weight of cement approved waterproofing compound about 20-30mm thick and finished smooth or ready to receive finish material as specified. Care shall be taken prior to filling all pipes passing through sunk portion are pressure tested by maintaining pressure for 24 hours and junctions of pipes passing through walls, slabs are well grouted and sealed. This shall be tested by ponding water for 100mm thickness and maintaining for 72 hours. FOH AREA. | Cu m | 5.55 | 5500 | 30525 | 5.2797 | 29038.1586 | as certify | 150mm rate change
4.6 | CIVIL | waterproofing | Brick bats coba | Filling brick bats coba (.... mm thick) | Providing and filling brick bats coba (.... mm thick) with cement mortar mixed in ratio 1:3:6 (1 cement : 3 sand : 6 block bats) including mixing of water proofing compound 4 % by weight of cement to sunk portions of toilets, deck etc. complete to the entire satisfaction of the PM. Further surfaces shall be screeded with (1:1.5:3) cement concrete mix with 4% by weight of cement approved waterproofing compound about 20-30mm thick and finished smooth or ready to receive finish material as specified. Care shall be taken prior to filling all pipes passing through sunk portion are pressure tested by maintaining pressure for 24 hours and junctions of pipes passing through walls, slabs are well grouted and sealed. This shall be tested by ponding water for 100mm thickness and maintaining for 72 hours. | Cu m
4.6.A | CIVIL | waterproofing | Brick bats coba | Filling brick bats coba (.... mm thick) | Providing and filling brick bats coba 150mm thick) with cement mortar mixed in ratio 1:3:6 (1 cement : 3 sand : 6 block bats) including mixing of water proofing compound 4 % by weight of cement to sunk portions of toilets, deck etc. complete to the entire satisfaction of the PM. Further surfaces shall be screeded with (1:1.5:3) cement concrete mix with 4% by weight of cement approved waterproofing compound about 20-30mm thick and finished smooth or ready to receive finish material as specified. Care shall be taken prior to filling all pipes passing through sunk portion are pressure tested by maintaining pressure for 24 hours and junctions of pipes passing through walls, slabs are well grouted and sealed. This shall be tested by ponding water for 100mm thickness and maintaining for 72 hours. WITH LIGHT WEIGHT SIPOREX BLOCK. | Cu m | 5.055 | 9500 | 48022.5 | 5.2454 | 49831.395 | as certify | 225mm hight rate change
4.7 | CIVIL | waterproofing | Crystalline waterproofing | Installing proprietary crystalline waterproofing system | Designing, providing and installing proprietary crystalline waterproofing system to inside surfaces of the water retaining structures System shall consist of preparation of surfaces including ‘V’ grooves at junctions and joints, pressure grouting the same and curing. Applying crystalline waterproofing compound one / two coat at specified intervals and as recommended by manufacturer and allowed to cure. Walls plastering and finished smooth with about 15mm thick with cement sand mortar 1:4 (1 cement : 4 sand) using 2% of waterproofing compound by weight of cement. Floors to have average 30 mm thick IPS to gradient 1:2:4 (1 cement : 2 sand : 4 aggregate) with waterproofing compound 2% be weight of cement including required wattas, rounding of corners; junctions with walls and floor finished smooth and cured. Tank shall be tested by filling the water and maintaining it for 72 hrs. leakage. Contractor shall provide 10 year guarantee for waterproofing on Rs.100/- stamp paper in a approved proforma. | Sq. m
4.7.1 |  |  |  |  | OHT Waterproofing | Sq m
4.7.2 |  |  |  |  | Basement Water Tank Waterproofing | Sq m
4.7.3 |  |  |  |  | STP Waterproofing | Sq m
4.8 | CIVIL | waterproofing | chemical water proofing system for Landscape areas | Waterproofing system to Landscape areas | Designing, providing and applying Waterproofing system to Landscape areas through approved agencies consisting of | Sq m
a) Cementious based chemical waterproofing coating (two / three coats) system including preparation of surfaces to receive approved chemicals, curing
b) Perlite concrete of density 450 kg/cum and of minimum 75 mm thickness at draining point and rest area sloped to drain water as detailed in drawing.
c) Perforated Mel drain system. ”Mel Drain” matrix soil filter cum drainage system from M/s WR Meadows Inc. USA. or.’J’ drain Inc. USA or equivalent approved.
d) 3.2 mm thick APP Polymer modified polyester reinforced (Garden Moply FP 4) of Texsa Ltd. or equivalent approved.
4.8.1 |  |  | Water proof screed | Membrane protected by 30 mm thick water proof screed in CM mix ratio (1:4) | Membrane protected by 30 mm thick water proof screed in CM mix ratio (1:4) spread over entire terrace area and finished to receive Architectural finish. Walls plastered with 12 mm thick CM 1:4. Work to include adding Polypropylene Fibermesh fibres with Microban to mortar in proportion recommended by the manufacturer with use of approved products and work carried out as per approved shop drawings, instructions and specifications of the manufacturer of product. Also include required preparation of the surface, etc. testing by pounding water for 72 hours and giving guarantee for 10 years on Rs.100/- Stamp paper in approved proforma. | Sq m
4.8.2 |  |  | Water proof screed | Membrane protected by 18/20 mm thick water proof screed in CM mix ratio (1:4) | Membrane protected by 18/20mm thick water proof screed in CM mix ratio (1:4) spread over entire terrace area and finished to receive Architectural finish. Walls plastered with 12 mm thick CM 1:4. Work to include adding Polypropylene Fibermesh fibres with Microban to mortar in proportion recommended by the manufacturer with use of approved products and work carried out as per approved shop drawings, instructions and specifications of the manufacturer of product. Also include required preparation of the surface, etc. testing by pounding water for 72 hours and giving guarantee for 10 years on Rs.100/- Stamp paper in approved proforma. FOR WET AREA. | Sq m | 36 | 591 | 21276 | 35.8194 | 21169.2654
4.9 | CIVIL | waterproofing | Terrace waterproofing | waterproofing consisting of light weight block bat coba in cement mortar mix in ratio of 1:5 | Designing, providing and installing average 110mm thick proprietary terrace waterproofing consisting of light weight block bat coba in cement mortar mix in ratio of 1:5 (1 cement : 5 sand) with approved waterproofing compound at the rate as specified by approved manufacturer including applying to cleaned, grouted concrete base surface, proprietary chemical water proofing system consisting of polymer modified acrylic bases coating in two coats in slurry form (total consumption of 1.5 Kg/Sqm) as approved by the PM and as directed by the approved manufacturer of waterproofing coating, and laying block bats to required slope; outlet and rain water pipes grouted (minimum thickness 75mm). Also proving and fixing 75mm thick Fomular metric extruded polystyrene insulation with U Value 0.051 Btu/Hr.Sft.oF, density 31 Kg/Cum and Comp. strength 250 kPa); including cleaning and preparing the surface, fixing and jointing with approved adhesive all complete. Further it shall be provided with protective layer, geotextile mat of 160 gsm min. and shall be loose laid over the roof slab. Laying of 1.14 mm thick approved Membrane conforming to ASTM D 6134-97 on horizontal surface and fully adhered on vertical surface. The size of Membrane shall be large enough to minimize the number of joints. Adjacent sheet shall be laid in similar fashion with an overlap at least 150 mm. The overlap shall be cleaned using a primer as specified by the manufacturer. The overlap joint then be sealed using a double sided quick seam splice tape as per manufacturer specification, sealing corners and drains etc. The Membrane will be mechanically fastened using base tie-in fastening system. The counter flashing will cover the top of the fastening system by a minimum of 100 mm. Sealing corners and drains etc. The Membrane shall be terminated on vertical surface using Aluminium Termination strip and sealed with water block and sealant. Thereafter protective layer of geotextile mat of 120 gsm shall be laid over Membrane with an overlap of 75 mm spot stuck with neoprene base bonding adhesive. Finally it shall be protected with 30mm thick IPS 1:2:4 (1 cement : 2 sand : 4 aggregates) with adding waterproofing compound 4% by weight of cement ready to receive floor finish. System to be carried over parapet wall about 300mm high from finish floor level. testing by ponding water about 200 mm high for 72 hrs. protecting till handover, testing for heat insulation etc. all complete as per specifications or equivalent as approved by the PM; contractor to provide guarantee for 10 years on Rs.100/- stamp paper in approved proforma. | Sq m
4.9.1 | CIVIL | waterproofing | Terrace waterproofing | providing and installing | Providing and installing proprietary in-depth crystalline waterproofing system to floor areas
[5 empty] | - Clean the RCC concrete surface with brush. Remove sharp protrusion by chipping and local repairs. | Sq m
[5 empty] | - Apply crystalline waterproofing compound one / two coat on dry surface at specified intervals and as recommended by manufacturer and allowed to cure. | Sq m
[5 empty] | TOTAL OF WATERPROOFING WORK |  |  |  | 202958.1 |  | 214155.075

## MB
MB Sheet CIVIL MASONRY BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU
SR.NO | Item Description | Unit | No | Length | Breadth | Total Quantity
A | General Site Works
4.4 | Laying proprietary chemical water proofing system ON THE MOTHER SLAB | [6 empty] | Certify
| electrical room | SQMT | 1 | 1.46 | 1.3 | 1.898 |  | 1.36
| kitchen area | SQMT | 1 | 6.49 | 2.46 | 15.9654
| live kitchen | SQMT | 1 | 5.1 | 2.86 | 14.586 |  | 4.94
| chamber | SQMT | 4 | 0.3 | 0.3 | 0.36
| chamber | SQMT | 2 | 0.3 | 0.6 | 0.36
| ramp | SQMT | 1 | 1 | 1.4 | 1.4
| Total |  |  |  |  | 34.5694 |  | 32.58
4.4.A | Laying proprietary chemical water proofing system ON THE VERTICAL SURFACES UPT0 900MM HEIGHT. | [6 empty] | Certify
| electrical room with ramp | SQMT | 4 | 1 | 1.46 | 5.84 |  | 2 | 0.9 | 1.36 | 2.448
| electrical room | SQMT | 2 | 1 | 1.3 | 2.6 |  | 1 | 0.9 | 1.3 | 1.17
| less door | SQMT | -2 | 0.9 | 0.75 | -1.35 |  | -2 | 0.9 | 0.75 | -1.35
| electrcal frot door | SQMT | 1 | 1 | 1.4 | 1.4 |  | 1 | 0.9 | 1.4 | 1.26
| kitchen front right and laft | SQMT | 2 | 1 | 6.49 | 12.98 |  | 2 | 0.9 | 6.49 | 11.682
| kitchen desh wall | SQMT | 3 | 1 | 2.46 | 7.38 |  | 3 | 1 | 2.46 | 7.38
| less door | SQMT | -2 | 0.9 | 0.78 | -1.404 |  | -3 | 0.9 | 0.78 | -2.106
| live kichan wall | SQMT | 2 | 0.9 | 5.1 | 9.18 |  | 2 | 0.9 | 4.94 | 8.892
| live kichan door side wall | SQMT | 2 | 0.9 | 2.86 | 5.148 |  | 2 | 0.9 | 2.86 | 5.148
| less door | SQMT | -2 | 0.8 | 0.9 | -1.44 |  | -2 | 0.8 | 0.9 | -1.44
| chmber | SQMT | 32 | 0.2 | 0.3 | 1.92 |  | 32 | 0.2 | 0.3 | 1.92
| chmber | SQMT | 16 | 0.2 | 0.6 | 1.92 |  | 16 | 0.2 | 0.6 | 1.92
| door dhar | SQMT | 6 | 1 | 0.2 | 1.2 |  | 6 | 1 | 0.2 | 1.2
| ramp[ | SQMT |  |  |  | 0
[6 empty] | 45.374 |  |  |  |  | 38.124
11.1 | 12mm thick Gypsum False Ceiling-FOH Area
| sofa side live kichan cold and hot wall ellevayin bb | SQMT | 1 | 9.886 | 8.664 | 85.6523 |  | 1 | 9.886 | 8.664 | 85.6523
| sofa side live kichan wall elevation bb | SQMT | 1 | 4.6 | 5 | 23 |  | 1 | 4.6 | 5 | 23
[7 empty] | deduction | -1 | 1.18 | 2.05 | -2.419
[8 empty] | -1 | 0.64 | 1 | -0.64
[6 empty] | 108.6523 |  |  |  |  | 105.5933
[6 empty] | 5.4326 |  |  |  |  | 5.2797
4.4.A | Filling light weight block bats (100 mm thick)
| electrical room | SQMT | 1 | 1.46 | 1.3 | 1.898 |  | 1 | 1.36 | 1.3 | 1.768
| door | SQMT | 1 | 1.5 | 1.1 | 1.65 |  | 1 | 1.5 | 1.1 | 1.65
| kitchen area | SQMT | 1 | 6.49 | 2.46 | 15.9654 |  | 1 | 6.49 | 2.46 | 15.9654
| live kitchen | SQMT | 1 | 5.1 | 2.86 | 14.586 |  | 1 | 5.1 | 2.86 | 14.586
| out side ramp | SQMT | 2 | 1 | 1 | 2 |  | 1 | 1 | 1 | 1
[6 empty] | 36.0994 |  |  |  |  | 34.9694
[6 empty] | 5.4149 |  |  |  |  | 5.2454
4.8.2 | Membrane protected by 18/20 mm thick water proof screed in CM mix ratio (1:4)
| electrical room | SQMT | 1 | 1.46 | 1.3 | 1.898
| door | SQMT | 1 | 1.5 | 1.1 | 1.65
| kitchen area | SQMT | 1 | 6.49 | 2.46 | 15.9654
| live kitchen | SQMT | 1 | 5.1 | 2.86 | 14.586
| chamber | SQMT | 4 | 0.3 | 0.3 | 0.36
| chamber | SQMT | 2 | 0.3 | 0.6 | 0.36
| out side ramp | SQMT | 1 | 1 | 1 | 1
35.8194

## E. Masonry & Plaster
FEBRUARY 2020
TRAVEL FOOD SERVICES
BOQ STANDARDISATION, IMPLEMENTATION AND COST CONSULTANCY |  |  |  |  | CIVIL MASONRY BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU
M&A Bill
SR. NO. | WBS | WBS Level1 | WBS Level 2 | SHORT ITEM DESCRIPTION | PARTICULARS | UOM | QTY. | Final rate | Amount | Qty | Amount | remark
GENERAL NOTES
a |  |  |  |  | Please refer to "Exhibit A - Basic rate of material" for the applicable base rates of materials
c |  |  |  |  | Items of works shall to be read in conjunction with Drawings, Specifications, Contractual terms and conditions and Trade Preambles to this BOQ as included in the RFP.
d |  |  |  |  | The quantities mentioned in the BOQ is tentative and may increase or decrease. Payment shall be restricted to the quantum of work executed and measured as per the defined mode of measurement.
e |  |  |  |  | The Mode of Measurement (in order of priority) is as follows:
(i) As defined in relevant item in the BOQ
(ii) As defined in the specification
(iii) As defined in IS-1200 (latest version) for relevant trade.
(iv) if mode is not defined in (i), (ii) and (iii), the standard industry practice shall be adopted.
Items of work and trade preambles are essential parts of the bill of quantities and are to be taken as mutually explanatory of one another. Requirement occurring in one is binding as though occurring in both. In resolving conflicts, discrepancies, errors or omissions as regards trade preambles & bill of quantities the following order of precedence shall be used but subject to PRIORITY OF DOCUMENTS as included in General Conditions of Contract: a. General Notes as included in this bill of quantities. b. Trade Preambles as included in RFP. c. Item Description as included in this bill of quantities.
All Masonry shall be with gap of 10mm filled with 1:10 cement mortar on all three sides. At top place 10mm thick approved bituminous impregnated sheets. Concrete block masonry shall be anchored by 250x50x3mm thick GI metal strip fixed with GI screws into concrete at every 600mm c/c.
6 |  |  |  |  | MASONRY WORK | [6 empty] | Certify qty
6.1 | CIVIL | Masonry | AAC concrete blocks | For 300mm or 200mm thick concrete block masonry | Providing and constructing 300mm /200mm thick concrete block masonry made out from AAC concrete blocks conforming to IS 2185 (Part-III) having minimum crushing strength 30 Kg/Sq. cm and maximum water absorption 10%, in cement sand mortar CM 1:5 (1 cement : 5 sand) mixed with approved non-shrinking compound as per manufacturer’s instructions complete with required raking out joints, curing, doing independent double legged scaffolding etc. as per specification at all heights, depths and leads to entire satisfaction of the PM.
6.1.1 |  |  |  | 300mm thick wall | for 300mm thick concrete block masonry | Sq. m
6.1.2 |  |  |  | 200mm thick wall | for 200mm thick concrete block masonry | Sq. m
6.2 | CIVIL | Masonry | AAC concrete blocks | 150mm or 100mm thick concrete block masonry | Providing and constructing 150mm /100mm thick concrete block masonry made out from AAC concrete blocks conforming to IS 2185 (Part-III) having minimum crushing strength 30 Kg/Sq. cm and maximum water absorption 10%, in cement mortar CM 1:4 (1 cement : 4 sand) mixed with approved non-shrinking compound as per manufacturer’s instructions, including providing RCC patli beam of 150mm x 100mm at every 1.00m C/C with 2 nos. 8 mm dia Tor bars and 6 mm dia links at 300 c/c in cement concrete of mix M 20, required formwork complete with raking out joints, curing, doing independent double legged scaffolding as per specifications etc. at all heights, depths and leads as directed by the PM to his entire satisfaction. (Patli beam is including reinforcement part of the item)
6.2.1 |  |  |  | 150mm thick wall | for 150mm thick concrete block masonry (UPTO TRUE CEILING LEVEL OF 6000MM HEIGHT) | Sq. m | 66.906 | 1614 | 107986.284 | 51.5415 | 83187.981
6.2.1.A |  |  |  | 150mm thick wall | for 150mm thick concrete block masonry (UPTO 3000MM HEIGHT) | Sq. m | 5.55 | 1500 | 8325 | 6.138 | 9207
6.2.2 |  |  |  | 100mm thick wall | for 100mm thick concrete block masonry (UPTO 1200MM HEIGHT) | Sq. m | 2.01 | 1360 | 2733.6 | 11.747 | 15975.92 | as certify
6.3 | CIVIL | Masonry | Solid concrete block masonry | 1) 200mm/150mm/100mm thick solid concrete block masonry | Providing and constructing 200mm/150mm/100mm thick solid concrete block masonry in superstructure with approved factory made blocks having minimum crushing strength 100 Kg/Sq. cm and maximum water absorption 10%, in cement mortar mix ratio CM 1:5 (1 cement: 5 Sand) mixed with approved non-shrinking compound, doing masonry in specified courses, complete with raking out joints, curing, doing independent double legged scaffolding, complete as per specifications etc. at all heights, depths and leads and as directed by PM to his entire satisfaction.
6.3.1 |  |  |  | 200mm thick wall | 200mm thick solid concrete block masonry in CM 1:5 | Sq. m
6.3.2 |  |  |  | 150mm thick wall | 150mm thick solid concrete block masonry in CM 1:4 | Sq. m
6.3.3 |  |  |  | 100mm thick wall | 100mm thick solid concrete block masonry in CM 1:4 | Sq. m
6.4 | CIVIL | Masonry | Bricks Masonry | 1) 230mm or more/half brick (115mm) thick masonry | Providing and constructing 230mm or more/115mm thick masonry with locally available approved quality bricks having minimum crushing strength 35 Kg/Sq. cm and water absorption maximum 20% in cement sand mortar CM 1:6 (1 cement : 6 Sand) mixed with approved non-shrinking compound as per manufacturer’s instruction in specified courses of approved bond and including raking out joints, curing, doing independent double legged scaffolding, all complete as per specifications etc. at all heights, depths and leads, dewatering area where required complete as per specifications etc. all as directed by PM to his entire satisfaction.
6.4.1 |  |  |  | 230mm or more thick wall | 230mm or more thick masonry in CM 1:6 (1 cement : 6 Sand) | Sq. m
6.4.2 |  |  |  | 115mm thick wall | half brick (115mm thick) masonry in CM 1:4 (1 cement : 4 Sand) | Sq. m
6.5.1 | CIVIL | Masonry | Rubble masonry | Random Rubble masonry | Providing and constructing Random Rubble masonry using cement mortar (1:4), including providing Header stones / Bond stones for every 0.50 Sq.m of masonry surface, corner stones/ quoin stones at corners not less than 0.03 Cum., hammer dressing on face, sides and bed with bushing on the exposed face not more than 20mm and face joints not more than 20mm, erecting and removal of scaffolding, raking out joints, flush pointing in CM (1:4), cleaning, wetting, filling with mortar, watering and providing weep holes as directed by PM etc. Complete to entire satisfaction of the PM. | Cu m
6.5.2 | Civil | Masonry | Rubble masonry | Uncoursed Rubble masonry | Providing and laying Uncoursed Rubble masonry of trap / granite / quartzite / gneiss stones in foundations, plinth, superstructure in 1:6 cement mortar including raking out joints, staging, scaffolding and curing, etc. complete as directed by Engineer-In-Charge. | Cum
6.6 | CIVIL | Masonry | Solid concrete block masonry | Bund wall with concrete block masonry | Providing and constructing 200mm thick solid concrete block masonry as Bund wall upto height of 450mm with approved factory made blocks having minimum crushing strength 100 Kg/Sq. cm and maximum water absorption 10%, in cement mortar mix ratio CM 1:5 (1 cement: 5 Sand) mixed with approved non-shrinking compound, doing masonry in specified courses, complete with raking out joints, curing, complete as per specifications etc. at all depths and leads and as directed by PM to his entire satisfaction. [ cement consumption= 0.12 Bag / Sqm ] | Sq. m
6.7 | Civil | Masonry | Chamber | Brick masonry chamber | Providing and constructing Brick masonry chambers with C.M. 1:4, 600mm heavy duty D.I. cover each including necessary scaffolding, finishing, curing etc. complete. with good quality bricks as directed by Engineer-In-Charge.
6.7.1 |  |  |  |  | 600 x 600 x D = 450mm (for rain water pipes) | Nos.
6.7.2 |  |  |  |  | 600 x 600 x D = 750mm avg. depth(for effluent drain) | Nos.
6.7.3 |  |  |  |  | 700 x 400 x 150mm D avg. depth(for effluent drain) | Nos. | 1 | 16000 | 16000 | 2 | 32000 |  | discuss sir
6.7.4 |  |  |  |  | 400 x 400 x 150mm D avg. depth(for effluent drain) | Nos. | 5 | 11000 | 55000 | 4 | 44000 |  | discuss sir
6.8 | CIVIL | Masonry | Light Weight Block | Siporex Block | Providing and applying of light weight brick wall (Siporex Block ) wall complete, as directed by Engineer-In-Charge. Having 3m and 6 m height . | Cum
6.9 | CIVIL | Masonry | Concrete Block | cement concrete hollow block | Providing and fixing up to floor five level precast cement concrete hollow block, including hoisting and setting in position with cement mortar 1:3 (1 cement : 3 coarse sand), cost of required centering, shuttering complete. | Cum
6.1 | CIVIL | Masonry | Raised Flooring | Debris filling | Providing and constructing Debris filling to raise the flooring as per drawing etc. complete as directed by Engineer-In-Charge | Cum
7 |  |  |  |  | PLASTERING WORK
7.1 | CIVIL | Plaster | Plaster by premix mortar | 12mm thick plaster with premix mortar | Providing and applying 12mm thick plaster with premix mortar mix of ratio CM 1:4 (1 cement : 4 sand) with air entraining agent Cebex 112, 150ml per bag of cement, to internal surfaces of concrete and masonry work; including raking out joints, hacking concrete surfaces and applying approved chemical bonding agent for receiving cement finished / dash coat plaster and applying a scratch coat over concrete surfaces by bonding / adhesive chemical coat as directed by approved manufacturer to create a key, cleaning / grooving deep junctions of concrete & masonry, grouting then back by mortar mixed with non shrinking compound along with packing of clean, fresh square cut aggregate; also providing and fixing 20 gauge PVC mesh @ 150 mm wide to junctions of concrete and masonry, preparing jambs, sills, grooves, pattas, wattas, rounding of corners, all complete as per architectural drawings, specifications and finished smooth with wooden rundha or as specified by the PM at all leads, depth and lifts, doing independent double-legged scaffolding, cleaning of surfaces, curing, complete as per specification and to the approval of the PM. (Location : Vertical wall / partition wall of any type) | Sq m
7.1.A |  |  |  |  | FOR THE BOTH SIDES OF NEW CONSTRUCTED BLOCK MASONRY UPTO 4300MM HEIGHT. | Sq. m | 91.091 | 914 | 83257.174 | 189.559 | 173256.926 | as certify
7.1.B |  |  |  |  | FOR THE BOTH SIDES OF NEW CONSTRUCTED BLOCK MASONRY UPTO 3000MM HEIGHT. | Sq. m | 11.1 | 914 | 10145.4
7.1.C |  |  |  |  | FOR THE BOTH SIDES OF NEW CONSTRUCTED BLOCK MASONRY UPTO 1200MM HEIGHT. | Sq. m | 4.02 | 914 | 3674.28
7.1.D |  |  |  |  | FOR THE ONE SIDE OF EXISING BLOCK MASONRY / COLUMNS UPTO 4300MM HEIGHT. | Sq. m | 132.44 | 914 | 121050.16
7.1.E |  |  |  |  | FOR THE ONE SIDE OF EXISING BLOCK MASONRY / COLUMNS UPTO 3000MM HEIGHT. | Sq. m | 51.9 | 914 | 47436.6
7.1.1 |  | common Plaster | Plaster by Ready mix cement mortar | 12mm thick plaster with Ready mix cement mortar | Providing and applying 12mm thick plaster with Ready mix cement mortar mix of CM 1:4 (1 cement : 4 sand) with air entraining agent Cebex 112, 150ml per bag of cement, to internal surfaces of concrete work; including hacking concrete surfaces then applying approved chemical bonding agent and applying a scratch coat over concrete surfaces by bonding / adhesive chemical coat as directed by approved manufacturer to create a key, cleaning / grooving deep junctions of concrete & masonry, grouting then back by mortar mixed with non shrinking compound along with packing of clean, fresh square cut aggregate, preparing grooves, pattas, wattas, rounding of corners, all complete as per architectural drawings, specifications and finished smooth with wooden rundha or as specified; at all leads, depth and lifts, doing independent double-legged scaffolding, cleaning of surfaces, curing, complete as per specification and to the approval of the PM. | Sq m
7.2 | CIVIL | Plaster | Gypsum plaster | Gypsum plaster to internal walls and ceilings | Providing, preparing and plastering readymade proprietary Gypsum plaster to internal walls and ceilings average 12mm thick, wall surfaces of concrete, masonry work, including doing jambs, sills, grooves, wattas, rounding of corners etc. all complete as per architectural drawing, specification and directed by PM, at all lift, lead and depth, doing independent double legged scaffolding, making gypsum plaster mix as per approved manufacturer’s instruction, providing and fixing 20 gauge GI chicken mesh 150 mm wide to junctions of concrete and masonry, hacking closely concrete surfaces, apply chemical adhesive coating on concrete surfaces and apply scratch coat plaster etc. complete as approved by PM. Plastering shall be to correct line, levels and plumb including curing, cleaning etc. complete to entire satisfaction of PM. | Sq m
7.3 | CIVIL | Plaster | Gypsum plaster | Gypsum plaster to walls / ceilings of ducts and inside the boxing masonry | - Do - as per Item No. 8.2 but to walls / ceilings of ducts and inside the boxing masonry including adding approved waterproofing compound 2% by weight of cement or as directed by the PM to his entire satisfaction. | Sq m
7.4 | CIVIL | Plaster | Double coat cement sand plaster | 25 mm thick double coat cement sand plaster | Providing and applying minimum 25 mm thick double coat cement sand plaster; first coat to be 15 mm thick Ready mix cement sand mortar of mix ratio CM 1:4 (1 cement : 4 sand) including adding 2% by weight of cement approved waterproofing compound of approved manufacturer, second coat to be 10 mm thick Ready mix cement sand mortar of mix ratio CM 1:3 (1 cement : 3 sand), finished sand face or as required to receive specified architectural external finish to correct line, plumb and level to external faces of walls, soffits/ceiling if any, including hacking concrete surfaces then applying chemical adhesive coating and a scratch/dash coat as a positive bond, curing the same, racking out junctions of masonry and concrete, then pointing and grouting using non-shrinking compound, joints grouted by pressing square crushed stone, further providing 150mm wide 20 gauge GI chicken mesh at junctions of concrete and masonry work, doing independent double legged scaffolding; at all levels and locations and leads. Item also include plastering to window sills, RCC cornices, making wattas, drip-moulds, pattas, grooves, doing curing, cleaning, all complete to the approval of the PM. (To External Surfaces) | Sq. m
7.5 | CIVIL | Plaster | Skimming plaster | Skimming plaster of approved make to internal dry wall surfaces. | Providing and applying Skimming plaster of approved make to internal dry wall surfaces as specified by the PM at all leads, depth and lifts, doing independent double-legged scaffolding, cleaning of surfaces, curing, complete as per specification and to the approval of the PM. (Location : Plaster to Internal dry walls) | Sq. m
7.6 | CIVIL | Plaster | White cement based putty | White cement based putty of average thickness 1 mm | Providing and applying white cement based putty of average thickness 1 mm, of approved brand and manufacturer, over the plastered wall surface to prepare the surface even and smooth complete. | Sq. m
7.7 | CIVIL | Plaster | Putty | Applying of Alltek / Birla or equivalent Putty to wall surfaces | Providing and applying of Alltek / Birla or equivalent Putty to wall surfaces. Putty not to be applied on those surfaces which are getting panelled. All wall surfaces to be marked for putty work and approval taken, etc. complete. As directed by Engineer-In-Charge. | Sq. m
7.8 | CIVIL | Plaster | Water Proofing | 2 Coat T20MM Water proofing of Ratio 1:4 CM | Providing and applying of 2 Coat T20MM Water proofing of Ratio 1:4 CM . Having 3m and 6 m height . | Sq. m
7.9 | CIVIL | Plaster | POP over Cement plaster | 6 to 8mm thick POP over Cement plaster | Providing and applying of 6 to 8mm thick POP over Cement plaster, etc. complete, as directed by Engineer-In-Charge. Having 3m and 6 m height . | Sq. m
[5 empty] | TOTAL OF PLASTERING WORK |  |  |  | 455608.498 |  | 357627.827

## MB Emasonry
MB Sheet CIVIL MASONRY BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU
SR.NO | Item Description | Unit | No | Length | Breadth | Total Quantity
A | General Site Works
6.2.1 | 150mm thick concrete block masonry UPTO TRUE CEILING LEVEL OF 6000MM HEIGHT | [5 empty] | Certify
| Service Kitchen Area Entry LHS Wall Making | SQMT | 1 | 5.1 | 7.5 | 38.25
| live kitchen | SQMT | 1 | 5 | 1.4 | 7
| live kitchen door side | SQMT | 1 | 2.46 | 1.4 | 3.444
| less door | SQMT | -1 | 0.9 | 1.4 | -1.26
| door exit | SQMT | 1 | 1.4 | 2.8 | 3.92
| bun wall | SQMT | 1 | 0.75 | 0.25 | 0.1875
51.5415
6.2.1.A | 150mm thick concrete block masonry UPTO TRUE CEILING LEVEL OF 3000MM HEIGHT
| kichen door | SQMT | 1 | 2.46 | 3.3 | 8.118
| less door | SQMT | -1 | 2.2 | 0.9 | -1.98
6.138
6.2.2 | 100mm thick concrete block masonry
| electrical wall | SQMT | 1 | 1.47 | 3.3 | 4.851 | 1 | 1.47 | 3.3 | 4.851
| electrical wall |  | 1 | 0.6 | 3.3 | 1.98 | 1 | 0.6 | 3.3 | 1.98
| electrical wall door above |  | 1 | 2.46 | 1.1 | 2.706 | 1 | 2.46 | 1.1 | 2.706
| dish wash |  | 2 | 1.7 | 1.3 | 4.42 | 1 | 1.7 | 1.3 | 2.21
[6 empty] | 13.957 |  |  |  | 11.747
6.7.3 | 700 x 400 x 150mm D avg. depth(for effluent drain) [pot wash and main chmber | NO | 2 |  |  | 2
6.7.4 | 400 x 400 x 150mm D avg. depth(for effluent drain) | NO | 4 |  |  | 4
7.1.A | 12mm thick plaster with premix mortar
| main wall | SQMT | 1 | 5.1 | 3.3 | 16.83 | 2 | 5.1 | 3.3 | 33.66
| live kitchen | SQMT | 2 | 5 | 1.4 | 14 | 2 | 5 | 1.4 | 14
| live kitchen entrance door side | SQMT | 2 | 2.46 | 1.4 | 6.888 | 2 | 2.46 | 1.4 | 6.888
| less door | SQMT | -2 | 0.9 | 1.4 | -2.52 | -2 | 0.9 | 1.4 | -2.52
| live kitchen door side | SQMT | 2 | 2.46 | 3.3 | 16.236 | 2 | 2.46 | 3.3 | 16.236
| less door | SQMT | -1 | 0.9 | 2.1 | -1.89 | -2 | 0.9 | 2.1 | -3.78
| door exit | SQMT | 3 | 1.4 | 3.3 | 13.86 | 3 | 1.4 | 3.3 | 13.86
| electrical wall | SQMT | 2 | 1.47 | 3.3 | 9.702 | 2 | 1.47 | 3.3 | 9.702
| electrical wall | SQMT | 1 | 1.65 | 3.3 | 5.445 | 1 | 1.65 | 3.3 | 5.445
| electrical wall door above | SQMT | 2 | 2.46 | 3.3 | 16.236 | 2 | 2.46 | 3.3 | 16.236
| less door | SQMT | -1 | 1.8 | 2.1 | -3.78 | -1 | 1.8 | 2.1 | -3.78
| kichan old wall | SQMT | 1 | 6.48 | 3.3 | 21.384 | 1 | 6.48 | 3.3 | 21.384
| dish wash | SQMT | 1 | 2.46 | 3.3 | 8.118 | 1 | 2.46 | 3.3 | 8.118
| dish wash | SQMT | 2 | 1.9 | 1.7 | 6.46 | 2 | 1.9 | 1.7 | 6.46
| dish wash | SQMT | 2 | 0.85 | 0.3 | 0.51 | 2 | 0.85 | 0.3 | 0.51
| live kichan back wall | SQMT | 1 | 4.9 | 3.3 | 16.17 | 1 | 4.9 | 3.3 | 16.17
| FOH area gray tile and marble | SQMT | 1 | 5 | 4.2 | 21 | 1 | 5 | 4.2 | 21
| back counter | SQMT | 1 | 2 | 4.2 | 8.4 | 1 | 1.9 | 4.2 | 7.98
| back counter | SQMT | 1 | 1.1 | 1.4 | 1.54 | 1 | 1.1 | 1.4 | 1.54
| chmber | SQMT | 4 | 2.2 | 0.2 | 1.76 | 2 | 0.75 | 0.3 | 0.45
| chmber | SQMT | 4 | 1.2 | 0.2 | 0.96
| chmber | SQMT | 2 | 2.8 | 0.2 | 1.12
| chmber | SQMT | 2 | 1.8 | 0.2 | 0.72
| bun wall | SQMT | 2 | 0.75 | 0.3 | 0.45
[6 empty] | 179.599 |  |  |  | 189.559

## G.Flooring
FEBRUARY 2020
TRAVEL FOOD SERVICES
BOQ STANDARDISATION, IMPLEMENTATION AND COST CONSULTANCY | [5 empty] | FLOOR FINISHING BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU | [7 empty] | M&A final bill
SR. NO. | SERVICE / MATERAL CODE | WBS | WBS Level1 | WBS Level 2 | SHORT ITEM DESCRIPTION | PARTICULARS | UOM | QTY. | Basic Rate of Material | Supply Rate | Fixing Rate | Total Rate (Supply +Fixing) | Total Amount | Qty | Amount | Remark
GENERAL NOTES
a | [5 empty] | Please refer to "Exhibit A - Basic rate of material" for the applicable base rates of materials
c | [5 empty] | Items of works shall to be read in conjunction with Drawings, Specifications, Contractual terms and conditions and Trade Preambles to this BOQ as included in the RFP.
d | [5 empty] | The quantities mentioned in the BOQ is tentative and may increase or decrease. Payment shall be restricted to the quantum of work executed and measured as per the defined mode of measurement.
e | [5 empty] | The Mode of Measurement (in order of priority) is as follows:
(i) As defined in relevant item in the BOQ
(ii) As defined in the specification
(iii) As defined in IS-1200 (latest version) for relevant trade.
(iv) if mode is not defined in (i), (ii) and (iii), the standard industry practice shall be adopted.
Items of work and trade preambles are essential parts of the bill of quantities and are to be taken as mutually explanatory of one another. Requirement occurring in one is binding as though occurring in both. In resolving conflicts, discrepancies, errors or omissions as regards trade preambles & bill of quantities the following order of precedence shall be used but subject to PRIORITY OF DOCUMENTS as included in General Conditions of Contract: a. General Notes as included in this bill of quantities. b. Trade Preambles as included in RFP. c. Item Description as included in this bill of quantities.
9 | [5 empty] | FLOORING WORK
9.1 |  | CIVIL | Flooring | Vacuum dewatered | 75mm thick vacuum dewatered | Providing, machine mixing and laying of 75mm thick vacuum dewatered (Tremix or equivalent) concrete grade M20 including steel form work, compaction, dewatering etc. as specified and as per recommendation of manufacturer of equipment, designing of bays and getting approval of PM, cutting structurally required grooves after concreting to allow expansion of joint, about 1/3rd depth of concrete and 6mm wide, filling grooves with pour quality bitumen sealant of approved make, power floating and broom finishing or finishing smooth as specified / instructed, cleaning, curing surface etc. all complete to the entire satisfaction of the PM. (Location : Parking areas) | Sq m
9.2 |  | CIVIL | Road Marking | Thermoplastic road / car park | Providing & Laying of hot applied thermoplastic road / car park | Providing & Laying of hot applied thermoplastic road / car park marking compound 1 to1.5 mm thick using indigenous modern propeller road marking machine including reflectorizing glass beads at 250grams per square meter area, thickness of 1 to 1.5 mm is exclusive of surface applied glass beads , as per the code of practice for Road marking with paints, including cleaning the Basement/Driveway surfaces for applying the road marking compound all as directed , including all materials, tools, Labours, brushes, equipment's, fuel etc., complete as per the satisfaction of PM.
9.2.1 | [5 empty] | Road / Car Park Marking (Width less than 200mm) | Rmt
9.2.2 | [5 empty] | Road / Car Park Marking | Sq m
9.3 |  | CIVIL | Road | Concrete Pavers Block | 80 mm thick interlocking unishape | Providing & fixing 80 mm thick interlocking unishape concrete pavers (monolithic- single layer precast concrete blocks) in grey cement in the carriageway having average crushing strength of not less than 50 N/mm2 as per technical specifications and IS Code 15658:2006, placed on average compacted thickness of 25 mm, well graded sand cushioning uniformly compacted with proper capacity mechanical compactor with the proper level, grade and camber etc. complete as specified and as directed by the Engineer. | Sq m
9.4 |  | CIVIL | Footpath | Concrete Pavers Block | 60 mm thick interlocking unishape | Providing & fixing 60 mm thick interlocking unishape concrete pavers (monolithic- single layer precast concrete blocks) in grey cement having average crushing strength of not less than 40 N/mm² as per technical specifications and IS Code 15658:2006, placed on average compacted thickness of 25 mm, well graded sand cushioning uniformly compacted with proper capacity mechanical compactor with required level, grade and camber etc. complete as specified and as directed by the Engineer. | Sq m
9.5 |  | CIVIL | Road | Concrete Pavers Block | 80 mm thick Concrete Pavers Block (removing & refixing) | Removing & refixing interlocking concrete pavers of 80 mm thick, of any size, shape and colour considering 10% breakage area of paver block while removing the same from position and replacing the same by new paver blocks having average crushing strength not less than 50 N/mm² as per technical specifications and IS Code 15658:2006, placed on average compacted thickness of 25 mm well graded sand cushioning uniformly compacted with proper capacity mechanical compactor with required level, grade and camber etc. complete as specified and as directed by the Engineer. | Sq m
9.6 |  | CIVIL | Footpath | Concrete Pavers Block | 60 mm thick Concrete Pavers Block (removing & refixing) | Removing & refixing interlocking concrete pavers of 60 mm thick, of any size, shape and colour considering 10% breakage area of paver block while removing same from position and replacing the same by new paver blocks having average crushing strength of not less than 40 N/mm² as per technical specifications and IS Code 15658:2006, placed on average compacted thickness of 25 mm well graded sand cushioning uniformly compacted with proper capacity mechanical compactor with required level, grade and camber etc. complete as specified and as directed by the Engineer. | Sq m
9.7 |  | CIVIL | Road | Concrete Pavers Block | 80 mm thick unishape … in Red (Terra Cotta), Black, Brown or any colour with pigment | Providing & Fixing 80 mm thick unishape grey cement concrete interlocking pavers in the carriageway (monolithic-single layer precast concrete blocks) in Red (Terra Cotta), Black, Brown or any colour with pigment @ 3% by weight of cement having average crushing strength of not less than 50 N/mm² as per technical specifications and IS Code 15658:2006, placed on average compacted thickness of 25 mm well graded sand cushioning uniformly compacted with proper capacity mechanical compactor with required level, grade and camber etc. Complete as specified and as directed by the Engineer | Sq m
9.8 |  | CIVIL | Footpath | Concrete Pavers Block | 60 mm thick unishape … in Red (Terra Cotta), Black, Brown or any colour with pigment | Providing & Fixing 60 mm thick unishape grey cement concrete interlocking pavers in the footpath with pigment @ 3% by weight of cement (monolithic-single layer precast concrete blocks manufactured in grey cement only) in Red ( Terra Cotta), Black, Brown or any colour having average crushing strength not less than 40 N/mm² as per technical specifications and IS Code 15658:2006, placed on average compacted thickness of 25 mm well graded sand cushioning uniformly compacted with proper capacity mechanical compactor with required level, grade and camber etc. complete as specified and as directed by the Engineer. | Sq m
9.9 |  | CIVIL | Footpath | Concrete Pavers Block | 60 mm thick Lacquer coated (Reflective) … Paver Blocks | Providing & fixing in the footpath, 60 mm thick Lacquer coated (Reflective) interlocking grey cement concrete pavers in Red ( Terra Cotta), Black, Brown, lemon yellow or any colour with vermeticular or any antiskid texture on top surface of approved pattern/ shape and colour having average crushing strength not less than 40 N/mm² manufactured in double layer precast concrete blocks as per technical specifications and IS CODE 15658:2006. The top layer of paver block should be 12 to 15 mm thick and consisting of cubical shape stone aggregate 8 mm size sieve 100% passing and retained on 4.75 mm size sieve, silica sand and with pure iron oxide ultra voilete stabilized pigment @ 5% by weight of cement and should be coated with lacquer having hard, high abrasive resistance and water repellent. The bottom layer should be 45 to 48 mm thick having 12 mm size sieve 100% passing aggregate as per technical specifications, placed on average compacted thickness of 25 mm well graded sand cushioning uniformly compacted with proper capacity mechanical compactor with required level, grade and camber etc. complete as specified and as directed by the Engineer. | Sq m
9.1 |  | CIVIL | Road/Parking | Concrete Pavers Block | 80 mm thick Lacquer coated (Reflective) … Paver Blocks | Providing & fixing in the carriageway 80 mm thick grey cement concrete Lacquer coated (Reflective) interlocking pavers in Red (Terra Cotta), Lemon Yellow, Bright Yellow or any colour with vermeticular or any antiskid texture on top surface of approved pattern/ shape and colour having average crushing strength not less than 50 N/mm² manufactured in double layer precast concrete blocks as per technical specifications and IS CODE 15658:2006. The top layer of paver block should be 12 to 15 mm thick and consisting of cubical shape stone aggregate 8 mm sieve 100% passing and retained on 4.75 mm size sieve, silica sand and with pure iron oxide ultra voilete stabilized pigment @ 5% by weight of white cement and should be coated with lacquer having hard, high abrasive resistance and water repellent.The bottom layer should be 65 to 68 mm thick having 12 mm sieve 100% passing aggregate as per technical specifications, placed on average compacted thickness of 25 mm well graded sand cushioning uniformly compacted with proper capacity mechanical compactor with required level, grade and camber etc. complete as specified and as directed by the Engineer. | Sq m
9.11 |  | CIVIL | Road | Concrete Pavers Block | 100 mm thick interlocking concrete unishape pavers | Providing & fixing in the carriageway 100 mm thick interlocking concrete unishape pavers (monolithic- single layer precast concrete blocks) of grey cement coloured having average crushing strength not less than 50 N/mm² as per technical specification and IS CODE 15658:2006, placed on average compacted thickness of 25 mm well graded sand cushioning uniformly compacted with proper capacity mechanical compactor with required level, grade and camber etc. Complete as specified and as directed by the Engineer. | Sq m
9.13 |  | CIVIL | Road | Concrete Pavers Block | 100 mm thick unishape … in Red (Terra Cotta), Black, Brown or any colour with pigment | Providing & Fixing in the carriageway interlocking 100 mm thick grey cement concrete unishape pavers in Red (Terra Cotta), Black, Brown or any colour unishape (monolithic-single layer precast concrete blocks) with pigment @ 3% by weight of cement having average crushing strength of not less than 50 N/mm² as per technical specifications and IS CODE 15658:2006, placed on average compacted thickness of 25 mm well graded sand cushioning uniformly compacted with proper capacity mechanical compactor with required level, grade and camber etc. complete as specified and as directed by the Engineer. | Sq m
9.14 |  | CIVIL | Road | Concrete Pavers Block | 100 mm thick unishape … in Red (Terra Cotta), Black, Brown or any colour with pigment (removing & refixing) | Removing & refixing interlocking concrete pavers of 100 mm thick, of any size, shape and colour considering 10% breakage area of paver block while removing same from position and replacing the same by new paver blocks having average crushing strength not less than 50N/mm² as per technical specifications and IS CODE 15658:2006, placed on average compacted thickness of 25 mm well graded sand cushioning uniformly compacted with proper capacity mechanical compactor with required level, grade and camber etc. complete as specified and as directed by the Engineer. | Sq m
9.16 |  | CIVIL | Footpath | Concrete Pavers Block | footpath 60mm thick lacquer … white cement pavers ... red (Terracotta) Black, Brown, Lemon Yellow or any colour | Providing & fixing in the footpath, 60 mm thick Lacquer coated (Reflective) interlocking white cement concrete pavers in red (Terracotta) Black, Brown, Lemon Yellow or any colour with vermeticular or any antiskid texture on top surface of approved pattern/ shape and colour having average crushing strength not less than 40 N/mm² as per technical specifications and IS CODE 15658:2006; manufactured in double layer precast concrete blocks. The top layer of paver block should be 12 to 15 mm thick and consisting of cubical shape stone aggregate 8 mm size sieve 100% passing and retained on 4.75 mm size sieve, silica sand and with pure iron oxide ultra violet stabilized pigment @ 5% by weight of white cement and should be coated with lacquer having hard, high abrasive resistance and water repellent. The bottom layer in grey cement should be 45 to 48 mm thick having 12mm size sieve 100% passing aggregates as per technical specifications, placed on average compacted thickness of 25 mm well graded sand cushioning uniformly compacted with proper capacity mechanical compactor with required level, grade and camber etc. complete as specified and as directed by the Engineer. | Sq m
9.17 |  | CIVIL | Footpath | Concrete Pavers Block | footpath 80mm thick lacquer … white cement pavers ... red (Terracotta) Black, Brown, Lemon Yellow or any colour | Providing & fixing in the footpath, 80 mm thick Lacquer coated (Reflective) interlocking white cement concrete pavers in red (Terra Cotta) Black, Brown, Lemon Yellow or any colour with vermeticular or any antiskid texture on top surface of approved pattern/ shape and colour having average crushing strength not less than 50 N/mm² as per technical specifications and IS CODE 15658:2006; manufactured in double layer precast concrete blocks. The top layer of paver block should be 12 to 15 mm thick and consisting of cubical shape stone aggregate 8 mm size sieve 100% passing and retained on 4.75 mm size sieve, silica sand and with pure iron oxide ultra violet stabilized pigment @ 5% by weight of white cement and should be coated with lacquer having hard, high abrasive resistance and water repellent. The bottom layer in grey cement should be 65 to 68 mm thick having 12 mm size sieve 100% passing aggregates as per technical specifications, placed on average compacted thickness of 25 mm well graded sand cushioning uniformly compacted with proper capacity mechanical compactor with required level, grade and camber etc. complete as specified and as directed by the Engineer. | Sq m
9.18 |  | CIVIL | Footpath | Concrete Pavers Block | 60mm thick Began it in grey/Black colour with Stone texture | Providing & fixing in the footpath Interlocking concrete paver block 60mm thick Began it in grey/Black colour with Stone texture on top surface of approved pattern/ shape and colour having average crushing strength not less than 40 N/mm² as per technical specifications and IS CODE 15658:2006; manufactured in double layer Interlocking concrete paver blocks Began it 12 to 15 mm thick and consisting of cubical shape Quartz stone aggregate 8 mm sieve 100% passing and retained on 4.75 mm size sieve, silica sand. The bottom layer should be 45 to 48 mm thick in grey cement having 12mm sieve 100% passing aggregates as per technical specifications, rested on average compacted thickness of 25 mm well graded sand cushioning uniformly compacted with proper capacity mechanical compactor with required level, grade and camber etc. complete as specified and as directed by the Engineer. | Sq m
9.19 |  | CIVIL | Footpath | Concrete Paving Slabs | footpath Concrete Paving Slabs (Flagstone) 400 X400 X60 mm thick | Providing & fixing in the footpath Concrete Paving Slabs (Flagstone) 400 X400 X60 mm thick or any approved size in grey or any specified colour with shot blasted texture or any approved texture on top surface of approved pattern/ shape and colour having average crushing strength not less than 40 N/mm² as per technical specifications and IS CODE 15658:2006; manufactured in double layer precast concrete Paving Slabs (Flagstone) 12 to 15 mm thick and consisting of cubical shape Quartz stone aggregate 8 mm sieve 100% passing and retained on 4.75 mm size sieve, silica sand .The bottom layer should be 45 to 48 mm thick in grey cement having 12mm sieve 100% passing aggregates as per technical specifications, rested on average compacted thickness of 25 mm well graded sand cushioning uniformly compacted with proper capacity mechanical compactor with required level, grade and camber etc. complete as specified and as directed by the Engineer. | Sq m
9.2 |  | CIVIL | Footpath | Concrete Paver blocks | footpath Concrete Paver blocks 200 X200X60 mm thick | Providing & fixing in the footpath Concrete Paver blocks 200 X200X60 mm thick or any approved size in grey or any specified colour with shot blasted texture or any approved texture on top surface of approved pattern/ shape and colour having average crushing strength not less than 40 N/mm² as per technical specifications and IS CODE 15658:2006; manufactured in double layer precast concrete Paver blocks 12 to 15 mm thick in top layer and consisting of cubical shape Quartz stone aggregate 8 mm sieve 100% passing and retain on 4.75mm size sieve, silica sand. The bottom layer should be 45 to 48 mm thick in grey cement having 12 mm sieve 100% passing aggregates as per technical specifications, rested on average compacted thickness 25 mm well graded sand cushioning uniformly compacted with proper capacity mechanical compactor with required level, grade and camber etc. complete as specified and as directed by the Engineer. | Sq m
9.21 |  | CIVIL | Footpath | cement concrete pavers | 60 mm thick Heritage paver interlocking white cement concrete pavers | Providing & fixing in the carriageway/footpath, 60 mm thick Heritage paver interlocking white cement concrete pavers in red (terra Cotta), black, brown, lemon colour with vermeticular or any antiskid texture on top surface of approved pattern/ shape and colour, having average crushing strength not less than 40 N/mm² as per technical specifications and IS CODE15658:2006; manufactured in double layer precast concrete blocks the top layer of paver block should be 12 to 15 mm thick and consisting of cubical shape stone aggregate 8mm sieve 100% passing and retained on 4.75 mm size sieve, silica sand and with pure iron oxide ultra violet stabilized pigment @ 5% by weight of cement. The bottom layer should be 45 to 48 mm thick in grey cement having 12 mm sieve 100% passing aggregates as per technical specifications, rested on average compacted thickness of 25 mm well graded sand cushioning uniformly compacted with proper capacity mechanical compactor with required level, grade and camber etc. complete as specified and as directed by the Engineer. | Sq m
9.22 |  | CIVIL | Footpath | cement concrete pavers | 80 mm thick Heritage paver interlocking white cement concrete pavers | Providing & fixing in the carriageway, 80 mm thick Heritage paver interlocking white cement concrete pavers in red (terra Cotta), black, brown, lemon colour with vermeticular or any antiskid texture on top surface of approved pattern/shape and colour having average crushing strength not less than 50 N/mm² as per technical specifications and IS CODE 15658:2006; manufactured in double layer precast concrete blocks the top layer of paver block should be 12 to 15 mm thick and consisting of cubical shape stone aggregate 8 mm sieve 100% passing and retain on 4.75 mm size sieve, silica sand and with pure iron oxide ultra violet stabilized pigment @ 5% by weight of cement. The bottom layer should be 65 to 68 mm thick in grey cement having 12 mm sieve 100% passing aggregates as per technical specifications rested on average compacted thickness of 25 mm well graded sand cushioning uniformly compacted with proper capacity mechanical compactor with required level, grade and camber etc. complete as specified and as directed by the Engineer. | Sq m
9.23 |  | CIVIL | Flooring | Kota stone flooring | 25mm thick Kota stone flooring - BOH AREA. | laying machine cut, machine polished approved 25mm thick Kota stone flooring, stone to be machine cut, machine polished, laid in pattern and sizes as detailed in drawing or as directed by PM, bedded over cement sand mortar of mix ratio of 1:6 (1 cement : 6 sand) including cleaning and preparing the surface for bedding, spreading neat cement slurry by using minimum cement about 2 kg/ sqm prior to bedding and spreading cement paste using minimum cement about 4.5 kg/sqm over bedding, joints to be cleaned and grouted with matching colour approved quality polymer based readymade grout, curing, machine polishing, cleaning, etc. to required line, level, etc. all complete at all depths, heights and leads to the satisfaction of the PM. | Sq m | 34 |  |  |  | 1721 | 58514 | 32.496 | 55925.616
9.24 |  | CIVIL | Flooring | Kota stone flooring | wide 25mm thick Kota stone | 25mm thick Kota stone of approved quality, colour, shade to treads, machine cut, machine polished; in one piece to full length of step. Treads are to be rounded at front and sides and all exposed edges machine polished. Further treads to have 2 nos. 6 x 3mm grooves on top at front or as detailed in drawing. Treads to be laid over well vibrated, compacted cement concrete screed of mix 1:2:4 (1 cement : 2 sand : 4 aggregate 12.5 mm) cement concrete screed using approved quality compatible adhesive (Bal / Laticrete or equivalent). Joints to be well cleaned and grouted with matching colour approved quality polymer based readymade grout, curing, cleaning, polishing, protecting till handing over etc., at all levels and locations, complete to the entire satisfaction of the PM. | Rmt | [5 empty] | 0
9.25 |  | CIVIL | Flooring | Kota stone flooring | Fixing 290mm wide 25mm thick Kota stone | Fixing 25mm thick Kota stone of approved quality, colour and shade for risers, machine cut and machine polished to full length of step in one piece or as directed as detailed in drawing. Stone fixed with approved compatible adhesive (Bal / Laticrete or equivalent approved) over plastered surface. Joints are well cleaned grouted with matching colour approved quality polymer based readymade grout, curing, machine, cleaned and where specified or shown in drawing exposed edge of stone rounded / chamfered and polished etc., at all levels and locations complete to the entire satisfaction of the PM. Location : Common Staircases. | Rmt | [5 empty] | 0
9.26 |  | CIVIL | Skirting | Kota Stone skirting | 100mm high and 25mm thick, Kota Stone skirting | Fixing 100mm high and 25mm thick approved machine cut, machine polished Kota Stone skirting of uniform shade as detailed in drawing. Stone fixed over plastered surface with approved compatible adhesive (Bal / Laticrete or equivalent approved) to correct line, level and plumb. Joints are well cleaned grouted with matching colour approved quality polymer based readymade grout, curing, cleaned and where specified or shown in drawing exposed faces / edge of stone rounded / chamfered and polished etc., at all levels and locations. complete to the entire satisfaction of the PM. | Rmt | [5 empty] | 0
9.26.1 |  |  | Skirting |  |  | Common Staircases | Rmt | [5 empty] | 0
9.26.2 |  |  | Skirting |  |  | -Do- as per Item No. 9.5 above but for inclined skirting parallel to staircase waist slab. | Rmt | [5 empty] | 0
9.27 |  | CIVIL | Strip | Kota Strip in Ramp -150mm | Kota Strip in Ramp -150mm | CP128;P&L Kota Strip in Ramp,-150mm.wide Providing and fixing 20-25mm thick 150mm wide Kota stone strip in ramp, including cost of 20-30mm thick cement bedding, mirror polishing, making V-Grooves, matching colour pigments in joints etc. complete as directed by Engineer-in-charge. | Rmt | [5 empty] | 0
9.27.A |  | CIVIL | Strip | Kota Strip in Ramp -100mm | Kota Strip in Ramp -100mm - BOH AREA. | CP128;P&L Kota Strip in Ramp,-150mm.wide Providing and fixing 20-25mm thick 150mm wide Kota stone strip in ramp, including cost of 20-30mm thick cement bedding, mirror polishing, making V-Grooves, matching colour pigments in joints etc. complete as directed by Engineer-in-charge. | Rmt | 10 |  |  |  | 450 | 4500 | 15.4 | 6930 | as certify
9.28 |  | CIVIL | Flooring | Rough Kota stone | Rough Kota stone | Providing and laying rough Kota stone tiles 25 mm to 30 mm thick of an approved quality and size for paving / flooring including cement mortar bedding of 25 mm thick in 1:4 proportion, cement float, pointing in cement mortar 1:3, cutting, dressing, levelling, jointing, pointing, curing, finishing etc. complete as directed by Engineer In Charge. | Sq m | [5 empty] | 0
9.29 |  | CIVIL | Flooring | Marble stone flooring. | 19mm thick Marble stone flooring. | Laying 19mm thick machine cut, machine polished Marble stone flooring of approved quality, colour, shade and pattern, laid in pattern and sizes as shown in drawing. using approved quality compatible adhesive (Kerakoll / Bal / Laticrete or equivalent). Joints to be well cleaned and grouted with matching colour approved quality polymer based readymade grout, curing, machine polishing, cleaning, protecting till handing over etc. to required line, level, etc., at all levels and locations, complete to the entire satisfaction of the PM. Location : Internal Staircases. (Supply of Marble through Part D - Provisional Sum of Supplies) | Sq m | [5 empty] | 0
9.3 |  | CIVIL | Skirting | Marble stone skirting. | Imported Marble stone skirting. | Supply and fixing Imported Marble stone skirting, at all levels and locations including shifting of materials from stores to work location, by approved compatible adhesive (Bal / Laticrete or equivalent approved) to correct line, level and plumb. Joints are well cleaned grouted with matching colour readymade approved grout, curing, machine polished where required cleaned. Further where specified or shown in drawing exposed edge of stone rounded / chamfered and mirror polished etc. complete to the entire satisfaction of the PM. | Rmt | [5 empty] | 0
9.31 |  | CIVIL | Skirting | Marble stone skirting. | 100mm high Imported Marble stone skirting. | Fixing of 100mm high Imported Marble stone skirting, at all levels and locations including shifting of materials from stores to work location, by approved compatible adhesive (Bal / Laticrete or equivalent approved) to correct line, level and plumb. Joints are well cleaned grouted with matching colour readymade approved grout, curing, machine polished where required cleaned. Further where specified or shown in drawing exposed edge of stone rounded / chamfered and mirror polished etc. complete to the entire satisfaction of the PM. Location : Internal Staircases - 100mm high Imported Marble skirting on Waist slab (Supply of Marble through Part D - Provisional Sum of Supplies) | Rmt | [5 empty] | 0
9.32 |  | CIVIL | Flooring | Marble stone flooring | polished Marble stone flooring | Supply & Laying machine cut, machine polished Marble stone flooring of approved quality, colour, shade and pattern, laid in pattern and sizes as shown in drawing. using approved quality compatible adhesive (Kerakoll / Bal / Laticrete or equivalent). Joints to be well cleaned and grouted with matching colour approved quality polymer based readymade grout, curing, machine polishing, cleaning, protecting till handing over etc. to required line, level, etc, at all levels and locations, complete to the entire satisfaction of the PM. | Sq m | [5 empty] | 0
9.33 |  | CIVIL | Flooring | Marble stone Riser. | Imported Marble stone Riser. | Fixing of Imported Marble stone Riser, at all levels and locations including shifting of materials from stores to work location, by approved compatible adhesive (Bal / Laticrete or equivalent approved) to correct line, level and plumb. Joints are well cleaned grouted with matching colour readymade approved grout, curing, machine polished where required cleaned. Further where specified or shown in drawing exposed edge of stone rounded / chamfered and mirror polished etc. complete to the entire satisfaction of the PM.. Location : Internal Staircases - Imported Marble 148mm wide Riser (Supply of Marble through Part D - Provisional Sum of Supplies). | Rmt | [5 empty] | 0
9.34 |  | CIVIL | Flooring | Marble stone Flooring | Imported Marble stone Flooring | Laying Imported Marble stone flooring, at all levels and locations including shifting of materials from stores to work location, over well vibrated, compacted screed (paid separately) using approved quality compatible adhesive (Kerakoll / Bal / Laticrete or equivalent). Joints to be well cleaned and grouted with matching colour approved quality polymer based readymade grout, curing, machine polishing, cleaning, protecting till handing over etc. to required line, level, etc. complete to the entire satisfaction of the PM. | Sq m | [5 empty] | 0
9.35 |  | CIVIL | Flooring | pre polished Marble Stone | 20mm average thick pre polished | Laying 20mm average thick pre polished and finished marble stone laid over an average 20 mm thick cement mortar 1:4 with a layer of grey cement slurry topping. Stone joints shall be pointed using Epoxy grout to match floor. Visible stone edges shall be rounded off (bull nosing) as shown on the drawing. Location: Toilet Ledge Wall - 150mm | Rmt | [5 empty] | 0
9.36 |  | CIVIL | Flooring | Vitrified tile flooring | POP ON VITRIFIED FLOORING | Providing and laying POP on vitrified flooring for protecting the tiles Including cleaning and laying polythene paper above tile. | Sq m | [5 empty] | 0
9.37 |  | CIVIL | Flooring | Vitrified tile flooring | Vitrified tile flooring | Providing and laying Vitrified tiles as specified below conforming to I.S.15622-2006 with water absorbtion less than 0.08% for flooring of an approved, quality, make and pattern /design for flooring including cement mortar bedding of 25 mm thick in 1:4 proportion, cutting, levelling, jointing, filling the joints by neat cement slurry or approved colour grout, curing, finishing etc. complete as directed by Engineer In Charge | [6 empty] | 0
9.37.1 |  |  |  |  | Tile size of 800 x 800mm | Tile size of 800 x 800mm | [6 empty] | 0
9.37.1.a | [5 empty] | glazed vitrified tiles of Size 800mm x 800mm | Sq m | [5 empty] | 0
9.37.1.b | [5 empty] | Anti Skid Vitrified Tile Flooring 800 x 800mm | Sq m | [5 empty] | 0
9.37.2 |  |  |  |  | Tile size of 600 x 600mm | Tile size of 600 x 600mm | [6 empty] | 0
9.37.2.a | [5 empty] | glazed vitrified tiles of Size 600mm x 600mm | Sq m | [5 empty] | 0
9.37.2.b |  |  |  |  | Printed - FOH AREA. | Anti Skid Vitrified Tile Flooring 600 x 600mm (Basic Cost INR. 2690.00/SM) | Sq m | 27.5 |  |  |  | 4750 | 130625 | 30.6665 | 145665.875
9.37.3 |  |  |  |  | Tile size of 300 x 300mm | Tile size of 300 x 300mm | [6 empty] | 0
9.37.3.a | [5 empty] | glazed vitrified tiles of Size 300mm x 300mm | Sq m | [5 empty] | 0
9.37.3.b | [5 empty] | Anti Skid Vitrified Tile Flooring 300 x 300mm | Sq m | [5 empty] | 0
9.37.4 |  |  |  |  | Tile size of 1200 x 600mm | Tile size of 600 x 600mm | [6 empty] | 0
9.37.4a | [5 empty] | glazed vitrified tiles of Size 1200mm x 600mm | Sq m | [5 empty] | 0
9.37.4,b |  |  |  |  | Cemented Finished - FOH AREA. | Anti Skid Vitrified Tile Flooring 1200 x 600mm (Basic Cost INR. 1345.00/SM) | Sq m | 73 |  |  |  | 3290 | 240170 | 73.7495 | 242635.8945
9.38 |  | CIVIL | Flooring | vitrified tile flooring | Pattern vitrified tile flooring | Providing and Fixing appvd 8"x8" Pattern vitrified tile flooring with roff cement bedding of appvd proportions as per the design & specifications. Joints to be filled properly with pigmented cement / epoxy grouts matching the tile. Flooring should be fixed in proper plumb line. Job to include cost of labour, material, cartage, loading, unloading, cutting, fixing and grouting. | Sq m | [5 empty] | 0
9.39 |  | CIVIL | Skirting | Vitrified tile Skirting, | Vitrified tile Skirting, | Providing and fixing vitrified tiles as specified below conforming to I.S. 15622-2006 of approved quality, pattern and colour for flush/projected skirting / riser including preparing the surface and levelling in the desired line, backing of 20 thk. cement mortar in proportion 1:3, square cut top edge or chamfered top edge in cement mortar 1:3,cement float, machine cutting, levelling, jointing, filling the joints with neat cement slurry or pigments mixed with cement, finishing, curing etc. complete as directed by Engineer in charge. | [6 empty] | 0
9.39.1 |  |  |  |  | 8mm thick | For 8mm Thk | [6 empty] | 0
9.39.1.a | [5 empty] | glazed vitrified tiles for height upto 150mm of 8mm Thk | Rmt | [5 empty] | 0
9.39.1.b | [5 empty] | glazed vitrified tiles for height upto 300mm of 8mm Thk | Rmt | [5 empty] | 0
9.39.1.c | [5 empty] | antiskid / matt vitrified tiles for height upto 150mm of 8mm Thk | Rmt | [5 empty] | 0
9.39.1.d | [5 empty] | antiskid / matt vitrified tiles for height upto 300mm of 8mm Thk | Rmt | [5 empty] | 0
9.39.2 |  |  |  |  | 10mm thick | For 10mm Thk | [6 empty] | 0
9.39.2.a | [5 empty] | glazed vitrified tiles for height upto 150mm of 10mm Thk | Rmt | [5 empty] | 0
9.39.2.b | [5 empty] | glazed vitrified tiles for height upto 300mm of 10mm Thk | Rmt | [5 empty] | 0
9.39.2.c | [5 empty] | antiskid / matt vitrified tiles for height upto 150mm of 10mm Thk | Rmt | [5 empty] | 0
9.39.2.d | [5 empty] | antiskid / matt vitrified tiles for height upto 300mm of 10mm Thk | Rmt | [5 empty] | 0
9.39.2.e |  |  |  |  | Cemented Finished - FOH AREA. | antiskid / matt vitrified tiles for height up to 100mm of 10mm Thk (Basic Cost INR. 1345.00/SM) | Rmt | 41.05 |  |  |  | 456 | 18718.8 | 41.98 | 19142.88
9.4 |  | CIVIL | Counter | granite Slab | 20mm thick Prefinished and polished granite | Fixing in position 20mm thick Prefinished and polished granite including providing opening, nosing at the visible edges and cut edges. Granite shall be fixed above the 25mm thick cudappa slab using adhesive of approved make. 50mm high vertical edge band shall be fixed at front of the Kitchen platform butting to granite bottom. Granite Platform shall be completed as shown on the drawing. Only plan area shall be measured. | [6 empty] | 0
9.40.1 | [5 empty] | Counter - 350mm wide | Rmt | [5 empty] | 0
9.40.2 | [5 empty] | Counter - 400mm wide | Rmt | [5 empty] | 0
9.40.3 | [5 empty] | Counter - 450mm wide | Rmt | [5 empty] | 0
9.40.4 | [5 empty] | Counter - 600mm wide | Rmt | [5 empty] | 0
9.41 |  | CIVIL | Strips in ramps | Granite Strip | 100MM WIDE JET BLACKGRANITE STRIP | Providing and Fixing 100 mm wide granite strips on sloping portions of entrance I ramps etc. using 19mm thk prepolished jet black granite on mortar bed (CM -1:4) with neat cement paste in overlapping fashion as per drawing so as to achieve the antis kid effect and to the complete satisfaction of engineer in charge. | Rmt | [5 empty] | 0
9.41.a |  | CIVIL | Strips in ramps | Granite Strip | 150MM WIDE JET BLACKGRANITE STRIP-FOH AREA's Floor. | Providing and Fixing 150 mm wide granite strips on sloping portions of entrance I ramps etc. using 19mm thk prepolished jet black granite on mortar bed (CM -1:4) with neat cement paste in overlapping fashion as per drawing so as to achieve the antis kid effect and to the complete satisfaction of engineer in charge. | Rmt | 20.6 |  |  |  | 810 | 16686 | 35.85 | 29038.5 | as certify qty revised from 20.60 to 35.85
9.41.b |  | CIVIL | Strips in ramps | Curved Granite Strip | 150MM WIDE CURVED JET BLACKGRANITE STRIP, FOH AREA'S FLOOR. | Providing and Fixing 150 mm wide granite strips on sloping portions of entrance I ramps etc. using 19mm thk prepolished jet black granite on mortar bed (CM -1:4) with neat cement paste in overlapping fashion as per drawing so as to achieve the antis kid effect and to the complete satisfaction of engineer in charge. | Rmt | 9.7 |  |  |  | 1000 | 9700 | 8.76 | 8760 | as certify
9.41.c |  | CIVIL | Strips in ramps | Curved Granite Strip | 300MM WIDE CURVED JET BLACKGRANITE STRIP-FOH AREA at BANQUET SIDE. | Providing and Fixing 300 mm wide granite strips on sloping portions of entrance I ramps etc. using 19mm thk prepolished jet black granite on mortar bed (CM -1:4) with neat cement paste in overlapping fashion as per drawing so as to achieve the antis kid effect and to the complete satisfaction of engineer in charge. | Rmt | 12.6 |  |  |  | 2000 | 25200 |  | 0
9.42 |  | CIVIL | Strip | Granite Slab | STN CIL 250MM JET BLACK GRANTE - AT ENTRANCE TO POS SECTION. | Providing and Fixing Stone (Type of stone and thickness of stone to be mentioned) sill (250 wide) with half round edges to RCC /Masonry surface using cement mortar 1: 4 closely jointed and pointed with matching colour grout. Rate to include cost of hand machine polishing if required. | Sq m |  |  |  |  | 5000 | 0 |  | 0
9.42.a |  | CIVIL | Strip | Granite Slab | STN CIL 200MM JET BLACK GRANTE-GLASS WINDOW AREA. | Providing and Fixing Stone (Type of stone and thickness of stone to be mentioned) sill (200 wide) with half round edges to RCC /Masonry surface using cement mortar 1: 4 closely jointed and pointed with matching colour grout. Rate to include cost of hand machine polishing if required. | Sq m | 3.3 |  |  |  | 4500 | 14850 | 1.848 | 8316 | as certify
9.42.b |  | CIVIL | Strip | Granite Slab | STN CIL 175MM JET BLACK GRANTE - POT WASH | Providing and Fixing Stone (Type of stone and thickness of stone to be mentioned) sill (175 wide) with half round edges to RCC /Masonry surface using cement mortar 1: 4 closely jointed and pointed with matching colour grout. Rate to include cost of hand machine polishing if required. | Sq m | 0.63 |  |  |  | 4200 | 2646 | 0 | 0
9.42.c |  | CIVIL | Strip | Granite Slab | STN CIL 100MM JET BLACK GRANTE-GLASS WINDOW AREA. | Providing and Fixing Stone (Type of stone and thickness of stone to be mentioned) sill (100 wide) with half round edges to RCC /Masonry surface using cement mortar 1: 4 closely jointed and pointed with matching colour grout. Rate to include cost of hand machine polishing if required. | Sq m | 1.65 |  |  |  | 4000 | 6600 |  | 0 | as certify
9.43 |  | CIVIL | Strip | Granite Slab | 450MM WIDE JET BLACK GRANITE | Providing, Cutting and Fixing 19mm Thk. Granite Top with 35mm front and 10mm edge radius to match floor and walls. The granite shall be cut to shape and fixed on 19mm commercial board backing supported on 50x50x6 mm angle frame grouted in the wall with well cut opening for wash basin /sink / faucet, the joint filled up by white cement and matching colour pigment as per directions by Engineer-in-charge.ln Jet Black Granite 450mm wide | Sq m | [5 empty] | 0
9.44 |  | CIVIL | Counter | Granite Slab | 450MM WIDE CHIMA PINK GRANITE | Providing, Cutting and Fixing 19mm Thk. Granite Top with 35mm front and 10mm edge radius to match floor and walls. The granite shall be cut to shape and fixed. On 19mm commercial board backing supported on 50x50x6mm angle frame grouted in the wall with well cut opening for washbasin / sink / faucet, the joint filled up by white cement and matching colour pigment as per directions by Engineer-in-charge."" In Chima Pink Granite 450mm wide. | Sq m | [5 empty] | 0
9.45 |  | CIVIL | Partition Wall | Granite Partition Wall | GRANITE PRTIN WALL B/W URINAL | Providing and fixing Granite partition wall between urinals, both side polished with 19 mm thick machine cut, mirror polished approved Italian Marble (Is it Granite or Italian Marble) about 545/445 mm wide fixed in wall, 1200mm high required supports, pins, clamps, GI brackets if a nv, grouted in wall, including cutting and finishing smooth and mirror polishing, complete as per detailed in drawing. (Basic Rate Rs. 150/· per sqft) | NOS | [5 empty] | 0
9.46 |  | C & I | Counter | Granite Slab | 600MM WIDE JET BLACKGRANITE | Providing, Cutting and Fixing 19mm Thk. Granite Top with 35mm front and 10mm edge radius to match floor and walls. The granite shall be cut to shape and fixed on 19mm commercial board backing supported on50x50x6 mm angle frame grouted in the wall with well cut opening for wash basin/ sink / faucet, the joint filled up by white cement and matching colour pigment asper directions by Engineer-in-charge.ln Jet Black Granite 600mm wide | Sq m | [5 empty] | 0
9.47 |  | INT | Counter | Granite Slab | PRO&F JET BLACK GRNTE F/6"-7" TH | PRO&F JET BLACK GRANITE F/6"-7" TH -Providing and fixing approved shade Stone for Treads and Risers in CM1:4 including.preparing and cleaning surfaces, spreading cement slurry using minimum cement of 2Kg/Sqm over prepared surface and 4.5Kg/Sqm over bedding Joints to be grouted with .matching colour.approved readymade grout, curing.cleaning.mirror polishing, including half round edgemoulding for treads and making 3Nos of non-slip grooves as directed injet black Black Granite 6"" to 7"" high Riser | [6 empty] | 0
9.48 |  | CIVIL | Flooring | Wooden flooring | Laminated Wooden flooring with 2mm thick PU foam | Laying Laminated Wooden flooring with 2mm thick PU foam underlay and adhesive of approved make as specified, at all levels and locations including shifting of materials from stores to work location, with new test method, including cleaning, treating batten prior to fixing and making groove/joint around edges as specified in drawing and by the manufacturer etc. all as detailed in technical specification, drawings and that of approved flooring manufacturer complete etc. to entire satisfaction of the PM. | Sq m | [5 empty] | 0
9.49 |  | CIVIL | Skirting | Marine Ply skirt | Laminated Marine Ply skirt | Providing and fixing in position 1mm thk laminate of approved shade over 12mm/19mm thk marine ply fixed with suitable adhesive & pressed properly.as directed by Engineer in charge. | Sq m | [5 empty] | 0
9.5 |  | CIVIL | Skirting | Laminated Wooden skirting | high Laminated Wooden skirting with 2mm thick | Laying 100mm high Laminated Wooden skirting with 2mm thick PU foam underlay and adhesive of approved make as specified, at all levels and locations including shifting of materials from stores to work location, with new test method, including cleaning, treating batten prior to fixing and making groove/joint around edges as specified in drawing and by the manufacturer etc. all as detailed in technical specification, drawings and that of approved flooring manufacturer complete etc. to entire satisfaction of the PM. | Rmt | [5 empty] | 0
9.51 |  | CIVIL | Skirting | PSTN Skirting | PSTN SKIRTING 150 MM HIGH 1.5MM | Providing and fixing in position 150mm high Laminate skirting (1.5 mm Thk) of approved make and glued to 12mm thk. Commercial ply backing of approved make, as per design and drawing. Flushed with the vertical surface etc. complete | Rmt | [5 empty] | 0
9.52 |  | CIVIL | Skirting | Ply Skirting | 6MM PLY F/SKIRTING 100MM HT F/GYPS | Ptn-providing and fixing 6mm ply for skirting 100mm high on gypsum partition for fixing tile skirting.item to include cutting refinishing of gypsum. | Rmt | [5 empty] | 0
9.53 |  | CIVIL | Flooring | metal floor | chequered metal floor | Providing, fixing approved chequered metal floor including all structural steel work in accordance with the design, drawings prepared by the Consultants. The rate of flooring work shall include cutting, grinding, machining, assembly, welding, jointing, of single / building up new sections with anchors, angles, beams, canopy, supports, column, trenches angel protections, trench covers etc., cost of fasteners (nuts, bolts and washers), pre-heating the sections to temperatures up to 250oC if thickness of the section is equal to or more than 25 mm. Fabrication will involve connections using plates, channels and angles, gusset plate, foundation bolts, cleats, fasteners, stiffeners etc. as per drawing, steel conforming to IS : 226 and IS : 2062 with minimum yield strength of 250 Mpa and up to 355 Mpa.(Location: Shafts) | Sq m | [5 empty] | 0
9.54 |  | CIVIL | Finish Floor | SS transition | Bronze finish SS transition | Fabricating and fixing of Bronze finish SS transition profile at the junction of Polished concrete/Carpet flooring, carpet/concrete finish vinyl floor, polished concrete/concrete finish vinyl floor, Marble/Carpet flooring, Marble/ polished concrete finish floor as per Architect's approval and design. | Sq m | [5 empty] | 0
9.55 |  | C & I | Skirting | SS Skirtings | SS Skirtings | Providing & fixing SS skirting 150mm height & 1mm thickness approved machine cut,as detailed in drawing and to the entire satisfaction of Engineer-In-Charge. | RMT | [5 empty] | 0
9.55.01 |  | C & I | Skirting | SS Skirting | SS Rose Gold Skirting with 6mm plywood (bwr, fire rated) backing. | Providing & fixing SS Rose Gold finished skirting 100mm height & 1mm thickness with 6mm edge bending approved machine cut, as detailed in drawing and to the entire satisfaction of Engineer-In-Charge. | RMT | 41.05 |  |  |  | 1925 | 79021.25 | 40.661 | 78272.425
9.56 |  | CIVIL | Mesh | GI Bird Mesh | GI Bird Mesh | Providing, fixing approved GI Bird Mesh including all structural steel work in accordance with the design, drawings prepared by the Consultants. | Sq m | [5 empty] | 0
9.57 |  | CIVIL | Skirting | ACP Skirting | Dark Grey ACP Skirting - 3" height | Providing and Fixing appvd acp skirting fixed on plywood base as per the design & specifications. Joints to be filled properly with pigmented cement / epoxy grouts matching the acp. Skirting should be fixed in proper plumb line. Job to include cost of labour, material, cartage, loading, unloading, cutting, fixing and grouting. | RFT | [5 empty] | 0
9.58 |  | CIVIL | Skirting | acp skirting | acp skirting fixed on plywood base | Providing and Fixing appvd acp skirting fixed on plywood base as per the design & specifications. Joints to be filled properly with pigmented cement / epoxy grouts matching the tile. Skirting should be fixed in proper plumb line. Job to include cost of labour, material, cartage, loading, unloading, cutting, fixing and grouting. | RMT | [5 empty] | 0
9.59 |  | CIVIL | Flooring | Vinyl Sheet | homogeneous & abrasion resistant 2mm thick Vinyl Sheet | Supply & Fixing homogeneous & abrasion resistant 2mm thick Vinyl Sheet. Design / colour to match as specified as approved, including cleaning of existing surface & using suitable adhesive to give smooth & even floor with all labour, material etc. as required for proper completion of work. Rates quoted should include cost of adhesives, fixing , cutting, welding etc. complete in all respects & as specified. | Sq m | [5 empty] | 0
9.6 |  | CIVIL | Flooring | approved panels | machine mixing and laying in approved panels | Providing, machine mixing and laying in approved panels of 50 mm thickness Indian patent floor in cement concrete of mix 1:2:4 (1 cement : 2 sand : 4 aggregate 12.5 mm) well vibrated, compacted including 45 x 3 mm thick glass dividing strip, fixed to correct level and finished smooth and cured by keeping surfaces well - covered and protected against excesses of any type. (The contractor will provide for preparation or surface by cleaning, hacking and exposing aggregate to achieve the best bond, and any curling, lifting or debonding noticed shall be rectified by the contractor at his cost), etc., at all levels and locations, complete to the entire satisfaction of the PM. (Location: Service Floor) | Sq m | [5 empty] | 0
9.61 |  | CIVIL | Flooring | China-mosaic tiles | broken China-mosaic tiles | Laying the flooring of broken China-mosaic (broken pieces of China glazed tiles) of approved colour set in 25 mm. average bed of C.M. 1:3 with waterproofing compound to correct level and slope (1:100) well compacted and finished; such that minimum coverage of China mosaic chips is about 90% of the total area of slab. The above treatment shall continue along the inner side of parapet or the adjoining wall upto 30cm. high as per the above specifications regarding cement mortar in shape of round vata with necessary groove etc. complete. | Sq m | [5 empty] | 0
9.62 |  | CIVIL | Flooring | EPU Flooring | EPU Flooring of 3mm thickness | Providing and applying antifungal self leveling 3mm EPU system including coving at floor wall junction, necessary surface preparation by cleaning and de-dusting. The System shall be executed in three stages, firstly by applying a solvent free epoxy primer which has a volumetric ratio of mixing @ 200 microns dft, then laying 1.8mm self leveling epoxy based screed and finally applying a solvent free EPU ( epoxy-polyurethane), self leveling coating to yield a dft of 1000 microns. The EPU coating shall be a two component with volumetric ratio of mixing. No fillers shall be added at the site while laying the self leveling EPU including Aisle or zone marking in different colours etc. complete as per manufacturers specifications and as directed & approved by Engineer In-Charge | Sq m | [5 empty] | 0
9.63 |  | CIVIL | Flooring | Floor Trap | PVC Floor trap 110mm dia. | Providing & fixing PVC Floor Trap OR multi floor trap of 110mm diameter, with necessary distance piece of 75mm & 110 mm dia pipe and 150x150 mm grating, making necessary SLAB/WALL holes and cutting walls, etc. complete.{110 mm x 75mm). | NOS | [5 empty] | 0
9.64 |  | CIVIL | Flooring | Floor Trap | PVC Heavy Duty Floor TRAP 110 X 75MM | PROVIDING & FIXING PVC HEAVY DUTY FLOOR TRAP 110X75MM . with necessary distance piece of 75mm & 110 mm dia pipe and 150x150 mm grating, making necessary SLAB/WALL holes and cutting walls, etc. complete.{110 mm x 75mm). | NOS | [5 empty] | 0
9.65 |  | CIVIL | Flooring | Loop pile patterned carpet | Imported Loop pile patterned carpet | Providing & Laying 600mm x 600mm Imported Loop pile patterned carpet of 20 ounce in tile form with antistatic rating of <3.5, PVC backing and having gauge of 1/10, min 6000 Green Label certification & confirming CRI standards as per the selection of the architect/clients, carpet to be of pile composition of thermoplastic polyolefin or other equivalent make confirming to relevant BS standards. Shall be inclusive of PVC Protective sheetcovering and protecting the carpet till the hand over, all carpet to be LEED certified for Platinum rating, Use all Carpet with CRI Green label plus certified. This means both carpet and carpet pad/backing has to be CRI Green label plus certified. And the carpet adhesive must meet or not exceed 50g/l of VOC content. Carpet Make: Interface, Milliken and Tandus | Sq m | [5 empty] | 0
9.66 |  | CIVIL | Flooring | Epoxy Grouting | Epoxy Grouting the joints | Epoxy Grouting the joints of flooring tiles having joints of 3 mm width, using epoxy grout mix of 0.70 kg of organic coated filler of desired shade (0.10 kg of hardener and 0.20 kg of resin per kg), including filling / grouting and finishing complete as per direction of Engineer-in- charge. Size of Tile 600x600 mm | Sq m | [5 empty] | 0
9.67 |  | C & I | Flooring | Anti skid treatment | Anti skid treatment | Providing & Applying of Anti skid treatment on all areas of flooring | Sq m | [5 empty] | 0
9.68 |  | CIVIL | Flooring | PP Cello Buble Guard | 250GSM PP Cello BUBLE GUARD | Providing, laying & removing 250 GSM PP Cello buble gaurd floor protector for protecting tile flooring and disposal of debris as directed. Vendor:M/s WIMPLAST | Sq m | [5 empty] | 0
9.69 |  | CIVIL | Counter | Slim Porcelain tile floor | Slim Porcelain tile floor on existing ply base raised flooring. | S/I of 3mm Thick Slim Porcelain tile floor on existing ply base raised flooring as per selection by client | Sq m | [5 empty] | 0
9.7 |  | CIVIL | Self Levelling Compound | self levelling compound | homogenous self levelling compound of thickness | Providing and finishing of homogenous self levelling compound of thickness minimum 3mm with master top 1200 of MBT degussa/ardex R70 P in approved colour after surface preparation by shot blasting with vaccine attachment etc. complete the rate should be inclusive of carrying out merged with wall levelling on one end floor on other end as per specification of manufacturer/architects. | Sq m | [5 empty] | 0
9.71 |  | CIVIL | Flooring | Indian patent floor | machine mixing and laying in approved panels 30mm thick (average) Indian patent floor | Providing, machine mixing and laying in approved panels 30mm thick (average) Indian patent floor in cement concrete mix of 1:2:4 (1 cement : 2 sand : 4 aggregate 12.5 mm) well vibrated, compacted including 25 x 3 mm thick glass dividing strip, fixed to correct level and finished smooth and cured by keeping surfaces well- covered and protected against excesses of any type. (The contractor will provide for preparation or surface by cleaning, hacking and exposing aggregate to achieve the best bond, and any curling, lifting or debonding noticed shall be rectified by the contractor at his cost), all complete at all heights and leads to the satisfaction of the PM. | Sq m | [5 empty] | 0
9.72 |  | CIVIL | Flooring | Screed | KERAKOLL or equivalent approved Screed System | KERAKOLL or equivalent approved Screed System, consisting of the following and installed per manufacturer’s written instructions: | Sq m | [5 empty] | 0
[6 empty] | a. Slurry Bond Coat on Existing Concrete Surface: P5 polymeric latex suitable for use as a high performance additive in cement based mortars and fine grain concretes. Increases substrate adhesion, reduces water absorption and enhances the level of compactness and flexibility. Ideal for slurry keys used in additional casting layers and in restoration work. | [6 empty] | 0
[6 empty] | b. Floor Screed / Bedding Mortar of average 30mm thickness: Keracem superior-technology, high-resistance hydraulic binder for screeds and heat radiant slabs, with normal setting and rapid drying, compensated shrinkage and high thermal conductivity; suitable for laying ceramic tiles, homogeneous tiles, natural stone, parquet and resilient materials with adhesives. | [6 empty] | 0
9.73 |  | CIVIL | Flooring | concrete screed | Providing and laying concrete screed | Providing and laying concrete screed(1:2:4) of specified thick laid in slope with one layer of 18 gauge chicken wire mesh including supply of all materials and labour curing finishing etc. all complete. Covered with approved cement tiles laid in cement mortar and finished as shown on the drawing and as specified under section ..... of Finishes technical specifications. | Sq m | [5 empty] | 0
9.74 |  | CIVIL | Flooring | concrete floor | 50mm thick cement concrete floor | Screed 50mm thickness - M20 Grade Concrete - Providing and laying 50mm thick cement concrete floor of M20 grade finished with a floating coat of neat cement finish using cement slurry @ 2.75 Kg. per Sqm. of floor area, laying the concrete in panels not exceeding 3m x 4m separated including cleaning the sub base, curing etc. complete as directed by the Engineer. | Sq m | [5 empty] | 0
9.75 |  | CIVIL | Flooring | Floor Maintanence | Cleaning the flooring, glass, formica | Cleaning the flooring, glass, formica etc. with first Acytone thinner then liquid cleaner with using cotton cloth etc. complete as per the instruction of Engineer-in-charge. | Sq m | [5 empty] | 0
[6 empty] | TOTAL OF FLOORING WORK | [6 empty] | 607231.05 |  | 594687.1905

## MB Gflooing
MB Sheet CIVIL MASONRY BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU
SR.NO | Item Description | Unit | No | Length | Breadth | Total Quantity
A | General Site Works
9.23 | 25mm thick Kota stone flooring - BOH AREA.
| kichan area | SQMT | 1 | 7.86 | 2.4 | 18.864
| live kichan area | SQMT | 1 | 4.8 | 2.78 | 13.344
| Live Kitchen Door Umbra Patta | SQMT | 2 | 0.16 | 0.9 | 0.288
32.496
9.27.A | Kota Strip in Ramp -100mm - BOH AREA
| door side | RMT | 7 | 0.9 |  | 6.3 | 6 | 0.9 | 5.4
| exite door | RMT | 15 | 1 |  | 15 | 10 | 1 | 10
[6 empty] | 21.3 |  |  | 15.4
9.37.2.b | Printed - FOH AREA.
| entrice area | SQMT | 1 | 1.05 | 7.83 | 8.2215
| cold area | SQMT | 1 | 5.6 | 2 | 11.2
| counter side | SQMT | 1 | 1 | 6 | 6
|  | SQMT | 1 | 1 | 5.245 | 5.245
30.6665
9.37.4,b | Cemented Finished - FOH AREA.
| sofa side | SQMT | 1 | 12.307 | 3.74 | 46.0282
| ceter | SQMT | 1 | 3 | 3.9 | 11.7
| couter side | SQMT | 1 | 3.363 | 4.764 | 16.0213
73.7495
9.39.2.e | Vitrified tile Skirting,
| live kichan area | RMT | 2 | 4.8 |  | 9.6
| live kichan area | RMT | 2 | 0.85 |  | 1.7
| live kichan area | RMT | 2 | 1.78 |  | 3.56
| ramp area | RMT | 3 | 1.48 |  | 4.44
| right wall kichan | RMT | 1 | 4.64 |  | 4.64
| lift wall | RMT | 1 | 5.49 |  | 5.49
| dish wash | RMT | 3 | 2.4 |  | 7.2
| dish wash | RMT | 2 | 0.85 |  | 1.7
| electrical room | RMT | 1 | 3.65 |  | 3.65
41.98
9.41.a | 150MM WIDE JET BLACKGRANITE STRIP-FOH AREA's Floor
| colum side (entrance façade outside) | Rmt | 1 | 6.9 |  | 6.9 | 1 | 6.94 | 6.94
| round (kitchen side wall) | Rmt | 1 | 5.3 |  | 5.3 | 1 | 3 | 3
| cove (straight live counter window flooring) | Rmt | 1 | 3 |  | 3 | 1 | 7.2 | 7.2
| start | Rmt | 1 | 5.4 |  | 5.4 | 1 | 6.4 | 6.4
12.31
[6 empty] | 20.6 |  |  | 35.85
9.41.b | Curved Granite Strip | Rmt | 1 | 4.5 |  | 4.5
|  | Rmt | 1 | 5.2 |  | 5.2
[6 empty] | 9.7 |  |  | 8.76
9.41.c | Granite Strip
| sofa side | Rmt | 1 | 12.31 |  | 12.31 |  | qty taken in 9.41a
9.42 | AT ENTRANCE TO POS SECTION. | rmt | 1 | 6.938 |  | 6.938 |  | qty taken in 9.41a
9.42.a | JET BLACK GRANTE-GLASS WINDOW AREA. | SQMT | 1 | 22.8 | 0.2 | 4.56 | 1 | 12 | 0.11 | 1.32
|  | SQMT | 1 | 4.8 | 0.2 | 0.96 | 1 | 4.8 | 0.11 | 0.528
5.52
9.55.01 | SS Rose Gold Skirting |  |  |  |  | 0 |  |  |  | 1.848
| entrance lift side column | RMT | 1 | 3.23 |  | 3.23
| entrance right side column | RMT | 1 | 0.2 |  | 0.2
| wall | RMT | 1 | 9.1 |  | 9.1
| live kichan | RMT | 1 | 5.6 |  | 5.6
| pandal wall | RMT | 1 | 4.931 |  | 4.931
| sofa martials at site | RMT | 1 | 12.7 |  | 12.7
| door side | RMT | 1 | 4.9 |  | 4.9
40.661

## H.Wall Finishes
FEBRUARY 2020
TRAVEL FOOD SERVICES
BOQ STANDARDISATION, IMPLEMENTATION AND COST CONSULTANCY |  |  |  |  | WALL FINISHING BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU |  |  |  |  | M&A Bill
SR. NO. | WBS | WBS Level1 | WBS Level2 | SHORT ITEM DESCRIPTION | PARTICULARS | UOM | QTY. | Final Rate | Total Amount | Qty | Amount |  | remark
GENERAL NOTES
a |  |  |  |  | Please refer to "Exhibit A - Basic rate of material" for the applicable base rates of materials
c |  |  |  |  | Items of works shall to be read in conjunction with Drawings, Specifications, Contractual terms and conditions and Trade Preambles to this BOQ as included in the RFP.
d |  |  |  |  | The quantities mentioned in the BOQ is tentative and may increase or decrease. Payment shall be restricted to the quantum of work executed and measured as per the defined mode of measurement.
e |  |  |  |  | The Mode of Measurement (in order of priority) is as follows:
(i) As defined in relevant item in the BOQ
(ii) As defined in the specification
(iii) As defined in IS-1200 (latest version) for relevant trade.
(iv) if mode is not defined in (i), (ii) and (iii), the standard industry practice shall be adopted.
Items of work and trade preambles are essential parts of the bill of quantities and are to be taken as mutually explanatory of one another. Requirement occurring in one is binding as though occurring in both. In resolving conflicts, discrepancies, errors or omissions as regards trade preambles & bill of quantities the following order of precedence shall be used but subject to PRIORITY OF DOCUMENTS as included in General Conditions of Contract: a. General Notes as included in this bill of quantities. b. Trade Preambles as included in RFP. c. Item Description as included in this bill of quantities.
10 |  |  |  |  | CLADDING WORK
10.1 | CIVIL | Dado | Marble stone Dado. | 19mm thick Marble stone Dado. | Laying 19mm thick machine cut, machine polished Marble stone Dado of approved quality, colour, shade and pattern, laid in pattern and sizes as shown in drawing. Joints to be well cleaned and grouted with matching colour approved quality polymer based readymade grout, curing, machine polishing, cleaning, protecting till handing over etc. to required line, level, etc, at all levels and locations, complete to the entire satisfaction of the PM. | Sq m
10.1.01 | CIVIL | Dado | Marble stone Dado. | 19mm thick Terrazzo Marble stone Dado. Basic Cost INR.4035.00 | Laying 19mm thick machine cut, machine polished Terrazzo Marble stone Dado of approved quality, colour, shade and pattern, laid in pattern and sizes as shown in drawing. Joints to be well cleaned and grouted with matching colour approved quality polymer based readymade grout, curing, machine polishing, cleaning, protecting till handing over etc. to required line, level, etc., at all levels and locations, complete to the entire satisfaction of the PM. Back Wall of the POS Section. | Sq m | 19 | 8148 | 154812 | 17.82 | 145197.36 | certify
10.2 | C & I | Cladding | Marble Cladding | ITALIAN MARBLE CLADDING | Providing and fixing machine cut and mirror polished approved coloured ITALIAN MARBLE SLAB with in lays of approvedsize,20mm +2mm thk. Of approved quality for required pattern on a bed of 1:4 CM 25mm average thickness including neat cement float, filling joints with neat coloured pigment,curing,polishing and cleaning etc. Complete. (Basic rate of ITALIAN marble Rs._______/-per Sq.M) | Sq m
10.3 | CIVIL | Dado | Vitrified tile | Vitrified tile dado | Fixing Vitrified tile dado , at all levels and locations including shifting of materials from stores to work location, using approved quality compatible adhesive (Kerakoll / Bal / Laticrete or equivalent). Joints to be well cleaned and grouted with matching colour approved quality polymer based readymade grout, curing, machine polishing, cleaning, protecting till handing over etc. to required line, level, etc. complete to the entire satisfaction of the PM. | Sq m
10.4 | C & I | Cladding | Vitrified Tiles | Vitrified Tile | Providing & fixing Vitrified tile dado of approved make & shade in required position including backing coat plaster in CM:1:4 including neat cement paste curing ,filling the joints with white cement & colour pigment to match the shade of cladding and cleaning etc. Complete. Light coloured glazed vitrified tiles/ Dark coloured glazed vitrified tiles/matt vitrified tiles/ Dark coloured antiskid / matt vitrified tiles. |  |  |  | 0
10.4.1 |  |  |  |  | Providing & fixing Vitrified tile Front Desk Glazed Tile. | Sq m
10.4.2 |  |  |  |  | Providing & fixing Vitrified Tiles Service Area | Sq m
10.4.3 |  |  |  | 600mm x 600mm Off White, Kajaria make, basic cost INR. 538.00/SM. | Providing & fixing Vitrified Tiles at Back Kitchen Area up to 2700mm Height. At Back Kitchen area. | Sq m | 51.435 | 2421 | 124524.135 | 87.46 | 211740.66
10.4.4 |  |  |  | 600mm x 600mm Off White, Kajaria make, basic cost INR. 538.00/SM. | Providing & fixing Vitrified Tiles at Back Kitchen Area up to 1350mm Height. At Back Kitchen area. | Sq m | 4.59 | 2421 | 11112.39 | 6.04 | 14622.84
10.4.5 |  |  |  | 600mm x 600mm Light Grey, Kajaria / other approved make, basic cost INR. 1345.00/SM. | Providing & fixing Vitrified Tiles at Display Kitchen Area up to 2700mm Height. At Back Kitchen area. | Sq m | 36.45 | 3390 | 123565.5 | 25.087 | 85044.93
10.5 | C & I | Cladding | Vitrified Tiles | Black and White Tiles for Angular Wall dado in appvd vitrified tiles | Providing and Fixing of Black and White Tiles for Angular Wall dado in appvd vitrified tiles as per the design & specifications. Joints to be filled properly with pigmented cement / epoxy grouts matching the tile/stone. Flooring should be fixed in proper plumb line . Job to include cost of labour, material, cartage, loading, unloading, cutting, fixing and grouting, etc. complete, as directed by Engineer-In-Charge. (width of Tile = ____ mm) | RMT
10.6 | CIVIL | Dado | Ceramic tile dado | Ceramic tile dado | Fixing Ceramic tile dado , at all levels and locations including shifting of materials from stores to work location, over well vibrated, compacted screed (paid separately) using approved quality compatible adhesive (Kerakoll / Bal / Laticrete or equivalent). Joints to be well cleaned and grouted with matching colour approved quality polymer based readymade grout, curing, machine polishing, cleaning, protecting till handing over etc. to required line, level, etc. complete to the entire satisfaction of the PM. | Sq m
10.7 | C & I | Glass | Lacquered Glass | 6MM LACQUERED GLASS | Providing and fixing 6 mm thick lacquered glass without designs, Rate shall include for providing necessary hardware's etc. complete as per drawing or as directed by the Engineer-in-charge. "Glass of Asahf/ Saint Gobain/ Sezal or approved equivalent make. | Sq m
10.8 | C & I | Glass | Lacquered Glass | 6MM THK LACQUERED GLASS ON PLY | Providing and fixing 6 mm thick lacquered glass in plain red or approved colour. (Glass manufactured by Ashai / Modi Guard/ Saint Gobain or equivalent approved make) fixed over ply surface with necessary adhesive. Excluding cost of ply surface but including fitting etc. complete. | Sq m
10.9 | C & I | Wall Façade | Glass Facade | Fixed Glazing in facade using 12mm thick, with U channel | Providing and fixing Fixed Glazing in facade using 12mm thick clear flawless toughened glass and fixed on top and bottom in 'U' channel. The top and bottom 'U' channels to be concealed within the floor and in the fase ceiling respectively. Rate to be all inclusive of AI 'U' channels, toughened glass, hardware. Finishing and fixing etc., complete, as directed by EIC. | Sq m
10.1 | C & I | Wall Façade | Glass Facade | GLASS FASCADE 12MM TOUGHEN GLASS | Providing and fixing Glass Facade made out of 12mm thick clear float, toughened glass (manufactured by AISI / Modi Guard / Sainte.Gobainorequivalent) fixed to the wooden/ RCC member at top and channel edge grooving floor as shown in the standard detailed drawing with necessary screws/ hold fasts. The glass shall be edge polished on all sides. (Drawings shall be provided for the Contractor to quote the rate) | Sq m
| C & I | Wall Window | Glass Window | GLASS WINDOW 12MM TOUGHEN GLASS @ DISPLAY KITCHEN. | Providing and fixing Glass Facade made out of 12mm thick clear float, toughened glass (manufactured by AISI / Modi Guard / Sainte.Gobainorequivalent) fixed to the wooden/ RCC member at top and channel edge grooving floor as shown in the standard detailed drawing with necessary screws/ hold fasts. The glass shall be edge polished on all sides. (For the display kitchen area, Heatproof & Clear Toughened ) | Sq m | 7.3438 | 5111 | 37533.9062 | 7.32 | 37412.52
10.11 | C & I | Cladding | ACP Clad | 4MM THK SPARKLEFINISHED ACP CLADD | Providing and fixing Aluminium Composite Panel cladding at all heights with 4mm thick exterior grade panels (0.5+3+0.5MM) of Alucobond make Timex Sparkle finished or equivalent make) as shade indicated in the Architect's drawing | Sq m
10.12 | C & I | Cladding | ACP Clad | 4MM THK MATT FINISH ACP BTH SO FRM | Providing and fixing aluminium composite panels (ACP) made out of 4mm thick (0.25+3.5+0.25) with LDPE core coloured, matt finish panels on both sides; (total thickness of the panel shall be 4mm) of approved make inclusive of anodising the aluminium sections a minimum of 20 micron thickness and providing, erecting and dismantling of scaffolding/staging as necessary up to a height of 15 feet from ground.( Drawings shall be provided to the contractor for quoting of rates. | M2
10.13 | C & I | Jali | ACP Jali | TIMEX ACP 4MM THK DESIGN CUT JALl | Providing and fixing 4 mm Thk Timex or Equivalent make ACP Jali as per with approved design and shade. ACP Jail cutting edge should be finished with duco paint as per approved shade etc. all to the complete satisfaction and as per the direction of the Engineer-in-charge. | M2
10.14 | C & I | Cladding | Brick clad tile finished | Brick clad tile finished | Providing and fixing Tile brick masonry work 5 cm thick with common burnt clay F.P.S. (non modular) tile bricks of class designation 10 in cement mortar 1:3 (1 cement : 3 coarse sand) in superstructure above plinth and upto floor five level. | Sq m
10.15 | C & I | Cladding | Brick clad tile finished | red artificial bricks of 8"x3" size pasted with adhesive | Providing and Fixing of red artificial bricks of 8"x3" size pasted with adhesive of appvd proportions as per the design & specifications. Joints to be filled properly with pigmented cement / epoxy grouts matching the brick. Brick horizontals should be fixed in proper plumb line . Job to include cost of labour, material, cartage, loading, unloading, cutting, fixing and grouting. | RMT
10.16 | C & I | Cladding | Terracotta bricks | Terracotta bricks over plywood | P&F Terracotta bricks with paint finish over Plywood | Sq m
10.17 | C & I | Cladding | Terracotta bricks | Terracotta bricks over plywood | P&F Terracotta bricks over Plywood | Sq m
10.18 | C & I | Finishing | Brick pattern in Ply | Brick pattern in Ply and finished with paint | P&F Brick pattern in Ply and finished with paint. | Sq m
10.19 | C & I | Cladding | wooden paneling | Veneer finished wooden paneling | S/I of 50mm Thk Veneer finished paneling in 12mm thk Ply, supported on aluminium frame work as per design and detailing | Sq m |  |  | 0
10.19.01 | C & I | Cladding | wooden paneling | Veneer finished wooden paneling | S/I of Veneer finished paneling over existing 12mm thk Ply Paneling supported on aluminium frame work as per design and detailing. Veneer finished with fire rated PU Polish. As per Elevation AA. | Sq m | 22.867 | 5100 | 116621.5776 | 22.8005 | 116282.55
10.19.02 | C & I | Cladding | wooden paneling | Veneer finished wooden paneling | S/I of Veneer finished paneling over existing 12mm thk Ply Paneling supported on aluminium frame work as per design and detailing. Veneer finished with fire rated PU Polish. As per Elevation BB. | Sq m | 11.8875 | 5100 | 60626.25 | 11.875 | 60562.5 |  | not acceptable qty 5.94
10.19.03 | C & I | Cladding | wooden paneling | Solid wooden paneling for artist's work.. | S/I of 19mm thick (red oak / ash wood) sold wooden paneling with 12mm thk Ply backing supported on aluminium frame work / wall as per design and detailing. Wood finished with fire rated PU Polish. As per Elevation AA. 1125mm x 400mm x 5 nos. | Sq m | 2.25 | 8900 | 20025 | 2.5 | 22250
10.2 | C & I | Cladding | wooden panelling | Mirror finished wooden panelling | S/I of 50mm Thk 6mm Thk mirror finished panelling behind bar display in 12mm thk Ply, supported on aluminium frame work as per design and detail. | Sq m
10.21 | C & I | Cladding | wooden pattern tiles | P&L OF WOODEN PATTERN TILES | P&L OF WOODEN PATTERN TILES Providing and Laying of Wooden Pattern Tiles ItKajaria Eternity (Assam Rosewood Size- 600·600) laid uniformly over 40 mm thick bed CM 1:4 with butt joints, using cement slurry below tiles for packing and as per architectural design, drawing and specifications. The work shall include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. | M2
10.22 | C & I | Cladding | Designer wall panelling | Designer wall panelling with outer frame made of Ply boxing | P&F Designer wall panelling with outer frame made of Ply boxing & finished in SS with brass coating and internal screen made of laser cut SS of 12mm thick finished with brass coating | Sq m
10.23 | C & I | Finishing | wooden beading | wooden beading with paint finish | Providing and fixing of 1"x1/2" wooden beading patty screwed to wall at intervals and flat oil paint finished same as wall shade. | Rmt |  |  | 0
10.23.01 | C & I | Finishing | wooden beading | wooden beading with PU Polish finish | Providing and fixing of 1"x1/2" wooden (seasoned red oak / ash wood) beading patty screwed / nailed to wall at intervals and PU Polish finished same as wall shade. As per Elevation BB over Veneer Paneling. | Rmt | 62.5 | 700 | 43750 | 57.5 | 40250 | certify
10.23.02 | C & I | Finishing | wooden beading | wooden beading with PU Polish finish | Providing and fixing of 1"x1/2" wooden (seasoned red oak / ash wood) beading patty screwed / nailed to wall at intervals and PU Polish finished same as wall shade. On the façade paneling. | Rmt | 198 | 700 | 138600 | 358.55 | 250985 | certify
10.23.03 | C & I | Finishing | wooden beading | wooden beading with PU Polish finish | Providing and fixing of 4"x3/4" wooden (seasoned red oak / ash wood) beading patty screwed / nailed to wall at intervals and PU Polish finished same as wall shade. As per Elevation BB + C1C1, for glass beading. | Rmt | 16.5 | 2450 | 40425 | 16.5 | 40425
10.23.04 | C & I | Finishing | wooden beading | wooden beading with PU Polish finish | Providing and fixing of 4"x3/4" wooden (seasoned red oak / ash wood) beading patty screwed / nailed to wall at intervals and PU Polish finished same as wall shade. As per Elevation BB + C1C1, for glass beading. | Rmt | 16.9 | 2450 | 41405 | 16.7 | 40915
10.23.05 | C & I | Finishing | wooden beading | wooden beading with PU Polish finish | Providing and fixing of 2"x3/4" wooden (seasoned red oak / ash wood) beading patty screwed / nailed to wall at intervals and PU Polish finished same as wall shade. As per Elevation BB at the divider partition fascia at Open Deck Units area. | Rmt | 7.6 | 1325 | 10070 | 7.6 | 10070 |  | chk mb 3+1
| C & I | Finishing | wooden beading | wooden beading with PU Polish finish | Providing and fixing of 6"x3/4" wooden (seasoned red oak / ash wood) beading patty screwed / nailed to wall at intervals and PU Polish finished same as wall shade. As per Elevation BB at the top of the Open Deck Units area. | Rmt | 3.4 | 3400 | 11560 | 3.4 | 11560
10.23.07 | C & I | Finishing | wooden baffle panel | Linear Wooden Baffle Panel - in PU Polish finish. | Linear Wooden Baffle Panel (Birch Plywood of 25mm thick in fire rated PU Polish), with supply & installation of Vertical Linear Wooden Baffle/Rafter Panel system consist of approved shade of 25mm thick birch plywood sections of specified size 25mm thick x 22mm to 250mm height or as per drawing with a centre to centre spacing of 75mm with complete standard installation system and necessary supports as per manufacturer's specifications / site condition. The baffle units are then attached on the existing plywood backing panel as per approval of the architect & detail drawings complete in all respect. Wood Grain Finish-Design as specified in drawing and in line with Architect approved. This item is for the front facade panel. | Sq.m | 4.38 | 7000 | 30660 |  | 0
10.24 | C & I | Cladding | wooden panelling | Fabric finished wooden panelling | P&F Fabric finished wooden panelling | Sq m
10.25 | C & I | Cladding | Designer wall panel | Designer wall panel made of laser cut | P&F Designer wall panel made of laser cut wooden panels with 50 X 50 mm Ms Frame. | Sq m
10.26 | C & I | Cladding | Col wall panel | COLUMN CLADDING W/LAMINATED PLY | Providing and fixing of Column cladding with 12mm thick ply and 1mm thick laminate (S.S finish),cladding to be protected with 24x 2mm brush steel S.S angle at corners. Further fixing 25 x 25 mm teak wood beading with round edge and painting . | Sq m
10.27 | C & I | Cladding | Commercial plywood panelling | 6MM THK MIR W/9MM CMCl PLYWOOD PNl | Providing and fixing 6mm thick mirror of approved quality with 9mm commercial Plywood panelling, 12mm thick beading to plywood, including Brush Steel finish S.S Mirror studs. | Sq m
10.28 | C & I | Cladding | Column Wall Panelling | COLUMN WALL PANELNG 50X32MM HARDWOOD FRAME | Providing and fixing in position Column wall panelling using 50x 32mm hardwood framework all-round the column at 600mm C/C, fixing with 12.5mm thick Gypsum board and finished good to receive directly painting over the exposed surfaces etc., complete all as per drawings and as directed by Engineer-In-charge. | Sq m
10.28.01 | C & I | Cladding | Wall Paneling | BOX PANELNG OF 200MM THICK 19MM PLY WOOD FRAME | Providing and fixing in 200mm box wall paneling using 19mm thick ply wood framework on the wall at 600mm C/C, fixing with 12mm thick ply wood finished good to receive directly painting over the exposed surfaces etc., complete all as per drawings and as directed by Engineer-In-charge. | Sq m | 11.34 | 4600 | 52164 | 7.56 | 34776 | certify
10.29 | C & I | Finishing | Laminate Beading | Laminate beading over tile finish | Providing and fixing 'Laminate beading over tile finish | Sq m
10.3 | C & I | Cladding | Laminate panelling | Laminate panelling | Providing and fixing 12mm commercial ply panelling with laminate finish as per the instruction of site engineer. | Sq m
10.31 | C & I | Cladding | Cube/Cuboidal Boxes | CONST & INSTALL OF CUBE/CUBOIDAL BOXES | Construction & installation of cube/ cuboidal boxes as per approved sizes and drawings details out of 19mm thk marine grade block board panels of appropriate sizes. All open edges of the panel to be protected with teak wood lipping fixed with fevicol and nailed in edges, all pieces will be fixed to each other and held in position with corner, block board brackets/ metal clamps etc complete. The box shall be finished with neatly cut laminates and bevelled edges joints with appropriate grade of fevicol etc complete. The bottom surface shall be fixed with 2 nos: 3/4" inch x 4"inch tall TW cross member as per design detail and shall have support of PVC clear bushes on base. | Sq m
10.32 | C & I | Finishing | plywood | plywood bulkhead | P&F of plywood bulkhead | Sq m
10.33 | C & I | Framework | Hardwood | Hardwood Framework | Providing and fixing in position Ply using 12mm thick commercial ply to masonry back ground/on wooden frame of 2" X 2" thk hard wood frame adhesives/screws and jointing compound of approved make / quality and finished with paint of approved make, colour, etc., complete as per instruction of site in charge | Sq m
10.33.a | C & I | Framework | Hardwood | Hardwood Framework | Pro & Fix 2"x2" Hardwood Framework Wooden/Ply of 19mm thickness. | Sq m
10.33.b | C & I | Framework | Hardwood | Hardwood Framework | Pro & Fix 2"x2" Hardwood Framework Wooden/Ply of 6mm thickness. | Sq m
10.34 | C & I | Framework | Aluminium | Aluminium Frame | Aluminium section of 2"x1.1/2" framework for partition in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling paneling framework,12 mm thk FR plywood fixed to framework with flat head, full thread, sheet metal screws with approved laminate finish | Sq m |  |  | 0
10.34.01 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Wall Paneling of 37mm thick. | Aluminium section of 2"x1" framework (out of vertical members at 600 mm c/c & with horizontal members at 600 mm c/c) for wall paneling in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling paneling framework,12 mm thk FR plywood fixed to framework with flat head, full thread, sheet metal screws without any finish. As per Elevation AA, above banquet Seating up to false ceiling level. | Sq m | 39.564 | 4100 | 162212.4 | 40.32 | 165312
10.34.02 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Wall Paneling of 37mm thick. | Aluminium section of 2"x1" framework (out of vertical members at 600 mm c/c & with horizontal members at 600 mm c/c) for wall paneling in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling paneling framework,12 mm thk FR plywood fixed to framework with flat head, full thread, sheet metal screws without any finish. As per Elevation BB, at glass display window wall up to false ceiling level, less glass opening area. | Sq m | 13.49 | 4100 | 55309 | 15.12 | 61992
10.34.03 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Wall Paneling of 37mm thick. | Aluminium section of 2"x1" framework (out of vertical members at 600 mm c/c & with horizontal members at 600 mm c/c) for wall paneling in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling paneling framework,12 mm thk FR plywood fixed to framework with flat head, full thread, sheet metal screws without any finish. Facade Paneling. | Sq m | 14.985 | 4100 | 61438.5 | 56.5545 | 231873.45
10.34.04 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Round Column Paneling of 37mm thick. | Aluminium section of 2"x1" framework + 19mm thick plywood framing horizontally (out of vertical members at 450 mm c/c & with horizontal members at 600 mm c/c) for round column paneling in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling paneling framework,12 mm thk FR plywood fixed to framework with flat head, full thread, sheet metal screws without any finish. As per Elevation BB, from ffl to false ceiling level. | Sq m | 11.5825 | 5500 | 63703.75 | 16.4 | 90200
10.34.05 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Wall Paneling of 50mm thick with Cove Light Provision. | Aluminium section of 1.5"x1.5" framework (out of vertical members at 400 mm c/c & with horizontal members at 600 mm c/c) for wall paneling in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling paneling framework,12 mm thk FR plywood fixed to framework with flat head, full thread, sheet metal screws with another layer of 4mm thick plywood finish to get the even surfaces and edges for stucco / selected paint finish. As per Elevation DD, 482mm W x 3650mm H x 54mm D x 8 Nos. | Sq m | 14.0744 | 4850 | 68260.84 | 13.8816 | 67325.76
10.34.06 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Wall Paneling of 74mm thick. | Aluminium section of 2"x1" framework (out of vertical members at 600 mm c/c & with horizontal members at 600 mm c/c) for wall paneling in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling paneling framework,12 mm thk FR plywood fixed to framework with flat head on both the surfaces, full thread, sheet metal screws without any finish. As per Elevation BB, at open display unit, up to the false ceiling level, the front partition to create the niches. | Sq m | 10.417 | 4850 | 50522.45 | 10.987 | 53286.95
10.34.07 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Top + Horizontal Wooden Shelve of 74mm thick. | Aluminium section of 2"x1" framework (out of vertical members at 600 mm c/c & with horizontal members at 400 mm c/c) for top / shelves in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling paneling framework,12 mm thk FR plywood fixed to framework with flat head on both the surfaces, full thread, sheet metal screws without any finish. As per Elevation BB, top and shelves above the open display unit. | Sq m | 5.94 | 5000 | 29700 | 6.408 | 32040
10.34.08 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Partition of 50mm thick. | Aluminium section of 2"x1" framework (out of vertical members at 400 mm c/c & with horizontal members at 600 mm c/c) for top / shelves in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling partition framework,12 mm thk FR plywood fixed to framework with flat head on both the surfaces, full thread, sheet metal screws with 1mm thick laminate finish. As per Elevation BB, divider partition at the display unit area with both surfaces in laminate finish. | Sq m | 3.42 | 4900 | 16758 | 3.822 | 18727.8 |  | to be clarify
10.34.09 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Partition of 50mm thick. | Aluminium section of 2"x1" framework (out of vertical members at 400 mm c/c & with horizontal members at 600 mm c/c) for top / shelves in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling partition framework,12 mm thk FR plywood fixed to framework with flat head, full thread, sheet metal screws with 1mm thick laminate finish. As per Elevation BB, both the sides panel at the display unit area with one surface in laminate finish. | Sq m | 3.42 | 4900 | 16758 | 3.822 | 18727.8 |  | to be clarify
10.34.10 | C & I | Framework | Aluminium | Aluminium Frame + Wooden Bulkhead of 75mm thick. | Aluminium section of 2"x1" framework (out of vertical members at 400 mm c/c & with horizontal members at 600 mm c/c) for top / shelves in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling partition framework,12 mm thk FR plywood fixed to framework with flat head, full thread, sheet metal screws with 1mm thick laminate finish. As per the front facade elevation with one surface in laminate finish. | Sq m | 5.899 | 5800 | 34214.2 | 3.24 | 18792 |  | to be clarify
10.34.a |  | Framework |  |  | Basic cost of 2"x1.1/2" Al section | Rft
10.34.b |  | Framework |  |  | Basic cost of F.R plywood | Sqft
10.35 | C & I | Cladding | Board | MDF Board | Providing & Fixing of 6mm thickness MDF Board of Size 4X8 Feet work must be done as per direction & instruction of Engineer in Charge. | ft
10.36 | C & I | Cladding | Board | Prelaminate Board | Providing and fixing 12mm thick pre-laminated board with white outer laminate (NOVOPAN) on four sides, over hard wood frame work. The sectional the hard wood shall be 42mm x 42mm. The frame work shall be @ 600mmc/c. The corner edges of the pre laminated board shall be chamfered @ 4Sdegrees to avoid the exposed edges on all the four corners. etc. complete as directed by Engineer in charge. | Sq m
10.37 | C & I | Framework | plywood | Water Proof Ply | Pro & Fix of Water proof Ply 12mm Thk. | Sq m
10.38 | C & I | Framework | Wooden | Water Proof Ply | Pro & Fix of Wooden Frame/ Ply 12MM Thk·only Wooden frame works | Sq m
10.39 | C & I | Framework | Wooden | Water Proof Ply | Pro & Fix of Wooden Frame/ Ply 12MM Thk·only Wooden frame works | Sq m
10.4 | CIVIL | Dado | Glazed tile Dado | GLAZED TILES DADO | Providing and fixing Tiles in Cladding / Dado 01 approved shade, size and pattern on masonry walls including border fixed in pattern as approved by fie and fixed with rich cement slurry over abacking coat plaster of 12mm thk. Cement mortar 1:3 and grouted with app. shade grout (Sal Grout) Rate to include, Tile cutting, cleaning of joints, finishing junction of plaster, curing etc. Complete and asper drawing. | Sq m
10.41 | CIVIL | Partition | Single Glazed Partition | Single Glazed Partition | Providing and fixing Single Glazed Partition with required patch fittings. | Sq m
10.42 | C & I | Cladding | Acrylic surface cladding | Acrylic surface cladding | Work Top treated with 6mm/12mm Acrylic Solid Surface (As per the Interior Head direction) on Ply Base | Sq m
10.43 | C & I | Cladding | Acrylic surface cladding | ACRYLIC SHEET | Providing and fixing of Acrylic sheet of approved Fissure design and make. | FT2
10.44 | C & I | Finishing | Onyx panelling | Onyx panelling | P&F of Onyx panelling having backlit provision | Sq m
10.45 | C & I | Cladding | Onyx wall Cladding | Onyx wall Cladding | P&F of Onyx Wall Cladding with laminated frame all around | Sq m
10.46 | C & I | Paint | Duco finish paint | Providing and fixing of Front Charcoal Panel board on plywood | Applying Duco finish paint on Glowood Charcoal panel after necessary surface preparation as directed by Engineer-in-charge | Sq m
10.47 | C & I | Paint | Paint finish | Stucco Paint finished wooden panelling | P&F Stucco Paint finished wooden panelling | Sq m
10.48 | C & I | Paint | paint finish | Ply with paint finish | Fixing Ply with paint finish | Sq m
10.49 | C & I | Finishing | Mirror | 6MM MIRROR ON EXIST WOODEN PARTITION | Provided and fixing 5mm thick mirror on the existing wooden partition with Mirror fixing S.S studs.as directed by Engineer in charge | Sq m
10.5 | C & I | Finishing | Mirror | 5PEC 6MM MIRROR W 3M ADHESIV TAP | Providing and fixing 6mm thk Mirror (Saint Gobain or equivalent) for Changing room of and with edges to be machine polished. The mirror is fixed with a 3M Self adhesive tape or silicon on to the 12mm thk commercial ply (MR Grade) on the back side. | Sq m
10.51 | C & I | Finishing | Mirror | 6mm Thk mirror finished panelling | S/I of 50mm Thk 6mm Thk mirror finished panelling behind bar display in 12mm thk Ply, supported on aluminium frame work as per design and detail. | Sq Ft
10.52 | C & I | Peg Wall | Hanging | F/PEG WALL HANGING | Fixing of Accessories/Equipment like Fire Extinguishers, lnsectocutor with necessary brackets/nut bolt/screws - Peg wall hanging | NOS
10.53 | C & I | Cladding | Awning system /PVC Cloth | AWNING SYSTEMW/PVC CLOTH | Providing and Fixing retractable awaning system with approved PVC cloth including M.S. supports, retracting system etc. complete | Sq m
10.54 | C & I | Cladding | Wall Paper | Wall Paper | P&F of Wall paper over Ply and framework | Sq m
10.55 | C & I | Cladding | Wall Paper | Wall Paper | P&F of Wall paper over POP Punning | Sq m
10.56 | C & I | Cladding | Picasso wall tile | Picasso wall tile | P&F Picasso wall tile | Sq m
10.57 | C & I | Cladding | G.I Roof sheet | Galvanise ROOF SHEET(24 GAUGE) | Providing & fixing precoated / prepainted galvanised roofing sheets of approved colour (24 Gauge thick) with accessories of approved quality & lengths including fixing the sheets, fixtures and fastening, screws, bolts and bitumen washers etc. complete as per drawings and specifications and as directed by Ele. | Sq m
10.58 | C & I | Cladding | Subway tile cladding | Subway tile cladding | Providing and fixing of app. Subway tile with appropriate proportion of cement and water to be align in plumb. | Sq m |  |  | 0
10.58.01 | C & I | Cladding | Subway tile cladding | Subway tile cladding. 75mm x 275mm, Basic Cost INR. 3120.00 | Providing and fixing of app. Subway tile with appropriate proportion of cement and water to be align in plumb. As per Elevation BB with selected & approved grouting. | Sq m | 11.38 | 5500 | 62590 | 11.38 | 62590
10.58.02 | C & I | Cladding | Subway tile cladding | Subway tile cladding over ply wood base. 75mm x 275mm, Basic Cost INR. 3120.00 | Providing and fixing of app. Subway tile with appropriate proportion of adhesive to be align in plumb over ply wood base. As per Elevation AA with selected & approved grouting. | Sq m | 16.3525 | 5500 | 89938.75 | 16.3742 | 90058.1
10.58.03 | C & I | Cladding | Subway tile cladding | Subway tile cladding over ply wood base. 75mm x 275mm, Basic Cost INR. 3120.00 | Providing and fixing of app. Subway tile with appropriate proportion of adhesive to be align in plumb over ply wood base. As per Elevation BB with selected & approved grouting. | Sq m | 13.6385 | 5500 | 75011.75 | 13.366 | 73513
10.59 | C & I | Cladding | Tile Cladding by slim Porcelain tile floor on existing ply base. | Tile Cladding by slim Porcelain tile floor on existing ply base. | S/I of 3mm Thick Slim Porcelain tile floor on existing ply base raised flooring as per selection by client. | Sq m
10.59.01 | C & I | Cladding | Ceramics Mosaic Tile Cladding. | Aqua Ceramic Mosaic (0.5"X0.5" on sheet)Tile Cladding on existing ply base. Basic Cost INR. 4304.00 | S/I of 3/4mm Thick Aqua Ceramic Mosaic (0.5"X0.5" on sheet)Tile Cladding on existing ply base raised flooring as per selection by client. As per Elevation BB, over the round column cladding area. | Sq m | 11.3 | 6600 | 74580 | 10.96 | 72336 | certify
10.6 | C & I | Cladding | finished column supported on MS pole clad with ply and finished with laminate | finished column supported on MS pole clad with ply and finished with laminate | 100 x 100mm finished columns supported on 75x75mm MS pole clad with ply and finished with laminate | Sq m
10.61 | C & I | Finishing | Laser cut design in Corian | Laser cut design in Corian | P&F Laser cut design in Corian | Sq m
10.62 | C & I | Finishing | Wall Landscape | Wall Landscape | Providing and fixing Landscape on walls. | Sq m
10.63 | C & I | Finishing | Pelmet | Pelmet | Providing and fixing pelmet made of Plywood and finished with wall paper, SS strip provided at the bottom edge of the pelmet as per drawing & etc. complete as directed by Engineer-in-charge.. | Sq m
10.64 | CIVIL | POP Punning | P&F of POP Punning | P&F of POP Punning | Providing and applying average 12 mm thk. POP mirror smooth punning to walls and existing ceiling including scraping and cleaning wherever required, to proper angle, line, level and plumb, ready to receive paint. Including protective, external corners of 20/25 SWG GI [India Gypsum or equivalent make], making all grooves, required scaffolding and protecting the surrounding areas and cleaning finished complete. | Sq m |  |  | 0
10.64.01 | CIVIL | POP Punning | P&F of POP Punning | P&F of POP Punning | Specifications same as above, for Elevation AA. | Sq m | 13.53 | 400 | 5412 | 15.17 | 6068
10.64.02 | CIVIL | POP Punning | P&F of POP Punning | P&F of POP Punning | Specifications same as above, for Elevation BB. | Sq m | 16.687 | 400 | 6674.8 | 7.56 | 3024
10.64.03 | CIVIL | POP Punning | P&F of POP Punning | P&F of POP Punning | Specifications same as above, for Elevation CC. | Sq m | 20.5 | 400 | 8200 | 20.5 | 8200
[5 empty] | TOTAL OF CLADDING WORK |  |  |  | 1898739.1989 |  | 2196161.22
0
0
Materials Specification: Materials should be as per specified in BOQ & details drawings. | [12 empty] | 0
0
1 | 19mm thick fire retardant (two hour Fire-Retardant) plywood's basic rate consider for 1614.00 / SM, Anchor / Kutty / Century / Green ply - Make | [11 empty] | 0
2 | Rest plywood's should as per item no. 1. | [11 empty] | 0
3 | Laminate basic cost INR 1325.00/Sheet. | [11 empty] | 0
4 | Venner basic cost INR. 1614.00/SQM. | [11 empty] | 0
5 | All adhesives should be Pidilite brand. | [11 empty] | 0
6 | All hardware's fittings should be as mentioned on BOQ / Equivalent to the mentioned brand. | [11 empty] | 0
7 | All glasses and mirror should be branded, like - Saint gobain / BIAL approved. | [11 empty] | 0
8 | Aluminium tube - 16 gauge, Jindal / equivalent make. | [11 empty] | 0
9 | All hardware fittings should be as per mentioned on BOQ / Equivalent / Branded. | [11 empty] | 0
10 | 1st quality old btc wood / selected & approved seasoned american red oak / american ash wood for all wooden work. | [11 empty] | 0
11 | Fire-Retardant pu polish as per BIAL Standard Guideline up to 2 hours fire-rated. | [11 empty] | 0
12 | MS / SS works with Jindal / Tata make. | [11 empty] | 0
13 | SS works with standard grade product and selected and approved high quality 304 grade ss sheet. | [11 empty] | 0
14 | All metal works to be carried out as per the BIAL guideline. | [11 empty] | 0
15 | Contractor team ahs to study the BIAL Guideline for further queries if any. | [11 empty] | 0
16 | All the Workshop Drawings to be prepared by the contracting team, construction can start upon mutual approval. | [11 empty] | 0
17 | All the materials has to up to BIAL's Standard as per their Guideline.

## MB H wall
MB Sheet CIVIL MASONRY BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU
SR.NO | Item Description | Unit | No | Length | Breadth | Total Quantity
A | General Site Works
10.1.01 | 19mm thick Terrazzo Marble stone Dado
| kitchen above window | SQMT | 1 | 2.1 | 1.5 | 3.15 | 1 | 2.1 | 1.5 | 3.15
| wall | SQMT | 1 | 2 | 3 | 6 | 1 | 2 | 3 | 6
| wall | SQMT | 1 | 2.1 | 4 | 8.4 | 1 | 2.1 | 4 | 8.4
| wall | SQMT | 1 | 0.9 | 1 | 0.9 | 1 | 0.9 | 0.3 | 0.27
[6 empty] | 18.45 |  |  |  | 17.82
10.4.3 | Providing & fixing Vitrified Tiles at Back Kitchen Area up to 2700mm Height. At Back Kitchen area.
| Service Kitchen Area LHS and RHS Wall Fixing of Dado Tiles | SQMT | 2 | 7.85 | 2.7 | 42.39
| less door | SQMT | -1 | 0.9 | 2.1 | -1.89
| Service Kitchen Area Back Wall Fixing of Dado Tiles | SQMT | 3 | 2.8 | 2.7 | 22.68
| less door | SQMT | -2 | 0.7 | 2.1 | -2.94
| less door | SQMT | -2 | 1 | 2.1 | -4.2
| Electrical Room Area Inside Wall Fixing of Dado Tiles | SQMT | 1 | 1.3 | 2.7 | 3.51
| Electrical Room Area RHS and LHS Wall Fixing of Dado Tiles | SQMT | 2 | 1.4 | 2.7 | 7.56
| Back Entry Door Top Wall Fixing of Dado Tiles | SQMT | 1 | 2 | 0.6 | 1.2
| Service Kitchen LHS Wall Fixing of Dado Tiles | SQMT | 1 | 1.48 | 2.85 | 4.218
| Door Vartical Dhar Fixing of Dado Tiles | SQMT | 4 | 5 | 0.2 | 4
| Live Kitchen Area Windows Wall Fixing of Dado Tiles | SQMT | 1 | 4.81 | 1.2 | 5.772
| Live Kitchen Area Windows Wall Fixing of Dado Tiles | SQMT | 2 | 0.9 | 1.2 | 2.16
| coffe Counter Area Back Wall Dado Tiles Fixing | SQMT | 1 | 3 | 1 | 3
87.46
10.4.4 | 1350mm Height. At Back Kitchen area dish wash
| dish wash door | SQMT | 2 | 1.9 | 1.5 | 5.7
|  | SQMT | 2 | 0.85 | 0.2 | 0.34
6.04
10.4.5 | Display Kitchen Area up to 2700mm Height
| Live Kitchen Area LHS Wall dado Tiles Fixing | SQMT | 1 | 4.85 | 2.7 | 13.095
| Live Kitchen Area Inside Door Wall dado Tiles Fixing | SQMT | 2 | 2.78 | 2.7 | 15.012
| Less Door | SQMT | -2 | 0.8 | 2 | -3.2
| glass above | SQMT | 2 | 0.3 | 0.3 | 0.18
25.087
Glass Window
| live kitchen | SQMT | 1 | 4.85 | 1.2 | 5.82
| door side | SQMT | 1 | 1.25 | 1.2 | 1.5
7.32
10.19.01 | Veneer finished wooden paneling AA
| veneer finished paneling 1 | SQMT | 1 | 1.255 | 3.1 | 3.8905
| veneer finished paneling 2 | SQMT | 1 | 2.41 | 3.1 | 7.471
| veneer finished paneling 3 | SQMT | 1 | 2.43 | 3.1 | 7.533
| veneer finished paneling 4 | SQMT | 1 | 1.26 | 3.1 | 3.906
22.8005
10.19.02 | Veneer finished wooden paneling BB | SQMT | 1 | 2.5 | 4.75 | 11.875 | lower portion rejected due to veneer become blackish | 0.5 | 2.5 | 4.75 | 5.9375
0
[6 empty] | 11.875 |  |  |  |  | 5.9375
10.19.03 | 'Solid wooden paneling for artist's work.. | SQMT | 5 | 1.25 | 0.4 | 2.5
10.23.01 | wooden beading
| live kichen | Rmt | 25 | 1.1 |  | 27.5 | below still | 23 | 1.1 | 25.3
|  | Rmt | 25 | 1.4 |  | 35 | above soffit | 23 | 1.4 | 32.2
62.5
57.5
10.23.02 | wooden beading
| OAK WOOD 25MM X12MM X 3550MM LANTH | RMT | 46 | 3.55 |  | 163.3 |  | 45 | 3.55 | 159.75
| OAK WOOD 25MM X12MM X 400MM LANTH | RMT | 137 | 0.71 |  | 97.27 |  | 140 | 0.71 | 99.4
| OAK WOOD 225MM X25MM X 500MM LANTH | NOS | 6 | 0.71 |  | 4.26 |  | 6 | 0.71 | 4.26
| OAK WOOD 200MM X25MM X 500MM LANTH | NOS | 12 | 0.71 |  | 8.52 |  | 12 | 0.71 | 8.52
| OAK WOOD 175MM X25MM X 500MM LANTH | NOS | 12 | 0.71 |  | 8.52 |  | 12 | 0.71 | 8.52
| OAK WOOD 150MM X25MM X 500MM LANTH | NOS | 12 | 0.71 |  | 8.52 |  | 12 | 0.71 | 8.52
| OAK WOOD 125MM X25MM X 500MM LANTH | NOS | 12 | 0.71 |  | 8.52 |  | 12 | 0.71 | 8.52
| OAK WOOD 100MM X25MM X 500MM LANTH | NOS | 12 | 0.71 |  | 8.52 |  | 12 | 0.71 | 8.52
| OAK WOOD 75MM X25MM X 500MM LANTH | NOS | 12 | 0.71 |  | 8.52 |  | 12 | 0.71 | 8.52
| OAK WOOD 50MM X25MM X 500MM LANTH | NOS | 12 | 0.71 |  | 8.52 |  | 12 | 0.71 | 8.52
| OAK WOOD 25MM X25MM X 500MM LANTH | NOS | 12 | 0.71 |  | 8.52 |  | 12 | 0.71 | 8.52
| OAK WOOD 25MM X12MM X 850MM LANTH | NOS | 50 | 0.71 |  | 35.5 |  | 38 | 0.71 | 26.98
[6 empty] | 368.49 |  |  |  | 358.55
10.23.03 | 'wooden beading with PU Polish finish
| glass | RMT | 2 | 4.75 |  | 9.5 | live kitchen glass
|  | RMT | 2 | 1.2 |  | 2.4
|  | RMT | 2 | 1.1 |  | 2.2
|  | RMT | 2 | 1.2 |  | 2.4
16.5
10.23.04 | 'wooden beading with PU Polish finish
|  | RMT | 2 | 4.75 |  | 9.5 | live kitchen glass outside
|  | RMT | 2 | 1.2 |  | 2.4
|  | RMT | 2 | 1.1 |  | 2.2
|  | RMT | 2 | 1.3 |  | 2.6
16.7
10.23.05 | ascia at Open Deck Units area. | RMT | 4 | 1.9 |  | 7.6 | 3+1 | chk
10.23.06 | Elevation BB at the top of the Open Deck Units area | RMT | 1 | 3.4 |  | 3.4
10.28.01 | BOX PANELNG OF 200MM THICK 19MM PLY WOOD FRAME | SQMT | 1 | 0.9 | 12.6 | 11.34 |  | 4 | 0.9 | 2.1 | 7.56
10.34.01 | Aluminium Frame + Wooden Wall Paneling AA | SQMT | 1 | 12.6 | 3.2 | 40.32
10.34.02 | Aluminium Frame + Wooden Wall Paneling BB |  | 1 | 4 | 5.4 | 21.6
| less glass |  | -1 | 1.2 | 5.4 | -6.48
15.12
10.34.03 | Aluminium Frame + Wooden Wall Paneling of 37mm thick.
| fasad RHS | SQMT | 1 | 2.3 | 7.5 | 17.25
| fasad LHS | SQMT | 1 | 1.1 | 7.5 | 8.25
| above opining entrance |  | 1 | 6.901 | 4.5 | 31.0545
56.5545
10.34.04 | Aluminium Frame + Wooden Round Column Paneling of 37mm thick. | SQMT | 1 | 4 | 4.1 | 16.4
10.34.05 | 'Aluminium Frame + Wooden Wall Paneling of 50mm thick with Cove Light Provision. | SQMT | 8 | 3.6 | 0.482 | 13.8816
10.34.06 | Aluminium Frame + Wooden Wall Paneling of 74mm thick. |  | 1 | 4.07 | 4.1 | 16.687
|  |  | -1 | 1.9 | 3 | -5.7
10.987
10.34.07 | Aluminium Frame + Wooden Top + Horizontal Wooden Shelve of 74mm thick | SQMT | 2 | 3.6 | 0.89 | 6.408 | odc soffit
10.34.08 | 'Aluminium Frame + Wooden Partition of 50mm thick | SQMT | 2 | 2.1 | 0.91 | 3.822 | to be clarify
10.34.09 | 'Aluminium Frame + Wooden Partition of 50mm thick. | SQMT | 2 | 2.1 | 0.91 | 3.822 | to be clarify
10.34.10 | 'Aluminium Frame + Wooden Bulkhead of 75mm thick | SQMT | 1 | 3.6 | 0.9 | 3.24 | to be clarify
10.58.01 | Subway tile cladding. 75mm x 275mm, Basic Cost | SQMT | 1 | 2.845 | 4 | 11.38
10.58.02 | Subway tile cladding over ply wood base. 75mm x 275mm
| subway AA 1 | SQMT | 1 | 2.13 | 3.1 | 6.603
| subway AA 2 | SQMT | 1 | 1.027 | 3.1 | 3.1837
| subway AA 3 | SQMT | 1 | 2.125 | 3.1 | 6.5875
16.3742
10.58.03 | Subway tile cladding over ply wood base. 75mm x 275mm | SQMT | 1 | 4.969 | 4 | 19.876
| less ope area | SQMT | -1 | 3.1 | 2.1 | -6.51
13.366
10.59.01 | 'Ceramics Mosaic Tile Cladding. | SQMT | 1 | 3 | 4 | 12 | round column | 1 | 2.74 | 4 | 10.96
10.64.02 | P&F of POP Punning(Specifications same as above, for Elevation AA. | SQMT | 1 | 3.7 | 4.1 | 15.17
10.64.02 | Specifications same as above, for Elevation BB. | SQMT | 3 | 1.2 | 2.1 | 7.56
10.64.03 | Specifications same as above, for Elevation CC. | SQMT | 1 | 5 | 4.1 | 20.5

## Counters & Others
FEBRUARY 2020
TRAVEL FOOD SERVICES
BOQ STANDARDISATION, IMPLEMENTATION AND COST CONSULTANCY |  |  |  |  | COUNTER & OTHERS BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU |  |  |  |  | M&A Bill
SR. NO. | SERVICE / MATERAL CODE | WBS | WBS Level2 | SHORT ITEM DESCRIPTION | PARTICULARS | UOM | Quantities | Rate | Amount | Qty | Amount
20 |  |  |  |  | COMPLETE COUNTER WORKS
20.1.01 |  | C & I | Flap door-Carpentry | Flap Door, Front Fascia with Veneer along with Corian finish. | P&F of Flap door in Curved Shape with 19mm thick plywood framing and 6mm flexible plywood cladding on it (bwr fire retardant bwr grade plywood - Archid / Kenwood make with pesticide treatment). Flap door's back of the surfaces and part of the front to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM) in 2 Hrs. fire rated PU polish. Top and rest part of the front fascia to be finished with 12mm thick Corian (ICE Queen W001 - DuPont make, basic rate INR. 10760.00/SM) with complete buffing / polish up to the mark. Includes 100mm ht. 1mm thick 304 grade SS (with selected and approved rose gold coating finished) skirting from inside. Rate including all necessary hardware fittings, heavy duty hinges, tower bolt, etc. Complete as per architectural detail drawing & site engineer's instruction. Size: 900mm L x 850mm H x 75mm thick. At the POS Area. | Nos. | 1 | 18500 | 18500 | 0.5 | 9250
20.1.02 |  | C & I | Foldable Shutter-Carpentry | Foldable Counter Top, Top & both Fascia with Corian finish. | P&F of Foldable Counter Top in Curved Shape with 19mm thick plywood (bwr fire retardant bwr grade plywood - Archid / Kenwood make with pesticide treatment). Foldable top and both fascia with 50mm edges to be finished with 12mm thick Corian (ICE Queen W001 - DuPont make, basic rate INR. 10760.00/SM) with complete buffing / polishing up to the mark. Bottom of the surface to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM) in 2 Hrs. fire rated PU polish. Rate including all necessary hardware fittings, heavy duty hinges, tower bolt, etc. Complete as per architectural detail drawing & site engineer's instruction. Size: 900mm L x 900mm D x 50mm thick. At the POS Area. | Nos. | 1 | 31500 | 31500 | 0.5 | 15750
20.1.03 |  | C & I | POS Counter-Carpentry | POS Counter Section with Corian Top & Fascia, fascia along with Veneer in PU Polish finish. | P&F of Curved Shape POS Counter with 19mm thick plywood structure & 12mm thick flexible plywood for front fascia (in two layers 12mm thick plywood to get the dual layer of the front fascia to make the necessary provision for the cove lighting and boxing for switch-socket installation) to get the curved shape and to make the dual layer of the front fascia (fire retardant plywood, Archid / Kenwood make with pesticide treatment). Counter's top and part of the fascia with internal edge of 50mm thick to be finished with 12mm thick Corian (ICE Queen W001 - DuPont make, basic rate INR. 10760.00/SM) with complete buffing / polish up to the mark. Counter's rest front fascia (the balance surfaces of Corian finish) other external surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Inside of the unit to be finished 1mm thick laminate (Formica / Heritage make, basic rate INR. 1325.00 / Sheet). Counter will be having five nos. of compartments. Three of the compartments will be having one no. of open space for cash machine provision, one no. of drawer with necessary draw compartment, one no. of open able shutter. And other four the compartments will be having one nos. of open able shutter with two nos. of wooden shelves (in 19mm thick plywood) on working side of the unit. Includes 100mm ht. 1mm thick 304 grade SS (with selected and approved rose gold coating finished) skirting from working side. Counter front fascia will having cove light provision as per details shown. Rate inclusive of all the necessary hardware fittings as required (like - heavy duty auto closing hinges, lock, grooves as handle, SS wire managers, etc. branded make) & necessary cut out for the services requirement. Complete as per architectural detail drawing & site engineer's instruction. Size: 5700mm Curved L (front fascia) x 900mm D x 900mm H x 1 no. | Sq. M. | 5.13 | 59180 | 303593.4 | 5.13 | 303593.4
20.1.04 |  | C & I | Dispenser Box-Carpentry | Dispenser Box with Corian finish. | P&F of Dispenser box with 12mm thick plywood structure (fire retardant plywood, Archid / Kenwood make with pesticide treatment), all surfaces of the dispenser box with 12mm thick Corian (ICE Queen W001 - DuPont make, basic rate INR. 10760.00/SM) with complete buffing / polish up to the mark, having provision of 100mm dia 4 nos. of SS containers, provisions for the mug container in said Corian finished. Rate including all necessary hardware fittings (branded make) & SS containers. Complete as per architectural detail drawing & site engineer's instruction. Size: 500mm L x 350mm H x 200mm D x 1 no. At the POS Area. | Nos. | 1 | 12500 | 12500 | 1 | 12500
20.1.05 |  | C & I | Back Counter-Carpentry | Back Counter with Corian Top & Fascia, front fascia with Veneer in PU Polish finish. | P&F of Back Working Counter with 19mm thick plywood structure & 12mm thick plywood back (fire retardant plywood, Archid / Kenwood make with pesticide treatment). Counter's top and edge of 50mm thick to be finished with 12mm thick Corian (ICE Queen W001 - DuPont make, basic rate INR. 10760.00/SM) with complete buffing / polish up to the mark. Counter front fascia external surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Inside of the unit to be finished 1mm thick laminate (Formica / Heritage make, basic rate INR. 1325.00 / Sheet). Counter will be having three nos of compartments. Counter's one of the compartments will be having one no. of open able shutter with two nos. wooden shelves (in 19mm thick plywood), the 2nd compartment will be having open space for kitchen equipment. Includes 100mm ht. 1mm thick 304 grade SS (with selected and approved rose gold coating finished) skirting from working side. Rate inclusive of all the necessary hardware fittings as required (like - heavy duty auto closing hinges, lock, handle, SS wire managers, etc. branded make) & necessary cut out for the services requirement. Complete as per architectural detail drawing & site engineer's instruction. Size: 2975mm L x 750mm D x 950mm H x 1 no. At the POS Area. | Sq. M. | 8.8506 | 43040 | 380930.9 | 3 | 129120
20.1.06 |  | C & I | Back Display Rack-Carpentry | Back Display with MS Framing in metal primer with Veneer in PU Polish finish. | P&F of Wooden Shelves with MS Framing in Veneer finish, with 12mm x 20mm x 1.35mm thick C-Class MS tube framing as the detailed drawings. MS framing to be treated with antirust red oxide metal primer with selected and approved fire rated. Outer surfaces of the framing to be cladded with 6mm thick plywood to get the even surfaces to finish with 4mm thick selected and approved make red oak veneer as per the detailed patterns (Basic rate INR. 1614.00/SM) in 2 Hrs. fire rated PU polish. Rate including ms welding works with necessary fire protection, all necessary hardware fittings to install the framing, including all necessary supports from the columns / walls / connecting supports, etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing & site engineer's instruction. Size: 3900mm L x 300mm W x 25mm thick x 2 nos. At the POS Area. | R.M. | 7.8 | 12912 | 100713.6 | 7.8 | 100713.6
20.1.07 |  | C & I | MS Framing-Carpentry | MS Framing in PU Paint for LED Screens Back. | P&F of MS Framing in PU Paint finish, with 25mm x 25mm x 2mm thick C-Class MS tube framing out of vertical members (two nos.) at 1920 mm c/c & with horizontal members (two nos.) at 440 mm c/c) as the detailed drawings. MS framing to be treated with antirust red oxide metal primer with selected and approved fire rated and to be finished with selected and approved PU Paint. Rate including ms welding works with necessary fire protection, all necessary hardware fittings to install the framing, including all necessary supports from the columns / walls / ceiling connecting supports, etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing & site engineer's instruction. Size: 1920mm L x 300mm W x 25mm thick x 1 no. At the POS Area. | Nos. | 1 | 15500 | 15500 |  | 0
20.1.08 |  | C & I | MS Framing-Carpentry | MS Framing in PU Paint to hold the Planter. | P&F of MS Framing in PU Paint finish, with 25mm x 25mm x 2mm thick C-Class MS tube framing out of vertical members (four nos.) at 200 mm c/c & with horizontal members (eight nos.) at top and bottom, with 25mm X 25mm x 2mm 'L' angel of 6 x nos to make the provision to install the wooden shelves as the detailed drawings. MS framing to be treated with antirust red oxide metal primer with selected and approved fire rated and to be finished with selected and approved PU Paint. Rate including ms welding works with necessary fire protection, all necessary hardware fittings to install the framing, including all necessary supports from the columns / walls / ceiling connecting supports, etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing & site engineer's instruction. Size: 7650mm L (in 'L' shape) x 200mm W x 200mm D x 12 nos. As per elevation AA, above banquet seating back. | R.M. | 91.8 | 405 | 37179 | 43.6248 | 17668.044 |  | CHK qty Certify 43.62 actual qty 91.8
20.1.09 |  | C & I | Wooden Shelves-Carpentry | Wooden Shelves Veneer in PU Polish finish. | P&F of Wooden Shelves, using 12mm thick plywood structure (fire retardant plywood, Archid / Kenwood make with pesticide treatment). Shelves top, bottom and edges of 50mm thick and 20mm thick to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Rate including ms welding works with necessary fire protection within the existing ms structure, all necessary hardware fittings to install the framing, including all necessary supports from the columns / walls / connecting supports, etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing & site engineer's instruction. Size: 2500mm L x 200mm W x 50mm thick x 6 nos. As per elevation AA, above banquet seating back. | R.M. | 15 | 3000 | 45000 | 15 | 45000
20.1.10 |  | C & I | Wooden Shelves-Carpentry | Wooden Shelves Veneer in PU Polish finish. | P&F of Wooden Shelves, using 12mm thick plywood structure (fire retardant plywood, Archid / Kenwood make with pesticide treatment). Shelves top, bottom and edges of 50mm thick and 20mm thick to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Rate including ms welding works with necessary fire protection within the existing ms structure, all necessary hardware fittings to install the framing, including all necessary supports from the columns / walls / connecting supports, etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing & site engineer's instruction. Size: 1425mm L x 200mm W x 50mm thick x 3 nos. As per elevation AA, above banquet seating back. | R.M. | 4.275 | 3000 | 12825 | 4.275 | 12825
20.1.11 |  | C & I | Wooden Shelves-Carpentry | Wooden Shelves Veneer in PU Polish finish. | P&F of Wooden Shelves, using 12mm thick plywood structure (fire retardant plywood, Archid / Kenwood make with pesticide treatment). Shelves top, bottom and edges of 50mm thick and 20mm thick to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Rate including ms welding works with necessary fire protection within the existing ms structure, all necessary hardware fittings to install the framing, including all necessary supports from the columns / walls / connecting supports, etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing & site engineer's instruction. Size: 200mm L x 200mm W x 50mm thick x 16 nos. As per elevation AA, above banquet seating back. | R.M. | 3.2 | 3500 | 11200 | 4.8 | 16800 | certify qty revised from 3.20 to 4.80
20.1.12 |  | C & I | Wooden Shelves-Carpentry | Wooden Shelves Veneer in PU Polish finish. | P&F of Wooden Shelves, using 12mm thick plywood structure (fire retardant plywood, Archid / Kenwood make with pesticide treatment). Shelves top, bottom and both edges of 50mm thick to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Rate including ms welding works with necessary fire protection within the existing ms structure, all necessary hardware fittings to install the framing, including all necessary supports from the columns / walls / connecting supports, etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing & site engineer's instruction. Size: 12600mm L x 275mm W x 50mm thick x 16 nos. As per elevation AA, above banquet seating back. | R.M. | 25.2 | 3000 | 75600 | 25.2 | 75600
20.1.13 |  | C & I | Wooden Shelves-Carpentry | Wooden Shelves Veneer in PU Polish finish. | P&F of Wooden Shelves, using 12mm thick plywood structure (fire retardant plywood, Archid / Kenwood make with pesticide treatment). Shelves top, bottom and edges of 50mm thick and 20mm thick to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Rate including ms welding works with necessary fire protection within the existing ms structure, all necessary hardware fittings to install the framing, including all necessary supports from the columns / walls / connecting supports, etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing & site engineer's instruction. Size: 5400mm L x 200mm W x 50mm thick x 1 no. As per elevation BB above the display glass area. | R.M. | 5.4 | 3000 | 16200 | 5.3 | 15900
20.1.14 |  | C & I | Counter-Carpentry | Condiment Counter with Corian Top & Edges, Front Fascia with Veneer in PU Polish finish. | P&F of Condiment Counter with 19mm thick plywood structure (fire retardant plywood, Archid / Kenwood make with pesticide treatment). Counter's top and edges of 38mm thick to be finished with 12mm thick Corian (ICE Queen W001 - DuPont make, basic rate INR. 10760.00/SM) with complete buffing / polish up to the mark. Counter will be having two nos. of compartments. Counter's all surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Inside of the unit to be finished 1mm thick laminate (Formica / Heritage make, basic rate INR. 1325.00 / Sheet). Counter will be having one no. of flap door (at the top of the counter with 300mm dia round ring of 25mm W x 25mm H in 3mm thick 304 grade matt finished SS sheet and flap door with same SS sheet. One of the compartments will be having one no. of open able shutter (in 19mm thick plywood and other part with two nos. of 25mm thick adjustable wooden shelves. Includes 150mm ht. 1mm thick 304 grade SS (with selected and approved rose gold coating finished) skirting for all the sides external surfaces. Rate inclusive of all the necessary hardware fittings as required (like - heavy duty auto closing hinges, lock, grooves as handle, SS wire managers, etc. branded make) & necessary cut out for the services requirement. Complete as per architectural detail drawing & site engineer's instruction. Size: 975mm L x 600mm D x 1050mm H x 1 no. At the entrance area. | Sq. M. | 1.0237 | 35000 | 35831.25 | 1.0237 | 35831.25
20.1.15 |  | C & I | Counter-Carpentry | Service Station with Veneer in PU Polish finish. | P&F of Service Station with 19mm thick plywood structure (fire retardant plywood, Archid / Kenwood make with pesticide treatment). Counter's all surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Inside of the unit to be finished 1mm thick laminate (Formica / Heritage make, basic rate INR. 1325.00 / Sheet). Counter will be having two nos. of open able shutter (in 19mm thick plywood with one nos. of 25mm thick adjustable wooden shelves and 150mm flush band as shown details. Includes 150mm ht. 1mm thick 304 grade SS (with selected and approved rose gold coating finished) skirting for all the sides external surfaces. Rate inclusive of all the necessary hardware fittings as required (like - heavy duty auto closing hinges, lock, grooves as handle, SS wire managers, etc. branded make) & necessary cut out for the services requirement. Complete as per architectural detail drawing & site engineer's instruction. Size: 1025mm L x 600mm D x 900mm H x 1 no. As per elevation AA, in-between the two banquet seating. | Sq. M. | 0.8775 | 35000 | 30712.5 | 0.882 | 30870
20.1.16 |  | C & I | Counter-Carpentry | Banquet Seating with Veneer in PU Polish finish. | P&F of Banquet Seating, having 600mm width x 350mm ht. slanted boxing with 19mm thick plywood framing and 19mm thick of the boxing (selected & approved make, fire-retardant bwr grade) for seating, having 75mm to 125mm thick. slanted back of 900mm ht with 19mm thick plywood framing & upholstery work (selected & approved density foam, fatherlite make) finished with selected & approved make fabrics / leatherette (basic cost INR. 1800.00 /Mtr. for both slanted back and seat). Banquet's all front surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish. Includes 150mm ht. 1mm thick 304 grade SS (with selected and approved rose gold coating finished) skirting for all the sides external surfaces. Rate including all necessary hardware fittings. Complete as per architectural detail drawing. Size: (5775+5800)mm L x 600mm W x 900mm height. | R. M. | 11.575 | 14580 | 168763.5 | 7.75 | 112995
20.1.17 |  | C & I | Carpentry | SS Foot Rail | P&F of 25mm dia 2mm thick 304 grade Round SS Foot Rail of 100mm Ht. with 20mm dia stands (matt hairline finish) at Counter's front fascia. The stand to be fixed on the existing flooring with necessary anchor / bolting / screwing system. Rate including all necessary hardware fittings. Complete as per architectural detail drawing & site engineer's instruction. Size: 5700mm Curved L x 100mm H. At the POS Counter. | R. M. | 5.7 | 3402 | 19391.4
[5 empty] | TOTAL OF COUNTER WORK |  |  |  | 1315940.55 |  | 934416.294
Materials Specification: Materials should be as per specified in BOQ & details drawings.
1 | 19mm thick fire retardant (two hour Fire-Retardant) plywood's basic rate consider for 1614.00 / SM, Anchor / Kutty / Century / Green ply - Make
2 | Rest plywood's should as per item no. 1.
3 | All adhesives should be Pidilite brand.
4 | All hardware's fittings should be as mentioned on BOQ / Equivalent to the mentioned brand.
5 | All glasses and mirror should be branded, like - Saint gobain / BIAL approved.
6 | Aluminium tube - 16 gauge, Jindal / equivalent make.
7 | All hardware fittings should be as per mentioned on BOQ / Equivalent / Branded.
8 | 1st quality old btc wood / selected & approved seasoned red oak wood for all wooden work.
9 | Fire-Retardant pu polish as per BIAL Standard Guideline up to 2 hours fire-rated.
10 | MS / SS works with Jindal / Tata make.
11 | SS works with standard grade product and selected and approved high quality 304 grade ss sheet.
12 | All metal works to be carried out as per the BIAL guideline.
13 | Contractor team ahs to study the BIAL Guideline for further queries if any.
14 | All the Workshop Drawings to be prepared by the contracting team, construction can start upon mutual approval.
15 | All the materials has to up to BIAL's Standard as per their Guideline.

## MB counter
MB Sheet CIVIL MASONRY BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU
SR.NO | Item Description | Unit | No | Length | Breadth | Total Quantity
A | General Site Works
20.1.01 | Flap Door, Front Fascia with Veneer along with Corian finish | NO | 1 |  |  | 1 | 0.5
0
20.1.02 | Foldable Shutter-Carpentry | NO | 1 |  |  | 1 | 0.5
0
20.1.03 | POS Counter Section with Corian Top & Fascia, fascia along with Veneer in PU Polish finish. | SQMT | 1 | 5.7 | 0.9 | 5.13 | cove not done properly
20.1.04 | Dispenser Box with Corian finish. | NO | 1 |  |  | 1
20.1.05 | Back Counter-Carpentry | SQMT | 1 | 3 | 1 | 3
20.1.06 | Back Display Rack-Carpentry | RMT | 2 | 3.9 |  | 7.8 |  |  |  | certify
20.1.08 | MS Framing in PU Paint to hold the Planter. | RMT | 12 | 7.65 |  | 91.8 |  | 12 | 3.6354 | 43.6248
20.1.09 | Wooden Shelves-Carpentry ELEVATION AA | RMT | 6 | 2.5 |  | 15
20.1.10 | Wooden Shelves-Carpentry ELEVATION AA | RMT | 3 | 1.425 |  | 4.275
20.1.11 | Wooden Shelves-Carpentry ELEVATION AA SMALL | RMT | 16 | 0.2 |  | 3.2 |  | 24 | 0.2 | 4.8
20.1.12 | Wooden Shelves-Carpentry ELEVATION AA TOP | RMT | 2 | 12.6 |  | 25.2
20.1.13 | Wooden Shelves-Carpentry ELEVATION BB | RMT | 1 | 5.3 |  | 5.3
20.1.14 | Condiment Counter with Corian Top & Edges, Front Fascia with Veneer in PU Polish finish. | SQMT | 1 | 0.975 | 1.05 | 1.0237
20.1.15 | Service Station with Veneer in PU Polish finish. | SQMT | 1 | 0.98 | 0.9 | 0.882
20.1.16 | Banquet Seating with Veneer in PU Polish finish. | RMT | 2 | 7.75 |  | 15.5
7.75

## I. Ceiling
FEBRUARY 2020
TRAVEL FOOD SERVICES
BOQ STANDARDISATION, IMPLEMENTATION AND COST CONSULTANCY | [5 empty] | CEILING FINISHING BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU
M&A Bill
SR. NO. | SERVICE / MATERAL CODE | WBS | WBS Level1 | WBS Level2 | SHORT ITEM DESCRIPTION | PARTICULARS | UOM | QTY. | Basic Rate of Material | Amount | Qty | Amount |  | remark
GENERAL NOTES
a | [5 empty] | Please refer to "Exhibit A - Basic rate of material" for the applicable base rates of materials
c | [5 empty] | Items of works shall to be read in conjunction with Drawings, Specifications, Contractual terms and conditions and Trade Preambles to this BOQ as included in the RFP.
d | [5 empty] | The quantities mentioned in the BOQ is tentative and may increase or decrease. Payment shall be restricted to the quantum of work executed and measured as per the defined mode of measurement.
e | [5 empty] | The Mode of Measurement (in order of priority) is as follows:
(I) As defined in relevant item in the BOQ
(ii) As defined in the specification
(iii) As defined in IS-1200 (latest version) for relevant trade.
(iv) if mode is not defined in (I), (ii) and (iii), the standard industry practice shall be adopted.
Items of work and trade preambles are essential parts of the bill of quantities and are to be taken as mutually explanatory of one another. Requirement occurring in one is binding as though occurring in both. In resolving conflicts, discrepancies, errors or omissions as regards trade preambles & bill of quantities the following order of precedence shall be used but subject to PRIORITY OF DOCUMENTS as included in General Conditions of Contract: a. General Notes as included in this bill of quantities. b. Trade Preambles as included in RFP. c. Item Description as included in this bill of quantities.
11 | [5 empty] | FALSE CEILING WORK
11.1 |  | C & I | Ceiling | False Ceiling | 12mm thick Gypsum False Ceiling-FOH Area | Providing and fixing 12mm thick Gypsum False Ceiling manufactured by India Gypsum or equivalent approved on G.I. frame work, in G.I. vertical supports at every 450mm c/c and horizontal runners at every 900mm c/c in brass screws to proper line and level. G.I. metal frame to be of 22 gauge folded strip of 50mm width to be used. All complete as per PM's instructions and specifications. The grid of frame work to be supported at every 1500mmx1500mm interval by MS rod anchored to the slab to support the G.I. framework. All vertical G.I. framework to be anchored to the slab by means of anchor fasteners including cornices and making holes/cutting and fixing with required framing for electrical fixtures, A.C. grills etc. Area of electrical fixtures will be paid full with ply on top of ceiling fixed to G.I. supports to receive spotlights etc. all other related works, at all levels and locations. Rate to include finishing with two or more coats of lustre paint in approved shade, colour and make. | Sq. m | 110 | 1345 | 147950 | 102.6234 | 138028.4407
11..1.a |  | C & I | Ceiling | False Ceiling | 12mm thick Ply wood backing for the Gypsum False Ceiling-FOH Area | Providing & Fixing of 12mm thick ply wood on the existing GI framing, before installation the 12mm thicj Gypsum board. | Sq. m | 110 | 1650 | 181500 | 102.6234 | 169328.5704
11.1.1 |  | C & I | Ceiling | False Ceiling | Toilets | -Do- as per Item No. 10.1 above but False ceiling with Moisture Resistance gypsum boards for Toilets. | Sq. m
11.2 |  | C & I | Ceiling | Access doors | Trap door/access doors (assumed 600mm x 600mm size) | Providing and creating trap door/access doors (assumed 600mm x 600mm size) made out of 12mm MDF board finished with approved Veneer and melamine polished, in Gypsum false ceiling including cutting to required size, recycled wood beading, creating grooves, required double legged scaffolding/staging etc. all complete as per reflected ceiling plan, at all levels and locations,and to the entire satisfaction of the PM/Architect. | Sq m
11.2.a |  | C & I | Ceiling | Access doors | Trap door/access doors (assumed 1600mm x 990mm size) | Providing and creating trap door/access doors (assumed 1600mm x 990mm size), Aluminium section of 2"x1" framework (out of vertical members at 425 mm c/c & with horizontal members at 52 mm c/c) for shutter framing in 16 SWG with cleats of 18 mm x 18mm, 12 SWG aluminium angle to be used for assembling paneling framework,6 mm thk FR plywood fixed to framework with flat head, full thread, sheet metal screws on both the surfaces with another layer of 4mm thick plywood finish to the bottom surface to get the even surfaces and edges for selected acrylic paint finish in Gypsum false ceiling including cutting to required size, recycled wood beading, creating grooves, required double legged scaffolding/staging etc. all complete as per reflected ceiling plan, at all levels and locations, and to the entire satisfaction of the PM/Architect. Bottom surfaces in selected acrylic paint finish and internal surfaces to be finished in selected and approved 1mm thick laminate finish. With all standard amd branded hardware fittings. Size: 1600mm L x 990mm W x 2 nos. | Sq m | 3.168 | 3766 | 11930.688 | 1.44 | 5423.04
11.3 |  | C & I | Ceiling | Bevelled Regular edge Ceiling | Mineral Fibre board tile with Bevelled Regular edge Ceiling. | Grid System - Silhouette Tile thickness - 15mm Edge detail - Regular edge Humidity resistance - 95% NRC -1 Light reflectance - 85% Fire performance - Class 0/Class 1 (BS 476) Sound Attenuation - 35 DB Lay-in Tile: 600 mm x 300 x 15 mm Mineral Fibreboard tile with Bevelled Regular edge Ceiling Suspension System Proprietary supplied ceiling suspension system to consist of 2mm or 3mm GI suspension rod/wire with adjustable butterfly clip securely affixed to structural ceiling using soffit angle fixing bracket and 10mm dia hook type anchor fastener.Ceiling suspension system to be fixed at interval (grid) of 1200mm in both directions. Grid System: Supply of proprietary silhouette System to consist of Main Runners @ 600mm and joined by Cross Tees @ 600mm to form overall grid opening of 600mm x 300mm. Additional cross tees are to be placed where appropriate for light fixtures, AC diffusers. The grid system used shall be hot dipped galvanized steel sections,with exposed surfaces chemically cleaned and capped prefinished in baked polyester paint Ceiling shall be laid with " L " angle as per drawing and as directed by Engineer-in-charge. | Sq m |  |  | 0 |  | 0
11.4 |  | C & I | Ceiling | Metal Ceiling | Micro Perforation Metal Ceiling of white colour with Black acoustic fleece. | Providing and fixing random Micro Perforation Metal Ceiling of white colour with Black acoustic fleece above with following specifications- Supply Laying micro perforated Tiles with 15mm Grid: Supply of GI 1800mmx600mmx0.5mm ceiling white tiles (random) perforated to 20mm dia holes with 15mm grid suspension system as per manufacturer's specifications. L shape Wall trim 19x19mm & T Grid 15mm(W)x38mm(H) included. Make- Armstrong/Fame line or equivalent. | Sq.m | 32.5 | 1775 | 57687.5 | 25.56 | 45369
11.5 |  | C & I | Ceiling | Baffle Ceiling | Linear Metal Baffle Ceiling (Wooden finished) with Black fleece | Linear Metal Baffle Ceiling (Wooden finished) with Black fleece above Supply & Installation of Vertical Linear Metal Baffle/Rafter ceiling system consist of pre painted (approved shade of powder coating) metal folded sections of specified size 25mm x 100mm or as per drawing with a centre to centre spacing of 125mm with complete standard suspension system and necessary supports as per manufacturer's specifications. The baffle units are then attached to L- channel carriers spaced at 1200mm c.c. and suspended with M6 threaded rod hangers spaced 1200mm c.c. Multiple lengths of baffles shall be connected using splice plates and ends covered with end caps as per manufacturers specification with GI lay in panels to be perforated with L15 pattern- 2.5 die hole and 16% opening having acoustic tissue laminated at the back as per approval of the architect & detail drawings complete in all respect. Note-The Baffle details to be co-ordinated and consulted with lighting consultant. Wood Grain Finish-Design as specified in drawing and in line with Architect approved Laminate Make- Armstrong or Fame line or equivalent. | Sq.m
11.5.1 |  | C & I | Ceiling | Baffle Ceiling | Linear Wooden Baffle Ceiling - in PU Polish finish. | Linear Wooden Baffle Ceiling (Birch Plywood of 25mm thick in fire rated PU Polish), with supply & installation of Vertical Linear Wooden Baffle/Rafter ceiling system consist of approved shade of 25mm thick birch plywood sections of specified size 25mm thick x 200mm to 300mm height or as per drawing with a centre to centre spacing of 200mm with complete standard suspension system and necessary supports as per manufacturer's specifications / site condition. The baffle units are then attached to L- channel carriers spaced at 1200mm c.c. and suspended with M6 threaded rod hangers spaced 1200mm c.c. and to installed on the existing plywood backing gypbard ceiling as per approval of the architect & detail drawings complete in all respect. Note-The Baffle details to be coordinated and consulted with lighting consultant. Wood Grain Finish-Design as specified in drawing and in line with Architect approved. This item is for the POS Counter area and next the proposed AHU Unit. | Sq.m | 15.8 | 5000 | 79000 | 8.7 | 43500 | certify | rate will be change
11.5.2 |  | C & I | Ceiling | Baffle Ceiling | Linear Wooden Baffle Ceiling - in PU Polish finish. | Linear Wooden Baffle Ceiling (Birch Plywood of 25mm thick in fire rated PU Polish), with supply & installation of Vertical Linear Wooden Baffle/Rafter ceiling system consist of approved shade of 25mm thick birch plywood sections of specified size 25mm thick x 200mm to 300mm height or as per drawing with a centre to centre spacing of starting point from 175mm to end point 800mm with complete standard suspension system and necessary supports as per manufacturer's specifications / site condition. The baffle units are then attached to L- channel carriers spaced at 1200mm c.c. and suspended with M6 threaded rod hangers spaced 1200mm c.c. and to installed on the existing plywood backing gypbard ceiling as per approval of the architect & detail drawings complete in all respect. Note-The Baffle details to be coordinated and consulted with lighting consultant. Wood Grain Finish-Design as specified in drawing and in line with Architect approved. This item is for the FOH area. | Sq.m | 54 | 5000 | 270000 | 32.7498 | 163749 | certify | rate will be change
11.6 |  | C & I | Ceiling | Ceiling Panel | Mineral fibre | K-13 Standard Grade, sound absorbing cellulose-base plaster, organic in nature, free of asbestos, fiberglass, or manmade mineral fibres and treated with fire resistant chemicals, sprayed with high pressure equipment to the substrate in white color, construction material Class B1 according to DIN 4102, to be sprayed at 30mm thickness, including protection cover for surfaces that are not to be sprayed.Clips,hangers,supports,sleeves and other attachments to substrate shall be fixed by other agencies prior to spray plaster activity whereas ducts, piping and other suspended equipment shall be placed / fixed after the spray activity. All materials shall be supplied in unopened containers bearing the name of manufacturer, product identification and reference to UL testing. The manufacturer or the applicator shall provide photocopies of material compliance with ASTM E-84 / U. L.723, tested at a minimum of 5” the Class I, Class A, Flame Spread: 5, Smoke Development: 5, ASTM E- 1042, Non corrosive per UMB- 80, Bond Deflection per ASTM E-759: 6” deflection in 10’ span – no spalling or delamination, Weight Per Sumter less than 1.7Kg/star. The plaster shall be cured with natural ventilation. The applicator / manufacturer shall provide with test data that the acoustical plaster gives absorption coefficient NRC 0.95 at 35mm the and meet the individual absorption coefficient at 125hz=0.26, at 250hz=0.62, at 500hz=1.02, at 1khz=1.07, at 2khz=0.96 at complete octave band. Erected Scaffolding, power and water to be supplied free of cost. Note: Cost to include satin finish enamel spray paint for all exposed MEP services in open ceiling areas as per approved design. Only plan area to be measured. Nothing additional will be paid for this item. | Sq. m
11.8 |  | C & I | Ceiling | False Ceiling | Classic lite micro look M15 false ceiling | Providing and fixing of CL-1 Exposed Tee Grid T-Bar Modular Ceiling 600x600mm.Armstrong ultima vector with peak form prelude 15/16" lnstaIlation shall be as per Manufacturers specifications (Armstrong).Comprises of 16 mm thick Texture of tile-Classicalite,edge of tile Micro look, framing With superfine M15 midrange Armstrong main and cross tee T-32*15*1.5mm (height * flange width of TEE *Thickness) galvanised section, exposed tee will be powder coated and with ARMSTRONG make suspension system i.e. anchor fastener, vertical hanger, hook clip etc.as described. To be laid at all heights cut to all shapes and sizes and in the required grid pattern with necessary support from the civil ceiling as per architects design, details and specifications. Including necessary light points/AC grills and other opening cuttings in the ceiling tiles with all necessary scaffolding labour and other materials complete. The work shall include wastages, labour, all lead and lifts at all levels. Loading and unloading, transportation and other incidental charges etc. Complete as directed by the Engineer-in-charge. | Sq. m
11.9 |  | C & I | Ceiling | Light Fitting | Support the light fittings, Mineral fibre false ceiling | Providing and fixing 6mm commercial plywood of where ever required to support the light fittings on the mineral fibre grid ceiling tiles, the size of the ply backing sheet shall be 600 x 600 mm. without any wooden supports including proper cutting to shape as a supporting member etc. complete as directed by EIC. | NOS
11.1 |  | C & I | Ceiling | False Ceiling | Gypsum false ceiling with cove & niche ultra from work. | Providing and fixing 12mm thick gypsum including cost of making niches & coves unto 200 mm wide and depth unto 200 mm or less and 100mm wide projected shelf with side Patti unto 75 mm and such other geometric elements based on rectangular geometry. As per position shown in Plans, sections and elevations of the ceiling drawings. The total side wall of these element shall not exceed 15% of the flat ceiling area. The entire ceiling shall be hung, mounted and stiffened with cross members with GI angle section fixed to the RC slab.Gypsteel sections and frame work (Ultra Make) shall be properly tied or as per manufacture specification for necessary load. and shall be made free of any deflection distortion or swinging sway or movement,The work includes cost of all materials,labour for cutting,fixing,levelling and making the ceiling elements aligned, level and straight,grinding and removing the blemishes,cutting of ceiling for installation of light fixtures,A/C grills,diffusers etc.as required and making good the same.making good any defects with POP and completing all works to the full satisfaction of the EIC in line with the plans elevations and sections.Drawing shall be provided to Contractor for quoting the rate.Rate to include cost of paper tape on joints of Gypsum Sheets.(India Gypsum or approved equivalent) including sanding, making even and finished ready to receive paint. Method of Measurement: The flat ceiling area as seen on plan shall be measured excluding undulations due to niches, troughs and design elements. He increase due to cove niches etc. is incremented in the rate by agreed percentage. | Sq. m
11.11 |  | C & I | Ceiling | Suspended Pipe | Suspended 20X20 mm square SS hollow pipe. | Providing and fixing suspended 20X20 mm SS hollow pipe fixed from true ceiling with 6mm the MS plate. Pipe to be brought down by 75mm from proposed false ceiling level to fix the led signage by VM team on SS hollow square pipe frame. Electrical cables shall be run through the hollow pipes for led signage. Rates shall including all screws and other necessary hardware etc. complete as per drawing and as directed by Engineer-in-charge. | M
11.12 |  | C & I | Ceiling | Pergola | Pergola ceiling | Providing and fixing Pergola ceiling of required pattern made of ply boxing finished with laminate as per drawing with two or more coats of lustre paint in approved shade, colour etc. complete as directed by Engineer-in-charge.. | Sq. m
11.13 |  | C & I | Ceiling | Wooden | wooden ceiling | Providing and fixing wooden ceiling made of ply with required framework & finished in laminate as per drawing with two or more coats of lustre paint in approved shade, colour etc. complete as directed by Engineer-in-charge.. | Sq. m
11.14 |  | C & I | Ceiling | Wooden | wooden pelmet | Providing and fixing pelmet made of wood and finished with wall paper, SS strip provided at the bottom edge of the pelmet as per drawing, etc. complete, as directed by Engineer-in-charge.. | Sq m
11.15 |  | C & I | Ceiling | Pergola | Pergola ceiling | Providing and fixing Pergola ceiling of required pattern made of SS rods ply boxing finished with laminate as per drawing with two or more coats of lustre paint in approved shade, colour etc. complete as directed by Engineer-in-charge.. | Sq. m
11.16 |  | C & I | Ceiling | Terracotta | Terracotta ceiling | Providing and fixing colour coated Terracotta ceiling with thickness _____ (6 to 15) mm as per drawing, etc. complete, as directed by EIC. | Sq. m
11.17 |  | C & I | Ceiling | Ceiling panel | Glass purlins | Providing and fixing Glass Ceiling with purlins used In single spans and continuous spans as per drawing. | Sq m
11.18 |  | C & I | Ceiling Finishing | Ceiling Finishing | cove ceiling finished with wood and fabric | Provide & fixing cove ceiling finished with wood & fabric with complete standard system and necessary supports as per manufacturer's specifications & complete as directed by Engineer-in-charge.. | Sq m
11.19 |  | C & I | Ceiling | Ceiling panel | fabric panel | Providing and fixing fabric panel of required thickness made of Wooden frame work and 19 mm plywood on both sides to form a double sided wooden partition of 200 mm thick . Ply surface shall be finished on both sides with fabric panel and SS Strip in-between the panels . | Sq m
11.2 |  | C & I | Ceiling Finishing | Ceiling Finishing | Laminated ceiling with Stretch fabric as per design & pattern. | Providing and fixing Laminate ceiling with Stretch fabric as per design and pattern as per drawing, etc. complete as directed by Engineer-in-charge.. | Sq m
11.21 |  | C & I | Ceiling Finishing | Hanging Threads | Hanging Threads as per pattern over the Gypsum ceiling | Providing and fixing Hanging Threads as per pattern over the Gypsum ceiling as per drawing & etc. complete as directed by Engineer-in-charge.. | Sq m
11.22 |  | C & I | Ceiling | Ceiling panel | Bison board panelling | Providing and fixing in position 12 mm thick Bison board panelling, with framework fabricated from, 50x35 hardwood 600 C/C, both ways, fixed to wall/ ceiling necessary supporting frame work, Supports, hardware.Consurnables as directed by EIC | Sq m
[6 empty] | TOTAL OF FALSE CEILING WORK |  |  |  | 748068.188 |  | 565398.0511
Materials Specification: Materials should be as per specified in BOQ & details drawings.
1 | 19mm thick fire retardant (two hour Fire-Retardant) plywood's basic rate consider for 1614.00 / SM, Anchor / Kutty / Century / Green ply - Make
2 | Rest plywood's should as per item no. 1.
3 | Laminate basic cost INR 1325.00/Sheet.
4 | Laminate basic cost INR 1325.00/Sheet.
5 | All adhesives should be Pidilite brand.
6 | All hardware's fittings should be as mentioned on BOQ / Equivalent to the mentioned brand.
7 | All glasses and mirror should be branded, like - Saint gobain / BIAL approved.
8 | Aluminium tube - 16 gauge, Jindal / equivalent make.
9 | All hardware fittings should be as per mentioned on BOQ / Equivalent / Branded.
10 | 1st quality old btc wood / selected & approved seasoned american red oak / american ash wood for all wooden work.
11 | Fire-Retardant pu polish as per BIAL Standard Guideline up to 2 hours fire-rated.
12 | MS / SS works with Jindal / Tata make.
13 | SS works with standard grade product and selected and approved high quality 304 grade ss sheet.
14 | All metal works to be carried out as per the BIAL guideline.
15 | Contractor team ahs to study the BIAL Guideline for further queries if any.
16 | All the Workshop Drawings to be prepared by the contracting team, construction can start upon mutual approval.
17 | All the materials has to up to BIAL's Standard as per their Guideline.
18 | All POP and False Ceiling materials should be Gypsteel India / Equivalent make as per the BIAL approved list
19 | Rate are inclusive of required scaffolding at site for the respective Interiors Works.
20 | All basic price may vary at the time final closer of this BOQ with assigned agency / agencies.
21 | Rate are inclusive of required scaffolding at site for the respective Interiors Works.
22 | All the materials has to up to BIAL's Standard as per their Guideline.
23 | Contractor team ahs to study the BIAL Guideline for further queries if any.
[6 empty] | Providing & Fixing of MS frame work size 2"x 2" thickness 5 mm for hanging false ceiling as per drawing. | Kg | 1200 | 250 | 300000
[5 empty] | 1 | Providing and erecting scaffolding / centering upto 5m in height with all fixtures, fastenings, etc. complete, as directed by Engineer-In-Charge. | Per Month | 1 | 15000 | 15000 |  | 7 oct mail
[5 empty] | 2 | Providing of Safety officer as per PMC & BIAL | Per Month | 1 | 34500 | 34500 |  | 7 oct mail
[5 empty] | 3 | Loss of labour due to entrance main gate to our site & vice versa approx distance 500 mtr. | Ls | 1 | 150000 | 150000 |  | 7 oct mail
[5 empty] | 4 | Providing of Housekeeping person | Per Month | 1 | 25000 | 25000 |  | 7 oct mail
[5 empty] | 5 | SITC of CO2 Type Fire Extinguisher 4.5 kgs. | Nos | 1 | 6500 | 6500 |  | 7 oct mail
[5 empty] | Marble stone Dado. | Laying 19mm thick machine cut, machine polished Terrazzo Marble stone Dado of approved quality, colour, shade and pattern, laid in pattern and sizes as shown in drawing. Joints to be well cleaned and grouted with matching colour approved quality polymer based readymade grout, curing, machine polishing, cleaning, protecting till handing over etc. to required line, level, etc., at all levels and locations, complete to the entire satisfaction of the PM. Back Wall of the POS Section. | Sq m | 19mm thick Terrazzo Marble stone Dado. Basic cost INR.4035.00 |  | As per sample passed for 19 mm thk Terrazzo Marble Stone Dado. BASIC COST IS RS.5219 |  | 7 oct mail

## MB j door
MB Sheet CIVIL MASONRY BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU
SR.NO | Item Description | Unit | No | Length | Breadth | Total Quantity
A | General Site Works
12.2.5 | 50mm thick solid core flush shutter
kitchen
| less column | NO | 1 |  |  | 1
12.16.1 | Entrance single leaf glass door 12mm thick Glass, with wooden doorframe. | NO | 1 |  |  | 1

## MB ceiling
MB Sheet CIVIL MASONRY BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU
SR.NO | Item Description | Unit | No | Length | Breadth | Total Quantity
A | General Site Works
11.1 | 12mm thick Gypsum False Ceiling-FOH Area
| sofa side live kichan cold and hot wall ellevayin bb | SQMT | 1 | 9.886 | 8.664 | 85.6523
| less column | SQMT | -1 | 2.048 | 1.186 | -2.4289
| less hot boxing | SQMT | -1 | 0.9 | 4 | -3.6
| sofa side live kichan wall elevation bb | SQMT | 1 | 4.6 | 5 | 23
102.6234
11..1.a | 12mm thick Ply wood backing for the Gypsum False Ceiling-FOH Area
| sofa side live kichan cold and hot wall ellevayin bb | SQMT | 1 | 9.886 | 8.664 | 85.6523
| less column | SQMT | -1 | 2.048 | 1.186 | -2.4289
| less hot boxing | SQMT | -1 | 0.9 | 4 | -3.6
| sofa side live kichan wall elevation bb | SQMT | 1 | 4.6 | 5 | 23
102.6234
11.2.a | Trap door/access doors (assumed 1600mm x 990mm size) | SQMT | 1 | 1.2 | 1.2 | 1.44
11.4 | Micro Perforation Metal Ceiling of white colour with Black acoustic fleece.
| live kichan area | SQMT | 1 | 4.8 | 2.78 | 13.344
| less hod | SQMT | -1 | 3.3 | 1.2 | -3.96
| kichan area | SQMT | 1 | 7.86 | 2.4 | 18.864
| less hod | SQMT | -2 | 1.12 | 1.2 | -2.688
25.56
certify
11.5.1 | Linear Wooden Baffle Ceiling - in PU Polish finish.
| AHU side | SQMT | 15 | 0.3 | 2.9 | 13.05 | 15 | 0.2 | 2.9 | 8.7
| main area | [8 empty] | 0
11.5.2 | 1 colum | SQMT | 1 | 0.2 | 0.73 | 0.146 | 1 | 0.2 | 0.73 | 0.146
| 1 sofa side | SQMT | 1 | 0.2 | 1.33 | 0.266 | 1 | 0.2 | 1.33 | 0.266
| 1 center | SQMT | 1 | 0.3 | 8.7 | 2.61 | 1 | 0.3 | 0.87 | 0.261
|  | SQMT | 1 | 0.2 | 1.873 | 0.3746 | 1 | 0.2 | 1.873 | 0.3746
|  | SQMT | 1 | 0.2 | 1.091 | 0.2182 | 1 | 0.2 | 1.091 | 0.2182
|  | SQMT | 1 | 0.3 | 0.933 | 0.2799 | 1 | 0.3 | 0.933 | 0.2799
|  | SQMT | 1 | 0.2 | 2.119 | 0.4238 | 1 | 0.2 | 2.119 | 0.4238
|  | SQMT | 1 | 0.2 | 0.92 | 0.184 | 1 | 0.2 | 0.92 | 0.184
|  | SQMT | 1 | 0.3 | 1.01 | 0.303 | 1 | 0.3 | 1.01 | 0.303
|  | SQMT | 1 | 0.2 | 2.359 | 0.4718 | 1 | 0.2 | 2.359 | 0.4718
|  | SQMT | 1 | 0.2 | 0.81 | 0.162 | 1 | 0.2 | 0.81 | 0.162
|  | SQMT | 1 | 0.3 | 1.089 | 0.3267 | 1 | 0.3 | 1.089 | 0.3267
|  | SQMT | 1 | 0.2 | 2.585 | 0.517 | 1 | 0.2 | 2.585 | 0.517
|  | SQMT | 1 | 0.2 | 0.774 | 0.1548 | 1 | 0.2 | 0.774 | 0.1548
|  | SQMT | 1 | 0.3 | 1.164 | 0.3492 | 1 | 0.3 | 1.164 | 0.3492
|  | SQMT | 1 | 0.2 | 2.796 | 0.5592 | 1 | 0.2 | 2.796 | 0.5592
|  | SQMT | 1 | 0.2 | 0.85 | 0.17 | 1 | 0.2 | 0.85 | 0.17
|  | SQMT | 1 | 0.3 | 1.246 | 0.3738 | 1 | 0.3 | 1.246 | 0.3738
|  | SQMT | 1 | 0.2 | 2.987 | 0.5974 | 1 | 0.2 | 2.987 | 0.5974
|  | SQMT | 1 | 0.2 | 1.52 | 0.304 | 1 | 0.2 | 1.52 | 0.304
|  | SQMT | 1 | 0.3 | 1.329 | 0.3987 | 1 | 0.3 | 1.329 | 0.3987
|  | SQMT | 1 | 0.2 | 3.154 | 0.6308 | 1 | 0.2 | 3.154 | 0.6308
|  | SQMT | 1 | 0.2 | 1.427 | 0.2854 | 1 | 0.2 | 1.427 | 0.2854
|  | SQMT | 1 | 0.3 | 1.411 | 0.4233 | 1 | 0.3 | 1.411 | 0.4233
|  | SQMT | 1 | 0.2 | 3.296 | 0.6592 | 1 | 0.2 | 3.296 | 0.6592
|  | SQMT | 1 | 0.2 | 2.027 | 0.4054 | 1 | 0.2 | 2.027 | 0.4054
|  | SQMT | 1 | 0.3 | 1.491 | 0.4473 | 1 | 0.3 | 1.491 | 0.4473
|  | SQMT | 1 | 0.2 | 2.41 | 0.482 | 1 | 0.2 | 2.41 | 0.482
|  | SQMT | 1 | 0.2 | 3 | 0.6 | 1 | 0.2 | 3 | 0.6
|  | SQMT | 1 | 0.3 | 1.567 | 0.4701 | 1 | 0.3 | 1.567 | 0.4701
|  | SQMT | 1 | 0.2 | 3.5 | 0.7 | 1 | 0.2 | 3.5 | 0.7
|  | SQMT | 1 | 0.2 | 2.4 | 0.48 | 1 | 0.2 | 2.4 | 0.48
|  | SQMT | 1 | 0.3 | 1.738 | 0.5214 | 1 | 0.3 | 1.738 | 0.5214
|  | SQMT | 1 | 0.2 | 3.548 | 0.7096 | 1 | 0.2 | 3.548 | 0.7096
|  | SQMT | 1 | 0.2 | 2.369 | 0.4738 | 1 | 0.2 | 2.369 | 0.4738
|  | SQMT | 1 | 0.3 | 1.639 | 0.4917 | 1 | 0.3 | 1.639 | 0.4917
|  | SQMT | 1 | 0.2 | 3.548 | 0.7096 | 1 | 0.2 | 3.548 | 0.7096
|  | SQMT | 1 | 0.2 | 1.784 | 0.3568 | 1 | 0.2 | 1.784 | 0.3568
|  | SQMT | 1 | 0.3 | 1.704 | 0.5112 | 1 | 0.3 | 1.704 | 0.5112
|  | SQMT | 1 | 0.2 | 3.569 | 0.7138 | 1 | 0.2 | 3.569 | 0.7138
|  | SQMT | 1 | 0.2 | 1.355 | 0.271 | 1 | 0.2 | 1.355 | 0.271
|  | SQMT | 1 | 0.3 | 1.762 | 0.5286 | 1 | 0.3 | 1.762 | 0.5286
|  | SQMT | 1 | 0.2 | 3.558 | 0.7116 | 1 | 0.2 | 3.558 | 0.7116
|  | SQMT | 1 | 0.2 | 1.065 | 0.213 | 1 | 0.2 | 1.065 | 0.213
|  | SQMT | 1 | 0.3 | 1.82 | 0.546 | 1 | 0.3 | 1.82 | 0.546
|  | SQMT | 1 | 0.2 | 3.515 | 0.703 | 1 | 0.2 | 3.515 | 0.703
|  | SQMT | 1 | 0.2 | 0.9 | 0.18 | 1 | 0.2 | 0.9 | 0.18
|  | SQMT | 1 | 0.3 | 1.853 | 0.5559 | 1 | 0.3 | 1.853 | 0.5559
|  | SQMT | 1 | 0.2 | 3.44 | 0.688 | 1 | 0.2 | 3.44 | 0.688
|  | SQMT | 1 | 0.2 | 0.9 | 0.18 | 1 | 0.2 | 0.9 | 0.18
|  | SQMT | 1 | 0.3 | 1.9 | 0.57 | 1 | 0.3 | 1.9 | 0.57
|  | SQMT | 1 | 0.2 | 3.336 | 0.6672 | 1 | 0.2 | 3.336 | 0.6672
|  | SQMT | 1 | 0.2 | 0.93 | 0.186 | 1 | 0.2 | 0.93 | 0.186
|  | SQMT | 1 | 0.3 | 1.908 | 0.5724 | 1 | 0.3 | 1.908 | 0.5724
|  | SQMT | 1 | 0.2 | 3.2 | 0.64 | 1 | 0.2 | 3.2 |  | not at site
|  | SQMT | 1 | 0.2 | 0.988 | 0.1976 | 1 | 0.2 | 0.988
|  | SQMT | 1 | 0.3 | 1.92 | 0.576 | 1 | 0.3 | 1.92
|  | SQMT | 1 | 0.2 | 2.553 | 0.5106 | 1 | 0.2 | 2.553 | 0.5106
|  | SQMT | 1 | 0.2 | 2.674 | 0.5348 | 1 | 0.2 | 2.674 | 0.5348
|  | SQMT | 1 | 0.2 | 2.683 | 0.5366 | 1 | 0.2 | 2.683 | 0.5366
|  | SQMT | 1 | 0.2 | 1.786 | 0.3572 | 1 | 0.2 | 1.786 | 0.3572
|  | SQMT | 1 | 0.2 | 1.023 | 0.2046 | 1 | 0.2 | 1.023 | 0.2046
|  | SQMT | 1 | 0.2 | 0.826 | 0.1652 | 1 | 0.2 | 0.826 | 0.1652
|  | SQMT | 1 | 0.2 | 0.531 | 0.1062 | 1 | 0.2 | 0.531 | 0.1062
|  | SQMT | 1 | 0.2 | 0.3 | 0.06 | 1 | 0.2 | 0.3 | 0.06
|  | SQMT | 1 | 0.2 | 0.13 | 0.026 | 1 | 0.2 | 0.13 | 0.026
| above couter | SQMT | 1 | 0.2 | 0.734 | 0.1468 | 1 | 0.2 | 0.734 | 0.1468
|  | SQMT | 1 | 0.2 | 1.098 | 0.2196 | 1 | 0.2 | 1.098 | 0.2196
|  | SQMT | 1 | 0.2 | 1.448 | 0.2896 | 1 | 0.2 | 1.448 | 0.2896
|  | SQMT | 1 | 0.2 | 1.709 | 0.3418 | 1 | 0.2 | 1.709 | 0.3418
|  | SQMT | 1 | 0.2 | 1.849 | 0.3698 | 1 | 0.2 | 1.849 | 0.3698
|  | SQMT | 1 | 0.2 | 1.977 | 0.3954 | 1 | 0.2 | 1.977 | 0.3954
|  | SQMT | 1 | 0.2 | 2.072 | 0.4144 | 1 | 0.2 | 2.072 | 0.4144
|  | SQMT | 1 | 0.2 | 2.14 | 0.428 | 1 | 0.2 | 2.14 | 0.428
|  | SQMT | 1 | 0.2 | 2.184 | 0.4368 | 1 | 0.2 | 2.184 | 0.4368
|  | SQMT | 1 | 0.2 | 2.208 | 0.4416 | 1 | 0.2 | 2.208 | 0.4416
|  | SQMT | 1 | 0.2 | 2.203 | 0.4406 | 1 | 0.2 | 2.203 | 0.4406
|  | SQMT | 1 | 0.2 | 2.178 | 0.4356 | 1 | 0.2 | 2.178 | 0.4356
|  | SQMT | 1 | 0.2 | 2.13 | 0.426 | 1 | 0.2 | 2.13 | 0.426
|  | SQMT | 1 | 0.2 | 2.057 | 0.4114 | 1 | 0.2 | 2.057 | 0.4114
|  | SQMT | 1 | 0.2 | 1.957 | 0.3914 | 1 | 0.2 | 1.957 | 0.3914
|  | SQMT | 1 | 0.2 | 1.822 | 0.3644 | 1 | 0.2 | 1.822 | 0.3644
|  | SQMT | 1 | 0.2 | 1.643 | 0.3286 | 1 | 0.2 | 1.643 | 0.3286
|  | SQMT | 1 | 0.2 | 1.397 | 0.2794 | 1 | 0.2 | 1.397 | 0.2794
|  | SQMT | 1 | 0.2 | 1.011 | 0.2022 | 1 | 0.2 | 1.011 | 0.2022
[6 empty] | 36.5124 |  |  |  | 32.7498

## J. Doors
FEBRUARY 2020
TRAVEL FOOD SERVICES
BOQ STANDARDISATION, IMPLEMENTATION AND COST CONSULTANCY |  |  |  |  | DOORS FINISHING BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU
M&A Bill
SR. NO. | WBS | WBS Level1 | WBS Level 2 | SHORT ITEM DESCRIPTION | PARTICULARS | UOM | QTY. | Basic Rate of Material | Amount | Qty | Amount | remark
GENERAL NOTES
a |  |  |  |  | Please refer to "Exhibit A - Basic rate of material" for the applicable base rates of materials
c |  |  |  |  | Items of works shall to be read in conjunction with Drawings, Specifications, Contractual terms and conditions and Trade Preambles to this BOQ as included in the RFP.
d |  |  |  |  | The quantities mentioned in the BOQ is tentative and may increase or decrease. Payment shall be restricted to the quantum of work executed and measured as per the defined mode of measurement.
e |  |  |  |  | The Mode of Measurement (in order of priority) is as follows:
(i) As defined in relevant item in the BOQ
(ii) As defined in the specification
(iii) As defined in IS-1200 (latest version) for relevant trade.
(iv) if mode is not defined in (i), (ii) and (iii), the standard industry practice shall be adopted.
Items of work and trade preambles are essential parts of the bill of quantities and are to be taken as mutually explanatory of one another. Requirement occurring in one is binding as though occurring in both. In resolving conflicts, discrepancies, errors or omissions as regards trade preambles & bill of quantities the following order of precedence shall be used but subject to PRIORITY OF DOCUMENTS as included in General Conditions of Contract: a. General Notes as included in this bill of quantities. b. Trade Preambles as included in RFP. c. Item Description as included in this bill of quantities.
12 |  |  |  |  | JOINERY & DOOR WORK
12.1 | Civil | Door | solid core flush shutter | 50mm thick solid core flush shutter | Providing and fixing factory made 50mm thick solid core flush shutter confirming to IS 2202 (Part - I); Shutter shall be manufactured with exterior quality synthetic adhesive forming marine ply surfaces, internally lipped as manufactured by M/s. Anchor or M/s. Kutty or equivalent. Shutter shall be finished with minimum 2 mm thick veneer and melamine polish in approved shade, colour and design. Further edges of shutter shall be provided with 6mm thick teakwood beadings using exterior quality synthetic adhesive, headless GI nails, screws, beading finished with melamine polish, etc, at all levels and locations, all complete to entire satisfaction of the PM. (Doors at Residential levels). Including providing, making and fixing door frames made out of approved quality, chemically treated, Kiln-seasoned, antitermite treated approved quality teak wood with shaped, grooved, metered joint arrangement, mouldings, rebates, including use of approved water repellent adhesive, GI screws, pins, etc. all exposed surfaces to be melamine polished in approved colour and shade, surfaces of frame in contact with masonry / concrete surfaces shall be painted with one coat of hot bitumen of approved quality, 3 nos. GI holdfast (split and 225 x 75 x 2 mm thick) / bolts on each side of frame well-grouted with cement concrete mix in a ratio of 1:2:4 (1 cement : 2 sand : 4 aggregate), etc, at all levels and locations, complete to the entire satisfaction of the PM. Iron Mongery: Only Items which are Listed in Part D, will be supplied through Part D - Provisional Sum of Supplies, Contractor to include fixing cost for the same & supply and fixing of all others.
12.1.1 |  |  |  |  | D01 - 1800 X 2400mm - Solid Core flush door finishes in veneer | No
12.1.2 |  |  |  |  | D02 - 1000 X 2400mm - Solid Core flush door finishes in veneer | No
12.1.3 |  |  |  |  | D03 - 900 X 2400mm - Solid Core flush door finishes in veneer | No
12.2 | Civil | Door | solid core flush shutter | 50mm thick solid core flush shutter | Providing and fixing factory made 50mm thick solid core flush shutter confirming to IS 2202 (Part - I); Shutter shall be manufactured with exterior quality synthetic adhesive forming marine ply surfaces, internally lipped as manufactured by M/s. Anchor or M/s. Kutty or equivalent. Shutter shall be finished with 1.5 mm thick laminated in approved shade and design with hot pressed at factory. Further edges of shutter shall be provided with 6mm thick teakwood beadings using exterior quality synthetic adhesive, headless GI nails, screws, beading finished with melamine polish, etc, at all levels and locations, all complete to entire satisfaction of the PM. (Shafts, Common & Service area doors) Including providing, making and fixing door frames of 200mm W x 60mm thickness made out of approved quality, chemically treated, Kiln-seasoned, antitermite treated approved quality red oak / ash wood with shaped, grooved, metered joint arrangement, mouldings, rebates, including use of approved water repellent adhesive, GI screws, pins, etc. all exposed surfaces to be melamine polished in approved colour and shade, surfaces of frame in contact with masonry / concrete surfaces shall be painted with one coat of hot bitumen of approved quality, 3 nos. GI holdfast (split and 225 x 75 x 2 mm thick) / bolts on each side of frame well-grouted with cement concrete mix in a ratio of 1:2:4 (1 cement : 2 sand : 4 aggregate), etc, at all levels and locations, complete to the entire satisfaction of the PM. Iron Mongery: Only Items which are Listed in Part D, will be supplied through Part D - Provisional Sum of Supplies, Contractor to include fixing cost for the same & supply and fixing of all others. 'Single leaf Solid Core flush door finishes with door frame
12.2.1 |  |  |  |  | D01 - 1800 X 2400mm - Solid Core flush door finishes in veneer | No
12.2.2 |  |  |  |  | D02 - 1200 X 2400mm - Solid Core flush door finishes in veneer | No
12.2.3 |  |  |  |  | D3 - 1500 X 2400mm | No
12.2.4 | Civil | Door | solid core flush shutter | Single Leaf Door - 50mm thick solid core flush shutter in laminate finish. | P&F of Single Leaf Door with door frame at the back entrance to the kitchen, over all size 1000mm x 2400mm, the back entrance to the kitchen. Using 50mm thick readymade fireproof block board shutter (selected & approved make, fire retardant bwr grade). Both the surfaces and edges of the door to be finished with 1mm thick laminate (basic cost INR. 1345.00 / SM). Rate inclusive of all hardware fittings like- heavy duty ball bearing butt hinges (code:9268610 - Hettich make), 300mm ht. x 25 mm dia SS 'H' handle (Hettich make- 2310, code:9228560O /zone make - OGH-55-25X300MM SSS - H Type Handle / Equivalent make) on shutters, heavy duty SS door stopper (Hettich-code:9250600), single type dead lock, tower bolt, Open type door closure (Hettich make- Item code:9227816), all necessary hardware fittings, etc. (all the hardware fittings should be Hettich / Dorset / Dorma / Ozone make / Equivalent make and to be approved by architect / site engineer), including 8mm thick clear glass vision panel (300mm L x 500mm H) to be fixed with the wooden beading and to be finished in said in polish. Having 304 grade 900mm height x 2mm thick SS Matte hairline finished kick plate on the both surfaces of the shutter. With doorframe out of 200mm W x 60mm thickness made out of approved quality, chemically treated, Kiln-seasoned, antitermite treated approved quality red oak / ash wood with shaped, grooved, metered joint arrangement, moldings, rebates, including use of approved water repellent adhesive, GI screws, pins, etc. all exposed surfaces to be melamine polished in approved colour and shade, surfaces of frame in contact with masonry / concrete surfaces shall be painted with one coat of hot bitumen of approved quality, 3 nos. GI holdfast (split and 225 x 75 x 2 mm thick) / bolts on each side of frame well-grouted with cement concrete mix in a ratio of 1:2:4 (1 cement : 2 sand : 4 aggregate), etc., at all levels and locations, complete to the entire satisfaction of the PM.Complete as per architectural detail drawing & site engineer's instruction. Size: 1000mm L x 2400mm H x 1 no. As per D3. | No | 1 | 38000 | 38000
12.2.5 | Civil | Door | solid core flush shutter | Single Leaf Door - 50mm thick solid core flush shutter in laminate finish. | P&F of Single Leaf Door with door frame at the divider to the display kitchen and prep. section, over all size 1000mm x 2400mm, the back entrance to the kitchen. Using 50mm thick readymade fireproof block board shutter (selected & approved make, fire retardant bwr grade). Both the surfaces and edges of the door to be finished with 1mm thick laminate (basic cost INR. 1345.00 / SM). Rate inclusive of all hardware fittings like- heavy duty ball bearing butt hinges (code:9268610 - Hettich make), 300mm ht. x 25 mm dia SS 'H' handle (Hettich make- 2310, code:9228560O /zone make - OGH-55-25X300MM SSS - H Type Handle / Equivalent make) on shutters, heavy duty SS door stopper (Hettich-code:9250600), single type dead lock, tower bolt, Open type door closure (Hettich make- Item code:9227816), all necessary hardware fittings, etc. (all the hardware fittings should be Hettich / Dorset / Dorma / Ozone make / Equivalent make and to be approved by architect / site engineer), including 8mm thick clear glass vision panel (300mm L x 500mm H) to be fixed with the wooden beading and to be finished in said polish. Having 304 grade 900mm height x 2mm thick SS Matte hairline finished kick plate on the both surfaces of the shutter. With doorframe out of 200mm W x 60mm thickness made out of approved quality, chemically treated, Kiln-seasoned, antitermite treated approved quality red oak / ash wood with shaped, grooved, metered joint arrangement, moldings, rebates, including use of approved water repellent adhesive, GI screws, pins, etc. all exposed surfaces to be melamine polished in approved colour and shade, surfaces of frame in contact with masonry / concrete surfaces shall be painted with one coat of hot bitumen of approved quality, 3 nos. GI holdfast (split and 225 x 75 x 2 mm thick) / bolts on each side of frame well-grouted with cement concrete mix in a ratio of 1:2:4 (1 cement : 2 sand : 4 aggregate), etc., at all levels and locations, complete to the entire satisfaction of the PM.Complete as per architectural detail drawing & site engineer's instruction. Size: 950mm L x 2200mm H x 1 no. As per D2. | No | 1 | 38000 | 38000 | 1 | 38000
12.2.6 | Civil | Door | solid core flush shutter | Single Leaf Door - 38mm thick solid core flush shutter in subway tile finish (tile to be considered separatly). | P&F of Single Leaf Door without door frame at the storage unit, over all size 900mm x 2100mm for storage unit. Using 38mm thick readymade fireproof block board shutter (selected & approved make, fire retardant bwr grade). Back of the surface and edges of the door to be finished with 1mm thick laminate (basic cost INR. 1345.00 / SM). Rate inclusive of all hardware fittings like- heavy duty ball bearing butt hinges (code:9268610 - Hettich make), heavy duty SS door stopper (Hettich-code:9250600), single type dead lock, tower bolt, all necessary hardware fittings, etc. (all the hardware fittings should be Hettich / Dorset / Dorma / Ozone make / Equivalent make and to be approved by architect / site engineer). complete to the entire satisfaction of the PM.Complete as per architectural detail drawing & site engineer's instruction. Size: 900mm L x 2100mm H x 1 no. As per Section ZZ. | No | 1 | 28000 | 28000
12.3 | Civil | Door | solid core flush door | Single Leaf Door | Providing and fixing factory made solid core flush door in single leaf 35mm thick, decorative types, of exterior grade, as per detailed drawings, conforming to IS :2202 1962(Revised)with approved face veneers on both face with/without glazing and venetians in the positions shown on the drawings or as directed, all necessary beads, moulding and lipping,holdfasts,mat finish stainless steel fixtures fastenings , finishing with French-polish/ waxing complete. Including providing, making and fixing door frames made out of approved quality, chemically treated, Kiln-seasoned, antitermite treated approved quality teak wood with shaped, grooved, metered joint arrangement, mouldings, rebates, including use of approved water repellent adhesive, GI screws, pins, etc. all exposed surfaces to be melamine polished in approved colour and shade, surfaces of frame in contact with masonry / concrete surfaces shall be painted with one coat of hot bitumen of approved quality, 3 nos. GI holdfast (split and 225 x 75 x 2 mm thick) / bolts on each side of frame well-grouted with cement concrete mix in a ratio of 1:2:4 (1 cement : 2 sand : 4 aggregate), etc, at all levels and locations, complete to the entire satisfaction of the PM. Iron Mongery: Only Items which are Listed in Part D, will be supplied through Part D - Provisional Sum of Supplies, Contractor to include fixing cost for the same & supply and fixing of all others. |  |  | 37500
12.3.1 |  |  |  |  | D03 - 900 X 2400mm - Toilet - Solid Core flush door finishes in veneer | No
12.3.2 |  |  |  |  | D03 - 900 X 2400mm - Toilet - Solid Core flush door finishes in laminate | No
12.3.3 |  |  |  |  | D04 - 850 X 2400mm - Toilet - Solid Core flush door finishes in laminate | No
12.3.4 |  |  |  |  | D05 - 750 X 2400mm - Wash area - Solid Core flush door finishes in laminate | No
12.4 | Civil | Door | Flush Door | Laminate Finished Flush Door(35mm) with Vision Panel | Providing and fixing Laminate Finished Flush Door(35mm) with Vision Panel decorative types,of exterior grade,as per detailed drawing. The following are the Sizes 1)750mm x 2100mm 2)900mm x 2100mm | Sq m
12.5 | Civil | Door | Flush Door | flush door with app. Laminate finished and 300mm dia Vision glass panel. | Flush Door:- P/Fixing of 35mm Thk flush door with app. Laminate finished and 300mm dia Vision glass panel, door to have concealed door closer, S.S. hinges and other necessary guard to complete door. | Sq m
12.6 | Civil | Door | Flush swing Door | 2-Way swing flush door | Flush swing Door:- P/Fixing of 25mm Thk 2-Way swing flush door with app. Laminate finished and door to be fixed in spring hinges other necessary guard to complete door. | Sq m
12.7 | Civil | Door | Fire retardant flush door | 42mm thick Fire retardant marine grade flush door | Flush Door:- S/I of 42mm thk fire retardant marine grade flush door, finished with app. Laminate, door to have toughened glass vision panel. | Sq m
12.8 | Civil | Shutters | Rolling Shutters | Supplying and fixing rolling shutters | Supplying and fixing rolling shutters of approved make, made of 80mm x 1.25mm M.S. Laths, interlocked together through their entire length, and jointed together, at the end by end locks, mounted on specially designed pipe shaft, with brackets, side guides 27.5 cm. long wire spring grade No. 2 and arrangement for inside and outside locking, with push and pull operation complete, including top cover 0.80mm thick (payment is to be made for the exact size of opening; where rolling shutter is to be fixed) complete in all respect as per specification, drawing and to the entire satisfaction of Engineer-In-Charge.
12.8.1 |  |  |  |  | Rolling Shutter - RS - 3000 X 2400mm | No
12.8.2 |  |  |  |  | Rolling Shutter - RS - 4500 X 2400mm | No
12.9 | C & I | SHUTTER | Motorised Shutter | GI ROLLING SHUTTER | MOTORISED GI ROLLING SHUTTER Providing & fixing motorised electrically operated type rolling shutter - curtain shall consist of interlocking corrugated laths or slots fabricated out of clod rolled steel strips confirming to IS 49201.Tne thickness fabricated out of steel sheets for the laths shall not be less than 1.25mm.The rolling shutters shall be of galvanised type. The various parts under "materials & fabrication" above shall be hot dipped galvanised, except for hood which can be made out of GI sheets readily available in the-market. The galvanising shall be effected by using 97.50% pure zinc arid the zinc-coating shall not be less than 230 gm per sq. meter, the coating shall tie free from flaking or peeling. The galvanising shall be done in accordance with 15·2629 and 6159.Detailed specifications shall be as per attached annexures. Measurement shall be made for clear masonry openings | Sq.m
12.1 | Civil | SHUTTER | Motorised GRILL TYPE ROLLING SHUTTER | MOTORISED GRILL TYPE ROLLING SHUTTER | Providing and fixing electrically operated and motorised with single phase 230v a/c power full motor which shall sits inside the Patti gauge, This shall be de clutch able so that shutter can be operated manually also including cost of multifunctional remote. Make: FFAC/yadalong. The shutter shall be grill type curtain made out of interlocking mild steel rods and Patti, using 12mm rods; 18# gauge Patti, 10 gauge bottom channels, 10# gauge side channel with good quality high tension coli spring with tab Patti drum, All etc. complete and including the cost of installation commissioning complete to the satisfaction of Engineer-In-Charge . | Sq m
12.11 | C & I | Shutter | GRILL TYPE ROLLING SHUTTER | GRILL TYPE ROLLING SHUTTER | Providing and fixing in position Metal door with grill shutter as per details in the drawings including fixing ironmongery etc. The frame to be made of 100mm x75mm MS box sections The Shutters to be grill which is welded to the Outer frame made of 50mm x50mm MS box sections This includes providing and fixing brush steel finished iron mongery like Ball bearing Hinges, Locks, Handles, Push Plates, Bolts, etc. (Dorma/ Geze/ Ingersoll /Shakti rand make) as indicated in the detail drawings and all surfaces of doors shall be finished with 2 coats of enamel paint over a coat of primer. | No.
12.12 | Civil | SHUTTER | SHUTTER | Fire Rated Rolling Shutters | Supply and installation of electrically motorised Fire Rated Rolling Shutters, for stability and integrity for up to 4 hours tested & comply with BS 476: Part 22: 1987; and are designed to close automatically in the event of fire or an alarmed event. Automatic closure will be thermally controlled by means of fusible link or any other suitable method. Supplier shall be approved such as Gandhi automations, Avians, or equivalent. Fire Rated Sliding Doors are available in single and double leaf doors with a maximum size of 8500 mm x 6000 mm and fire resistant to EN 16034:2014 Standards. | Sq m
12.13 | Civil | Doors | Fire rated door | Fire rated door with frame | Providing, supplying and fixing 2 hours fire rated door with frame 143mm x 57mm size out of hot dip galvanized mild steel sheet of 1.6mm thickness including required angle threshold of hot dip galvanized mild steel angle of section 35 x 35mm, or base ties of 1.25mm pressed hot dip galvanized mild steel welded or rigidly fixed together by mechanical means, frames shall be fixed with bolts / 3 nos. G.I. holdfast 225 x 20 x 4 mm with split end on either side and well grouted with cement concrete mix 1:3:6 adjustable lugs with split end tail to each jamb, including stainless steel butt hinges strengthened with SS pins, lock strike-plate, shock absorbers as specified and 46 mm thick single leaf shutter made out of minimum 1.25 mm thick galvanised sheet insulated with special designed fire rated and tested in accredit laboratory approved by PM/Architect, as per latest Indian Standard 3614 Part II. Further include priming with Zinc-Phosphate Stoving Primer and finishing with Polyurethane Aliphatic grade paint in approved shade and colour complete, at all levels and locations, as per drawing to the entire satisfaction of the PM. Ironmongery (Included in Contractor scope): a) SS ball bearing butt Hinges 102mm x 76mm x 3mm - 4 Nos. b) SS Panic Bar (Push type) - 1 No. c) Mortise dead bolt with both side key operation cylinder - 1 No. d) SS heavy duty door closer - 1 No. e) SS 300mm long x 22mm dia D type pull handles - 1 Pair f) Vision panel of size 200mm x 300mm with 6mm thick fire rated glass
12.13.1 |  |  |  |  | D06 - 1200 X 2400mm Metal door with vision panel 2hr fire rated | No
12.13.2 |  |  |  |  | D07 - 1800 X 2400mm - Solid core flush door finished in metal | No
12.13.3 |  |  |  |  | D07 - 1200 X 2400mm - Solid core flush door finished in metal | No
12.14 | Civil | Doors | Fire rated non-metallic (wooden) fire door | Fire Rated Metal door with pressed steel frame and shutter | Providing and fixing in position Fire Rated Metal door with pressed steel frame and shutter as per manufacturer's details and as mentioned in the drawings including fixing ironmongery etc of MPP System Schroders make. This includes providing and fixing brush steel finished iron mongery like Ball bearing Hinges, Mortise Locks, Handles, Push Plates, Bolts, Door Closer, etc. (Dorma/ Geze/ Ingersoll /Shakti rand make) as indicated in the detail drawings and all surfaces of doors shall be finished with 2 coats of Fire rating paint over a coat of primer to achieve the fire rating as indicated in the detail drawings. Frame : Providing and fixing of approved teak wood frame of section 150mm x 75mm with fire Intumescent seal strips of size 10mm x 4mm for the fire smoke sealing mounted in the grooves of the frame and coated with the fire retardant Intumescent coating. Shutter : Providing of 55mm thick asbestos free fire/smoke check shutter of 120mins fire rating comprising of two approved make 9mm thick Calcium Silicate Boards, 100mm x 30mm Hardwood internal approved hard wood timber frame work with the infill of 30mm thick 96 Kg/Cum insulated material, coated with FR silicate coating on both sides for insulation and faced with 4mm thick Water Proof Ply with Fire and Smoke Strips of size 10mm x 4mm mounted in the grooves in the shutter on all sides except bottom with teak wood beading including using approved intumescent sealant to seal the gaps between board and Shutter beading. The shutter to be finished with 1.5mm thick approved laminate on both sides. Ironmongery to be as approved, with fire rating and as detailed in Drawings to the entire satisfaction of PM. Ironmongery (Included in Contractor scope): a) SS ball bearing butt Hinges 102mm x 76mm x 3mm - 4 Nos. b) SS Panic Bar (Push type) - 1 No. c) Mortise dead bolt with both side key operation cylinder - 1 No. d) SS heavy duty door closer - 1 No. e) SS 300mm long x 22mm dia D type pull handles - 1 Pair f) Vision panel of size 200mm x 300mm with 6mm thick fire rated glass | Sq m
12.15 | Civil | WIREMESH DOOR | WIREMESH DOOR | Double leaf Wire Mesh Doors | Providing and fixing Double leaf Wire Mesh Doors with:" Steel Shapes, Plates, and Bars conforming to ASTM A36/A36M*.Cold-Formed Steel conforming to AISI SG03-3.* Wire Mesh: Carbon steel wire, woven diamond mesh, intermediate crimped. 10gage wire, 38 mm 1-1/2 inch, mesh. * Frames shall be 32 x 13 x.s mrn (1 x 1/4 x 1/2 x 1/8 inch) channels with32 x 3 mm (1-114·x 1/8 inch) flat bar cover on top and bottom ratls-andon hinge stile and a 35 x 20 x 3 mm (1~3/8-x3/4~x"J.i8 inch) angleriveted.to the dcck stile. * Provide 2 pairs of regular weight, wrought. Steel x non-removable pin, butt hinges riveted or welded to the door and the door opening frame for each door. Consider average door opening size as 2000 x 2100 mm . | Sq m
12.16 | Civil | Glass Door | Glass Door | Entrance double door 12mm thick Glass, Make Dorma/ equivalent approved. | Providing and fixing Entrance double Door in 12mm thick clear flawless Toughened Glass and fixed with stainless steel Patch fitting (Brush finish) from Dorma make or equivalent. Door to be provided with stainless steel / brushed steel handle from Dorma or approved equivalent company. Floor spring to be of Dorms make or equivalent. Rate to be all inclusive of Patch fitting, glass, lock, hardware, finishing, fixing, etc. complete. | Sq m
12.16.1 | Civil | Glass Door | Glass Door | Entrance single leaf glass door 12mm thick Glass, with wooden doorframe. | P&F of Single Leaf Glass Door with Doorframe, over all size 900mm x 2400mm @ Entrance to POS Section from display kitchen, with 200mm x 50mm thick seasoned red oak / ash wooden doorframe. Doors in 12mm thick (Heat Proof Toughened Glass in two parts, with service window provision of 450mm height) thick clear toughened glass. Using 75mm x 50mm thick seasoned red oak / ash wooden framing to be polished with Fire-Retardant pu polish. Rate inclusive of all hardware fittings like- door spring (BTS80F-Dorma make), 600mm Ht. 'H' handle (Dorma make) in metal Fire-Retardant rose gold colour in chrome finished. Rate includes all necessary hardware fittings, etc. (all the fittings should be approved by architect / site engineer) . Complete as per architectural detail drawing & site engineer's instruction. Size: 900mm L x 2400mm H x 1 no. | No. | 1 | 37500 | 37500 | 1 | 37500
12.17 | Civil | Glass Door | Glass Door | Toughened glass panel with CEP treated, | Glass Door:- S/I of 12mm Thk toughened glass panel with CEP treated, Door to have frosted vinyl film as per Detail by Id. | Sq m
12.18 | Civil | Glass Door | Accessories | Floor spring Glass Door, Ozone make | Provide and fixing of Floor Spring FS 8400 of Ozone make or equivalent as per manufacturer's specification, etc. complete, & as directed by Engineer-In-Charge. | EA
12.19 | Civil | Sliding Glass Door | Sliding Glass Door | Automated sliding door with ES 200 operator | Providing and fixing the automated sliding door with ES 200 operator with ST Hex profile with both side fixed panel of Dorma make with required structural support all complete with 12 mm thick clear toughened glass with fine frame profile and clamping rails. Sensors for proximity detection to be provided on both sides of door for 2 sliding door shutters, and the fixed glass panels shall have sealing brush arrangement all around. Size of opening 2.0 m x 2.7 m approximately or as per drawing. The operator & profile shall have cover of SS finish. The door shall have power back up module for emergency operations, manual override system in case of power failure, and for fire evacuation, the door shall have possibility of remaining fully open. Rate to include supply and fixing of 12 mm thick clear toughened glass of Make Asahi/Saint Gobain or equivalent. | Sq m
12.2 | C & I | Glass Door | Accessories | P&F OZONE MAKE PULL HANDLE OGH 1132X600 | Providing and fixing of Pull Handle OGH 1132 x 600 of Ozone make as per manufacturer's specification & as directed by Engineer-In-Charge. | EA
12.21 | C & I | Glass Door | Accessories | S&F OZONE MK SS TOP PATCH CAT NO-OPF2 | Providing and fixing of Ozone Make Stainless steel Top Patch cat no. OPF·2 as directed by Engineer-In-Charge . | Nos
12.22 | C & I | Glass Door | Accessories | S&F OZONE MK SS PIVOT CAT NO- OSSPF-GDP | Providing and fixing of Ozone Make Stainless steel PIVOT cat no. OSSPF-GDP Top pivot with 10mm diameter pin Wear resistant SS 304 pivot pin Pivot held in overhead structure Material:-Stainless Steel Grade 304 Finish:- SSS. as directed by Engineer-In-Charge. | Nos
12.23 | C & I | Glass Door | Accessories | S&F OZONE MK SS BOTOM PATC CAT NO-OPF-3 | Providing and fixing of Ozone Make Stainless steel Bottom Patch cat no.OPF·3 Interchangeable patch faces to keep bolt head on same side Adjustable pivot point of 55/65mm Secure Without Cover Compatible with OZONE Floor Spring-FS7400, FS8400, FS9400, FS10400 and FS 11400 Material:-Stainless Steel Grade 304 Finish:- SS as directed by Engineer-In-Charge. | Nos
12.24 | C & I | Glass Door | Accessories | S&FOZONE MK SS CORN PAT LOCK CATNO-OPL-1 | Providing and fixing of Ozone Make Stainless steel Corner Patch Lock with strike Plate. cat no OPL·1 as directed by Engineer-In-Charge. | Nos
12.25 | C & I | Glass Door | Accessories | S&FOZONE MK SS DOOR H Handle CATNO-OGH-5S | Providing and fixing of Ozone Make Stainless steel Glass Door Handle Ht type Size 1100 x 32 mm , cat no OGH-55 as directed by Engineer-In-Charge. | Nos
12.26 | C & I | Glass Door | Accessories | SUN GLASS FILM,LLUMAR-MAGNUMNT | Providing & Fixing of Sun Glass Film of Lumbar make with Specification Magnum NT 100 SR Solar & Security Series on Inner face of explosed Glass. | Sq.m
12.27 | C & I | Glass Door | Glass Door | Coloured Film of "LLUMAR | Providing and Fixing Coloured Film of "LLUMAR"make and colour including cleaning the Glass surface with approved liquid and Film,cutouts as per design and detailed drawing or as directed by engineer-in-charge etc. Complete. | Sq.m
12.28 | Civil | Flap Door | Flap Door | Corian Finished Flap Door (25mm) | providing and fixing Corian Finished Flap Door (25mm) having size-750mmx1100mm as per drawing. | Sq m
12.29 | Civil | Windows | Sliding windows | Anodized or powder coated Global make aluminium sliding windows | Providing and fixing of Anodized or powder coated Global make aluminium sliding windows by using special sections Viz: Two / Three track gutter (GAL – 1833, GAL – 1853), Two/Three track side & Top (GAL-2911,GAL-2915), Shutter plain (GAL-1820), Interlock (GAL-1837), Runner (GAL-1824) with necessary TPI make bearing roller, guide, Star Lock, 5mm thick clear float Saint gobain make glass including EPDM gasket complete. | M2
12.3 | Civil | Doors | Doors | Hollow metal door | Providing and fixing of Hollow metal door at all levels from ISO 9001-2000 certified Manufacturer. All hollow metal general doors with or without vision panel. Pressed Galvanised steel Single /Double leaf to required sizes of approved make Shakti Hormann or approved equivalent which consists of frame, shutter, infill and finish as detailed below and conforming to IS 277.Door frame shall be Single rebate frame profile of size 100 x 57 mm made out of 1.20mm thick galvanised steel sheet (18 gauge). Frames should be Metered and field assembled with self tabs. Frames should be provided with back plate bracket and anchor fasteners for installation on a finished plastered masonry wall opening. Once frame installed should be grouted with cement slurry if recommended on the clear masonry opening. Door leaf should be 46mm thick fully flush double skin door with or without vision lite. Door leaf shall be manufactured from 0.8mm (22 gauge) minimum thick galvanised steel sheet. The internal construction of the door should be rigid with steel stiffeners/ pads and reinforcement. The infill material shall be resin bonded honeycomb core. All doors should be factory prepped for receiving appropriate hardware and provided with necessary reinforcement for hinges, locks, and door closers. The edges should be interlocked with lock seam. For pair of doors astragals will be provided as required. 150x750mm Vision lite wherever applicable should be asper joinery details with a screw on glass beading on the inside. The glass should be 5mm clear toughened glass. Louvers when recommended should be site proof and shall be flush fixed on the external surface. All doors and frames shall be finished with polyurethane aliphatic grade paint of approved colour. The door leaf and frame shall have passed minimum 250 hours of salt spray test.Rate should include supply and installation of door and necessary hardware set. | M2
12.31 | C & I | wooden frame | wooden frame | Wooden frame work | Providing & Fixing 12mm plywood without Aluminium or wooden frame work including all fasteners, fixings, etc. complete as directed by Engineer-In-Charge | SQM
12.32 | C & I | wooden frame | wooden frame | Hard Wooden frame work | Providing & Fixing 12mm thick plywood with 50x50mm hard wood frame including all fasteners, fixings, etc. complete as directed by Engineer-In-Charge | SQM
13 |  |  |  |  | Maintenance of Doors and shutters
13.1 | C & I | Jamb line | Jamb line | Jamb line in ply supported in wooden frame work | Providing and fixing Jamb Line:- S/ Making of jamb line (Size:- 60 x 450) in ply supported in wooden frame work, jamb line clad with 12mm thk T.W. as per Design Detail by ID. | RMT
13.2 | C & I | Jamb line | Jamb line | jamb line 90mm thk Granite in sill/jams 250mm wide | Providing and fixing Jamb Line with 19mm thk Granite in sill/jambs, and 250mm wide etc.as per Design Detail by ID. | RMT
13.3 | C & I | Lock | Lever Lock | fixing Godrej seven lever lock for rolling shutter. | Providing and fixing LEVER LOCK F/ROLLING SHUTTER· Providing and fixing Godrej seven lever lock for rolling shutter. | NOS
13.4 | C & I | Door | Accessories | Door Stopper | Providing and fixing Door Stopper.Mukund or equivalent make. Approximate wt. 0.128 Kg/piece , these stoppers are manufactured using quality established essential material in mind set industry norms. These stoppers are widely installed in commercial and residential places and are accessible in plentiful sizes and shapes. Clients can buy these from us at most reasonable prices. | E.A
141500
75500
Materials Specification: Materials should be as per specified in BOQ & details drawings.
|  |  | 1 | 19mm thick fire retardant (two hour Fire-Retardant) plywood's basic rate consider for 1614.00 / SM, Anchor / Kutty / Century / Green ply - Make
|  |  | 2 | Rest plywood's should as per item no. 1.
|  |  | 3 | Laminate basic cost INR 1325.00/Sheet.
|  |  | 4 | Venner basic cost INR. 1614.00/SQM.
|  |  | 5 | All adhesives should be Pidilite brand.
|  |  | 6 | All hardware's fittings should be as mentioned on BOQ / Equivalent to the mentioned brand.
|  |  | 7 | All glasses and mirror should be branded, like - Saint gobain / BIAL approved.
|  |  | 8 | Aluminium tube - 16 gauge, Jindal / equivalent make.
|  |  | 9 | All hardware fittings should be as per mentioned on BOQ / Equivalent / Branded.
|  |  | 10 | 1st quality old btc wood / selected & approved seasoned american red oak / american ash wood for all wooden work.
|  |  | 11 | Fire-Retardant pu polish as per BIAL Standard Guideline up to 2 hours fire-rated.
|  |  | 12 | MS / SS works with Jindal / Tata make.
|  |  | 13 | SS works with standard grade product and selected and approved high quality 304 grade ss sheet.
|  |  | 14 | All metal works to be carried out as per the BIAL guideline.
|  |  | 15 | Contractor team ahs to study the BIAL Guideline for further queries if any.
|  |  | 16 | All the Workshop Drawings to be prepared by the contracting team, construction can start upon mutual approval.
|  |  | 17 | All the materials has to up to BIAL's Standard as per their Guideline.

## L.Painting
FEBRUARY 2020
TRAVEL FOOD SERVICES
BOQ STANDARDISATION, IMPLEMENTATION AND COST CONSULTANCY |  |  |  |  | PAINTING BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU
M&A Bill
SR. NO. | WBS | WBS Level1 | WBS Level 2 | SHORT ITEM DESCRIPTION | PARTICULARS | UOM | QTY. | Basic Rate of Material | Amount | Qty | Amount | remark
14 |  |  |  |  | PAINTING WORK
14.1 | C & I | Painting | Acrylic Paint | One coat approved primer and two coats of acrylic Paint | Rub down clean, fill cracks holes with approved filler sand and prepare and apply one coat approved primer and two coats of acrylic Paint Finish, Cost to include necessary staging, scaffolding and curing at all levels and elevations, materials, labours, curing, scaffolding and all lead, lifts etc, all complete to the complete satisfaction of the Project In charge. all as per drawings and specified in finishes specification. (Location: Ceiling) 1 COAT PRIMER + 2 COATS PAINT
14.1.1 |  |  | Acrylic Paint |  | to all levels | Sq m
14.2 | C & I | Painting | White wash | white wash to ceiling soffits | Providing and applying white wash to ceiling soffits with base preparation including all other necessary related works and as shown in the drawing as specified and as directed. (Plan area alone shall be measured. Rate shall include cost for applying paint to all levels, level differences, bulkheads, cove lights etc.) (Location: Ceiling)
14.2.1 |  |  | White wash | at Ceiling | to all levels | Sq m
14.2.2 |  |  | White wash | at Ceiling | Residential floors | Sq m
14.3 | C & I | Painting | Cement paint | Cement paint to ceiling soffits | Providing and applying cement paint to ceiling soffits with base preparation including all other necessary related works and as shown in the drawing as specified and as directed. (Plan area alone shall be measured. Rate shall include cost for applying paint to all levels, level differences, bulkheads, cove lights etc) (Location: Ceiling GF & Podium) | Sq m
14.4 | C & I | Painting | Acrylic Paint - Wall | One coat approved primer and two coats of acrylic Paint Finish | Rub down clean, fill cracks holes with approved filler sand and prepare and apply one coat approved primer and two coats of acrylic Paint Finish, Cost to include necessary staging, scaffolding and curing at all levels and elevations, materials, labours, curing, scaffolding and all lead, lifts etc, all complete to the complete satisfaction of the Project Incharge. all as per drawings and specified in finishes specification. (Location: Wall) 1 COAT PRIMER + 2 COATS PAINT
14.4.1 |  |  |  | At Wall | to all levels | Sq m
14.4.2 |  |  |  | At Wall | Residential floors | Sq m
14.4.3 |  |  |  | At Wall | Lift Lobbies - Residential floors | Sq m
14.4.4 |  |  |  | At Wall | Staircase walls - Residential floors | Sq m
14.4.5 |  |  |  | At Wall | LMR Walls | Sq m
14.4.6 |  |  |  | At Wall | Pump room Walls | Sq m
14.4.7 |  |  |  | At Wall | Staircase Soffit finish
14.4.7.1 |  |  |  | At Wall | Foundation to Podium | Sq m
14.4.7.2 |  |  |  | At Wall | Residential floors | Sq m
14.5 | C & I | Painting | White wash | White wash to walls | Providing and applying white wash to walls with base preparation including all other necessary related works and as shown in the drawing as specified and as directed. (Plan area alone shall be measured. Rate shall include cost for applying paint to all levels, level differences, bulkheads, cove lights etc) (Location: Walls)
14.5.1 |  |  |  | At Wall | to all levels
14.5.2 |  |  |  | At Wall | Foundation to Podium | Sq m
14.5.3 |  |  |  | At Wall | Residential floors | Sq m
14.5.4 |  |  |  | At Wall | Service, Fire check and Refugee Floor - Walls | Sq m
14.5.5 |  |  |  | At Wall | Shaft Finish
14.5.5.1 |  |  |  | At Wall | Foundation to Podium | Sq m
14.5.5.2 |  |  |  | At Wall | Residential floors | Sq m
14.5.5.3 |  |  |  | At Wall | Lift Shaft Finish | Sq m
14.6 | C & I | Painting | Oil bound distemper | Oil bound distemper - interior surfaces | Oil Bound distemper - 'Providing one coat of approved matching primer and two coats of paint of approved manufacture, brand, colour and shade on interior surfaces including cleaning and preparing surfaces, applying coat of putty, scaffolding etc. complete (for all heights of walls & concrete surfaces), as directed by Engineer-In-Charge. Note : Approved manufacturer shall be Berger Paints/ Jenson & Nicholson/ Asian Paints/ Dulux or equivalent 1 COAT PRIMER + 2 COATS PAINT | Sq m
14.7 | C & I | Painting | Exterior emulsion | External paint | Providing one coat of approved matching primer and two coats of "APEX or Apex Ultima exterior emulsion paint " or approved equivalent with approved colour and shade on exterior surfaces including cleaning, preparing surface, scaffolding, curing etc. complete (for all heights of walls & concrete surfaces), as directed by Engineer-In-Charge.
14.7.1 |  |  |  |  | 1 COAT PRIMER + 2 COATS PAINT | Sq m
14.7.2 |  |  |  |  | 2 COATS PRIMER + 2 COATS PAINT | Sq m
14.8 | C & I | Painting | Exterior emulsion paint of Low VOC | Exterior emulsion paint of Low VOC | Providing one coat of approved matching primer and two coats of "APEX or Apex Ultima exterior emulsion paint " or approved equivalent of Low VOC (“Volatile Organic Compounds”) with approved colour and shade on exterior surfaces including cleaning, preparing surface, scaffolding, curing etc. complete (for all heights of walls & concrete surfaces), as directed by Engineer-In-Charge.
14.8.1 |  |  |  |  | 1 COAT PRIMER + 2 COATS PAINT | Sq m
14.8.2 |  |  |  |  | 2 COATS PRIMER + 2 COATS PAINT | Sq m
14.9 | C & I | Painting | Lustre paint | Applying interior wall finish Lustre paint | Providing and applying interior wall finish Lustre paint of approved make over new or old internal wall surface as detailed below Scrapping the surface with emery paper and wipe clean. Applying Asian / Berger / Nerolac / Dulux Paints or equivalent wall primer with brush with mineral turpentine with brush 8 to 10% and oil 15 to 20% with roller and allowing to dry for a period 6 to 8 hours. Applying Asian / Berger / Nerolac / Dulux Paints or equivalent Acrylic wall putty with appropriate proportion of water allowing to dry for period 4 to 6 hours. Scrapping with Emery paper 180 and wipe clean. Applying Asian / Berger / Nerolac / Dulux Paints or equivalent wall primer with brush with mineral turpentine 8 to 10% and oil 15 to 20% with roller Scrapping Emery paper 320 and wipe clean, Applying Asian / Berger / Nerolac / Dulux Paints or equivalent interior wall finish lustre 1st coat with brush/rubber/spray with mineral turpentine 7 to 9% and Oil with roller 19 to 21% After 8 hours of activity Applying 2nd coat of Asian / Berger / Nerolac / Dulux Paints or equivalent interior wall finish Lustre with mineral turpentine 7 to 9 % with brush and Oil with roller 19 to 21% after allowing dry for the period of 6 to 8 hours activity, including scaffolding if necessary preparing surface by thoroughly cleaning oil, grease, dirt and other materials as required, etc. complete. as directed by Engineer-In-Charge. 2 COAT PRIMER + 2 COATS PUTTY + 2 COATS LUSTRE PAINT | Sqm
14.1 | C & I | Painting | Emulsion paint | Royale Luxury Emulsion paint of approved make over new or old internal wall surface | Providing and applying Royale Luxury Emulsion paint of approved make over new or old internal wall surface as detailed below Scrapping for surface with emery paper and wipe clean for area. Applying Asian / Berger /Nerolac / Dulux Paints or equivalent wall primer with brush by adding mineral turpentine oil by 8 to 10 % or water by 15 to 20% allowing to dry for 6 to 8 hours. After applying Asian / Berger / Nerolac / Dulux Paints or equivalent acrylic wall putty with appropriate proportion of water of allow to dry for period of 4 to 6 hours of activity. Scrapping with emery paper and wipe clean Applying paints Royale Luxury emulsion 1st coat with brush water content water 40 to 45% or 65 to 70% by role Applying paints Royale luxury emulsion 2nd coat with brush with water content 40 to 45 % or 65 to 70 % by roller. 2 COAT PRIMER + 1 COAT PUTTY + 2 COATS PAINT | Sqm
14.11 | C & I | Painting | Textured synthetic paint | Applying two coats of textured synthetic paint of approved shade and quality and one coat of primer | Providing and applying two coats of textured synthetic paint of approved shade and quality and one coat of primer before applying textured paint including scaffolding if necessary preparing surface by thoroughly cleaning oil, grease, dirt and other materials as required, etc. complete, as directed by Engineer-In-Charge. 1 COAT PRIMER + 2 COATS PAINT | Sqm
14.12 | C & I | Painting | Epoxy paint | Applying Epoxy paint (two or more coats) at all locations | Providing and applying Epoxy paint (two or more coats) at all locations prepared and applied as per manufacturer’s specifications including appropriate priming coat, including scaffolding if necessary preparing surface by thoroughly cleaning oil, grease, dirt and other materials as required, etc. complete, as directed by Engineer-In-Charge.
14.12.1 |  |  |  |  | On steel work | Sqm
14.12.2 |  |  |  |  | On concrete work | Sqm
14.13 | C & I | Painting | Bitumastic paint | Applying Painting (two or more coats) on rain water, soil waste and vent pipes and fittings | Providing and applying Painting (two or more coats) on rain water, soil waste and vent pipes and fittings with black anticorrosive bitumastic paint of approved brand and manufacture, over and including a priming of ready mixed zinc chromate yellow primer on new work/ old work, including scaffolding if necessary preparing surface by thoroughly cleaning oil, grease, dirt and other materials as required, etc. complete, as directed by Engineer-In-Charge.
14.13.1 |  |  |  |  | 100 mm diameter pipes | Rmt
14.13.2 |  |  |  |  | 150 mm diameter pipes | Rmt
14.14 | C & I | Painting | Synthetic Enamel paint | Applying Painting (two or more coats) on rain water, soil waste and vent pipes | Providing and applying Painting (two or more coats) on rain water, soil waste and vent pipes and fittings with synthetic enamel paint of approved brand and manufacture and required colour over a priming coat of approved steel primer on new work/ old work, including scaffolding if necessary preparing surface by thoroughly cleaning oil, grease, dirt and other materials as required, etc. complete, as directed by Engineer-In-Charge.
14.14.1 |  |  |  |  | 100 mm diameter pipes | Rmt
14.14.2 |  |  |  |  | 150 mm diameter pipes | Rmt
14.15 | C & I | Painting | Fire Retardant paint | Applying two coats of Fire Retardant paint on cleaned wood / ply surface @ 3.5 sqm per litre per coat | Providing and applying two coats of Fire Retardant paint on cleaned wood / ply surface @ 3.5 sqm per litre per coat including preparation of base surface as per recommendations of manufacturer to make the surface fire retardant, including scaffolding if necessary preparing surface by thoroughly cleaning oil, grease, dirt and other materials as required, etc. complete, as directed by Engineer-In-Charge. 2 COATS PAINT | Sqm
14.16 | C & I | Painting | Primer | Applying priming coats with primer of approved brand and manufacture | Providing and applying priming coats with primer of approved brand and manufacture, having low VOC (Volatile Organic Compound ) content. | Sqm
14.16.1 |  |  | Primer |  | With ready mixed pink or grey primer on wood work (hard and soft wood) having VOC content less than 50 grams/ litre | Sqm
14.16.2 |  |  | Primer |  | With water thinnable cement primer on wall surface having VOC content less than 50 grams/litre sqm | Sqm
14.17 | C & I | Painting | Epoxy paint to Structural Steel | Painting to Structural Steel work with Epoxy primer & Epoxy paint | Providing and applying painting to Structural Steel work with Epoxy primer & Epoxy paint of approved quality & make including preparation of surface as per IS 2074 or as per approved paint manufacturer specification and including scaffolding etc. all complete as directed & instructed by owner/ engineer. thickness of each coat of primer and paint and application shall be as per approved paint manufacturer's specifications (Rate shall include cost of supply of paint) two coat of epoxy primer & two coat of epoxy paint including preparation of steel surface to the requirement of paint manufacturer's specification. 2 COATS PRIMER + 2 COATS PAINT | MT
14.18 | C & I | Painting | Enamel paint to Structural Steel | Painting to Structural Steel work with Zinc chromate primer & Enamel paint | Providing and applying painting to Structural Steel work with Zinc chromate primer & Enamel paint of approved quality & make including preparation of surface as per IS 2074 or as per approved paint manufacturer specification and including scaffolding etc. all complete as directed & instructed by owner/ engineer. thickness of each coat of primer and paint and application shall be as per approved paint manufacturer's specifications (Rate shall include cost of supply of paint) two coat of primer & two coat of paint including preparation of steel surface to the requirement of paint manufacturer's specification. 2 COATS PRIMER + 2 COATS PAINT | MT
14.19 | C & I | Painting | Black board paint | Applying two coats of Black board paint of approved shade | Providing and applying two coats of Black board paint of approved shade and quality and one coat of primer before applying paint including scaffolding if necessary preparing surface by thoroughly cleaning oil, grease, dirt and other materials as required, etc. complete, as directed by Engineer-In-Charge. Make:- Asian Paints - 3 Mangoes Black board paint or equivalent. 1 COAT PRIMER + 2 COATS PAINT | Sqm
14.2 | C & I | Painting | Stucco paint | Applying two coats of Stucco paint of approved shade | Providing and applying two coats of Stucco paint of approved shade and quality and one coat of primer before applying textured paint including scaffolding if necessary preparing surface by thoroughly cleaning oil, grease, dirt and other materials as required, etc. complete, as directed by Engineer-In-Charge. Make:- Asian Paints - Royale Play Stucco or equivalent 1 COAT PRIMER + 2 COATS PAINT | Sqm
14.21 | C & I | Painting | Red Oxide primer & Synthetic Enamel paint | Applying two coats of Synthetic Enamel paint of approved shade and quality and one coat of Red Oxide primer | Providing and applying two coats of Synthetic Enamel paint of approved shade and quality and one coat of Red Oxide primer before applying Enamel paint including scaffolding if necessary preparing surface by thoroughly cleaning oil, grease, dirt and other materials as required, etc. complete, as directed by Engineer-In-Charge. Make:- Asian Paints/ Berger or equivalent. 1 COAT PRIMER + 2 COATS PAINT | Sqm
14.22 | C & I | Painting | Epoxy primer & Coal Tar paint | Applying one coat of zinc-rich Epoxy primer and two coats of Coal Tar Epoxy Paint to all concrete surfaces | Providing and applying one coat of zinc-rich Epoxy primer and two coats of Coal Tar Epoxy Paint to all concrete surfaces in contact with earth in foundation and substructure including all cost of material, labour, scaffolding if necessary, transportation and preparing the surfaces by cleaning, washing, brushing, etc. complete as directed by Engineer-In-Charge and as per specification. 1 COAT PRIMER + 2 COATS PAINT | Sqm
14.23 | C & I | Painting | Creative Artwork painting | Applying Artistic replication based on a preconceaved design | Creative Artwork painting Providing and applying Artistic replication based on a preconceaved design to be done over the prefinished wall surface, as per drawing, including scaffolding if necessary preparing surface by thoroughly cleaning oil, grease, dirt and other materials as required, etc. complete, as directed by Engineer-In-Charge. | Sqm
14.24 | C & I | Painting | Interior Emulsion Velvet Touch Paint - Wall | One coat approved primer and Two Coat of Interior Emulsion Velvet Touch Paint Finish | P&A of Matte Velvet Touch Fire Retardant Paint (Apcolite Premium Matte - Royal Ivory 0331-Asian Paint / equivalent) on Birla Putty / POP Punning finished walls with removing loose particles and paint flakes, scraping with sandpaper to ensure that the surface is dry and free from dust, dirt or grease. Apply a coat of wall primer, using deco prime wall primer (solvent thinnable) on wall surfaces with fill and level the minor undulations of wall by applying Asian paint enamel / oil wall putty and ensure that the surface is uniformly smooth by sanding, after putty work. One liberal coat of deco prime wall primer (solvent thinned) is recommended on puttied areas before applying the top coat. The primer should be allowed to dry for 10 to 12 hours, there after painting the surface in two finishing coats over base primer coat to achieve even finish. Allow the first coat to dry completely for a minimum of 10 to 12 hours. Once the first coat is dry, just rub the surface gently with sandpaper in order to remove the loose and small particles. After finishing the first coat, start applying the second coat of paint and leave the surface to dry completely for a minimum 10 to 12 hours. All these process and application to be done as per the manufactures' instruction with high quality tools to get the best quality of the paint finish. Complete up to the mark & site engineer's instruction. It is up to 4000mm height walls. | Sqm | 79.7764 | 430 | 34303.852 | #VALUE! | 18588.9
14.25 | C & I | Painting | Interior Emulsion Velvet Touch Paint - Wall | One coat approved primer and Two Coat of Interior Emulsion Acrylic Paint Finish | P&A of Fire Retardant Acrylic Paint (Ivory 0331-Asian Paint / Equivalent) on Gypboard finished false ceiling with removing loose particles and paint flakes, scraping with sandpaper to ensure that the surface is dry and free from dust, dirt or grease. Apply a coat of wall primer, using deco prime primer on the surfaces with fill and level the minor undulations of true ceiling by applying Asian paint wall putty and ensure that the surface is uniformly smooth by sanding, after putty work. One liberal coat of deco prime wall primer (solvent thinned) is recommended on puttied areas before applying the top coat. The primer should be allowed to dry for 6 to 8 hours, there after painting the surface in two finishing coats over base primer coat to achieve even finish. Allow the first coat to dry completely for a minimum of 6 to 8 hours. Once the first coat is dry, just rub the surface gently with sandpaper in order to remove the loose and small particles. After finishing the first coat, start applying the second coat of paint and leave the surface to dry completely for a minimum 6 to 8 hours. All these process and application to be done as per the manufactures' instruction with high quality tools to get the best quality of the paint finish. Complete up to the mark & site engineer's instruction. | Sqm | 110 | 396 | 43560 | 102.6234 | 40638.8569
77863.852
[5 empty] | TOTAL OF PAINTING WORK | [5 empty] | 59227.7569
Materials Specification: Materials should be as per specified in BOQ & details drawings.
1 | All the materials should be Asian Paints / Equivalent make as per the BIAL approved list.
2 | Rate are inclusive of required scaffolding at site for the respective Interiors Works.
3 | All basic price may vary at the time final closer of this BOQ with assigned agency / agencies.
4 | Rate are inclusive of required scaffolding at site for the respective Interiors Works.
5 | All the materials has to up to BIAL's Standard as per their Guideline.
6 | Contractor team has to study the BIAL Guideline for further queries if any.
7 | Contractor team has to submit samples to the concerned team / BIAL for further approvals prior to start on site execution.

## MB L PAINTING
MB Sheet CIVIL MASONRY BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU
SR.NO | Item Description | Unit | No | Length | Breadth | Total Quantity
A | General Site Works
14.24 | P&F of POP Punning(Specifications same as above, for Elevation AA. | SQMT | 1 | 3.7 | 4.1 | 15.17
| Specifications same as above, for Elevation BB. | SQMT | 3 | 1.2 | 2.1 | 7.56
| Specifications same as above, for Elevation CC. | SQMT | 1 | 5 | 4.1 | 20.5
#VALUE!
14.25 | 12mm thick Gypsum False Ceiling-FOH Area
| sofa side live kichan cold and hot wall ellevayin bb | SQMT | 1 | 9.886 | 8.664 | 85.6523
| less column | SQMT | -1 | 2.048 | 1.186 | -2.4289
| less hot boxing | SQMT | -1 | 0.9 | 4 | -3.6
| sofa side live kichan wall elevation bb | SQMT | 1 | 4.6 | 5 | 23
102.6234

## N. Miscellaneous
FEBRUARY 2020
TRAVEL FOOD SERVICES
BOQ STANDARDISATION, IMPLEMENTATION AND COST CONSULTANCY |  |  |  |  | MISCELLANEOUS BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU
M&A Bill
SR. NO. | WBS | WBS Level1 | WBS Level2 | SHORT ITEM DESCRIPTION | PARTICULARS | UOM | QTY. | Basic Rate of Material | Amount | Qty | Amount | remark
GENERAL NOTES
a |  |  |  |  | Please refer to "Exhibit A - Basic rate of material" for the applicable base rates of materials
c |  |  |  |  | Items of works shall to be read in conjunction with Drawings, Specifications, Contractual terms and conditions and Trade Preambles to this BOQ as included in the RFP.
d |  |  |  |  | The quantities mentioned in the BOQ is tentative and may increase or decrease. Payment shall be restricted to the quantum of work executed and measured as per the defined mode of measurement.
e |  |  |  |  | The Mode of Measurement (in order of priority) is as follows:
(i) As defined in relevant item in the BOQ
(ii) As defined in the specification
(iii) As defined in IS-1200 (latest version) for relevant trade.
(iv) if mode is not defined in (i), (ii) and (iii), the standard industry practice shall be adopted.
Items of work and trade preambles are essential parts of the bill of quantities and are to be taken as mutually explanatory of one another. Requirement occurring in one is binding as though occurring in both. In resolving conflicts, discrepancies, errors or omissions as regards trade preambles & bill of quantities the following order of precedence shall be used but subject to PRIORITY OF DOCUMENTS as included in General Conditions of Contract: a. General Notes as included in this bill of quantities. b. Trade Preambles as included in RFP. c. Item Description as included in this bill of quantities.
17 |  |  |  |  | MISCELLANEOUS & JOINERY WORK
17.1 | Civil | Staircase/ Ramps | SS Railing | Railing @ 900mm high above finish floor level | Providing, fixing, fabricating railing @ 900mm high above finish floor level, in profile made out of 50mm x 40mm Stainless steel (grade 304) uprights (end and intermediate) at about 1000mm c/c, 3 nos. of SS inclined runners of 19mm dia and 50 mm dia SS pipe matt finish as hand rail, SS rosette cover fixed with SS. pins, dowels, clamps, rubber, screws, gaskets etc. including required jointing and sealing with approved quality silicon sealant etc, at all levels and locations, all complete as per detail drawing, specification to entire satisfaction of PM. Work includes preparing shop drawings to scale with joinery and fixing details and further includes providing samples and preparing full scale mock-up samples for approval. As per site measurement correction to dimension with approval of the PM shall be made. (Residential floors) | Rmt
17.1.1 | Civil | Front Railing | Wooden Railing | Wooden Railing in PU Polish finish @ 900mm high above finish floor level at the front façade of the unit. | Providing, fixing, Wooden railing @ 900mm high above finish floor level, out of 75mm x 50mm seasoned red oak / ash wood framing uprights and 50mm x 50mm vertical grids at about 225mm c/c, 16 nos. and 25mm x 25mm ms tube grids of 10 nos in PU matt paint finish. With 5 nos of seasoned red oak / ash wooden panel of 355mm x 355mm x 38mm thick. All wooden surfaces tobe finished in fire rtaed PU polish. Including required jointing and sealing with approved quality silicon sealant etc, at all levels and locations, all complete as per detail drawing, specification to entire satisfaction of PM. Work includes preparing shop drawings to scale with joinery and fixing details and further includes providing samples and preparing full scale mock-up samples for approval. As per site measurement correction to dimension with approval of the PM shall be made. Size: 5000mm L x 900mm H x 1 no. | Rmt | 5 | 8200 | 41000 | 5 | 41000 | Not acceptable as per drawing made
17.1.1 | Civil | Front Wooden Framing | Vertical Wooden Framing | Wooden Railing in PU Polish finish @ 900mm high above finish floor level at the front façade of the unit. | Providing, fixing, Vertical wooden framing, out of 50mm x 50mm seasoned red oak / ash wood framing both vertical sides and 75mm x 50mm vertical grids at about 400mm c/c, 5 nos. All wooden surfaces to be finished in fire rated PU polish. Including required jointing and sealing with approved quality silicon sealant etc., at all levels and locations, all complete as per detail drawing, specification to entire satisfaction of PM. Work includes preparing shop drawings to scale with joinery and fixing details and further includes providing samples and preparing full scale mock-up samples for approval. As per site measurement correction to dimension with approval of the PM shall be made. Size: 2750mm H x 600mm W x 1 no. | Rmt | 2.75 | 8200 | 22550 | 3.6 | 29520
17.1.3 | Civil | Front Planter Box | Wooden Planter Box | Wooden Planter Box in PU Polish finish @ 900mm high above finish floor level at the front façade of the unit. | Providing, fixing, Wooden Planter Box, Using 12mm thick plywood for the planter box (fire retardant plywood, Archid / Kenwood make with pesticide treatment) and all surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00/SM). All the veneer and wooden surfaces to be finished in 2 Hrs. fire rated PU polish.. Including required jointing and sealing with approved quality silicon sealant etc., at all levels and locations, all complete as per detail drawing, specification to entire satisfaction of PM. Work includes preparing shop drawings to scale with joinery and fixing details and further includes providing samples and preparing full scale mock-up samples for approval. As per site measurement correction to dimension with approval of the PM shall be made. Size: 600mm L x 125mm D x 125mm H x 5 nos. | No. | 5 | 4300 | 21500 | 5 | 21500
17.2 | Civil | Staircase/ Ramps | SS Railing over Staircase Pardi | 50 mm dia SS pipe (304 grade) matt finish as hand rail | Providing and fixing 50 mm dia SS pipe (304 grade) matt finish as hand rail over staircase pardi supported on 20mm x 20mm SS (304 grade) uprights at required intervals fixed with SS pins, dowels, clamps, rubber, screws, gaskets etc. including welding, required jointing and sealing with approved quality silicon sealant etc, at all levels and locations, all complete as per detail drawing, specification to entire satisfaction of PM. (Residential floors) | Rmt |  |  | 0
17.3 | Civil | Staircase/ Ramps | MS Railing | M. S. railing @ 900mm high above finish floor level, in profile made out of 50mm x 40mm uprights | Providing, fixing, fabricating M. S. railing @ 900mm high above finish floor level, in profile made out of 50mm x 40mm uprights (end and intermediate), runners, and 50 mm dia pipe as hand rail, rosette cover fixed with pins, dowels, clamps, rubber, screws, gaskets etc. including required jointing and sealing with approved quality silicon sealant etc, at all levels and locations, all complete as per detail drawing, specification to entire satisfaction of PM. Work includes preparing shop drawings to scale with joinery and fixing details and further includes providing samples and preparing full scale mock-up samples for approval. As per site measurement correction to dimension with approval of the PM shall be made. |  |  |  | 0
17.3.1 |  |  |  |  | MS Handrail-Wall | Rmt |  |  | 0
17.3.2 |  |  |  |  | MS Handrail- Over RCC Pardi as per design as specified by consultants | Rmt |  |  | 0
17.4 | C & I | Stainless steel railing | SS RAILING 304G 50MM DIA | 50mm dia.SS pipe handrail fixed on 38mm dia.SS vertical members | Providing and fixing in position Stainless steel railing of 304 Grade as per the architectural design,drawings,includes 50mm dia.SS pipe handrail fixed on 38mm dia.SS vertical members (at suitable positions) and 20mm dia horizontal members(3No.), fixing to the 12mm dia S.S.member and specifications including necessary anchor fasteners, etc. complete as per drawing with all lead and lift of all levels, loading and unloading, transportation, curing etc, and all other incidental charges etc. complete and as directed by Engineer-in-charge.as per drawing. | RMT |  |  | 0
17.5 | C & I | Stainless steel hand rail | SS HAND RAIL 304 GRADE 50MM DIA | 50mm dia. S.S. pipe handrail fixed with 2mm thk. and 12mm dia S.S.plate, | Providing and fixing in position Stainless steel hand rail of 304Grade as per architectural design, drawings includes 50mm dia. S.S. pipe handrail fixed with 2mm thk. and 12mm dia S.S.plate, including necessary anchor fasteners, fittings and SS plates as per drawing with all leads and lifts of all levels, loading and unloading, transportation, curing, etc. and all other incidental charges etc. complete and as directed by Engineer-in·charge.(Only Hand rail with Bracket support). | RMT |  |  | 0
17.6 | C & I | Column guards | MS column guards at corner | MS column guards at corners made out of 25x25x6mm thick MS angle section | Providing and fixing MS column guards at corners made out of 25x25x6mm thick MS angle section about 1500 mm high fixed in floor by grouting about 150 mm deep as per detail drawings, MS section to be finished with two coats of primer, two under coats and one finished coat of approved synthetic enamel paint all as per instruction and entire satisfaction the of the PM / Architect, at all levels and locations. | Kg |  |  | 0
17.7 | C & I | Column guards | POWDER COATED ALU ANGLE 25x25x2 mm | Aluminium angle of size 25x25x2 mm thick powder coated to match the approved colour | Providing & fixing aluminium angle of size 25x25x2 mm thick powder coated to match the approved colour at the edge of column cladding to protect column edge, with high bond adhesive. Work including material,labor,tools,tackles,transportation,lead,lift,hardware,consumables etc. Complete as directed by EIC. | RMT |  |  | 0
17.8 | C & I | Column guards | GI Corner Edge Angle | GI corner edge angle guard 50x50x6 mm | Providing & fixing of GI corner edge angle guard 50x50x6 mm for walls including all screws & other hardware, etc. complete, as directed by Engineer-In-Charge. | RMT |  |  | 0
17.9 | C & I | Column guards | Column edge protection | Aluminium angle of size 38x38x2mm and finished with 50 to 60-micron powder coating of approved colour | Providing & fixing Jindal Hindalco make Aluminium angle of size 38x38x2mm and finished with 50 to 60-micron powder coating of approved colour. Aluminium angle to be pasted with hi bond epoxy adhesive, on the existing vitrified tile edge column edge as edge protection, Edge gaps of the aluminium angle to be finished with clear silicon sealant after pasting. Work including all material, labour, tools, tackles, transportation, lead, lift,hardware,consumables etc. Complete as directed by EIC. | RMT | 21.6 | 485 | 10476 | 12 | 5820
17.1 | Civil | Grating covers | Heavy duty 75mm thick M.S. Grating | Heavy duty 75mm thick M.S. Grating with framing suitable fixed to structure | Providing and fixing in position heavy duty 75mm thick M.S. Grating with framing suitable fixed to structure, the works shall be complete as specified and as directed by Engineer | Sqm |  |  | 0
17.11 | Civil | Steel work | For GI items | Steel work welded in built up sections / framed work hot dipped galvanized | Providing, fabricating and fixing Steel work welded in built up sections / framed work hot dipped galvanized including cutting, hoisting, fixing in position in gratings, frames, ladders, cat walks, platforms etc, at all levels and locations, as required and directed by the PM. | Kg |  |  | 0
17.12 | Civil | Louvers | Metal Louvers for Ceiling/ Wall | Fixing metal louvers. fixed with pins, dowels, clamps, rubber, screws, gaskets etc. | Providing and fixing metal louvers. fixed with pins, dowels, clamps, rubber, screws, gaskets etc. including welding, required jointing and sealing with approved quality silicon sealant etc, at all levels and locations, all complete as per detail drawing, specification to entire satisfaction of PM.. complete in all respect. |  |  |  | 0
17.12.1 |  |  |  |  | Metal Louver - on Floor / Ceiling | Sq m |  |  | 0
17.12.2 |  |  |  |  | Metal Louver - on Wall | Sq m |  |  | 0
17.13 | Civil | Tank | PVC coated steps | Fixing in position the PVC coated steps of size 300x150mm for UG Sump and OH Tank | Providing and fixing in position the PVC coated steps of size 300x150mm for UG Sump and OH Tank including placing 150mm inside concrete (while doing form work), aligning during concreting, grouting the junction if required, cleaning etc., | No |  |  | 0
17.14 | Civil | Manhole | Heavy Duty Cast Iron manhole cover | Heavy Duty Cast Iron manhole cover 2'-0" x 2'-0" inner size with framing and Cover | Providing and fixing in position Heavy Duty Cast Iron manhole cover 2'-0" x 2'-0" inner size with framing and Cover system suitable fixed to structure, the works shall be complete as specified and as directed by Engineer | No |  |  | 0
17.15 | Civil | Drainage | Subsoil drainage system | Subsoil drainage system as per design as specified including trenching, Pipework, Ductwork, sand fill / rock fill with graded material | Provide and supplying Subsoil drainage system as per design as specified including trenching, Pipework, Ductwork, sand fill / rock fill with graded material. Porous subsoil drain pipes laid in trench with open joints. With specified filter media etc. including excavation, blinding, and ducting for new in situ oil interceptor & Sand / drain pits at designated levels etc all. as per project managers instruction. | Sq m |  |  | 0
17.16 | C & I | Curtain | PVC STRIP CURTAIN W/ACCESSORIES | Fixing of PVC Strip curtain with required accessories | PRO & FIX PVC STRIP CURTAIN W/ACCESSORIES-Providing and fixing of PVC Strip curtain with required accessories including with necessary materials etc., complete. For BO Hentry area. Specs: See through, UV resistant, clear transparent and soft, temp. range -5C to +50C | Sq m |  |  | 0
17.17 | C & I | Curtains | Curtains | Curtains for Frisking Area | Supply and Fixing of Curtains for Frisking Area, Curtain of Size 1.20 m X 2.10 m, etc. complete and as directed by Engineer-In-charge. | Nos |  |  | 0
17.18 | C & I | Hook | Coat Hook | Position S.S. coat hook, all etc | Providing and fixing in position S.S. coat hook, all etc., complete, as per specifications | Nos |  |  | 0
17.19 | C & I | Laminated sheet | Laminated sheet of 1.0 mm thk. | Laminated sheet of 1.0 mm thk. of approved shade and brand such as sun mica/ Formica /decolam or any other | Providing & Fixing Laminated sheet of 1.0 mm thk. of approved shade and brand such as sun mica/ Formica /decolam or any other equivalent quality for the places such as table top wooden partition, doors, etc. complete. As directed by the Engineer in charge. | Sq m | 16.357 | 1245 | 20364.465 | 4.5 | 5602.5
17.2 | C & I | Board | Notice Board | Fixing in position NOTICE BOARD 900X600MM using 19mm thick white acrylic sheet | Providing and fixing in position NOTICE BOARD 900X600MM using 19mm thick white acrylic sheet all per design, detailed drawings etc., complete and as directed by Engineer-In-charge. All fittings and fixtures shall be of Keku/ Hettich or equivalent make only. | Nos |  |  | 0
17.21 | C & I | Carpet | Synthetic fibre carpet | laying washable woven synthetic fibre carpet | Providing and laying washable woven synthetic fibre carpet, avg. 4-5 mm thick of approved pattern & shade, of carpet roll width range 4-5 mt. & length range 15-25 mt. in specified area over smooth cement surface, such as to make the complete floor, in one uniform layer including laying and fixing edge and transition accessories including edge and threshold trims as approved, preparing the hard underfloor with smooth cement screed laid in C.M. 1:6, neat cement jointed, all curing, laying the carpet, keeping the surface protected until handover, preparing the mock-up for approval and ensuring same approved from Architect/Engineer-in charge, item installed cleaned complete. Carpet fibre to be synthetic of DUPONT SORONA type and grade, pile 1400/4 ply air twisted, weft Bono weft 850 & 440 tex, pile weight avg. 1500 gm/sqm, weave type flat weave jacquard, backing of Acrylic based glue, etc. complete as directed by Engineer-In-Charge. | Sq m |  |  | 0
17.22 | C & I | Carpet | Flocked Carpet rolls flooring | Flocked Carpet rolls flooring having a density of 70 million fibers of nylons 6.6 per sqm firmly | Providing and Fixing of Flocked Carpet rolls flooring having a density of 70 million fibers of nylons 6.6 per sqm firmly anchored into a waterproof backing and having an average recycled content of 20%. The carpet must inhibit the growth of Bacteria and Fungi. The Carpet must be Zero Emission carpet (Emission below detection limit after 28 days in accordance to ISO 16000-9 requirements). Fire Test EN-13501, Appearance Retention Hexapod ISO 140-8, Friction Slip resistance Test EN 14041 Class DS, Sanitized anti- microbial treatment with resilient water proof backing. The carpet should be anti static and thickness shall be 4.0 to 5.0 mm with approximate weight of 1.8 kg/ sqm. dimensional stability as per ISO 2551 : <0.2% .Slip Resistance as per DIN 51097 : >0.7 Dry and Wet. Light fastness as per EN ISO 105 B02 : ≥ 6. Commercial heavy as per EN 685 : Class 33. Acoustical Impact Sound Absorption ENISO 717-2 : 20 dB. Reaction to fire as per EN 13501-1 : Bfl-s1. The rate shall be inclusive of fixing at site with if necessary border and fixing arrangement as per the drawings and direction of Engineer in charge complete in all respect. Flooring should be done as per manufacturers specifications and as directed by engineer in charge. | Sq m |  |  | 0
17.23 | C & I | Mat | PVC Mat | Heavy duty PVC Mat-1800X1200 MM heavy duty PVC Mat-1800X1200 MM | Providing heavy duty PVC Mat-1800X1200 MM of approved make as per the specs, drawings and directions of Engineer-In-charge | Sq m |  |  | 0
17.24 | C & I | Flex | Temporary Flex | Temporary Flex for Cordoning of area by using wooden framework | Providing and erecting Temporary Flex for Cordoning of area by using wooden framework of hard wood of size 50mm x 50mm at spacing of 1200mm centre to centre, both horizontally and vertically, for height up to 3.5 mts, with one face covered with Chinese flex sheet, double skinned, 10 ounce thick Media, Print Medium solvent printing, fixed by use of approved adhesive, etc. complete. The Artwork for printing will be given by Engineer-In-Charge. | Sq m | 48 | 1883 | 90384 | 19.28 | 36304.24
17.25 | C & I | Flex | White flex partitioning | White flex partitioning for cordoning off portions of store | Providing & Fixing plain White flex partitioning fixed on M.S.Square frame 25 x 25 mm (18 gauge) for cordoning off portions of store, storage areas, Other areas as required along with access door of same frame & flex material. Rate to include all material, labour, hardware, tools, tackles, etc. complete, as directed by Engineer-In-Charge.
17.26 | C & I | Storage | Storage Racks | SLOTTED ANGLE RACK - 5 SHELF | Providing and fixing in position SLOTTED ANGLE RACK - 5 SHELF (SLOTTED ANGLE BOLTLESS M.S. POWDER COATED STORAGE RACK) Key hole type vertical frame, WPC Board removable shelves placed over beams made out of 202 Grade stainless steel, anti rust and anti Magnetic (Rack Dimensions - 36" x 18" x 72" HT) | Nos
17.27 | C & I | Storage | Storage Racks | SS STORAGE RACK - 5 SHELF 18g SS shelves double beaded on all sides | Providing and fixing in position SS STORAGE RACK - 5 SHELF 18g SS shelves double beaded on all sides, stiffed with 25 x 100 x 25mm hat channels, 38mm sq legs fitted with adjustable nylon bullet feets made out of 202 Grade stainless steel, anti rust and anti Magnetic (Rack Dimensions - 3'9" x 24" x 72"HT) | Nos
17.28 | C & I | Storage | Metal Rack | Installation of metal rack of size between width 1200 to l800 mm and height 2000 to 5000 mm | Supply & Installation of metal rack of size between width 1200 to l800 mm and height 2000 to 5000 mm all as per site condition, such the installed rack free of movement after loading and rack is in plumb, all work, etc. complete, as directed by Engineer-In-Charge. | Nos
17.29 | C & I | Storage | shelving and racking units | shelving and racking units such as wall units, floor loungers etc. | Assembly and installation of shelving and racking units such as wall units, floor loungers, heapers, wall shelfs, units as per the layout drawing and manufacturer's instructions as directed excluding cost of transportation from Ware House to Store/ Lounge. (Ware House to arrange for delivery of required materials to Store)
17.3 | C & I | Shifting and Lifting | Shifting and Lifting heavy equipments | Equipments like large panels, 6 ft to 12 ft freezers, Bakery equipments, etc. | Shifting and lifting heavy equipments like large panels, 6 ft to 12 ft freezers, Bakery equipments, etc. through building internal cut-outs to upper floors Upto 4 floors. As per layout and as directed by EIC. | MT
17.31 | C & I | Material Supply on site | By vehicle | LOADING/UNLOADING OF VEHICLE AT SITE | Loading/ Unloading of vehicle at site, including labour charges for loading or unloading of miscellaneous construction materials at site including stacking, etc. complete, as directed by Engineer-In-Charge. | Hours
17.32 | House keeping | Maintenance | House keeping | PVC Strip curtain with required accessories | PROVIDING PVC Strip curtain with required accessories | Nos
17.33 | Civil | Cleaning during construction | Cleaning Construction area & floor | Cleaning of construction site area & floor and to a neat working condition on a daily basis | Cleaning of construction site area & floor and to a neat working condition on a daily basis, including the cost of cleaning consumables, machinery etc, complete by deploying a team of necessary unskilled but trained cleaning persons during the course of construction and fit out till complete stage, as per instructions & direction of EIC. | Sq m
17.34 | Civil | Dock leveller | Dock Leveller | Dock Leveller of 15 Tonnes capacity with all accessories | Supply and installation of Dock Leveller of 15 Tonnes capacity with all accessories, Deck length-2730, Deck width-2130, Deck height-480 mm, Platform checker plate-8mm thick, Powerpack-01 hp, Bumper-150x100-02 pair or as per approved manufacturer's recommendation, etc. complete and as directed by Engineer-In-Charge. | Nos.
17.35 | Civil | Tarpaulin sheet | Tarpaulin sheet | Cordoning of area by using framework of hard wood | Cordoning of area by using framework of hard wood of size 50mm x 50mm at spacing of 1200mm centre to centre, both horizontally and vertically, for height upto 3.50m, with one face covered with tarpaulin sheet, double skinned, 200 micron thick. etc. complete as directed by EIC. | Sq m
17.36 | Civil | GI sheets | GI corrugated sheets | GI corrugated sheets 2mm or 3mm thick | Providing and fixing GI corrugated sheets 2mm or 3mm thick, at various heights with all fixtures, fastenings, etc. complete. Make: Tata, Jindal or equivalent. | Sqm
17.37 | Civil | GI sheets | Barricading with GI sheets | Barricading with GI sheets | Providing and fixing GI corrugated sheets 2mm or 3mm thick, for barricading, painting with OBD, at various heights with all fixtures, fastenings, etc. complete, as directed by Engineer-In-Charge. Make: Tata, Jindal or equivalent | Sqm
17.38 | C & I | Crane for lifting | crane for lifting heavy equipments | Hiring of crane for lifting heavy equipments | Hiring of crane for lifting heavy equipments like condensers, Chillers, DG, etc., to TERRACE or other levels by using crane from outside the building. Height upto 20mtrs. Placing all heavy equipments as per layout and as directed by Engineer-In-Charge. | Hours
17.39 | Civil | Safety | Fire/ Welding blanket | Fire/ Welding blanket 2.00 metres x 2.00 metres x 0.82mm thickness | Providing and supplying, Fire/ Welding blanket 2.00 metres x 2.00 metres x 0.82mm thickness, 2 side Silicon fiberglass, temperature resistance 950 to 1100 Degree Centigrade, etc. complete, as directed by Engineer-In-Charge. | Sqm
17.4 | C & I | Manpower deployment | Unskilled Labour charges | Unskilled Labour charges | Charges for Supply of unskilled labour Charges for supply of unskilled labour for Supply for of unskilled labour for labour misc work at site. (8 hrs working + 1 hr lunch). | MDY
17.41 | Civil | Welding | Welding work | Welding work to Miscellaneous | Welding work related to Miscellaneous work | LS
17.42 | Civil | Scaffolding | Scaffolding | scaffolding / centering upto 5m in height with all fixtures | Providing and erecting scaffolding / centering upto 5m in height with all fixtures, fastenings, etc. complete, as directed by Engineer-In-Charge. | Cum
17.42.1 |  |  | Scaffolding |  | Metal scaffolding
17.42.2 |  |  | Scaffolding |  | Bamboo scaffolding
[5 empty] | MISCELLANEOUS & JOINERY WORK | [5 empty] | 139746.74
206274.465
Materials Specification: Materials should be as per specified in BOQ & details drawings.
1 | 19mm thick fire retardant (two hour Fire-Retardant) plywood's basic rate consider for 1614.00 / SM, Anchor / Kutty / Century / Green ply - Make
2 | Rest plywood's should as per item no. 1.
3 | Laminate basic cost INR 1325.00/Sheet.
4 | Venner basic cost INR. 1614.00/SQM.
5 | All adhesives should be Pidilite brand.
6 | All hardware's fittings should be as mentioned on BOQ / Equivalent to the mentioned brand.
7 | All glasses and mirror should be branded, like - Saint gobain / BIAL approved.
8 | Aluminium tube - 16 gauge, Jindal / equivalent make.
9 | All hardware fittings should be as per mentioned on BOQ / Equivalent / Branded.
10 | 1st quality old btc wood / selected & approved seasoned american red oak / american ash wood for all wooden work.
11 | Fire-Retardant pu polish as per BIAL Standard Guideline up to 2 hours fire-rated.
12 | MS / SS works with Jindal / Tata make.
13 | SS works with standard grade product and selected and approved high quality 304 grade ss sheet.
14 | All metal works to be carried out as per the BIAL guideline.
15 | Contractor team ahs to study the BIAL Guideline for further queries if any.
16 | All the Workshop Drawings to be prepared by the contracting team, construction can start upon mutual approval.
17 | All the materials has to up to BIAL's Standard as per their Guideline.

## MB N. Miscellaneous
MB Sheet CIVIL MASONRY BOQ OF GULLY KITCHEN - UNIT NO. 3T75-06-T2-BIAL-BENGALURU
SR.NO | Item Description | Unit | No | Length | Breadth | Total Quantity
A | General Site Works
17.1.1 | Wooden Railing | RMT | 1 | 5 |  | 5 | rejected
0
0
17.1.1 | 75mm x 50mm vertical grids at about 400mm | RMT | 5 | 0.72 |  | 3.6
17.1.3 | Wooden Planter Box | NO | 5 |  |  | 5
17.9 | Column guards | RMT | 10 | 1.2 |  | 12
17.19 | Laminated sheet of 1.0 mm thk. | SQMT | 1 | 3.5 | 0.2 | 0.7
|  | SQMT | 1 | 4 | 0.2 | 0.8
|  | SQMT | 1 | 2 | 1.5 | 3
4.5
17.24 | Temporary Flex for Cordoning of area by using wooden framework | SQMT | 1 | 7 | 2.44 | 17.08
|  | SQMT | 1 | 1 | 2.2 | 2.2
19.28

## P.Geotech
FEBRUARY 2020
TRAVEL FOOD SERVICES
BOQ STANDARDISATION, IMPLEMENTATION AND COST CONSULTANCY
SR. NO. | SERVICE / MATERAL CODE | WBS | WBS Level2 | SHORT ITEM DESCRIPTION | PARTICULARS | UOM | Basic Rate of Material | Supply Rate | Fixing Rate | Total Rate (Supply +Fixing) | Total Amount
1 |  | Civil | Geotechnical Investigation |  | Mobilization and demobilisation charges of drilling equipment calyx rig and manpower. | L.S.
2 |  |  |  |  | Cleaning of bushes on way on the way of approaching bore location. | L.S.
3 |  |  |  |  | Drilling in soil and collection of soil samples | RM
4 |  |  |  |  | Drilling hard rock NX/BX size bore hole depth upto 25 mtr depth | RM
5 |  |  |  |  | Drilling hard rock NX/BX size bore hole depth upto 25 mtr to 30 mtr depth. | RM
6 |  |  |  |  | SPT in soil. | each
7 |  |  |  |  | Preservation of soil and rock sample in core box. | each
8 |  |  |  |  | Laboratory Testing of Rock Sample.
[5 empty] | (i) Uniaxial compressive strength | each
[5 empty] | (ii) Natural and dry density and specific gravity | each
[5 empty] | (iii) Water absorption and porosity and moisture content | each
[5 empty] | (iv) Point Load Index | each
9 |  |  |  |  | Laboratory Testing of Soil Samples
[5 empty] | (i) Grain Size Analysis | each
[5 empty] | (ii) Hydrometer Analysis | each
[5 empty] | (iii) Atterberg Limits (liquid limit, plastic limit, shrinkage limit) | each
[5 empty] | (iv) Natural Moisture Content | each
[5 empty] | (v) Specific Gravity and & Bulk Density | each
10 |  |  |  |  | Direct shear test | RO
11 |  |  |  |  | #Chemical Tests (soil) pH, Chloride, Sulphate (water soluble and acid extract) and carbonate content (in some locations also organic content) | each
12 |  |  |  |  | #Chemical Tests (ground water) including in tunnels pH, Chloride, Sulphate (water soluble & acid extract) and carbonate content. | each
13 |  |  |  |  | Preparation and submission of Factual Report giving all the Field and Laboratory Test Results, Graphs, Charts, tables, geo profiles. 3 (three) copies with a soft copy in CD. | LS
NOTE:-
calyx drilling Method of core drilling performed by the rotation of a steel cylinder and cutting with chilled shot, about 2.4 mm diameter, which cuts a formation core. Circulating water carries the cuttings up to a basket-like space at the top of the core barrel. The core is wedged into the barrel and pulled up one barrel-length at a time. Shafts up to 2 m diameter can be drilled, and holes to a depth of more than 300 m.