## Final
|  |  | Genesis Architects Pvt Ltd |  |  |  |  | ARA Designs
| Sno | Description | Service code | Services description | Qty. | UoM | Unit Price Rs. | Services description | Qty. | UoM | Unit Price Rs.
| 1 | Design Consultancy | Type 1 | For Kiosk Model (Upto 200 sqft) | 1 | LS | 200000 | F&B Kiosk upto 250 sqft | 1 | LS | 175000
outlet with seating | 2 |  | Type 2 | For F&B QSR (Stand alone)(600 Sq Ft) | 1 | Sqft | 300 | F&B up to 5000 sqft | 1 | Sqft | 350 | o
| 3 |  | Type 3 | For Retail Store | 1 | Sqft | 175 | F&B above 5000 sqft | 1 | Sqft | 300
| 4 |  | Type 4 | Food Court | 1 | Sqft | 300
Retail & Commercial
[8 empty] | Kiosk upto 250 sqft | 1 | LS | 130000
[8 empty] | up to 5000 sqft | 1 | Sqft | 250
[8 empty] | above 5000 sqft | 1 | Sqft | 200
All rates are excluding GST
Commercial Terms
|  | Order Placement by |  | Semolina Kitchens Pvt Ltd |  |  |  | Semolina Kitchens Pvt Ltd
|  | Out of Pocket Exp. |  | Reimbuserment at actual |  |  |  | Reimbuserment at actual
|  |  |  | Airfare - Economy, Loadging & Boarding and other exp. As per approval by EIC |  |  |  | Airfare - Economy, Loadging & Boarding in 4/5* for principal architech, for associate guest house or 3/4* hotel and other exp. As per approval by EIC
|  | No. of Visits |  | 4 visit/ each project to be approved by EIC, if additional required to be approved by EIC with reasoning |  |  |  | 4 visit/ each project to be approved by EIC, if additional required to be approved by EIC with reasoning
|  |  |  | All visit to be approved by EIC |  |  |  | All visit to be approved by EIC
|  | Mobilization |  | immediately after PO and details requested for pre meeting |  |  |  | immediately after PO and details requested for pre meeting
|  | Completion |  | Design & Tender doc with in 2 months |  |  |  | Design & Tender doc with in 2 months
|  | Payment term |  | 10% after kick off meeting (Site feasibility & Project discussion) - 25% after completion of Concept design - 25% after completion of detailed design - 25% after completion of BOQ & tender document - 15% after closeout or within 6 months from tender document submission whichever is earlier. |  |  |  | 15% after kick off meeting - 25% after completion of Concept design - 25% after completion of detailed design - 25% after completion of BOQ & tender document - 5% after GFC - 5% after closeout or within 6 months from tender document whichever is earlier.
|  |  |  | All payment to release with in 15 days from date of invoice submission |  |  |  | All payment to release with in 15 days from date of invoice submission
|  | Others |  | Any changes after acceptance of any work completed shall be considered as additional work. |  |  |  | Any changes after acceptance of any work completed shall be considered as additional work.
Walk through & 360 degree view not included