## CIVIL M SHEET
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:- 20.03.2024
Project : Duty Free Arrival T3 Lucknow
W/O No :
Name of the Work : CVL INT Duty Free Arrival
FDS MEASUREMENT SHEET
S. No. | BOQItem. Code | Specification | No. | W | H | Total Qty | UOM | Remark
Dismantling
1 | 1A | Dismantling of existing flooring to the mother slab, with the help of permissible tools & during the specifies time of the day so as to minimise the disturbance to the adjacent occupants/users etc
FOH Area
|  | Dismantling of existing flooring | Sqm | 17.9 | 35 | 1 | 626.5
626.5
|  | Total Qty |  |  |  | 626.5
|  | WO Qty |  |  |  | 642 | Sqm
|  | FDS Qty |  |  |  | 626.5
Dismantling
2 | 2A | Demolishing of brick work in cement mortar & cleaning the site for work able
LED Desplay Curve Area
|  | LED Desplay Curve Area | CUM
0
|  | Total Qty |  |  |  | 0
|  | WO Qty |  |  |  | 10 | CUM
|  | FDS Qty |  |  |  | 0
Dismantling
2 | 2B | Demolishing of brick work in cement mortar & cleaning the site for work able
|  | 115mm brick wall | Sqm
|  | Total Qty |  |  |  | 0
|  | WO Qty |  |  |  | 10 | Sqm
|  | FDS Qty |  |  |  | 0
Dismantling
3 |  | Dismantling of existing floor & wall tiles with base mortar & cleaning the site for work able condition.
| 3A | Existing floor & wall
|  | BOH AREA | Sqm | 1 | 25 | 1 | 25
25
|  | Total Qty |  |  |  | 25
|  | WO Qty |  |  |  | 25 | Sqm
|  | FDS Qty |  |  |  | 25
Dismantling
4 |  | Dismantling of existing Door with frame & stacking the same in the premises.
| 4A | Ceilling
|  | Total Qty |  |  |  | 0
|  | WO Qty |  |  |  | 2 | Nos
|  | FDS Qty |  |  |  | 0
Dismantling
5 |  | Dismantling of RCC works in beams, columns, slabs etc. including sub-base, cutting and removal of reinforcement, stacking of serviceable material.
5A
0
|  | Total Qty |  |  |  | 0
|  | WO Qty |  |  |  | 5 | Cum
|  | FDS Qty |  |  |  | 0
Dismantling
6 |  | Disposal of building rubbish / malba / similar unserviceable, dismantled or waste materials by mechanical means, including loading, transporting, unloading to approved municipal dumping ground or as approved by Engineer-in-charge, beyond 50 m initial lead, for all leads and lifts complete.
| 6A | Disposal of building rubbish / malba
|  | BOH Area | Cum | 5.61 | 4.14 | 1 | 23.2254
|  | FOH Area | Cum | 15 | 3.4 | 1 | 51
74.2254
|  | Total Qty |  |  |  | 74.2254
|  | WO Qty |  |  |  | 75 | Cum
|  | FDS Qty |  |  |  | 74.2254
Dismantling
7 |  | Dismantling of existing plaster with P.O.P. & cleaning the site for workable
| 7A | Dismantling of existing plaster Ceilling | Sqm | 2 | 1.24 | 12 | 29.76
|  | Total Qty |  |  |  | 29.76
|  | WO Qty |  |  |  | 30 | Sqm
|  | FDS Qty |  |  |  | 29.76
Dismantling
8 |  | Dismantling of cement concrete flooring & cleaning the site for workable
| 8A | BOH AREA & FOH AREA | Cum | 4.3 | 14 | 2 | 120.4
|  |  | Cum | 0.4 | 18 | 2 | 14.4
|  |  | Cum | 0.4 | 2.1 | 46 | 38.64
173.44
|  | Total Qty |  |  |  | 173.44
|  | WO Qty |  |  |  | 180 | Cum
|  | FDS Qty |  |  |  | 173.44
Cleaning
9 |  | Removing of Cinder filling & cleaning the site for workable
| 9A | Cleaning the site for workable
|  | FOH AREA & BOH AREA | Cum |  |  |  | 2
|  | Total Qty |  |  |  | 2
|  | WO Qty |  |  |  | 2 | Cum
|  | FDS Qty |  |  |  | 2
PCC
10 |  | Providing & laying PCC 1:2:4 ( 1Cement:2 Caorse sand:4 Caorse aggregates 10 mm downgraded) as screed concrete etc complete including centring & shuttering & removal of form work as per drawings & instructions of Project in Charge complete for all leads, lifts, levels, heights .
| 10A | For Raceway | Cum | 0.4 | 11 | 1 | 4.4
|  |  | Cum | 0.4 | 18 | 1 | 7.2
|  |  | Cum | 0.4 | 2.1 | 32 | 26.88
34.08
|  | Total Qty |  |  |  | 34.08
|  | WO Qty |  |  |  | 25.68 | Cum
|  | FDS Qty |  |  |  | 34.08
RCC
11 |  | Providing Providing and laying autoclaved aerated cement blocks masonry with 150mm/230mm/300 mm thick AAC blocks in super structure above plinth level up to floor V level with RCC band at sill level and lintel level with approved block laying polymer modified adhesive mortar all complete as per direction of Engineer-in-Charge. (The payment of RCC band and reinforcement shall be made for seperately)
11A
|  | Total Qty |  |  |  | 0
|  | WO Qty |  |  |  | 13.51 | Cum
|  | FDS Qty |  |  |  | 0
Reinforced cement
12 |  | Reinforced cement concrete work in vertical and horizontal fins individually or forming box louvers, bands, facials and eaves boards above plinth level up to floor five level, excluding the cost of centring , shuttering, finishing and reinforcement with 1:11/2:3 ( 1 cement:11/2 coarse sand:3 Coarse Aggregates) Cement Concrete etc complete as per drawings.
| 12A | FLOORING
|  | Total Qty |  |  |  | 0
|  | WO Qty |  |  |  | 0.55 | Cum
|  | FDS Qty |  |  |  | 0
RCC Work
13 |  | Steel reinforcement for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete above plinth level.
13A
|  | Total Qty |  |  |  | 0
|  | WO Qty |  |  |  | 66.24 | Kg
|  | FDS Qty |  |  |  | 0
PlasteringWork
14 |  | Plastering the exposed surface of AAC block work with Cement plaster 12mm thick in cement mortar 1:3( 1 cement:3fine sand) etc complete for all leads, lifts & heights as per drawings and instructions of Project-in-Charge.
| 14A | FOH AREA | Sqm | 17 | 1 | 1 | 1 | 17
17
|  | Total Qty |  |  |  | 17
|  | WO Qty |  |  |  | 135.09 | Sqm
|  | FDS Qty |  |  |  | 17
| B | DOORS & WINDOWS
17 |  | Providing and fixing 38 mm. thick flush door shutters core of block board construction with well matched 1mm thick laminate sheet of approved make & shade on both faces of shutter including all required fittings such as 4 nos. 125 mm. size SS bearing hinges with necessary SS screws and S.S. fittings including handles, tower bolts, door stopper, rubber buffer,Teak wood lipping etc. complete in all respect.( Basic cost of laminate @ 60/- Sqft) ( Actual size of shutter to be measured & paid ).
| 17A | BOH AREA 1 | 1 | 1200 | 2400 | 2.88
|  | Display Wall D2 | 1 | 1500 | 2400 | 3.6
|  | BOH AREA | 1 | 1200 | 2400 | 2.88
9.36
|  | Total Qty |  |  |  | 9.36
|  | WO Qty |  |  |  | 7.2 | Sqm
|  | FDS Qty |  |  |  | 9.36
| B | DOORS & WINDOWS
18 |  | Providing & fixing Teak wood 1st quality of central province, wood work in frames of doors, windows etc, including fixing the door frames in the opening with fastners etc as per drawing complete, PU polished with polish of approved shade & texture as per sample etc. complete as per instructions of project-in-Charge and drawings..
| 18A | BOH AREA 1 | CUM | 0.1 | 0.1 | 2.4 | 3 | 0.072
0.072
|  | Total Qty |  |  |  | 0.072
|  | WO Qty |  |  |  | 0.06 | Cum
|  | FDS Qty |  |  |  | 0.072
Door Profile
19 |  | Providing & fixing white ash wood moulding of size 100x100mm of profile, pattern, design as per drawing. the moulding shall be fixed in the enterance capsule in circular/semi circular profile etc complete as per drawing & instructions of Project-in-Charge at all heights, levels, lead, lifts etc The vendor is required to get teh sample approved before procuring. Rate includes PU Polishing of approved make etc.
| 19A | BOH AREA Door Profile | RMR | 15 | 1 | 3 | 45
45
|  | Total Qty |  |  |  | 45
|  | WO Qty |  |  |  | 20 | Rmt
|  | FDS Qty |  |  |  | 45
door closer
20 |  | Providing & fixing concealed Hydraulic door closer of approved make including all fixing arrangement complete in all respect.
| 20A | BOH AREA Door | EACH | 4 |  |  | 4
4
|  | Total Qty |  |  |  | 4
|  | WO Qty |  |  |  | 4 | Each
|  | FDS Qty |  |  |  | 4
Door Lock
21 |  | Providing & fixing Door Lock ( Motrise lever one side knob cylinder & one side key finish in rose gold SS ) of approved make including all fixing arrangement complete in all respect. | 2 | Each
| 21A | BHH AREA Door
|  | Total Qty |  |  |  | 2
|  | WO Qty |  |  |  | 2 | Each
|  | FDS Qty |  |  |  | 2
digital panel
22 |  | rrangement , push pull type, heavy duty ss bearing hinges minimum 6 nos. Of minimum 5" high preferably concealed type , handle , locking arrangement etc as per drawing & instructions of Project-in-Charge, all teh materials such as HDHMR FR frame, back panel, providing 7 fixing stoppers at teh back for panel to rest on teh designated position.( PVD coated sheet etc shall be paid under relevant item). providing of heavy duty 360° rotatable CASTORS. MS frame or wooden frame shall be paid separately. The shop drawing shall be prepared by teh vendor for approval for teh said arrangement.The rate is inclusive of making nitches for concealing Locking arrangement strips, hinges etc wherever required and to teh extent required
| 22A |  | Nos
|  | Total Qty |  |  |  | 1
|  | WO Qty |  |  |  | 1 | Each
|  | FDS Qty |  |  |  | 1
VITRIFIED TILES 600X600MM-T2
23 |  | Providing and laying Vitrified tiles in floor in different sizes (thickness to be specified by the manufacturer) with water absorption less than 0.08% and conforming to IS:15622, of approved brand & manufacturer, in all colours and shade, laid on 20 mm thick cement mortar 1:4 (1 cement: 4 coarse sand) jointing with grey cement slurry @3.3 kg/sqm including grouting the joints with white cement and matching pigments etc. The tiles must be cut with the zero chipping diamond cutter only . Laying of tiles will be done with the notch trowel, plier, wedge, clips of required thickness, leveling system and rubber mallet for placing the tiles gently etc complete
| 23A | BOH AREA | SQM | 0.6 | 0.6 | 221 | 79.56
79.56
|  | Total Qty |  |  |  | 79.56
|  | WO Qty |  |  |  | 88.88 | Sqm
|  | FDS Qty |  |  |  | 79.56
VITRIFIED TILES 1200X600MM-T2
24 |  | Providing and laying Vitrified tiles in floor in different sizes (thickness to be specified by the manufacturer) with water absorption less than 0.08% and conforming to IS:15622, of approved brand & manufacturer, in all colours and shade, laid on 20 mm thick cement mortar 1:4 (1 cement: 4 coarse sand) jointing with grey cement slurry @3.3 kg/sqm including grouting the joints with white cement and matching pigments etc. The tiles must be cut with the zero chipping diamond cutter only . Laying of tiles will be done with the notch trowel, plier, wedge, clips of required thickness, leveling system and rubber mallet for placing the tiles gently etc complete
| 24A | FOH AREA | SQM | 1.2 | 0.6 | 820 | 590.4
590.4
|  | Total Qty |  |  |  | 590.4
|  | WO Qty |  |  |  | 295 | Sqm
|  | FDS Qty |  |  |  | 590.4
25 |  | Providing & Fixing 'T' profile made of BRASS Strip of Size 5mm on top x 4mm thick x 25mm deep of approved brand, shade, colour, texture, finish as per sample approved of size OR As per detail dwg., fixed with approved adhesive as per profile & shape in teh flooring as per drawing and instructions of Project-in-Charge.
| 25A | T PROFILE | RMT
|  | Froor Leaf | Rmt | 15.1 |  | 10 | 151
|  | FOH AREA Steep | Rmt | 65 |  | 1 | 65
216
|  | Total Qty |  |  |  | 216
|  | WO Qty |  |  |  | 230.36 | Rmt
|  | FDS Qty |  |  |  | 216
Italian marble as inlay including cutting flooring
26 |  | Italian marble as inlay including cutting flooring done with VITRFIED Tiles as per item no. 5 above, in the desired profile colour, shade, texture ( profile circular , semi circular, parabolic profile etc as per drawing etc complete including disposal of wastage to the dumping ground to be located by the Vendor complete . The rate is inclusive of all wastages which may be there as per drawing. The actual finish area shall be measured for payment i.e. of inlay portion. The measurements shall be done only once even though there may be two or more combinations of tiles to be used as inlay
| 26A | Italian marble as inlay including cutting flooring LEAF | SQM | 2.7 | 1.2 | 10 | 32.4
|  | Total Qty |  |  |  | 32.4
|  | WO Qty |  |  |  | 24.53 | Sqm
|  | FDS Qty |  |  |  | 32.4
18 mm thick Italian Marble stone slab
27 |  | Italian marble as inlay including cutting flooring done with VITRFIED Tiles as per item no. 5 above, in the desired profile colour, shade, texture ( profile circular , semi circular, parabolic profile etc as per drawing etc complete including disposal of wastage to the dumping ground to be located by the Vendor complete . The rate is inclusive of all wastages which may be there as per drawing. The actual finish area shall be measured for payment i.e. of inlay portion. The measurements shall be done only once even though there may be two or more combinations of tiles to be used as inlay
| 27A | 18 mm thick Italian Marble stone slab Leaf | SQM | 2.7 | 1.2 | 10 | 32.4
|  | 18 mm thick Italian Marble stone slab Planter Area | SQM | 0.5 | 29.2 | 1 | 14.6
47
|  | Total Qty |  |  |  | 47
|  | WO Qty |  |  |  | 60.54 | Sqm
|  | FDS Qty |  |  |  | 47
false ceiling tiles 600X600MM
28 |  | stiched double webbed white with 6mm reveal profile (white/black),comprising of main-T runners of size 15x42mm of length 3000 mm, cross - T of size 15x42 mm of length 1200 mm and secondary intermediate cross- T of size 15x42 mm of length 600mm to form grid module of size 600 x 600 mm, suspended from ceiling using galvanised mild steel items (galvanizing @ 80 grams per sqm) i.e. 50 mm long, 8 mmouter diameter M-6 dash fasteners, 6 mm dia fully threaded hanger rod upto 1000 mm length and L-shape level adjuster of size 85x25x2 mm. Galvanised iron perimeter wall angle of size 22x19x0.40 mm of length 3000 mm to be fixed on periphery wall / partition with the help of plastic rawl plugs at 450 mm center to center and 40mm long dry wall S.S screws. The work shall be carried out as per specifications, drawing and as per directions of the Engineer-in-Charge. With 15 mm thick integral densified micro edge light weight Calcium Silicate Tiles
| 28A | BOH AREA | SQM | 0.6 | 0.6 | 221 | 79.56
79.56
|  | Total Qty |  |  |  | 79.56
|  | WO Qty |  |  |  | 80.15 | Sqm
|  | FDS Qty |  |  |  | 79.56
Fire Rated Board Gypsum False Ceiling
29 |  | lange of 20mm and another flange of 30mm and a web of 28mm) screw fixed to brick wall/partition/ hanging with existing ceiling / existing MS framework and suspended GI frame with the help of approved screws at 600mm centers. Then suspending USGBORAL ST-50 fully knurled intermediate section (45mm x 0.90mm thick with two flanges of 15mm each) from the soffit at 1220mm centers with USG B
| 29A | FOH AREA 1 | SQM | 35 | 19 | 1 | 665
|  | FOH AREA Cove | SQM | 1 | 165 | 1 | 165
|  | Less BoH AREA | SQM | -79.5 |  |  | -79.5
750.5
|  | Total Qty |  |  |  | 750.5
|  | WO Qty |  |  |  | 624.64 | Sqm
|  | FDS Qty |  |  |  | 750.5
LACQURED GLASS IN FALSE CEILING
30 |  | LACQURED GLASS IN FALSE CEILING: Providing and fixing false ceiling at all height including providing and fixing of frame work made of special sections, power pressed from M.S. sheets and galvanized with zinc coating of 120 gms/sqm (both side inclusive) as per IS : 277 and consisting of angle cleats of size 25 mm wide x 1.6 mm thick with flanges of 27 mm and 37mm, at 1200 mm centre to centre, one flange fixed to the ceiling with dash fastener 12.5 mm dia x 50mm long with 6mm dia bolts, other flange of cleat fixed to the angle hangers of 25x10x0.50 mm of required length with nuts & bolts of required size and other end of angle hanger fixed with intermediate G.I. channels 45x15x0.9 mm running at the spacing of 1200 mm centre to centre, to which the ceiling section 0.5 mm thick bottom wedge of 80 mm with tapered flanges of 26 mm each having lips of 10.5 mm, at 450 mm centre
| 30A | FOH AREA 1 | SQM | 36 | 1.2 | 1 | 43.2
|  | FOH AREA Round Ceilling | SQM | 2.4 | 2.4 | 1 | 5.76
48.96
|  | Total Qty |  |  |  | 48.96
|  | WO Qty |  |  |  | 38.5 | Sqm
|  | FDS Qty |  |  |  | 48.96
Providing & fixing Leaf made of HDHMR FR Board 12mm thick
31 |  | look 24mm thick from sides, cut out for fixing lights 2nos as per drawing, painted with emulsion paint of approved brand & manufacture, shade, texture etc in three or more coats over a coat of approved wood primer on all sides of leaf (exposed surfaces), over it paisley paint motif shall be painted with approved shade of emulsion paint of approved brand & manufacture , shade, texture as per pattern approved, stencil & sample needs to be got approved before starting teh work at site it shall be only on lower visible side, the leaf shall have MS tubular frame as shown in teh drawings this MS frame shall be paid under separate item
| 31A | FOH AREA Round Ceilling | SQM | 2.7 | 1.2 | 14 | 45.36
45.36
|  | Total Qty |  |  |  | 45.36
|  | WO Qty |  |  |  | 33.6 | Sqm
|  | FDS Qty |  |  |  | 45.36
Smaller leaf cluster area L2
32 |  | look 24mm thick from sides, cut out for fixing lights 2nos as per drawing, painted with emulsion paint of approved brand & manufacture, shade, texture etc in three or more coats over a coat of approved wood primer on all sides of leaf (exposed surfaces), over it paisley paint motif shall be painted with approved shade of emulsion paint of approved brand & manufacture , shade, texture as per pattern approved, stencil & sample needs to be got approved before starting teh work at site it shall be only on lower visible side, the leaf shall have MS tubular frame as shown in teh drawings this MS frame shall be paid under separate item
| 32A | FOH AREA Ceilling Big Leaf | SQM | 2.1 | 2.1 | 3 | 13.23
|  | FOH AREA Ceilling Small Leaf | SQM | 1.2 | 1.2 | 4 | 5.76
18.99
|  | Total Qty |  |  |  | 18.99
|  | WO Qty |  |  |  | 9.66 | Sqm
|  | FDS Qty |  |  |  | 18.99
HDHMR FR 12mm thick board over existing MS Tubular frame
37 |  | B. HDHMR FR 12mm thick board over existing MS Tubular frame with SS screws counter sunk including making necessary openings for wires etc. as per drawings & instructions of Project In Charge.
| 37A | Wall Partation Belt Area | SQM | 35 | 9 | 2 | 630
|  | less Planter Area | SQM | -10 | 4.2 | 2 | -84
|  | Less Coloum | SQM | -1.2 | 9 | 2 | -21.6
|  | Light Box Entry Gate Area No 1 & 2 | SQM | 16 | 0.6 | 2 | 19.2
|  | Wall Partation Entry Gate Out Side | SQM | 13.2 | 5 | 1 | 66
|  | Wall Partation Entry Gate Right Side | SQM | 4.9 | 5 | 1 | 24.5
|  | Light Box Belt Area No 21 | SQM | 12 | 0.56 | 1 | 6.72
|  | Light Box Belt Area No 20 | SQM | 22 | 0.56 | 1 | 12.32
|  | Light Box Belt Area No 19 | SQM | 12 | 0.56 | 1 | 6.72
|  | Light Box Belt Area No 18 | SQM | 10 | 0.56 | 1 | 5.6
|  | Light Box Belt Area No 17 | SQM | 10 | 0.56 | 1 | 5.6
|  | Ovel Shep Entry Gate | SQM | 12 | 5 | 2 | 120
|  | Ovel Shep Entry Gate Grove | SQM | 3.5 | 5 | 2 | 35
|  | Ovel Shep Top Corve Partation | SQM | 1 | 6 | 4 | 24
|  | Wall Partation Entry Gate Left WallTo Boh Area | SQM | 32.7 | 5 | 1 | 163.5
|  | Less Door | SQM | -1 | 2.4 | 1 | -2.4
|  | Wall Partation Boh Area | SQM | 36.9 | 5 | 1 | 184.5
|  | Wall Partation Boh Area Out Side | SQM | 9 | 5 | 1 | 45
|  | Less Door | SQM | -1 | 2.4 | 1 | -2.4
|  | Less D Door | SQM | -1.4 | 2.4 | 1 | -3.36
|  | Skerting Boh Areaa | SQM | 37 | 0.1 | 1 | 3.7
|  | Light Box Boh Area Out Side No 22,23,24 | SQM | 8 | 0.56 | 3 | 13.44
|  | Partation Above Wall Way FOH AREA | SQM | 79.4 | 2.4 | 1 | 190.56
|  | Partation Above Wall Way FOH AREA For SS Sheet | SQM | 79.4 | 0.12 | 2 | 19.056
|  | Skerting FOH Areaa | SQM | 102 | 0.1 | 1 | 10.2
|  | Skerting Belt Areaa | SQM | 35 | 0.1 | 1 | 3.5
|  | Light Box FOH AREA No 14,15,03 | SQM | 1 | 4.2 | 3 | 12.6
|  | Round Glass Partation FOH AREA | SQM | 1 | 8 | 1 | 8
|  | Round Glass Partation FOH AREA Top | SQM | 2.4 | 2.4 | 1 | 5.76
|  | FOH AREA Glass Partation Big | SQM | 36 | 2.4 | 1 | 86.4
|  | Leaf Ply | SQM | 2.7 | 1.2 | 14 | 45.36
1633.476
|  | Total Qty |  |  |  | 1633.476
|  | WO Qty |  |  |  | 2011.35 | Sqm
|  | FDS Qty |  |  |  | 1633.476
Providing & pasting 1mm thick laminate
38 |  | Providing & pasting 1mm thick laminate of approved brand & manufacture, shade, colour over existing 12mm thick HDHMR board as per drawing etc complete
| 38A | Light Box Entry Gate Area No 2 | SQM | 3.2 | 3.56 | 1 | 11.392
|  | Light Box Entry Gate Area No 1 | SQM | 4.1 | 3.56 | 1 | 14.596
|  | Light Box Belt Area No 21 | SQM | 3.9 | 2 | 1 | 7.8
|  | Light Box Belt Area No 20 | SQM | 7.8 | 0.56 | 1 | 4.368
|  | Light Box Belt Area No 19 | SQM | 3.9 | 2 | 1 | 7.8
|  | Light Box Belt Area No 18 | SQM | 2.75 | 2 | 1 | 5.5
|  | Light Box Belt Area No 17 | SQM | 2.75 | 2 | 1 | 5.5
|  | Light Box Boh Area Out Side No 22,23,24 | SQM | 2.463 | 2.1 | 3 | 15.5169
|  | Light Box FOH AREA No 14,15,03 | SQM | 1 | 4.2 | 3 | 12.6
85.0729
|  | Total Qty |  |  |  | 85.0729
|  | WO Qty |  |  |  | 66.35 | Sqm
|  | FDS Qty |  |  |  | 85.0729
HDHMR FR 12mm thick board
39 |  | HDHMR FR 12mm thick board over existing MS Tubular frame with SS screws counter sunk including making necessary openings for wires etc. as per drawings & instructions of Project In Charge. Base frame shall be measured & paid separately be it wooden battens or MS tubular section. LED light with acrylic sheet shall also be measured and paid separately, cavity for fixing teh light is to be provided in teh frame made under this item. ( this stem is to be operated for small width panelling say up to 200mm)
| 39A | Exit Portal Molding | SQM | 21 | 0.3 | 1 | 6.3
|  | Entry Portal Molding patti | SQM | 41 | 0.3 | 1 | 12.3
|  | Door Molding | SQM | 5.2 | 0.3 | 1 | 1.56
|  | Entry Gate Portal | Sqm | 4.5 | 5 | 2 | 45
|  | Entry Portal Molding patti Out Side | SQM | 0.5 | 5 | 16 | 40
105.16
|  | Total Qty |  |  |  | 105.16
|  | WO Qty |  |  |  | 146.09 | Sqm
|  | FDS Qty |  |  |  | 105.16
Additional acrylic sheet member
40 |  | Providing & Fixing additional acrylic sheet member of 300mm wide as additional frame to Entry/Exit gates/doors as per drawing. The 300mm wide panel as additional frame shall consist of 2x3mmthick acrylic transparent sheets of approved brand & manufacture sandwiched together after placing Mangalorian Fabric of approved shade, pattern, design, sealing the ends with approved sealant. Fixing
| 40A | FOH AREAEntry Gate Horizontal | Sqm | 0.3 | 3.9 | 2 | 2.34
|  | FOH AREAEntry Gate Vartical | Sqm | 0.3 | 4.18 | 4 | 5.016
7.356
|  | Total Qty |  |  |  | 7.356
|  | WO Qty |  |  |  | 7.37 | Sqm
|  | FDS Qty |  |  |  | 7.356
Providing & fixing 1mm thick SS304 grade, PVD coated sheet on teh box sections
41 |  | Providing & fixing 1mm thick SS304 grade, PVD coated sheet on teh box sections. The PVD coating shall be minimum 5 micron in thickness of approved shade, colour, texture as per approved sample. The sheet shall be screwed with teh HDHMR FR Board as peroxided under separate item, with SS 304 grade counter sunk screws PVD coated with matching shade etc complete.
| 41A | Partation Above Wall Way FOH AREA For SS Sheet | SQM | 79.4 | 0.2 | 2 | 31.76
|  | Wall Way Joint Patti | SQM | 0.025 | 2.4 | 49 | 2.94
|  | Light Box Belt Area No 21 | SQM | 12 | 0.6 | 1 | 7.2
|  | Light Box Belt Area No 20 | SQM | 20 | 0.6 | 1 | 12
|  | Light Box Belt Area No 19 | SQM | 12 | 0.6 | 1 | 7.2
|  | Light Box Belt Area No 18 | SQM | 10 | 0.6 | 1 | 6
|  | Light Box Belt Area No 17 | SQM | 10 | 0.6 | 1 | 6
|  | Exit Portal Molding | SQM | 20 | 0.4 | 1 | 8
|  | Round Glass Partation FOH AREA | SQM | 8 | 0.6 | 1 | 4.8
|  | FOH AREA Glass Partation Big | SQM | 36 | 0.5 | 2 | 36
|  | Light Box Entry Gate Area No 1 & 2 | SQM | 4 | 0.7 | 2 | 5.6
|  | Light Box Entry Gate Area No 1 & 2 | SQM | 11 | 0.6 | 2 | 13.2
|  | Light Box Boh Area Out Side No 22,23,24 | SQM | 9.5 | 0.6 | 3 | 17.1
|  | Door Wartical | SQM | 2.6 | 0.6 | 2 | 3.12
|  | Ovel Shep Entry Gate inside | SQM | 4.5 | 4.5 | 2 | 40.5
|  | Ovel Shep Entry Gate Out Side | SQM | 5.6 | 4.5 | 2 | 50.4
|  | Ovel Shep Entry Gate Vartical Area | SQM | 2 | 4.5 | 4 | 36
287.82
|  | Total Qty |  |  |  | 287.82
|  | WO Qty |  |  |  | 438.86 | Sqm
|  | FDS Qty |  |  |  | 287.82
Providing & fixing 1mm CNC thick SS304 grade, PVD coated sheet on teh box sections
42 |  | Providing & fixing 1mm thick SS304 grade, PVD coated sheet on teh box sections. The PVD coating shall be minimum 5 micron in thickness of approved shade, colour, texture as per approved sample. The sheet shall be screwed with teh HDHMR FR Board as peroxided under separate item, with SS 304 grade counter sunk screws PVD coated with matching shade etc complete.
| 42A | Partation Above Wall Way FOH AREA | SQM | 79.4 | 1.2 | 1 | 95.28
|  | BOH AREA OUT SIDE | SQM | 2.5 | 1.2 | 4 | 12
107.28
|  | Total Qty |  |  |  | 107.28
|  | WO Qty |  |  |  | 116.4 | Sqm
|  | FDS Qty |  |  |  | 107.28
Painting three or more coats of texture paint ( interior grade)
43 |  | Painting three or more coats of texture paint ( interior grade) including rubbing & repairing with putty for achieving even surface etc with paint of approved brand & manufacture etc complete as per directions of Project in Charge for leads, levels & heights.
| 43A | FOH AREA Ceilling Leaf | SQM | 2.7 | 1.2 | 14 | 45.36
|  | Total Qty |  |  |  | 45.36
|  | WO Qty |  |  |  | 103.88 | Sqm
|  | FDS Qty |  |  |  | 45.36
Painting synthetic enamel paint three or more coats
44 |  | Painting synthetic enamel paint three or more coats to give smooth & even shade with a paint of approved quality, brand & manufacture etc complete as per instructions of Project In Charge
| 44A | FOH AREA Ceilling | SQM | 35 | 17 | 1 | 595
|  | FOH AREA Cove | SQM | 0.5 | 45 | 8 | 180
|  | Wall Partation Belt Area 1 | Sqm | 6.5 | 4.8 | 1 | 31.2
|  | Wall Partation Belt Area 2 | Sqm | 16.9 | 4.8 | 1 | 81.12
|  | Wall Partation Belt Area 3 | Sqm | 16.9 | 4.8 | 1 | 81.12
|  | Wall Partation Belt Area 4 | Sqm | 1.5 | 4.8 | 1 | 7.2
|  | Wall Partation Belt Area 5 | Sqm | 12 | 4.8 | 1 | 57.6
|  | Wall Partation Belt Area In Side 1 | Sqm | 16.9 | 5 | 1 | 84.5
|  | Wall Partation Belt Area In Side 2 | Sqm | 6.5 | 5 | 1 | 32.5
|  | Wall Partation Belt Area In Side 3 | Sqm | 1.5 | 1 | 1 | 1.5
|  | Wall Partation Belt Area Exting Wall | Sqm | 16 | 5 | 1 | 80
|  | Wall Partation Entry Portal Right Wall | Sqm | 4.8 | 5 | 1 | 24
|  | Wall Partation Entry Portal Left Wall | Sqm | 35 | 4.8 | 1 | 168
|  | Wall Partation BOH AREA | Sqm | 38.4 | 4.8 | 1 | 184.32
|  | Wall Partation Above Wall Way | Sqm | 68.4 | 1.3 | 1 | 88.92
1696.98
|  | Total Qty |  |  |  | 1696.98
|  | WO Qty |  |  |  | 1843.6 | Sqm
|  | FDS Qty |  |  |  | 1696.98
Painting three or more coats with emulsion paint of approved brand
45 |  | Painting three or more coats with emulsion paint of approved brand & manufacture, shade, texture etc over a coat of approved wood primer on all exposed surfaces, over it paisley paint motif with a 'dye' shall be painted with approved shade of emulsion paint of approved brand & manufacture , shade, texture as per pattern approved, stencil & sample needs to be got approved before starting the work. The rate is inclusive of all the operations described above for all leads, lifts, heights as per drawings complete.
| 45A | FOH AREA Ceilling | SQM | 1.7 | 25 | 7 | 297.5
|  | FOH AREA Ceilling 2 | SQM | 1.5 | 1.2 | 7 | 12.6
Total Qty
|  | WO Qty |  |  |  | 1843.6 | Sqm
|  | FDS Qty |  |  |  | 0
Fixing arrangements only for chandelier
46 |  | Fixing arrangements only for chandelier of approved design, pattern, size, configuration etc as per sample approved as per directions of Project-in-Charge
| 46A | Entry Gate | Each | 1 | 1 | 1 | 1
|  | Total Qty |  |  |  | 1
|  | WO Qty |  |  |  | 1 | Each
|  | FDS Qty |  |  |  | 1
Height of barricading
47 |  | posts/horizontal members/bracings covered with 1.63mm thick MS sheet. The sheet shall be fixed with 30x5mm MS flat by suitable welding/riveting. The panels shall be made so that gap of 50cm above the ground is available making overall height as 2.5m. MS channel ISLC 75 @ 5.70 kg/m, 50cm long shall be provided at the bottom having oval shaped holes of size 50x25mm at both ends with 50cm long MS angle 40x40x6mm bracing. Suitable arrangement shall be made to fix the
| 47A | ALL AREA Barricading | RMT | 200 | 1 | 1 | 200
|  | Total Qty |  |  |  | 200
|  | WO Qty |  |  |  | 200 | RMT
|  | FDS Qty |  |  |  | 200
POS & TILLS COUNTER
48 |  | Providing & fixing POS / TILLS Counter with Back Unit storage, storage structure Made in 18mm HDHMR Board and finish in 1mm thick Laminate as approved/detail dwg., main counter front will be +150mm high from counter top finish level and curve from one side end as per design / detail dwg., counter Top and front will be finish in Solid acrylic surface, front will be cover with 6mm thick corion cladding in base with SS 304 Grade 1mm thick CNC cut design PVD finish sheet over pasted, storgae will be made in openable shutters with4 no of drawer each pedestial x 2nos in below the front counter and openable shutters, for back storages only openable shutters with complete requiremenst of hardware as per approved makes, cost also include the 100mm PVD finish skirting as per detail drawing.
| 48A | Sale Counter | Each | 1 | 1 | 1 | 1
|  | Total Qty |  |  |  | 1
|  | WO Qty |  |  |  | 1 | Each
|  | FDS Qty |  |  |  | 1
POP Plaster ENTERANCE CAPSULE
48 |  | Providing 10 mm thick plaster of Paris (gypsum anhydrous) ceiling up to a height of 5 m above floor level, over first class kail wood strips 25x6 mm with 10 mm gap in between and reinforced with rabbit wire mesh fixed to GI Frame or wooden frame as per directions of Project-in-Charge
| 48A | Ovel Ceilling | Sqm | 7 | 2 | 1 | 14
|  | Total Qty |  |  |  | 14
|  | WO Qty |  |  |  | 12 | Sqm
|  | FDS Qty |  |  |  | 14
Cornice with Pelmet/Cove above
49 |  | Cornice with Pelmet/Cove above : 115 wide x 100 high or as per detail dwg comple with Pre-cast POP Arc Cornice as per approved design/dwg, fix and pasted on wall/partition with base as per requirements
| 49A | Ovel Ceilling Cove | Rmt | 15 | 1 | 1 | 15
|  | Total Qty |  |  |  | 15
|  | WO Qty |  |  |  | 13 | Rmt
|  | FDS Qty |  |  |  | 15
POP PUNNING
50 |  | POP Punning : Providing & applying Water Resistant and Quick Drying, Non Curable Type of average 12-15 mm thick plaster of Paris and wiremesh at joints of diff. material to the walls and columns in square plumb line and level. The cost to include scraping and removing the existing neeru finish and also the hacking the surface of walls/columns. After leveling, the surfaces to be finished to receive paint . Rate to include provisioning of grooves as per design. The POP puning to be carried out 100mm above the finished ceiling level and not for the area above.
| 50A | Existing Wall | Sqm | 16 | 5 | 1 | 80
|  | BOH AREA | Sqm | 8 | 5 | 1 | 40
120
|  | Total Qty |  |  |  | 120
|  | WO Qty |  |  |  | 258.38 | Sqm
|  | FDS Qty |  |  |  | 120
Curve Threshold/Ledge
52 |  | Curve Threshold/Ledge : Providing & supplying custom made factor finish Linear Curve Threshold/Ledge fix on floor made of MS Tubular frame of secion 25x25mmx1.8mm thick cladded with 8mm flexi ply as per plan design and finish in Marble stone (cost excluded) with size approx 50MM w x 100MM High or as per design/dwg, with made as per the detail and size approved in detail dwg.
| 52A | Cove Planter Area | Rmt | 34.8 | 1 | 2 | 69.6
|  | Total Qty |  |  |  | 69.6
|  | WO Qty |  |  |  | 86.49 | Sqm
|  | FDS Qty |  |  |  | 69.6
Duco / PU Paint
53 |  | Duco / PU Paint : Providing & Applying Duco / PU Paint as per approved color, shade and sample approve by the Architect, base to be prepare on dry surface with smooth / plain with proper sanding with duco / PU patti 3-4 coat and make it smooth to receive the final finish paint with spray machine including base primer complete as the instructuion by the manufacturer or satisfactory level of finish by the Project Incharge.
| 53A | Partation Above Wall Way FOH AREA | SQM | 79.4 | 1 | 1 | 79.4
|  | BOH AREA OUT SIDE | SQM | 2.5 | 1 | 4 | 10
89.4
|  | Total Qty |  |  |  | 89.4
|  | WO Qty |  |  |  | 141.04 | Sqm
|  | FDS Qty |  |  |  | 89.4
SALE COUNTER
54 |  | Last Minute Sale Counter - Providing and fixing LMS Counter made in 18mm thick HDHMR Board structure with shelf, finish in 1mm thick laminate all over with edge finish in match laminate, shelf sytem to be rest on SS 304 grade Pipe with PVD finish color as approved and pipe to be fix in center and cover from bottom to top and overall legth of shelfs as per detail design / drawing., cost include of modesty in base with 100mm high PVD finish SS Skirting with complete requirements.
| 54A | FOH AREA | Each | 2 | 1 | 1 | 2
|  | Total Qty |  |  |  | 2
|  | WO Qty |  |  |  | 2 | Each
|  | FDS Qty |  |  |  | 2
Circular Toy Station Gandola :
55 |  | Circular Toy Station Gandola : P/f Circular Toy station gandola made in 18mm thick HDHMR Board shelf of factory finish with top/bottom/edge finish in 1mm thick laminate as per approved, shelf will be fix on center SS 304 Grade Pole finish in PVD finish color as per approved, cost to include the base modesty with front of 100mm high skirting in SS with PVD finish and complete as per detail drawign.
| 55A | FOH AREA | Each | 1 | 1 | 1 | 1
|  | Total Qty |  |  |  | 1
|  | WO Qty |  |  |  | 1 | Each
|  | FDS Qty |  |  |  | 1
Access Panel Trap Doors
56 |  | Providing Access Panel Trap Doors with not more than 1/16" shadow/gap on finished surfaces. Panel inlay duplicates wall and ceiling specifications to ensure acoustic integrity. Hardware free finish, opens with concealed touch-latches. The panel can be removed completely for full access. Access Panels arrive ready for installation with factory installed gypsum board inlay. Aluminium extrusion with gypsum board installed. Size- 450x450 mm
| 56A | FOH AREA | Each | 4 | 1 | 1 | 4
|  | Total Qty |  |  |  | 4
|  | WO Qty |  |  |  | 4 | Each
|  | FDS Qty |  |  |  | 4
LED Recessed 25W LED, colour temperature of 4000K, Continues U Profile, B = 50mm, H = 35mm.
57 |  | temperature of 4000K, Continues U Profile, B = 50mm, H = 35mm. Recessed with Trim luminaire Slash S with HPE (High-Performance Efficiency) LED (Light Emitting Diode) system power: 24 W / 4 Feet, Luminous flux of luminaire 2640 lm / 4 Feet, Colour temperature of 4000 K, Neutral white, CRI > 80, 230 V constant current driver, 70 % of luminous flux after 50,000 operating hours, Energy-efficient LEDs, Direct light emission, Luminaire profile in aluminium, Polyester powder-white coloured coat applied over a 5- stage pre-treatment, snap-fit satin diffuser for homogenous light distribution, ZHLS (ZERO HALOGEN LOW SMOKE) internal wiring, integral Electronic control gear Protection class I, IP 40, L = 40000 mm, B = 50 mm, H = 35 mm
| 57A | FOH AREA Entry Gate | Rmt | 40 | 1 | 1 | 40
|  | Total Qty |  |  |  | 40
|  | WO Qty |  |  |  | 40 | Each
|  | FDS Qty |  |  |  | 40
LIQUOR WALL BAY
58 |  | created by fixing 12mm thick HDHMR FR Ply of 900x 650mm. The top box shall have wooden battens as detailed for skirting Box at bottom for sturdiness & painted the same way. The front shall have two 6mm thick Acrylic sheets, front one clear & the back milky white(translucent/opaque) of approved brand & manufacture to retain in between advertisement material/display material in the form of paper thin sheet about 1mm thick or so, fixed to teh box with AUTO SNAP CHANNEL with PVDF coated finish of Aluminium metal. the depth of front box( acrylic Sheets) shall be 100mm and shall have all around 100 mm wide 18mm thick HDHMR FR Ply to make the over all thickness 38mm with 1mm laminate (L-02) finish. The box shall have LED Lights of high intensity to glow the advertisement sheet from behind. The box shall be fitted with power point 16 amp & 5 amp switch & socket with appropriate Box
| 58A | FOH AREA | Each | 14 | 1 | 1 | 14
|  | Total Qty |  |  |  | 14
|  | WO Qty |  |  |  | 11 | Each
|  | FDS Qty |  |  |  | 14
Light Box
59 |  | created by fixing 12mm thick HDHMR FR Ply of 900x 650mm. The top box shall have wooden battens as detailed for skirting Box at bottom for sturdiness & painted the same way. The front shall have two 6mm thick Acrylic sheets, front one clear & the back milky white(translucent/opaque) of approved brand & manufacture to retain in between advertisement material/display material in the form of paper thin sheet about 1mm thick or so, fixed to teh box with AUTO SNAP CHANNEL with PVDF coated finish of Aluminium metal. the depth of front box( acrylic Sheets) shall be 100mm and shall have all around 100 mm wide 18mm thick HDHMR FR Ply to make the over all thickness 38mm with 1mm laminate (L-02) finish. The box shall have LED Lights of high intensity to glow the advertisement sheet from behind. The box shall be fitted with power point 16 amp & 5 amp switch & socket with appropriate Box
| 59A | FOH AREA | Each | 17 | 1 | 1 | 17
|  | Total Qty |  |  |  | 17
|  | WO Qty |  |  |  | 4 | Each
|  | FDS Qty |  |  |  | 17
PERFUMES & COSMETICS WALL WAY
60 |  | created by fixing 12mm thick HDHMR FR Ply of 900x 650mm. The top box shall have wooden battens as detailed for skirting Box at bottom for sturdiness & painted the same way. The front shall have two 6mm thick Acrylic sheets, front one clear & the back milky white(translucent/opaque) of approved brand & manufacture to retain in between advertisement material/display material in the form of paper thin sheet about 1mm thick or so, fixed to teh box with AUTO SNAP CHANNEL with PVDF coated finish of Aluminium metal. the depth of front box( acrylic Sheets) shall be 100mm and shall have all around 100 mm wide 18mm thick HDHMR FR Ply to make the over all thickness 38mm with 1mm laminate (L-02) finish. The box shall have LED Lights of high intensity to glow the advertisement sheet from behind. The box shall be fitted with power point 16 amp & 5 amp switch & socket with appropriate Box
| 60 | FOH AREA | Each | 8 | 1 | 1 | 8
|  | Total Qty |  |  |  | 8
|  | WO Qty |  |  |  | 3 | Each
|  | FDS Qty |  |  |  | 8
CONFECTIONERY WALL WAY
| 60A | FOH AREA | Each | 8 | 1 | 1 | 8
|  | Total Qty |  |  |  | 8
|  | WO Qty |  |  |  | 14 | Each
|  | FDS Qty |  |  |  | 8
LIQUER GANDOLA : SIZE 1500x800x1350mm
| 60B | FOH AREA | Each | 5 | 1 | 1 | 5
|  | Total Qty |  |  |  | 5
|  | WO Qty |  |  |  | 4 | Each
|  | FDS Qty |  |  |  | 5
LIQUER GANDOLA : SIZE 1000x800x1350mm
| 60C | FOH AREA | Each | 5 | 1 | 1 | 5
|  | Total Qty |  |  |  | 5
|  | WO Qty |  |  |  | 3 | Each
|  | FDS Qty |  |  |  | 5
PERFUME & COSMETICS GANDOLA SIZE 1000x800x1350mm
| 60D | FOH AREA | Each | 4 | 1 | 1 | 4
|  | Total Qty |  |  |  | 4
|  | WO Qty |  |  |  | 6 | Each
|  | FDS Qty |  |  |  | 4
ELECTRONICS GANDOLA SIZE 1000x900x1350mm
| 60E | FOH AREA | Each | 4 | 1 | 1 | 4
|  | Total Qty |  |  |  | 4
|  | WO Qty |  |  |  | 6 | Each
|  | FDS Qty |  |  |  | 4
WATCHES GANDOLA 1000x450x1150
| 60F | FOH AREA | Each | 3 | 1 | 1 | 3
|  | Total Qty |  |  |  | 3
|  | WO Qty |  |  |  | 4 | Each
|  | FDS Qty |  |  |  | 3
SUN GLASSES GANDOLA 1000x500x1350
| 60G | FOH AREA | Each | 3 | 1 | 1 | 3
|  | Total Qty |  |  |  | 3
|  | WO Qty |  |  |  | 2 | Each
|  | FDS Qty |  |  |  | 3
TOYS GONDOLA
| 60G | FOH AREA | Each | 1 | 1 | 1 | 1
|  | Total Qty |  |  |  | 1
|  | WO Qty |  |  |  | 1 | Each
|  | FDS Qty |  |  |  | 1
CONFECTIONERY GANDOLA
| 60H | FOH AREA | Each | 4 | 1 | 1 | 4
|  | Total Qty |  |  |  | 4
|  | WO Qty |  |  |  | 3 | Each
|  | FDS Qty |  |  |  | 4
SUPERMART GANDOLA
| 60I | FOH AREA | Each | 2 | 1 | 1 | 2
|  | Total Qty |  |  |  | 2
|  | WO Qty |  |  |  | 2 | Each
|  | FDS Qty |  |  |  | 2
LUGGAGE WALL BAY 1000x500x2500mm
| 60J | FOH AREA | Each | 3 | 1 | 1 | 3
|  | Total Qty |  |  |  | 3
|  | WO Qty |  |  |  | 4 | Each
|  | FDS Qty |  |  |  | 3
LUGGAGE GONDOLA 1000X800MM
| 60K | FOH AREA | Each | 1 | 1 | 1 | 1
|  | Total Qty |  |  |  | 1
|  | WO Qty |  |  |  | 1 | Each
|  | FDS Qty |  |  |  | 1
LUGGAGE PODIUM
| 60N | FOH AREA | Each | 1 | 1 | 1 | 1
|  | Total Qty |  |  |  | 1
|  | WO Qty |  |  |  | 1 | Each
|  | FDS Qty |  |  |  | 1
1000x500x700mm FLAT TABLE
| 60M | FOH AREA | Each | 1 | 1 | 1 | 1
|  | Total Qty |  |  |  | 1
|  | WO Qty |  |  |  | 1 | Each
|  | FDS Qty |  |  |  | 1
900x500x600mm FLAT TABLE
| 60 O | FOH AREA | Each | 1 | 1 | 1 | 1
|  | Total Qty |  |  |  | 1
|  | WO Qty |  |  |  | 1 | Each
|  | FDS Qty |  |  |  | 1
| EXTRA | HANDBAG ,HW, SUPERMARCKET , TOYS,TRAVELS,
| 60 P | FOH AREA | Each | 16 | 1 | 1 | 16
|  | Total Qty |  |  |  | 16
|  | WO Qty |  |  |  | 0 | Each
|  | FDS Qty |  |  |  | 16
| EXTRA | HANDBAG ,HW, GANDOLA
| 60 P | FOH AREA | Each | 2 | 1 | 1 | 2
|  | Total Qty |  |  |  | 2
|  | WO Qty |  |  |  | 0 | Each
|  | FDS Qty |  |  |  | 2
| J | Extra Work 3 D Acrylic Letter
Lucknow Duty Free : 50 mm Acrylic Holo Box Letter 3 D With Lit Lasar Cut Lucknow Duty Free PU Painted , As Per Colour
| 1 | FOH Area | Nos | 1
|  | Total Qty |  |  |  | 1
|  | WO Qty |  |  |  | 1 | Each
|  | FDS Qty |  |  |  | 1
| J | Extra Work 3 D Acrylic sandwich
| 2 | Application of 3 mm sandwich acrylic on Departure wall-bay
| 1 | FOH Area | Nos | 17
|  | Total Qty |  |  |  | 64
|  | WO Qty |  |  |  | 17 | Each
|  | FDS Qty |  |  |  | 64
| J | Extra Work 3 D Acrylic sandwich
| 2 | Application of 3 mm sandwich acrylic on Departure Gandola
| 1 | FOH Area | Nos | 15
|  | Total Qty |  |  |  | 63
|  | WO Qty |  |  |  | 15 | Each
|  | FDS Qty |  |  |  | 63

## Estimate Cip Lounge T3 Lucknow
Client : M/s Semolina Kitchen
Project : CIP Lounge Lucknow
W/O No : Date -
Name of the Work : NT Item
Contractor : IMPULSE BRANDING SOLUTIONS
SL.No | Product Name | PARTICULAR | Unit | Qty | Rate | Amount
1 | BTU Meeter | Supply & installation tPrime™ Series 280T-S ULTRASONIC HEAT METERSpire Metering is a global leader in flow and energy management solutions. Through continuous innovation, we transform complex ultrasonic technology into affordable, reliable solutions for accurate flow and energy measurement. As per Deta Sheet | Nos | 1 | 56400 | 56400
2 | Electrical Meeter | Supply & installation Liberty 370 Three-phase, dual-register, switched electricity meter | Nos | 1 | 23500 | 23500
3 | Water Tank | supplier of 200 Litre Plastic Loft Water Tank. We are actively engaged in presenting an exclusive range of Loft 200 Litre Plastic Loft Water Tank. The offered tanks are manufactured using optimum quality plastic and advanced technology by our skilled professionals. | Nos | 1 | 4500 | 4500
4 | WATER SUPPLY | Providing and fixing Chlorinated Polyvinyl Chloride (CPVC) pipes, having thermal stability for hot & cold water supply, including all CPVC plain & brass threaded fittings, including fixing the pipe with clamps at 1.00 m spacing. This includes jointing of pipes & fittings with one step CPVC solvent cement and testing of joints | LS | 1 | 12400 | 12400
5 | Plumbing Material For Kitchen | 2x2 MT | Nos | 2 | 1000 | 2000
|  | 1.5x2 MT | Nos | 2 | 409 | 818
|  | 2x2 Union | Nos | 4 | 350 | 1400
|  | 2x1.25 Union | Nos | 3 | 320 | 960
|  | 2 inch ,T | Nos | 3 | 596 | 1788
|  | Cpvc elbow 2 inch | Nos | 6 | 365 | 2190
|  | GT-T,1/2 inch | Nos | 1 | 240 | 240
|  | 4 inch nippal | Nos | 1 | 540 | 540
|  | 1/2x.75 socket | Nos | 1 | 450 | 450
|  | 4 inch GT nippal | Nos | 1 | 1250 | 1250
|  | Teplan Tape | Nos | 5 | 75 | 375
|  | Angle valve | Nos | 8 | 1250 | 10000
|  | X-Nippal | Nos | 6 | 350 | 2100
|  | 75 inch end cap cpvc | Nos | 4 | 75 | 300
|  | .75 inch T cpvc | Nos | 4 | 150 | 600
|  | Cpvc plane elbow | Nos | 4 | 165 | 660
|  | brash elbow | Nos | 4 | 430 | 1720
|  | 1/2 inch cpvc elbow | Nos | 4 | 175 | 700
|  | 1/2 inch T cpvc | Nos | 4 | 150 | 600
|  | 1/2 inch socket | Nos | 4 | 200 | 800
|  | 1/2 to .75 T | Nos | 4 | 210 | 840
|  | 1/2 to .75 socket | Nos | 4 | 239 | 956
|  | 20 mm CPVC pipe | Rmt | 5 | 320 | 1600
|  | 18 mm CPVC pipe | Rmt | 5 | 320 | 1600
|  | 40 mm CPVC pipe | Rmt | 5 | 540 | 2700
|  | sink mixer | Nos | 3 | 5460 | 16380
|  | Installation Charges | Ls | 1 | 17500 | 17500
|  | Total |  |  |  | 167867
|  | GST@18% |  |  |  | 30216.06
|  | Net Total |  |  |  | 198083.06