## SUMMARY
| DATE | 2023-10-31
SL NO | BILLING DETAILS | DAIVIK (Descope) | TFS | TOTAL | Purchase proposal(TFS scope)
A | BILLING 1 | 243691.8708 | 44864 | 288555.8708 | 44864
B | BILLING 2 | 211017.2249 | 170852.5 | 381869.7249 | 120452.5
C | BILLING 3 | 34990.5151 | 110232.5862 | 145223.1014 | closure post project clarification
| GRAND TOTAL | 489699.6108 | 325949.0862 | 815648.6971

## BILLING 1
NAME OF THE PROJECT |  | JAMIE'S PIZZERIA
SHAH ENTERPRISES
SUMMARY OF TILES WORK
[6 empty] | TFS |  |  | DAIVIK
Sr. No. | Item Description | QTY | UNIT | RATE | AMOUNT | Qty | Rate | Amount | Qty | Rate | Amount
1 | GREEN TILES ( 300 X 100 ) | 29.243 | SQ. M. | 1291.68 | 37772.5982 |  |  | 0 | 29.243 | 1291.68 | 37772.5982
2 | WHITE TILES ( 300 X 600 ) | 57.583 | SQ. M. | 699.66 | 40288.5218 |  |  | 0 | 57.583 | 699.66 | 40288.5218
3 | PINK TILES ( 100 X 100 ) | 8.2 | SQ. M. | 1291.68 | 10591.776 |  |  | 0 | 8.2 | 1291.68 | 10591.776
4 | FLOOR TILES ( 600 X 600 ) | 11.12 | SQ. M. | 699.66 | 7780.2192 |  |  | 0 | 11.12 | 699.66 | 7780.2192
5 | FLOOR TILES ( 1200 X 600 ) | 72.46 | SQ. M. | 699.66 | 50697.3636 |  |  | 0 | 72.46 | 699.66 | 50697.3636
6 | KOTA STONE 4 SIDE CUTTING & FITTING | 59.6355 | SQ. M. | 1184 | 70608.432 |  |  | 0 | 59.6355 | 1184 | 70608.432
7 | KOTA SKIRTING CUTTING, CHAMFERING, POLISHING & FIXING | 76.1 | RMT. | 393.6 | 29952.96 |  |  | 0 | 76.1 | 393.6 | 29952.96
8 | CHAMBER INSIDE FINISH TILE WORK & SS JAIL FITTING 300 X 300 DEPTH 100mm | 3 | NOS | 3000 | 9000 |  |  | 0 | 3 | 3000 | 9000
9 | CHAMBER INSIDE FINISH TILE WORK & SS JAIL FITTING 300 X 600 DEPTH 100mm | 2 | NOS | 5000 | 10000 |  |  | 0 | 2 | 5000 | 10000
10 | SS CORNER GUARD ( 600 X 600 ) | 28.04 | RMT. | 1600 | 44864 | 28.04 | 1600 | 44864 |  | 1600 | 0
[8 empty] | 0 |  |  | 0
[5 empty] | 311555.8708 |  |  | 44864 |  |  | 266691.8708
A | MATERIAL BILL |  |  |  | 77000 |  |  | 0 |  |  | 77000
B | TOTAL |  |  |  | 388555.8708 |  |  | 44864 |  |  | 343691.8708
C | Less: payment received |  |  |  | 100000 | [5 empty] | 100000
GRAND TOTAL ( A + B + C ) |  |  |  |  | 288555.8708 |  |  | 44864 |  |  | 243691.8708

## BILLING 2
|  |  |  | Date | 45188 | TFS |  |  | DAIVIK |  |  | Proposed | Purchase remark
SL NO | DESCRIPTION OF WORK | UNIT | QTY | RATE | AMOUNT | QTY | RATE | AMOUNT | QTY | RATE | AMOUNT | Amount
1 | Angel Cock Providing & Fixing | nos | 28 | 3350 | 93800 | 28 | 2100 | 58800 | 28 | 1250 | 35000 | 35000 | Confirmation required from project team on whether its SITC or supply only Make & invoice required as there is huge rate difference
2 | Sink Cock single Liver Providing & Fixing | nos | 2 | 4800 | 9600 | 2 | 3950 | 7900 | 2 | 850 | 1700 | 1700
3 | Sink Cock Double Liver Providing & Fixing | nos | 4 | 6800 | 27200 | 4 | 5950 | 23800 | 4 | 850 | 3400 | 3400 | Confirmation required from project team on whether its SITC or supply only Make & invoice required as there is huge rate difference
4 | Conection Pipe Providing & Fixing | feet | 45 | 650 | 29250 | 45 | 650 | 29250 |  |  | 0 | 29250 | Confirmation required from project team on whether its SITC or supply only Make & invoice required as there is huge rate difference
5 | CP Hex Nipple Providing & Fixing | nos | 9 | 470 | 4230 | 9 | 470 | 4230 |  |  | 0 | 4230
6 | Waste Pipe Providing & Fixing | feet | 12 | 80 | 960 | 12 | 80 | 960 |  |  | 0 | 960
7 | 38 X 1/2, CP Bush Providing & Fixing | nos | 1 | 430 | 430 | 1 | 430 | 430 |  |  | 0 | 430
8 | Grittings Jali Providing & fixing | nos | 5 | 1200 | 6000 |  |  | 0 | 5 | 1200 | 6000
9 | Pree Rines Installation only | nos | 1 | 2500 | 2500 | 1 | 2500 | 2500 |  |  | 0 | 2500
10 | Grees trap Installation only | nos | 2 | 3500 | 7000 | 2 | 3500 | 7000 |  |  | 0 | 7000
11 | Foot operated installation only | nos | 1 | 450 | 450 | 1 | 450 | 450 |  |  | 0 | 450
12 | UPVC pipe for drain line 50mm dia Providing & Fixing | feet | 13.5 | 345 | 4657.5 | 13.5 | 345 | 4657.5 |  |  | 0 | 4657.5
13 | Union joint of 50mm dia | nos | 7 | 855 | 5985 | 7 | 855 | 5985 |  |  | 0 | 5985
14 | T 50mm | nos | 2 | 450 | 900 | 2 | 450 | 900 |  |  | 0 | 900
15 | Elbow 50mm | nos | 15 | 550 | 8250 | 15 | 550 | 8250 |  |  | 0 | 8250
16 | FTA 50mm | nos | 4 | 385 | 1540 | 4 | 385 | 1540 |  |  | 0 | 1540
17 | MTA 50mm | nos | 4 | 425 | 1700 | 4 | 425 | 1700 |  |  | 0 | 1700
18 | CPVC 20mm pipe Providing & Fixing | feet | 18 | 283 | 5094 |  |  | 0 | 18 | 283 | 5094
19 | WATER METER SUPPLY &FIXING | NOS | 0 | 8500 | 0 |  |  | 0 | 0 |  | 0
A | PLUMBING WORK TOTAL |  |  |  | 209546.5 |  |  | 158352.5 |  |  | 51194
1 | BAR Counter Front area Dado Tile fixing | Sqmtr | 8.8755 | 1291 | 11458.2249 | 8.8755 |  | 0 | 8.8755 | 1291 | 11458.2249
2 | WEBER Tile Adhesive Chemical | Kg | 60 | 325 | 19500 | 60 |  | 0 | 60 | 325 | 19500
3 | Grout Providing & Filling | Kg | 30 | 120 | 3600 | 30 |  | 0 | 30 | 120 | 3600
4 | Water Proofing work for chamber | nos | 5 | 2500 | 12500 | 5 | 2500 | 12500 |  |  | 0 | 12500
B | WALL DADO TILING WORK TOTAL |  |  |  | 47058.2249 |  |  | 12500 |  |  | 34558.2249
22 | Armstrong Ceiling work installation only | sqft | 699 | 35 | 24465 | 699 |  | 0 | 699 | 35 | 24465
C | CEILING WORK TOTAL |  |  |  | 24465 |  |  | 0 |  |  | 24465
23 | Manpower providing | pax | 84 | 1200 | 100800 |  |  | 0 | 84 | 1200 | 100800
D | MANPOWER TOTAL |  |  |  | 100800 | 0 | 0 | 0 |  |  | 100800
[8 empty] | 0 | 0 |  | 0
| TOTAL(A+B+C+D) |  |  |  | 381869.7249 | 0 | 0 | 170852.5 | 0 | 0 | 211017.2249 | 120452.5
[8 empty] | 0 | 0 |  | 0
| GRAND TOTAL |  |  |  | 381869.7249 |  |  | 0 | 0 |  | 0

## BILLING 3
JAMES PIZZARIES | [7 empty] | DATE- | 45230
Sr.No | Descripition | NOS | LENGTH | BREADTH | HEIGHT | UNIT | QTY | PRICE | AMOUNT | TFS | DAIVIK | Remarks (RS) | Purchase Remark
SNAG WORKS
1 | BrokenTile 600X300 Fixing | lumpsum | [5 empty] | 2500 | 2500 |  | 2500
2 | Kota cutting and laying as per requirement@cold room entrance | 1 | 1450 | 30 |  | Rmtr | 1.45 | 5412 | 7847.4 | 7847.4 |  | New requirement
3 | SS Door skirting providing and fixing | 1 | 860 | 220 |  | Sqmtr | 0.1892 | 13450 | 2544.74 |  | 2544.74
4 | SS sheet Providing & fixing over wooden partition near pizza oven both side and top | 1 | 1960 | 960 |  |  | 1.8816
|  | 1 | 1730 | 965 |  |  | 1.6695
|  | 1 | 1960 | 175 |  |  | 0.343
[6 empty] | Sqmtr | 3.8941 | 13450 | 52374.9725 | 52374.9725 |  | Daivik already completed veneer work. This was later added. | The description of work & if this is veneer work then basic rate for same is missing
5 | Store Room wooden boxing for wire pasted white Laminate over it | 1 | 2900 |  |  | Rmtr | 2.9 | 3300 | 9570 | 9570 |  | Not in Daivik scope
6 | Front Logo façade back side texture retouching | 1 | 1730 | 965 |  | Sqmtr | 1.6695 | 538 | 898.1641 |  | 898.1641
7 | Service Counter-1 Front door both side polish | 2 | 1250 | 800 |  | Sqmtr | 2 | 2690 | 5380 |  | 5380
8 | Sofa Glass wooden beeding fixing | 1 | 1050 |  |  | Rmtr | 1.05 | 264 | 277.2 |  | 277.2
9 | Vertical wall partition wooden cladding filling in lower side | lumpsum | [5 empty] | 2500 | 2500 |  | 2500
10 | Service Counter-2 Front door both side polish | 2 | 960 | 820 |  | Sqmtr | 1.5744 | 2690 | 4235.136 |  | 4235.136
11 | Water Meter installation | lumpsum | [5 empty] | 10000 | 10000 |  | 10000
12 | SS Sheet providing &fixing near Basin | 1 | 1500 | 530 |  | Sqmtr | 0.795 | 13450 | 10692.75 | 10692.75 |  | not in Daivik scope
13 | SS sheet Providing & fixing for guarding wire near oven | 1 | 1965 | 135 |  | Sqmtr | 0.26527 | 13450 | 3567.9488 | 3567.9488 |  | not in Daivik scope
14 | DB boxing having 1 door with 2 hinges and 1 push magnet | 1 | 1525 | 480 |  |  | 0.732
|  | 1 | 1525 | 410 |  |  | 0.62525
[6 empty] | Sqmtr | 1.3573 | 16140 | 21906.015 | 21906.015 |  | not in Daivik scope
15 | Anti Skid sticker providing and fixing | 1 | 2000 |  |  | Rmtr | 2 | 1155 | 2310 | 2310 |  | Not in Daivik scope
16 | Radium Sticker providing and fixing | 1 | 900 |  |  |  | 0.9
|  | 1 | 800 |  |  |  | 0.8
[6 empty] | Rmtr | 1.7 | 1155 | 1963.5 | 1963.5 |  | Not in Daivik scope
17 | 100mm height Fluted Glass Providing & installstion | 1 | 420 |  |  |  | 0.42
|  | 1 | 865 |  |  |  | 0.865
|  | 1 | 1380 |  |  |  | 1.38
|  | 1 | 880 |  |  |  | 0.88
|  | 1 | 350 |  |  |  | 0.35
[6 empty] | Rmtr | 3.895 | 1485 | 5784.075 |  | 5784.075
18 | Black paint on front façade both side | 2 | 1000 |  |  |  | 2
|  | 2 | 1200 |  |  |  | 2.4
[6 empty] | Rmtr | 4.4 | 198 | 871.2 |  | 871.2
TOTAL | [8 empty] | 145223.1014 | 110232.5862 | 34990.5151 | 0
GRAND TOTAL | [8 empty] | 145223.1014

## MEASUREMENT SHEET-1
JAMES PIZZARIES
Sr.No | Descripition | LENGTH | BREADTH | HEIGHT | QTY
PLUMBING
A | CP FITTING
1 | Angel Cock |  |  |  | 28
2 | Sink Cock single Liver |  |  |  | 2
3 | Sink Cock Double Liver |  |  |  | 4
4 | Conection Pipe 3 ft |  |  |  | 15
5 | CP Hex Nipple |  |  |  | 9
6 | Waste Pipe |  |  |  | 4
7 | 38 X 1/2, CP Bush |  |  |  | 1
8 | Grittings Jali |  |  |  | 5
9 | Pree Rines only Installation |  |  |  | 1
10 | Gris trape only Installation |  |  |  | 2
B | UPVC
1 | UPVC Pipe |  |  |  | 4.5 Mtr
2 | Unoin 50mm |  |  |  | 7
3 | Tee 50mm |  |  |  | 2
4 | Albo 50mm |  |  |  | 15
5 | FTA 50mm |  |  |  | 4
6 | MTA 40mm |  |  |  | 4
C | CPVC
1 | CPVC 20mm Pipe |  |  |  | 6 Mtr
DADO WORK
1 | Counter Front area Dado Tile fixing | 5.91 |  | 0.97 | 5.7327
|  | 0.77 |  | 0.83 | 0.6391
|  | 2.58 |  | 0.97 | 2.5026
[5 empty] | 8.8744 | SQMTR
ARMSRONG CELLING WORK
A | Kitchen inside storage | 5.92 | 2.12 |  | 12.5504
| LESS | -0.22 | 0.8 |  | -0.176
| Emergency Exit Oppsite area celling | 1.1 | 1.28 |  | 1.408
| Dish wash area oppsite | 4.35 | 2.15 |  | 9.3525
| Dish wash entry door upward celling | 0.63 | 0.96 |  | 0.6048
| Counter Area | 8.18 | 2.47 |  | 20.2046
| Counter Area Reworked 2 times | 4.75 | 2.47 |  | 11.7325
| Liqure Store room inside | 1.43 | 1.06 |  | 1.5158
B | Live Kitchen Entry | 2.67 | 3.33 |  | 8.8911
| Less Oppset | -1.44 | 1.26 |  | -1.8144
[5 empty] | 64.2693 | SQMTR
MANPOWER DETAILS
|  | No of labour | Attandance |  | TOTAL
2023-08-12 | CARPENTER | 5 | 2 |  | 10
2023-08-13 | CARPENTER | 6 | 1 |  | 6
2023-08-14 | CARPENTER | 9 | 3 |  | 27
2023-08-15 | CARPENTER | 8 | 1 |  | 8
2023-08-16 | CARPENTER | 6 | 2 |  | 12
2023-08-17 | CARPENTER | 4 | 2 |  | 8
2023-08-18 | CARPENTER | 2 | 3 |  | 6
2023-08-18 | CARPENTER | 1 | 2 |  | 2
2023-08-18 | CARPENTER | 1 | 1 |  | 1
2023-08-19 | CARPENTER | 4 | 1 |  | 4
[5 empty] | 84 | PAX

## MEASUREMENT SHEET-2
JAMES PIZZARIES
Sr.No | Descripition | NOS | LENGTH | BREADTH | HEIGHT | UNIT | QTY
SNAG WORKS
1 | BrokenTile 600X300 Fixing | 1
2 | Kota cutting and laying as per requirement@cold room entrance | 1 | 1450 | 30
3 | SS Door skirting providing and fixing | 1 | 860 | 220 |  | Sqmtr | 0.1892
4 | SS sheet Providing & fixing over wooden partition near pizza oven both side and top | 1 | 1960 | 960 |  |  | 1.8816
|  | 1 | 1730 | 965 |  |  | 1.6695
|  | 1 | 1960 | 175 |  |  | 0.343
[6 empty] | Sqmtr | 3.8941
5 | Store Room wooden boxing for wire | 1 | 205 | 75 | 2900 | Sqmtr | 1.0295
6 | Front Logo façade back side texture retouching | 1 | 1730 | 965 |  | Sqmtr | 1.6695
7 | Service Counter-1 Front door both side polish | 2 | 1250 | 800 |  | Sqmtr | 2
8 | Sofa Glass wooden bit fixing | 1 | 1050 |  |  | Rmtr | 1.05
9 | Vertical wall partition wooden cladding filling in lower side | 1
10 | Service Counter-2 Front door both side polish | 2 | 960 | 820 |  | Sqmtr | 1.5744
11 | Water Meter installation | 1
12 | SS Sheet providing &fixing near Basin | 1 | 1500 | 530 |  | Sqmtr | 0.795
13 | SS sheet Providing & fixing for guarding wire near oven | 1 | 1965 | 135 |  | Sqmtr | 0.26527
14 | DB boxing having 1 door with 2 hinges and 1 push magnet | 1 | 1525 | 480 |  | Sqmtr | 0.732
|  | 1 | 1525 | 410 |  |  | 0.62525
[6 empty] | Sqmtr | 1.3573
15 | Anti Skid sticker providing and fixing | 1 | 2000 |  |  | Rmtr | 2
16 | Radium Sticker providing and fixing | 1 | 900 |  |  |  | 0.9
|  | 1 | 800 |  |  |  | 0.8
[6 empty] | Rmtr | 1.7
17 | 100mm height Fluted Glass Providing & installstion | 1 | 420 |  |  |  | 0.42
|  | 1 | 865 |  |  |  | 0.865
|  | 1 | 1380 |  |  |  | 1.38
|  | 1 | 880 |  |  |  | 0.88
|  | 1 | 350 |  |  |  | 0.35
[6 empty] | Rmtr | 3.895
18 | Black paint on front façade both side | 2 | 1000 |  |  |  | 2
|  | 2 | 1200 |  |  |  | 2.4
[6 empty] | Rmtr | 4.4