## REPAIRING WORK BOQ
S.No. | Nature of work | Unit | Qty as per Site | Rate | Amount | TFS Rate | TFS Amount | Remarks
1 | Grid CELING LIGHT PROVIDING AND FIXING (600X600) GRID.(1year warrenty) | Nos | 6 | 2850 | 17100 | 2850 | 17100 | ok
| Bikaner |  |  |  | 0
2 | BIKANER KITCHEN & BARBEQUE ALL WALL TILE GROUTING. | SQFT | 100 | 6 | 600 | 6 | 600 | ok
3 | HOOD DUCT CONNECTION FOR FRESH AIR (HOOD SIZE 6'). Hood connection -7000 +travelling 3600 + fooding 1000 (11600*15% margin 1750=13340/2=6670 | Nos | 2 | 6670 | 13340 | 3500 | 7000 | Quotation rate 3500/nos
4 | OGT CONNECTION WITH 3 SINK FITTINGS. | Nos | 1 | 4000 | 4000 | 4000 | 4000 | ok
5 | 3 SINK HANGING WITH FITTINGS AND DRAIN CONNECTION. | Nos | 1 | 2500 | 2500 | 2500 | 2500 | ok
| Bikaner |  |  |  | 0 |  | 0
6 | SINK DARIN COONNECTION WITH WASTE PIPE . |  |  |  | 0 |  | 0
| Barbeque | Nos | 2 | 1250 | 2500 | 500 | 1000 | ok
| Gianis | Nos | 1 | 1250 | 1250 | 500 | 500 | ok
[5 empty] | 0 |  | 0
7 | WATER INLET CONNECTION WITH PIPING FOR BARBEQUE SINK. (WITH 40 RFT PIPE. | Nos | 1 | 3500 | 3500 | 3500 | 3500 | ok
8 | ONLY INSTALLATION OF CORION PATTI P/F AND FITTING | RFT | 5 | 300 | 1500 | 300 | 1500 | ok
| Bikaner |  |  |  | 0 |  | 0
9 | ALL CORNER GUARD SILICON IN BIKANER STORE SOMETHING. | RFT | 1508.8 | 29 | 43755.2 | 25 | 37460.88 | ok
10 | ALL BIKANERKITCHEN FLOOR CORNER GROUTING. | LS | 1 | 3000 | 3000 | 3000 | 3000 | ok
11 | BIKANER AND BARBEQUE KITCHEN AREA WALL TILE CHANGE (P/F) SOMETHING. (2X1) | NOS | 15 | 375 | 5625 | 375 | 5625 | 2' x 2' tile, refixing rate is 375/tile, ok
| Barbeque |  |  |  | 0 |  | 0
12 | FLOOR KOTA CHANGE IN BIKANER AND BARBEQUE FLOOR. |  |  |  | 0 |  | 0
| Barbeque | NOS | 6 | 450 | 2700 | 450 | 2700 | ok
| Bikaner Inside | NOS | 17 | 450 | 7650 | 450 | 7650 | ok
| Bikaner Gallery | NOS | 8 | 450 | 3600 | 450 | 3600 | ok
13 | GRANITE MOLDING FIXING DOORFRAME SOMETHING. | RFT |  | 65 | 0 |  | 0
| Bikaner |  | 19 | 120 | 2280 | 120 | 2280
16 | WALL TILE CHANGE IN GIANIS COUTER .(8 +23) | NOS | 20 | 375 | 7500 | 375 | 7500 | ok
17 | MOP SINK DRAIN LINE REPAIRING AND COUNTER HOLE FILLING IN GIANIS MOP SINK AREA. | NOS | 1 | 2000 | 2000 | 2000 | 2000 | ok
18 | CEILING CRACK REPAIRING AND CEILING PAINT IN GIANIS CEILING. | SQFT | 96 | 50 | 4800 | 50 | 4800 | ok
19 | RED PAINT IN GAINIS SWING COUNTER DOOR AREA. |  |  |  | 0 |  | 0
| Green paint in Barbique | LS | 1 | 750 | 750 | 750 | 750 | ok
| gianis | LS | 1 | 750 | 750 | 750 | 750 | ok
[5 empty] | 0 |  | 0
20 | ALL KOTA FLOOR REPAIRING AND GROUTING IN BIKANER AND BABEQUE FLOOR. | LS |  | 5000 | 0 |  | 0
22 | ALL DRAIN CHAMBER GRID SS JALI LEVELING IN BIKANER AND BARBEQUE (1'X1'). (NEW LOCATION ) | NOS |  | 1050 | 0 |  | 0
| Barbeque | NOS | 2 | 1050 | 2100 | 1050 | 2100 | ok
| Gianis | NOS | 1 | 1050 | 1050 | 1050 | 1050 | ok
| Bikaner | NOS | 3 | 1050 | 3150 | 1050 | 3150 | ok
[5 empty] | 0 |  | 0
23 | BIKANER COUNTER GRANITE SKINTING PROVIDING AND FIXING. | RFT |  | 400 | 0 |  | 0
24 | ALL BIKANER WALL TILE CEMAGE TILE PROVIDING AND FIXING. | NOS | 138 | 375 | 51750 | 375 | 51750 | 2' x 2' tile, refixing rate is 375/tile, ok
30 | Ducting Work Removal | NOS | 5 | 2250 | 11250 | 2250 | 11250 | ok
31 | P/F Duct | NOS | 5 | 14500 | 72500 | 14500 | 72500 | ok
32 | Wooden Door Moulding with Polish |  |  |  | 0 |  | 0
| Bikaner | Rft | 105 | 65 | 6825 | 65 | 6825 | ok
| Office Door | Rft | 70 | 65 | 4550 | 65 | 4550 | ok
33 | Grill in Bikaner | nos | 2 | 1150 | 2300 | 1150 | 2300 | ok
34 | Grill in Barbique | nos | 1 | 1150 | 1150 | 1150 | 1150 | ok
35 | Collar | nos | 3 | 2850 | 8550 | 2850 | 8550 | ok
36 | Door Bend In Barbeque | nos | 2 | 850 | 1700 | 850 | 1700 | ok
|  |  |  | Total | 297575.2 |  | 282690.88
|  |  | GST |  | 53563.536 |  | 50884.3584
|  |  | G.Total |  | 351138.736 |  | 333575.2384