## Extra item Tracker
TFS Taco Bell, T1 Delhi
EXTRA ITEMS LIST
Negotitated rates 24 -May
Sr. No | Description of Extra Items | Unit | Appox Qty | Rate | Amount | Rate | Amount | Reason for Extra Item | Approval Status | Projects Commnets | Projects Commnets 20th May | Purchase Remarks
1 | Supply&installation of S.S Grating size,( 600mm x 600mm,900mm*300mm,560mm*300mm) in 16 swg 25mm x25mm Square Pipe around the Frame and 20mmX 20mm Square pipe in center of frame with SS closed tray (304 SWR). Complete as per architectural detail drawing & Site Engineer's instruction. (100 mm Dia S.S 304 grade finish unions reducers/coupling or 75mm Dia S.S 304 grade finish unions reducers/coupling or 50mm Dia S.S 304 grade finish unions reducers/coupling) | LS | 1 | 171896.25 | 171896.25 | 171896 | 171896 | Extra requirement raised by GMR and TFS team during the execution |  | Why vendor is building extra item it was part of orginal BOQ | Items approved please close commerical | Approved with Back rates provided for Elite steel work
2 | Copper pipes and tubes shall be hand tempered conforming to requirements of EN 1057 ( formerly BS 2871) Table X , half and the fittings shall confirm the EN-1254-I ( Formerly BS 864: part-02). The fittings shall be end feed capillary fittings within wall/ceiling / floor including cutting & chasing the wall/ floor, jointing, making connection to fixtures, equipment and piping with purposes made connectors, etc. including insulation of closed cell elastomeric nitrile rubber. thermal conductivity of elastometric nitrile rubber shall not exceed 0.038w/m deg K. The insultaion should have fire performance and thickness of nitrile rubber should be 9mm (for hot water piping) | rft | 50 | 1751.45 | 87572.5 | 1550 | 77500 | Extra requirement raised by GMR and TFS team during the execution |  | Qty is , ok Purchase to close commerical | Qty is , ok Purchase to close commerical | Final rates negotiated to 1550
3 | Providing and fixing Elect Pannel as per sld | Nos | 1 | 181125 | 181125 | 181125 | 181125 | AS PER DRAWING NOT IN PO | RATE ALREADY APPROVED ON Email dated 29-04-2024 by beenu ji | Qty is , ok Purchase to close commerical | Qty is , ok Purchase to close commerical | Rates Approved & verified with BBN energy system Quotation 1.59 Lacs
4 | MS Structure | Kg | 1200 | 175 | 210000 | 0 | 0 | Additional work | RATE APPROVED by Beenu ji on Call | Already PO Issued | Already PO Issued | PO already issued
5 | DMB | sft | 16.25 | 1115.73 | 18130.6125 | 1115.73 | 18130.6125 | AS PER DRAWING NOT IN PO |  | Qty is , ok Purchase to close commerical | Qty is , ok Purchase to close commerical | Approved
6 | 6mm Ply for floor protection | sqft | 800 | 37.03 | 29624 | 37.03 | 29624 | Floor protection instructed by TFS team |  | Qty is , ok Purchase to close commerical | Qty is , ok Purchase to close commerical | Rates Approved,Basic price Rs22/Sq ft checked with Invoice
7 | SS frame for Trench (150 rft approx) | job | 150 | 224.825 | 33723.75 | 225 | 33750 | Extra requirement raised by GMR and TFS team during the execution |  | Qty is , ok Purchase to close commerical | Qty is , ok Purchase to close commerical
8 | Fire Rated Paint on MS Frame | sft | 712.5 | 8 | 5700 | 0 | 0 | AS PER GMR team |  | Part of MS Work | Part of MS Work | Items to be removed
9 | GI Electrical Conduit Difference Amount | [6 empty] | Extra requirement raised by GMR and TFS team during the execution |  | PR Uploaded with DIAL Guideline Then why asking for additional | Vendor is aksing for too much, he is charging 266 RMT | Rates approved Basic price difference of Rs 28/- between MS & GI conduit
9.1 | Difference in GI and MS conduct of 20 & 25 mm | Rmt | 2200 | 66.93 | 147246 | 35 | 77000
10 | Latecrete chemical
| Total |  |  |  | 885018.1125 |  | 589025.6125
| Gst @ 18% |  |  |  | 159303.2602 |  | 106024.6102
| G. Total |  |  |  | 1044321.3728 |  | 695050.2228

## Index sheet
List of supporting documents
Bill no. 1 | SS Chambers | Pending
Bill no. 2 | Fitting for SS Chamber | Attached
Bill no. 3 | Pannel | Attached
Bill no. 4 | Copper pipe | Attached
Bill no. 5 | 6 mm ply | Attached
Bill no. 6 | Gi conduct | Attached
Bill no. 7 | MS conduct | Attached
Bill no. 8 | Labor of copper pipe | Attached

## ss Chamber
S.NO | ITEM | UNIT | QTY | RATE | AMOUNT
1 | IC CHAMBER SS FINISH IN 304 WITH IN OUT CONNECTION
A | 600*600*250 | NOS | 1 | 29250 |  | Purchase Bill attached
| 560*300*200 | NOS | 1 | 16500 |  | Purchase Bill attached
| 900*300*200 | NOS | 1 | 25500 |  | Purchase Bill attached
| 900*300*175 | NOS | 1 | 25500 |  | Purchase Bill attached
| 560*300*200 | NOS | 1 | 16500 |  | Purchase Bill attached
113250
| FITTING | NOS | 5 | 1800 | 9000 | Purchased on cash
122250
| LOADING/UNLOADING@5% |  |  |  | 6112.5
| CARTAGE @ 5% |  |  |  | 6112.5
A | MATERIAL TOTAL |  |  |  | 134475
| LABOUR | NOS | 5 | 3000 | 15000
B | LABOUR TOTAL |  |  |  | 15000
C | TOTAL A+B |  |  |  | 149475
E | TOTAL C+D |  |  |  | 149475
F | PROFIT @ 15% |  |  |  | 22421.25
| TOTAL E+F |  |  |  | 171896.25

## Copper pipe
S.NO | ITEM | UNIT | QTY | RATE | AMOUNT
1 | COPPER PIPEING 22MM | RFT
| PIPE | RFT | 1 | 619 | 619 | Purchase bill attached
| FITTING | RFT | 1 | 323 | 323 | Purchase bill attached
| INSULATION | RFT | 1 | 78 | 78 | Purchase bill attached
|  |  |  | PER RFT | 1020
| LOADING/UNLOADING@5% |  |  |  | 51
| CARTAGE @ 5% |  |  |  | 51
| WASTAGE @5% |  |  |  | 51
A | MATERIAL TOTAL |  |  |  | 1173
| LABOUR | RFT | 1 | 350 | 350 | Purchase bill attached
B | LABOUR TOTAL |  |  |  | 350
C | TOTAL A+B |  |  |  | 1523
E | TOTAL C+D |  |  |  | 1523
F | PROFIT @ 15% |  |  |  | 228.45
| TOTAL E+F |  |  | PER RFT | 1751.45

## Detail of Pannel electrical
S.NO | ITEM | UNIT | QTY | RATE | AMOUNT
1 | PANNEL
| PANNEL COSTING | NOS | 1 | 135000 | 135000 | PI attach
| LOADING/UNLOADING | NOS | 1 | 5000 | 5000
| CARTAGE | NOS | 1 | 5000 | 5000
A | MATERIAL TOTAL |  |  |  | 145000
| LABOUR | NOS | 1 | 12500 | 12500
B | LABOUR TOTAL |  |  |  | 12500
C | TOTAL A+B |  |  |  | 157500
E | TOTAL C+D |  |  |  | 157500
F | PROFIT @ 15% |  |  |  | 23625
| TOTAL E+F |  |  |  | 181125

## Dmb
S.NO | ITEM | UNIT | QTY | RATE | AMOUNT
1 | dmb | sft
| ms pipe | RFT | 44.75 | 60 | 2685
| ply 19mm | sft | 34 | 118 | 4012
| fixing material | l.s | 1 | 1000 | 1000
| paint | sft | 34 | 15 | 510
|  |  |  | per sft | 8207
| CARTAGE/loading/unloading |  |  |  | 4000
| WASTAGE |  |  |  | 1000
A | MATERIAL TOTAL |  |  |  | 13207
| LABOUR PIPE | RFT | 44.75 | 25 | 1118.75
| LABOUR PLY | SFT | 34 | 30 | 1020
| LABOUR PAINT | SFT | 35 | 12 | 420
B | LABOUR TOTAL |  |  |  | 2558.75
C | TOTAL A+B |  |  |  | 15765.75
F | PROFIT @ 15% |  |  |  | 2364.8625
| TOTAL E+F |  |  |  | 18130.6125
|  |  |  | PER SFT | 1115.73

## 6 mm ply for protection
S.NO | ITEM | UNIT | QTY | RATE | AMOUNT
1 | Cost of 5 mm commercial ply | sft | 1 | 22 | 22 | Purchase bill attached
| LOADING/UNLOADING@5% |  |  | 1.1 | 0
| CARTAGE @ 5% |  |  | 1.1 | 0
| WASTAGE @0 % |  |  |  | 0
A | MATERIAL TOTAL |  | 1 | 24.2 | 24.2
0
| LABOUR and tape | sft | 1 | 8 | 8
B | LABOUR TOTAL |  |  |  | 8
C | TOTAL A+B |  |  |  | 32.2
E | TOTAL C+D |  |  |  | 32.2
F | PROFIT @ 15% |  |  |  | 4.83
| TOTAL E+F |  |  | PER RFT | 37.03

## ss frame trench
S.NO | ITEM | UNIT | QTY | RATE | AMOUNT
1 | SS TRENCH | RFT
| ANGLE | RFT | 1 | 150 | 150
|  |  |  | PER RFT | 150
| LOADING/UNLOADING@10% |  |  |  | 3.75
| CARTAGE @ 10% |  |  |  | 3.75
| WASTAGE @5% |  |  |  | 3
A | MATERIAL TOTAL |  |  |  | 160.5
| LABOUR | RFT | 1 | 35 | 35
B | LABOUR TOTAL |  |  |  | 35
C | TOTAL A+B |  |  |  | 195.5
F | PROFIT @ 15% |  |  |  | 29.325
| TOTAL E+F |  |  | PER RFT | 224.825

## GI CONDUCT
sno | Description | unit | qty | Rate | Amount | Remarks
1 | Price of Ms conduct per rmt | rmt | 1 | 62 |  | Purchase bill attached
2 | Price of GI conduct per rmt | rmt | 1 | 95.2 |  | Purchase bill attached
| Difference in the above | rmt | 1 | 33.2
Add | Deffierence in fiiting | rmt | 1 | 10
Add | Difference in Labor | rmt | 1 | 15
| Total of above |  |  | 58.2
Add | Profit @ 15% | Rmt | 1 | 8.73
| Total | Rmt | 1 | 66.93