## PriceBidservice
SubItemUniqueCode | ItemCode | ItemName | UOM | Rate | Quantity | Remarks | SupplierRate
165964 | 1.0 | AIR DISTRIBUTION SYSTEM |  | 0.00 | 0.00 |  | 0
165965 | 1.1 | GI sheet metal rectangular duct |  | 0.00 | 0.00 |  | 0
165966 |  | Supply, Fabrication, Installation, Testing Commissioning of following gauges of ducting complete with splitters, neccessary supports, dampers, and turning vanes as per specification and HVAC layout. Aproved Makes JINDAL, TATA, SAIL, Equivalent. All exposed ducts and supports shall be painting with 2 coats of primer 2 coats of epoxy paint. (Make-JSW ESSAR) |  | 0.00 | 0.00 |  | 0
165967 | a | 24 gauge ducting - 0.63 mm thickness (Width upto - 750mm) | Sq. mt | 0.00 | 13.00 | 250x150mm Supply air duct is Pending Around 65 Sqm of Works Completed at Site but no Proper alignment and dampers and diffusers not fixed. Alignment is not as per drawing., Rectifcation to be done | 0
165968 | b | 22 gauge ducting - 0.80 mm thickness (Width 751 - 1500) | Sq. mt | 0.00 | 10.00 |  | 0
165969 | 2.0 | XLPE Insulation (Supply Exhaust Fresh Air Duct) |  | 0.00 | 0.00 |  | 0
165970 |  | Providing and fixing XLPE insulation by applying adhesive on ducts complete as per specifications and drawings. Make-SUPREME PARAMOUNT. (Exhaust- out side insulation, Fresh air -outside insulation, Supply- Inside insulation, Supply-outside painted.) |  | 0.00 | 0.00 |  | 0
165971 | a | 13 mm thick | Sq. mt | 0.00 | 23.00 | Insulation not done Properly on Exsisting 240 Sqmt, Rectifcation to be done | 0
165972 | 3.0 | Continous Linear Grilles |  | 0.00 | 0.00 |  | 0
165973 |  | Extruded Aluminium Powder Coated Continous Linear Grilles Of Required Airflow Angles (0 15 30 45 degree deflection 1 or 2 way) with four side flanges as per requirements. (Make - AIRVISION COSMOS) |  | 0.00 | 0.00 |  | 0
165974 | a | 6 Width | Rmt | 0.00 | 9.00 |  | 0
165975 | b | 8 Width | Rmt | 0.00 | 3.00 |  | 0
165976 | 4.0 | Supply Air Square Grille |  | 0.00 | 0.00 |  | 0
165977 |  | Supply, installation of aluminium extruded white powder-coated supply air square grilles with four side flanges (0 22.5 45 degree deflection 1 or 2 way), with aluminium powder coated, multiple flape type with dampers. (Kitchen Area) |  | 0.00 | 0.00 |  | 0
165978 | a | Neck Size - 12 x 12 (Outer Size - 14 x 14 ) | Nos. | 0.00 | 7.00 |  | 0
165979 | 5.0 | Return Air Square Grille |  | 0.00 | 0.00 |  | 0
165980 |  | Return air square grills without damper shall be four side flanges with active sizes as given below. |  | 0.00 | 0.00 |  | 0
165981 | a | Neck Size - 14 x 14 (Outer Size - 16 x 16 ) | Nos. | 0.00 | 8.00 |  | 0
165982 | 6.0 | Canvass Connection |  | 0.00 | 0.00 |  | 0
165983 | a | Installation of Double Canvass connection for all air outlet inlet, Fire retardant type with GI flanges for Units. | Nos. | 0.00 | 2.00 |  | 0
165984 | 7.0 | Volume Control Damper (make - Cosmos Caryaire Air Product) |  | 0.00 | 0.00 |  | 0
165985 |  | Supply Installation of volume control damper made of 100x40x1.55mm thk galvanised steel frame with opposed blades of 1.55mm galvanised sheet steel. | Sq. mt | 0.00 | 3.00 |  | 0
165986 | 8.0 | Supply Air Gypsum 4 way Diffuser (Diffuser to be mounted on collar with damper) |  | 0.00 | 0.00 |  | 0
165987 |  | Supply, installation of aluminium extruded white powdercoated four way square diffuser with damper. Make-AIRVISION COSMOS |  | 0.00 | 0.00 |  | 0
165988 | a | Neck Size - 12 x 12 (Outer Size - 15 x 15 ) | Nos. | 0.00 | 4.00 |  | 0
165989 | 9.0 | Collar Damper (make - Cosmos Caryaire Air Product) |  | 0.00 | 0.00 |  | 0
165990 | a | Supply Installation of Collar Damper gear operated with vertical blades. | Sq.mt | 0.00 | 2.00 |  | 0