## Sheet1
Date | SRNO | Pkg | Task By | Task | Status | Remark | Remark by developer
2024-01-02 | 1 | GST | Ashish | Page of Payload and etc as per talk | Pending
| 2 | WFL | Ashish | Testing of RFC if any New | Pending
| 3 | Grasim | Ashish | Minor Topics understand with nikunj and divert to Swapnil | Pending
| 4 | Grasim | Ashish | Major Topics Kuntal will discuss and divert to you | Pending | Discuss
| 5 | NFIC | Ashish | Confirm test done and transfer to be done by Kuntal | Pending
| 6 | K-corp | Nikunj | Check New Page Logic in Uat for reject and total with new cycle | Pending | With Snehal
| 7 | K-corp | Nikunj | Sit with Foram and Snehal phase -2 whole demo finish | Pending
| 8 | K-corp | Nikunj | Budget upload / download proper check and make demo data with Nikunj/Snehal -> Mihir | Pending
| 9 | Petronas | Nikunj | RFC Part | Pending
| 10 | K-corp | Foram | Sit with Foram and Snehal phase -2 whole demo finish | Pending
| 11 | K-corp | Mihir | Budget upload / download proper check and make demo data with Nikunj/Snehal -> Mihir | Pending
| 12 | K-corp | Kishan | Changes for Phase 2 and remaining of Vendor Registration | Pending
| 13 | Signode | Kishan | Topics with snehal / Nikunj | Pending
| 14 | Grasim | Swapnil | Minor Topics understand with nikunj and divert to Swapnil | Pending
| 15 | WFL | Swapnil | Tesing the full cycle | Pending
| 16 | K-corp | Swapnil | Print level changes if any | Pending
| 17 | Petronas | Jenish | Data Transfer development and pkg testing | Pending
| 18 | WFL | Brijesh | New E-mail console exe | Pending | Discuss with Ashish / Kuntal
| 19 | SDDCL | Rahul | Pr Details on schedular | Pending | Discuss with Ashish / Kuntal
| 20 | Welspun | Rahul | Auction Save Check Line level and lot level Tie Prevention |  | Ask Kishan/Nikunj to show the issue - Get help with Ashish